## Fire Mobilization Back Up
Description | [7 empty] | Prior to Shut Down |  |  | During Shutdown |  |  | Post Shutdown
Team # | Name | Role | Functional Group | Crew Task | Mobilization Type | Unit Rate of Mobs | # of Mobs | Date | Location | Activity | Date | Location | Activity | Date | Location | Activity
1 | Clarke, Barry Edward | Ground Work Subforeperson | Assembly | Assemblng Structures | Mob/Demob - Lattice Assembly Crew | 37490 | 2 | 2021-07-17 | WF5 C090 | Built Structures | 2021-07-22 | WF10 E201 | Built Structures | 2021-09-10 | WF5 C096 | Built Structures
2 | Scott, Darren E | Assembler Sub-Foreperson | Assembly | Assemblng Structures | Mob/Demob - Lattice Assembly Crew | 37490 | 2 | 2021-07-20 | WF5 C096 | Built Structures | 2021-07-21 | WF10 E007 | Built Structures | 2021-09-23 | WF5 C126 | Built Structures
3 | Clarke, Travis Anthony | Assembler Sub-Foreperson | Assembly | Assemblng Structures | Mob/Demob - Lattice Assembly Crew | 37490 | 2 | 2021-07-20 | WF5 C093 | Built Structures | 2021-07-21 | WF10 E200 | Built Structures | 2021-09-08 | WF5 C094 | Built Structures
4 | Rodney McCarthy | Assembler Sub-Foreperson | Assembly | Assemblng Structures | Mob/Demob - Lattice Assembly Crew | 37490 | 2 | 2021-07-17 | WF5 C084 -C094 | Built Structures | 2021-07-22 | WF5 -> WF11 | Site Spotted E200 to F020 | 2021-08-31 | WF10->WF3&5 | Supervised structure assembly WF3 and WF5
1 | Thomas Howes | Crew Lead | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-20 | WF4 B204-B216 | Plumbing Structures B204-216 | 2021-07-20 | WF10 E014 | Get all equipment moved off ROW to laydowns for hauling and mobilize it to E014 | 2021-08-12 | WF7 D001 | Move from Thunder Bay to marathon, to D001
2 | Robert Bjerkelund | Crew Lead | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-18 | WF1 | Completed a001, prepped a002 | 2021-07-23 | Moving equipment due to fire ban. | Walked equipment out of ROW, structures A002 and B197 and mobilized to E014 | 2021-08-30 | WF5 | Move cranes and equipment to str C049 prep guy towers
3 | Greg Gagnon | Crew Lead | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-18 | WF1 | Completed a001 | 2021-07-23 | Moving equipment due to fire ban. | Finish setting leg extensions at E014 | 2021-08-30 | WF5 | Move cranes and equipment to str C049 prep guy towers
4 | Derek Hynes | Crew Lead | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-18 | WF1 | Prepped a002 | 2021-07-23 | Moving equipment due to fire ban. | Move equipment to E013. | 2021-08-30 | WF5 | Move cranes and equipment to str C049 prep guy towers
5 | Danny Lavhey | Crew Lead | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-19 | WF4 | Finished erection at B198 | 2021-07-20 | Moved to Fire Safe Zone | Move equipment to marathon | 2021-08-12 | WF1 | Move equipment out from A002
6 | Pierce McCarthy | Crew Lead | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-19 | WF4 | Completed structure B198 | 2021-07-20 | Moved to Fire Safe Zone | Move equipment to Thunder Bay | 2021-08-27 | WF3 | Moved all Crane and Equipment from Structure B025 to Structure A080
1 | Joshua Thibodeau | Site Foreman | Foundations | Rock Hammering | Mob/Demob - Helical Pile Installation Crew | 161510 | 2 | 2021-07-19 | WF3 B193 | back filled B193 took grout and stub to C068 went to tbay picked up hammer | 2021-07-31 | WF10 F002 | hammering rock E210,F002,003,028,031 | 2021-11-12 | WF6 C210 | C210 set and C211 set move to C212 and get set up
2 | Scott Cougnon | Site Foreman | Foundations | Rock Hammering | Mob/Demob - Helical Pile Installation Crew | 161510 | 2 | 2021-07-07 | WF5 C102 | Ron core drilled at Str C102 and C103. Greg did covid test and did QC sheets all afternoon in room at Valhalla. Rest of guys get LOA only. No hours worked. | 2021-07-21 | WF11 F222 | Excavate and hammer rock for rock anchors. Build access to Leg A, Str F222. | 2021-12-15 | WF6 C212 | Picked up mini ex @ km 600 rd. General clean up. drilled site C212 for leg ext.
3 | Roland Bruce | Site Foreman | Foundations | Rock Hammering | Mob/Demob - Helical Pile Installation Crew | 161510 | 2 | 2021-07-14 | WF5 C106 | core drilled C106 stock pilled fill C069 | 2021-07-31 | WF10 F002 | hammering rock E210,F002,003,028,031 | 2021-09-27 | WF5 C074 | Prepped Str C074 fully Set base pf structure Set top section of structure Moved manlifts to structure C073 Set two sets of legs
4 | Bradley Rose | Site Foreman | Foundations | Rock Hammering | Mob/Demob - Helical Pile Installation Crew | 161510 | 2 | 2021-07-11 | WF5 C106 | hammering rock C106 tied re bar C59 moved CRUX out of C064 delivered material to C049,50 back filled C047 stockpiled 49 | 2021-07-30 | WF10 E218 | moved equipment in to E210,E218,F003,F031 | 2021-09-16 | WF1 A066 | Pick up crew trucks in Thunder Bay Drive to nipigon check into camp Pickup Rigging Change out BS-01 at str A66
5 | Nathanial McNutt | Site Foreman | Foundations | Rock Drill | Mob/Demob - Helical Pile Installation Crew | 161510 | 2 | 2021-07-20 | WF5 C055 | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 2021-07-23 | WF11 F218 | Walk drill from the laydown to STR F218, Drill leg D. 4 holes at 4.1m with braces and dowels | 2021-11-11 | WF5 C040 | STR C040 delivered material. Move drill to Pays Plat. STR F088 installed steel plates and tower shoes with survey. Summit QC Reports
6 | John Power | Site Foreman | Foundations | Rock Drill | Mob/Demob - Helical Pile Installation Crew | 161510 | 2 | 2021-07-04 | WF1 A002 | Bust rock with drill for forms on A002. Travel to marathon and back for drilling supplies. | 2021-07-22 | WF11 F218 | Travel from thunder bay to wawa, gather drilling supplies for the next day | 2021-08-18 | WF5 C106 | Travel to site F034-Drill Leg B 3 holes at 4.1m with braces. Travel to Scheriber, drive to C106 and check if sites are ready to be drilled.
7 | Mike Brushett | Site Foreman | Foundations | Grouting | Mob/Demob - Drilled Pier Installation Crew | 220020 | 2 | 2021-07-20 | WF5 C072 | Drove tp C072 grouted rods on Leg C and loaded grout for C050 drove there and helped out the crew on location and started to grout rods on Legs C and D drove grout truck out to entrance. Went to pays plates to get the other grout truck and take it to the entrance and drove back to Nipigon | 2021-07-28 | WF11 F218,F220,F221 | Drove to site carried bars in to F218,F220 and F221 and dropped bars in for the stubs to be put. Got everything levelled and holes cleaned out for the stubs | 2021-08-13 | WF5 C050 | Drove from White River to C050 set up truck cleaned out rod holes and helped drill dowel holes ready to grout in the morning
8 | Ryan Ballard | Site Foreman | Foundations | Grouting | Mob/Demob - Drilled Pier Installation Crew | 220020 | 2 | 2021-07-19 | WF4 B203 | STR B203 Installed plate, loaded plates for other strs | 2021-08-05 | WF10 F002 | Poured anchor rods STR F002,E218,E213,E210 and E 204. Drove from Tb to Wawa, check sites and STR's | 2021-08-17 | WF5 C091 | Delivered material to cooks lake (CPD and pea stone)Delivered stubs to STR C091.
9 | Shelden Hardiman | Crew Lead | Foundations | Grouting | Mob/Demob - Drilled Pier Installation Crew | 220020 | 2 | 2021-07-18 | WF5 C069 | Completed steel setting on str C069 but still needs dowels installed and rebar cage.started to travel excavator drill rig to str C050 to redrill one hole. Hauled the grout truck up str C069 hill with the excavator | 2021-07-30 | WF10 F221 | Finished up str f221 then went to visit Keith’s site cause he had a couple questions,returned dozer to laydown and brought backhoe back in. Then travelled loader into str F215 from copper head access into km 14 on Anjigami and picked up steel at laydown and carried to site and placed the bar and waited for stubs to be delivered | 2021-08-29 | WF5 C106 | Lowbed to Cooks Lake to C105, C106, C110 & C119 Went to KM 9 on Paint Lake 2 picked up Stubs for STR 34. Travelled Excavator to Site 1 hr. 3 more Stubs to cut braces for. Start STR F189
10 | Wayne Hiscock | Site Foreman | Foundations | Forming | Mob/Demob - Drilled Pier Installation Crew | 220020 | 2 | 2021-07-13 | WF5 C106 | hammered rock C106 stock pilled fill antler tied re bar A002 | 2021-08-07 | WF10 F029 | STR F029, poured grout pads. F029 intalled stubs and skew them with survey | 2021-10-16 | WF5 C100 | Galvanize stub legs CO99,C100,C101,C102,C103
11 | Dakota Lloyd | Site Foreman | Foundations | Forming | Mob/Demob - Drilled Pier Installation Crew | 220020 | 2 | 2021-07-19 | WF4 B203 | STR B203 Installed plate, loaded plates for other strs | 2021-08-11 | WF10 F005 | STR F005 Set/Level/Skew stubs with survey LEGS A,B,C,D. Measure and cut braces LEG A, measure and cut dowels, | 2021-09-22 | WF6 C228 | Rework STRS C228
**Note: Mobilization paid for only two of the erection crews above. The remaining four erection crews were put on standby and paid under the contract standby rate.
2 | Robert Bjerkelund |  | Erection | Erecting Structures | Mob/Demob - Tower Erection Crew | 156590 | 2 | 2021-07-18 | WF1 | Completed a001, prepped a002 | 2021-07-20 | WF1->WF10 | Walked equipment out of ROW, structures A002 and B197 and mobilized to E014 | 2021-08-30 | WF10->WF5 | Move cranes and equipment to str C049 prep guy towers