## Document Change Log
Change Item | Location of Change (Tab Name) | Description of Change | Date | Comments

## Cover Page
Summary of Forest Fire Force Majeure Event | [6 empty] | Last Update: 2022-04-08 (Rev: 3)
Discipline / Activity | Category Description | Base Pricing (Exhibit B Pricing)* | Revised Pricing (Actual JTD Costs) | Price Delta | Supporting Tabs | Comments
Mobilization Events | The Ontario Ministry of Northern Development, Mines, Natural Resources and Forestry imposed restrictions under Emergency Area Order 2021-13 (EAO-13) on July 19, 2021 which effectively shut-down all active work in Workfronts 1 through 6 and the western limit of Workfront 7 [Structures D001 to D017]. As the fire shut-down work in in Workfronts 1 through 6 and the western limit of Workfront 7 [Structures D001 to D017], Valard mobilized all crews to east of the Pic River (east of Marathon, Ontario) in order to perform as much work as possible to keep the Project moving forward. This resulted in addiitional mobilization of crews. | 0 | 0 | 0 | Mobilization Events - Fire Mobilization - B-2.3C Bid_Sheet | Mobilization events from West to East and from East to West.
Erection Crew Standby | Valard attempted to mobilize as many crews from the west side of the Project to the East side to mitigate loss and maximize productivity despite the unanticipated Order. Valard was performing significant erection work at the time of the suspension. While some erection crews were able to be relocated to the East side of the Project, there was simply not enough work space available for erection workers as there would have been but for the fire and associated suspension. The result was several erection workers were unable to work until the Order was lifted. To highlight this, Valard provides an overview of the anticipated erection crew days highlighted on had the fire not incurred and compares that to the actual crew days spent during the period of suspension. These crew days were turned into lost crew weeks for the period of shutdown. As there is an applicable Contractual Unit Rate for Erection Crew standby, Valard has quantified its claim on that basis. Significantly, having no knowledge when this Order would be lifted, Valard was left in a state of uncertainty, and the decisions as to staffing and resourcing had to be made in light of the unpredictable situation. | 0 | 1957357.1429 | 1957357.1429 | Erection Crew Standby | See 'Erection Crew Standby' tab for detail of lost productive days
Equipment Standby | There was equipment stranded in the restricted fire zone. It was initially determined by the parties that it is only proper to charge standby for the equipment actually planned to be used during the period of shutdown. Valard relies on Force Account Rates which the parties have used to calculate losses previously, to quantify this loss. Significantly, not all equipment could be remobilized the east side of the Project. There was restricted workfront on the east side of the process, and Valard was already trying to fit as many Project resources as possible on this half of the Project. Further equipment would have contributed to an already existing congested worksite problem, potentially leading to further productivity losses. | 0 | 0 | 0 | Equipment Standby
Direct Activity Supervision | Valard incurred additional supervisor time due to the fire. Supervisors can cover a sufficient amount of resources (crews) when provided with long stretches of linear workfront. The Order suspending work resulted in Valard’s team having to plan resources in a reactionary manner, which resulted in putting smaller amounts of crews spread out along the east side of the Project in a piecemeal manner. Not having the lengthy stretches of workfront, resulted in supervision not being able to be allocated in a profitable manner. Valard estimates that two additional Right of Way Supervisors, two additional foundation supervisors, two additional assembly supervisors, two additional erection supervisors and two additional stringing supervisors were necessary. | 0 | 1695307.7167 | 1695307.7167 | Direct Activity Supervision | Additional ROW, Foundation, Assembly, Erection, and Stringing supervision detailed in 'Direct Activity Supervision' tab
Fire Mitigation | Valard captured costs relating to the procurement and transportation of fire suppression equipment, as well as necessary training for its team. | 0 | 286320.3925 | 286320.3925 | Fire Mitigation | Procurement and required resources for the placement of fire suppression equipment. Includes supplies such as additional fire caches.
Camps | Due to the fire, Nipigon camp, on the west side of the Project was required to stay open longer. This resulted in additional camp operational costs, including facility fees, entities, rent charges and security being incurred to Valard. The period of two months the fire stopped work in the west portion of the Project, resulted in two months the camp needed to stay open longer [camp was initially intended to close at the end of September, 2021, and did not actually close until the end of November, 2021. In order to quantify the camp extension, Valard applied a reduced Force Account Rate (reduced as the camp was not operational). | 0 | 109200 | 109200 | Camps - Mandays | Extension of Nipigon Camp
All Season Access | The loss of construction time in western portion of the Project had the potential to result in significant schedule extension and associated costs (at the time there was no indication how long the Order could stay in place for). To attempt to mitigate the delay, Valard moved resources over to the eastern side of the Project. While the increase of resources on the eastern portion of the Project allowed a greater volume of work to be performed during the shut-down period, overall progress was still significantly hindered due to replanning time, remobilization, and an overall hindered productivity due to the now patchwork deployment of resources on a crowed east portion of the Project. Following the shutdown period, Valard sought to regain schedule and reduce impacts of the experienced delay. Work in the west was then pushed into the 2021-2022 winter. To ensure available resources could be dedicated to the west side of the Project during the 2021-2022 winter season, Valard attempted to realize an early start on the remaining work in Workfront six. This could only be accomplished by beginging work in that area prior to the planned winter season, and altering the planned use of a winter access road to an all-season road. While time was saved, reducing the need for costs associated with schedule extension, the alteration of the construction plan resulted in additional construction costs. | 0 | 0 | 0 | All Season Access | While time was saved, reducing the need for costs associated with schedule extension, the alteration of the construction plan resulted in additional construction costs. A brief description of these costs are outlined below: Construction Activities: Significantly, development of winter access roads are less costly than construction of all season roads. Valard is seeking the delta between subcontractor unit rates, plus markup, for the difference between performing all-season access and winter access roads. In addition, developing all-season access requires procurement of material, namely gravel, as well as hauling and spreading costs of that gravel. The cost of this material could have been avoided for all sections of the access road that were initially planned to be performed as winter roads. Winter access also allows Valard to take advantage of the use of snowfill crossings. As a portion of this work could no longer proceed in the winter, Valard could no longer use snowfill crossings and instead had to incur the cost associated with use of a bridge, culvert or rigmat. Maintenance Costs: There is significantly more maintenance costs associated with maintaining an all-season access road as compared to performing winter maintenance. Reclamation Costs: Reclamation work for winter access is minimal. However, reclamation work for all-season access roads is significantly more, involving recountering the land, removing gravel and reseeding areas. There are minimal reclamation costs associated with winter access. NOTE: A listing of all season roads built is included in the 'All Season Access - Roads Built' Tab
Total: |  | 0 | 4048185.252 | 4048185.252

## Mobilization Events - Fires
Forest Fires - Mobilizations & Demobilizations |  |  |  |  | Comments
Crew | Schedule B2 Mob/Demb Rate | Number of Crews | Number of Mobs | Cost
Helical Pile | 0 | 6 | 2 | 0 | Upon shutdown on the West portion of the project due to fire the crews listed moved to the Eastern portion of the project where fire restrictions were not in place in order to continue project progression - This was the first mobilization event. Upon lifting of the fire restrictions crews were required to mobilize back to the Western portion of the project - this is the 2nd mobilization event. A total of two mobilization events apply to applicable crews
Drilled Pier | 0 | 5 | 2 | 0
Lattice Assembly | 0 | 4 | 2 | 0
Tower Erection | 0 | 2 | 2 | 0
0

## Mobilization - B-2.3C Bid_Sheet
|  |  |  | EXHIBIT B-2.3C |  | Project Name: | East - West Ontario Transmission Tie Line
[6 empty] | Basis of Data: | #REF!
[7 empty] | QTY | [5 empty] | Unit | Unit |  |  | Helicopter
|  | Mt'l | Cost |  |  | Reference | Dia | Lgth | Width |  | Estimate |  | Costs | Costs | Material | Labor | Services | Total
| WBS | Code | Code | Description |  | QTY / Notes: | Ft | Ft | Ft | QTY | QTY | UOM | Material | Labor (Subcontract) | $ | $ | $ | $
Transmission Line, Engineering
ENG | Eng |  | 1 | Engineering and Design | [7 empty] | km | 0 | 0 | 0 | 0 | 0 | 0
ENG | Eng |  | 1 | Route Survey AKA: Plan & Profile | [7 empty] | km | 0 | 0 | 0 | 0 | 0 | 0
ENG | Eng |  | 1 | Route Geotech. Info (percentage of all Structures) | [7 empty] | Tangents | 0 | 0 | 0 | 0 | 0 | 0
ENG | Eng |  | 1 | Review of Transmission & Tech Support | [7 empty] | km | 0 | 0 | 0 | 0 | 0 | 0
Poles per
|  |  |  | Assemble & Install Lattice Structures, Ground Installed (Populated from Input Sheet) | Designation |  |  |  |  | Tangent
F17-31:All Quantities & Unit Costs inputted in tab "B-2 Structure_Install_Input". Material provided by NEER, installation by Contractor.
STRUC | Assmb | Struc | 10.4 | Guyed Y, Light | GTL | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Guyed Y, Heavy | GTH | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Guyed Y, FC | GTF | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Tower, Light | STL | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Tower, Heavy | STH | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Tower, FC | STF | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Small Angle | SRF | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Strain 0 - 30 | SSX | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 0 - 30 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 30-90 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 30-90 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 60 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 90 | SDM/SDV | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Three- Pole Dead End | SSH | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
STRUC | Assmb | Struc | 10.4 | Three- Pole Dead End | SDH | [5 empty] | #REF! | Tangents |  | #VALUE! |  | #VALUE! |  | #VALUE!
|  |  |  | Assemble & Install Lattice Structures, Helicopter Installed (Populated from Input Sheet) | Designation
F35-49:All Quantities & Unit Costs inputted in tab "B-2 Structure_Install_Input". Material provided by NEER, installation by Contractor.
STRUC | Assmb | Struc | 10.4 | Guyed Y, Light | GTL | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Guyed Y, Heavy | GTH | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Guyed Y, FC | GTF | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Tower, Light | STL | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Tower, Heavy | STH | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Tower, FC | STF | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Small Angle | SRF | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Strain 0 - 30 | SSX | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 0 - 30 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 30-90 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 30-90 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 60 | SDX | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Self Supporting Deadend 90 | SDM/SDV | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Three- Pole Dead End | SSH | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
STRUC | Assmb | Struc | 10.4 | Three- Pole Dead End | SDH | [5 empty] | #REF! | Tangents |  | #VALUE! |  |  | #REF! | #REF!
Structures Other:
F53:Include material & labor for installaing structure number & safety signs. F54: Include material & Labor to install Bird Discouragers on structure.
STRUC | Struc |  | 10.4 | Structure Number Assembly & Safety Signs | [6 empty] | #REF! | Ea. |  |  | #REF! | #REF! |  | #REF!
STRUC | Struc |  | 10.4 | Bird Discouragers | [6 empty] | #REF! | Ea. |  |  | #REF! | #REF! |  | #REF!
Foundations Guyed-Y:
F58-59:Include all material, labor, and construction equipment to install Guy Wire, including assemblies
STRUC | STRUC |  | 10.4 | Guy Wires + Assemblies, Structure Types GTL & GTH | [6 empty] | #REF! | Ea. |  |  | #REF! | #REF! |  | #REF!
STRUC | STRUC |  | 10.4 | Guy Wires + Assemblies, Structure Type GTH | [6 empty] | #REF! | Ea. |  |  | #REF! | #REF! |  | #REF!
Guy Anchors
|  |  |  | F65-72:Include all material, labor, and construction equipment to install Guy Anchors | Designation
FOND | Fond |  | 4 | Guy Anchor, Rock | AN1 | SP-01 |  |  |  |  | 292 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Single Anchors w/ Secondary Grout | AN2 | SP-01 |  |  |  |  | 0 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Double Soil Anchors | AN3 | SP-01 |  |  |  |  | 0 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Double Soil Anchors | AN3 | SP-02 |  |  |  |  | 216 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Double Soil Anchors | AN3 | SP-03 |  |  |  |  | 24 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Double Soil Anchors w/ Secondary Grout | AN4 | SP-04 |  |  |  |  | 0 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Double Soil Anchors w/ Secondary Grout | AN4 | SP-05 |  |  |  |  | 8 | Ea. |  |  | 0 | 0 |  | 0
FOND | Fond |  | 4 | Guy Anchor, Double Soil Anchors w/ Secondary Grout | AN4 | SP-06 |  |  |  |  | 0 | Ea. |  |  | 0 | 0 |  | 0
Structure Foundations (Populated from Input Sheet)
|  |  |  | F77-104:All Quantities & Unit Costs inputted in tab "B-2 Foundation_Install_Input". | Designation | Soil Conditions
FOND | Fond |  | 4 | Guyed Y Micropile Foundation with Precast Cap | F-1 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Guyed Y Micropile Foundation with Precast Cap | F-1 | SP-2 | [5 empty] | Ea.
FOND | Fond |  | 4 | Guyed Y Helical Foundation with Cast in Place Cap | F-2 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Guyed Y Helical Foundation with Cast in Place Cap | F-3 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Drilled Pier, 2.8 Meter Depth, 762MM Dia & Less | F-3 | ALL | GTL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 2.8 Meter Depth, 762 < Diameter >= 1828.8 | F-3 | ALL | GTL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 2.8 Meter Depth, 1828.8 < Diameter >= 2438.4 | F-3 | ALL | GTL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 2.8 Meter Depth, 2438.4 < Diameter >= 3657.4 | F-3 | ALL | GTL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 12.8 Meter Depth, 762MM Dia & Less | F-3 | ALL | STL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 12.8 Meter Depth, 762 < Diameter >= 1828.8 | F-3 | ALL | STL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 12.8 Meter Depth, 1828.8 < Diameter >= 2438.4 | F-3 | ALL | STL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Drilled Pier, 12.8 Meter Depth, 2438.4 < Diameter >= 3657.4 | F-3 | ALL | STL |  |  |  |  | Ea.
FOND | Fond |  | 4 | Guyed Y Grillage | F-4 | SP-2 | [5 empty] | Ea.
FOND | Fond |  | 4 | Guyed Y Grillage | F-4 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Guyed Y Grillage | F-4 | SP-4 | [5 empty] | Ea.
FOND | Fond |  | 4 | Guyed Y Grillage | F-4 | SP-5 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Micropile Foundation with Cast in Place Cap | F-5 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Micropile Foundation with Cast in Place Cap | F-5 | SP-2 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Micropile Foundation with Cast in Place Cap | F-5 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Helical Pier Foundation with Cast in Place Cap | F-6 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Helical Pier Foundation with Cast in Place Cap | F-7 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Grillage Foundation | F-8 | SP-2 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Grillage Foundation | F-8 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Grillage Foundation | F-8 | SP-4 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting Grillage Foundation | F-8 | SP-5 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting H Pile Foundation | F-9 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Supporting H Pile Foundation | F-9 | SP-2 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Suporting Monopole Micropile Foundation, SDH | F-10 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Suporting Monopole Micropile Foundation, SSH | F-10 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Suporting Monopole Micropile Foundation, SDM | F-10 | SP-1 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Suporting Monopole Helical Pier Foundation, SDH | F-11 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Suporting Monopole Helical Pier Foundation, SSH | F-11 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Self-Suporting Monopole Helical Pier Foundation, SDM | F-11 | SP-3 | [5 empty] | Ea.
FOND | Fond |  | 4 | Contractor Foundation Alternate Proposal | [7 empty] | Ea. |  |  |  | #REF! |  | #REF!
FOND | Fond |  | 4 | Contractor Foundation Alternate Proposal - Foundation Engineering | [6 empty] | 1 | Lot |  |  | 0 | 396000 |  | 396000
FOND | Fond |  | 4 | Contractor Foundation Alternate Proposal - Geotechnical Investigation | [6 empty] | 1 | Lot |  |  | 0 | 820250 |  | 820250
Conductor, wire, fiber, suspension & clamp:
F109: Include Quantitiy, Labor, and Construction Equipment Costs to Install Conductor. Material provided by NEER.
F110-114:Include all material, labor, and construction equipment to install. Please provide Quantity as well.
COND | Wire | Wire | 10.4 | Conductor |  | Grackle | 1192 kcmil |  | ACSR |  | 101.5253 | km |  |  |  | 8752554.4109 |  | 8752554.4109
COND | Wire |  | 10.4 | Conductor Splice Assembly |  | 10400 | m per Reel |  |  |  | 193 | Ea |  |  | 79190.0114 | 212063.4678 |  | 291253.4792
COND | Wire |  | 10.4 | Conductor Compression Deadend, Single Tongue |  | 1.533 | lbs/ft |  |  |  | 396 | Ea |  |  | 244796.7258 | 395558.7975 |  | 640355.5233
COND | Wire |  | 10.4 | Conductor Compression Deadend, Double Tongue | [7 empty] | Ea |  |  | 0 | 0 |  | 0
COND | Wire |  | 10.4 | Conductor Spacers | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Wire |  | 10.4 | Conductor Vibration Dampers | [6 empty] | 1818 | Ea. |  |  | 89183.1263 | 71246.2941 |  | 160429.4203
COND | Wire |  | 10.4 | Air Flow Spoilers | [6 empty] | 1610 | Ea. |  |  | 147733.6 | 615271.7614 |  | 763005.3614
COND | Wire |  | 10.4 | Shield Wire
F119-129:Include all material, labor, and construction equipment to install. Please provide Quantity as well.
F130-131: Include all material, labor, and construction equipment to install.
COND | Wire | Wire | 10.4 | OPGW Cable: Fiber | [6 empty] | 101.5253 | km |  |  |  | 1772142.329 |  | 1772142.329
COND | Wire |  | 10.4 | OPGW Cable: (Splice Box) | [6 empty] | 22 | Ea. |  |  | 39894.514 | 27763.9824 |  | 67658.4964
COND | Wire |  | 10.4 | OPGW Cable: (Splicing & Testing) | [6 empty] | 22 | Ea. |  |  | 0 | 64782.6033 |  | 64782.6033
COND | Wire | Wire | 10.4 | OHGW Cable (mostly used for double circuits) | [6 empty] | 101.5253 | km |  |  |  | 1439764.515 |  | 1439764.515
COND | Wire |  | 10.4 | Shield Wire Splice Assembly | [6 empty] | 32.0293 | Ea. |  |  | 6405.8585 | 12797.4281 |  | 19203.2865
COND | Wire |  | 10.4 | Fiber Repeater Stations | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Wire |  | 10.4 | Suspension Clamps For OPGW / OHGW (Shield Wire Assembly) Tangents | [6 empty] | 126 | Ea. |  |  | 40112.4528 | 96207.9139 |  | 136320.3667
COND | Wire |  | 10.4 | Suspension Clamps For OPGW / OHGW (Shield Wire Assembly) Dead End | [6 empty] | 120 | Ea. |  |  | 43539.588 | 91626.5847 |  | 135166.1727
COND | Wire |  | 10.4 | Strain Clamp For OPGW / OHGW | [6 empty] | 66 | Ea. |  |  | 34525.5636 | 43950.9762 |  | 78476.5398
COND | Wire |  | 10.4 | Vibration Dampers, Shield Wire | [6 empty] | 349 | Ea. |  |  | 10906.3373 | 13677.0951 |  | 24583.4324
COND | Wire |  | 10.4 | Vibration Dampers, OPGW | [6 empty] | 588 | Ea. |  |  | 19087.362 | 23043.3556 |  | 42130.7176
COND | Wire |  | 10.4 | Bird Diverter Assembly - Shield Wire | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Wire |  | 10.4 | Bird Diverter Assembly - OPGW | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Insul |  |  | Insulators
COND |  |  |  | F133-146: Include all material, labor, and construction equipment to install. Please provide Quantity as well.
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 120K, Composite | [6 empty] | 914 | Ea. |  |  | 349760.5738 | 872361.4136 |  | 1222121.9873
COND | Insul |  | 10.4 | Suspension Insulator, V-String, 120K Composite | [6 empty] | 220 | Ea. |  |  | 180792.6296 | 209977.5831 |  | 390770.2127
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 160K, Composite | [6 empty] | 184 | Ea. |  |  | 83268.6885 | 175617.615 |  | 258886.3035
COND | Insul |  | 10.4 | Suspension Insulator, V-String, 160K Composite | [6 empty] | 32 | Ea. |  |  | 32428.16 | 30542.1949 |  | 62970.3549
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 178K, Composite | [6 empty] | 126 | Ea. |  |  | 93259.971 | 120259.8924 |  | 213519.8634
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 120K, Ceramic | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 160K, Ceramic | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 222K, Ceramic | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Insul |  | 10.4 | Suspension Insulator, Post, 120K, Ceramic | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 120K, Glass | [6 empty] | 198 | Ea. |  |  | 129506.85 | 87901.9543 |  | 217408.8043
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 160K, Glass | [6 empty] | 84 | Ea. |  |  | 173088.594 | 65260.5404 |  | 238349.1344
COND | Insul |  | 10.4 | Suspension Insulator, I-String, 222K, Glass | [6 empty] | 312 | Ea. |  |  | 309054.798 | 242396.3023 |  | 551451.1003
COND | Insul |  | Suspension Insulator, Post, 120K, Composite | Suspension Insulator, Post, 120K, Glass | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  |  | Assembly, Supension
F133-146: Include all material, labor, and construction equipment to install. Please provide Quantity as well.
COND | Assb |  | 10.4 | Assembly, Supension, I-String | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Assembly, Supension, V-String | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Assembly, Supension, Post | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Suspension Clamp for Grackle Cable | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Strain Clamp for Grackle Cable | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Animal / Bird Guards | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Misc. Anchor Shackle, Ball Eye, etc. (1 Lot Per Structure) | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
COND | Assb |  | 10.4 | Grounding:
F159-165:Include all material, labor, and construction equipment to install. Please provide Quantity as well. This includes ground wire, ground rods, and all caldwelds.
COND | Assb |  | 10.4 | Grounding - Counterpoise in Rock | [6 empty] | 84.1862 | Ea. |  |  | 11365.1344 | 68639.8623 |  | 80004.9967
COND | Assb |  | 10.4 | Grounding - Counterpoise in Soil | [6 empty] | 196.2063 | Ea. |  |  | 26487.8471 | 91720.8896 |  | 118208.7367
COND | Assb |  | 10.4 | Grounding - Rock Anchor | [6 empty] | 30.0241 | Ea. |  |  | 1200.9649 | 3133.8882 |  | 4334.8531
COND | Assb |  | 10.4 | Grounding - Rod in Rock | [6 empty] | 30.0241 | Ea. |  |  | 1574.6752 | 24479.6907 |  | 26054.3659
COND | Assb |  | 10.4 | Grounding - Rod in Soil | [6 empty] | 240.193 | Ea. |  |  | 12597.4303 | 112276.1167 |  | 124873.547
COND | Assb |  | 10.4 | Grounding - Fence | [6 empty] | 27.3776 | Ea. |  |  | 3559.0906 | 12798.2637 |  | 16357.3542
COND | Assb |  | 10.4 | Grounding - Misc., Railroad | [6 empty] | 2.7378 | Ea. |  |  | 2395.5417 | 4803.5186 |  | 7199.0603
COND | Assb
Roads, Access Ways, misc. civil
Right of Way Clearing
CIV | Clear |  | 2 | Clearing Hand | [6 empty] | 97.7266 | Ac. |  |  | 0 | 621395.7819 |  | 621395.7819
CIV | Clear |  | 2 | Clearing Mechanical | [6 empty] | 126.9382 | Ac. |  |  | 0 | 248073.9928 |  | 248073.9928
CIV | Clear |  | 2 | Grubbing | [6 empty] | 956.9099 | Ac. |  |  | 0 | 3641885.1712 |  | 3641885.1712
CIV | Clear |  | 2 | Timber Removal | [6 empty] | 1289.6206 | Ac. |  |  | 0 | 7451069.2771 |  | 7451069.2771
CIV | Clear |  | 2 | Debris Removal | [6 empty] | 1404.0505 | Ac. |  |  | 0 | 60663.1178 |  | 60663.1178
CIV | Clear |  | 2 | ROW Restoration | [6 empty] | 40.1475 | Ac. |  |  | 0 | 9703.8073 |  | 9703.8073
CIV | Acc |  | 2 | Cut & Fill for site access & Crane pads | [6 empty] | 14495.9571 | m^3 |  |  | 0 | 477068.121 |  | 477068.121
CIV | Acc |  | 2 | Structure Equipment Access | [6 empty] | 68.9423 | Ac. |  |  | 0 | 1395167.7084 |  | 1395167.7084
CIV | Acc |  | 2 | Site / Transmission Access roads:
CIV | Acc |  | 2 | AN - New Road | [6 empty] | 3443363.0345 | Sf. |  |  | 0 | 3894367.5456 |  | 3894367.5456
CIV | Upgd |  | 2 | AU1 - Existing Road, Minor Upgrade | [6 empty] | 557915.6203 | Sf. |  |  | 0 | 99652.4325 |  | 99652.4325
CIV | Upgd |  | 2 | AU2 - Existing Road, Major Upgrade | [6 empty] | 7925665.735 | Sf. |  |  | 0 | 6811968.6636 |  | 6811968.6636
CIV | Acc |  | 2 | AE1 - Existing Road Repair | [6 empty] | 2393789.1677 | Sf. |  |  | 0 | 100646.6448 |  | 100646.6448
CIV | Acc |  | 2 | AE2 - Municipal and Provincial Roads and Highways | [7 empty] | Sf. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Wetland Roads | [6 empty] | 230944.5248 | Sf. |  |  | 0 | 251024.2643 |  | 251024.2643
CIV | Acc |  | 2 | Water Crossing, Culvert, 0.5M Dia, 1M Length | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Water Crossing, Culvert, 1.5M Dia, 3M Length | [6 empty] | 37 | Ea. |  |  | 0 | 388544.1172 |  | 388544.1172
CIV | Acc |  | 2 | Water Crossing, Culvert, 2.5M Dia, 5M Length | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Water Crossing, Culvert, 3.0M Dia, 7M Length | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Water Crossing, Bridge 0.5M Dia, 1M Length | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Water Crossing, Bridge 1.5M Dia, 3M Length | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Water Crossing, Bridge, 2.5M Dia, 5M Length | [6 empty] | 19 | Ea. |  |  | 0 | 97349.5151 |  | 97349.5151
CIV | Acc |  | 2 | Water Crossing, Bridge, 3.0M Dia, 7M Length | [6 empty] | 34 | Ea. |  |  | 0 | 946763.0185 |  | 946763.0185
CIV | Acc |  | 2 | Water Crossing, Greater than 7M Length | [7 empty] | Ea. |  |  | 0 | 0 |  | 0
CIV | Acc |  | 2 | Maintence Road Way | [6 empty] | 14551678.0823 | Sf. |  |  | 0 | 1421636.4962 |  | 1421636.4962
CIV | Acc |  | 2 | Gravel Removal Costs | [6 empty] | 1958991.3508 | Sf. |  |  | 0 | 1995193.8865 |  | 1995193.8865
CIV | Yds |  | 3 | Laydown Yard | [6 empty] | 5.75 | Ac. |  |  | 0 | 224479.8712 |  | 224479.8712
CIV | Yds |  | 3 | Staging Yards | [7 empty] | Ac. |  |  | 0 | 0 |  | 0
CIV | Yds |  | 3 | Restoration - ROW / access ways / laydowns | [6 empty] | 315.3786 | Ac. |  |  | 0 | 1834651.708 |  | 1834651.708
CIV | Acc |  | 2 | SWPPP/BMPs - design, furnish, Install, monitor, maintain, remove (hay bails, silt fencing, etc. | [6 empty] | 1404.0505 | Ac. |  |  | 0 | 2180860.204 |  | 2180860.204
CIV | Yds |  | 3 | Fencing, repair, new Permanent | [6 empty] | 681.3726 | m. |  |  | 0 | 7699.5099 |  | 7699.5099
CIV | Yds |  | 3 | Fencing, Temporary | [6 empty] | 454.2484 | m. |  |  | 0 | 6404.902 |  | 6404.902
Special Considerations:
CIV | Yds |  | 3 | Construction / Traffic Control | [6 empty] | 5.4 | Mo |  |  | 0 | 109890 |  | 109890
CIV | Yds |  | 3 | Construction Security | [6 empty] | 5.4 | Mo |  |  | 0 | 124200 |  | 124200
Contractors Other Costs
GA | COC |  | 13 | Field Offices, Temp Facilities, Man-Camps, Staff, G & A, Contractor | [6 empty] | 1 | Lot |  |  | 0 | 614660 |  | 614660
GA | COC |  | 13 | Contractor Mob/DeMob | [6 empty] | 1 | Lot |  |  | 0 | 527316.7167 |  | 527316.7167
GA | COC |  | 13 | Move Around - Clearing | [7 empty] | Crew |  | 64691.63 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Access Road Installation | [7 empty] | Crew |  | 74468.26 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Grillage Foundation Installation | [7 empty] | Crew |  | 61830 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Tower Erection | [7 empty] | Crew |  | 86200 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Stringing | [7 empty] | Crew |  | 254940 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Site Preparation | [7 empty] | Crew |  | 11620 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Blocking | [7 empty] | Crew |  | 6140 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Lattice Assembly | [7 empty] | Crew |  | 24880 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Guy Installation | [7 empty] | Crew |  | 18680 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Plumbing | [7 empty] | Crew |  | 3320 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Helical Pile Installation | [7 empty] | Crew |  | 31670 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Micro-pile or Anchor Installation | [7 empty] | Crew |  | 46110 | 0 | 0 |  | 0
GA | COC |  | 13 | Move Around - Drilled Pier Installation | [7 empty] | Crew |  | 43150 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Clearing Crew | [7 empty] | Weekly |  | 349340 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Access Road Installation Crew | [7 empty] | Weekly |  | 402130 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Grillage Foundation Installation Crew | [7 empty] | Weekly |  | 297510 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Tower Erection Crew | [7 empty] | Weekly |  | 548060 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Stringing Crew | [7 empty] | Weekly |  | 1038130 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Site Preparation Crew | [7 empty] | Weekly |  | 55920 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Blocking Crew | [7 empty] | Weekly |  | 29530 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Lattice Assembly Crew | [7 empty] | Weekly |  | 131220 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Guy Installation Crew | [7 empty] | Weekly |  | 179720 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Plumbing Crew | [7 empty] | Weekly |  | 63760 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Helical Installation Crew | [7 empty] | Weekly |  | 171010 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Micro-pile or Anchor Installation Crew | [7 empty] | Weekly |  | 120870 | 0 | 0 |  | 0
GA | COC |  | 13 | Stand By Rate - Drilled Pier Installation Crew | [7 empty] | Weekly |  | 232970 | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
GA | COC | [13 empty] | 0 | 0 |  | 0
CS | CS |  | 13 | Construction Surveying | [6 empty] | 1 | Lot |  | 1128230 | 0 | 1128230 |  | 1128230
CS | CS |  | 13 | Material Management, Contractor | [6 empty] | 1 | Lot |  | 434240 | 0 | 434240 |  | 434240
CS | COC |  | 13 | Testing & Commissiong, Contractor | [6 empty] | 1 | Lot |  | 13870 | 0 | 13870 |  | 13870
PM | COC |  | 13 | Project Management | [6 empty] | 1 | Lot |  |  | 0 | 11094300 |  | 11094300
PM | COC |  | 13 | Contractor Foundation Alternate Proposal - Foundation Engineering | [7 empty] | Lot |  |  | 0 | 0 |  | 0
PM | COC |  | 13 | Contractor Foundation Alternate Proposal - Geotechnical Investigation | [7 empty] | Lot |  |  | 0 | 0 |  | 0
GA | COC |  | 13 | Performance / Payment Bonds | [6 empty] | 1 | Lot |  |  | 0 | 157894 |  | 157894
CS | COC |  | 13 | Permitting Support | [6 empty] | 1 | Lot |  |  | 0 | 22556 |  | 22556
TAX | TAX |  | 13 | Taxes | [10 empty] | 0 | 0 |  | 0
[11 empty] | Subtotal Transmission Costs |  |  |  | #REF! | #VALUE! | #REF! | #VALUE!
|  |  |  | SUMMARY | [10 empty] | Material | Labor & Equipment
STRUC |  |  |  | Structures | [10 empty] | #REF! | #VALUE! |  | #REF!
FOND |  |  |  | Foundations | [10 empty] | 0 | #REF! |  | #REF!
COND |  |  |  | Conductor | [10 empty] | 2165716.0886 | 15754621.2407 |  | 17920337.3293
CIV |  |  |  | Civil Work | [10 empty] | 0 | 34400359.7567 |  | 34400359.7567
PM |  |  |  | Project Management | [10 empty] | 0 | 11094300 |  | 11094300
CS |  |  |  | Material Management, Testing, Commisioning, Permitting Support | [10 empty] | 0 | 1598896 |  | 1598896
GA |  |  |  | Contractor G&A, Mob & DeMob, Field Offices, Man Camps | [10 empty] | 0 | 1299870.7167 |  | 1299870.7167
TAX |  |  |  | Taxes | [10 empty] | 0 | 0 |  | 0
Additional Instructions
F169:Include labor costs to clear the right of way of all vegetation by hand.
F170: Include labor & construction equipment costs to clear the right of way of all vegetation mechannilcally.
F171:Include labor & construction equipment costs to clear the right of way to grub stumps, shrubs, & rubbish.
F172: Include labor & construction equipment costs to clear the right of way of trees, stumps, brush, & roots. Include disposal by methods meeting the requirements of all applicable standards.
F173: Include labor & construction equipment costs to clear the right of way of rubbish & other objectionable material. Include disposal by methods meeting the requirements of all applicable standards.
F174: Include all material, labor, & construction equipment costs to restore the Right of Way through reclaimation, restoration, & seeding due to ROW Clearing activities.
F175: Include labor & construction equipment costs to for the earthwork provide a suitable crane pad.
F176: Include labor & construction equipment costs to provide a suitable crane pad.
F178: Include all material, labor, & construction equipment costs to upgrade existing access roads.
F179: Include all material, labor, & construction equipment costs to upgrade existing access roads not in wetland and that do not require matting.
F180: Include all material, labor, & construction equipment costs to upgrade existing access roads in wetland or that require matting.
F182: Include all material, labor, & construction equipment costs to maintain all existing and newly build access.
F183: Include all material, labor, & construction equipment costs to construct the primary laydown yard.
F184: Include all material, labor, & construction equipment costs to construct the staging yards along the route.
F185: Include all material, labor, & construction equipment costs to restore the Right of Way through reclaimation, restoration, & seeding due to ROW access, laydown yard, & staging yard construction.
F186: Include all material, labor, & construction equipment costs for the compliance & implementation of the Storm Water Pollution Prevetion Plan (SWPPP). Contractor shall install appropriate Best Management Practices (BMP’s). Contractor shall survey and evaluate the site to determine the necessary measures to comply with the SWPPP. Contractor shall provide all excavation, embankment preparation, drainage contours and culverts necessary to preclude excessive erosion and degradation of site due to water runoff. Contractor shall monitor site conditions during construction and identify areas of extreme runoff and erosion and shall provide rip-rap, water bars, sediment traps or velocity dampers in areas that experience severe or unordinary erosion. Contractor shall prepare maps showing location and type of BMP installed and used for Project Site. Contractor shall conduct regular inspections of BMP’s in accordance with the SWPPP requirements. Contractor shall document, record and maintain all documentation relating to SWPPP. Contractor shall provide a package at the end of the Project for turnover to Operations detailing what BMP’s remain. The package shall detail the requirements of the SWPPP, including a plan for maintenance and removal.
F187: Include all material, labor, & construction equipment costs to construct new permanent fencing and repair/replace exisiting fencing along the ROW.
F188: Include all material, labor, & construction equipment costs to install temporary fencing required during construction.
F190: Include all costs associated with traffic control during construction
F191: Include all costs associated with security during construction; based on two, ten-hour shifts, seven days a week.
F193: Include all costs to supply and install all required field office trailers, facilities, storage, sanitiation, dumpsters, trash, and man camps. Include all costs for building permitting, payments & coordiation with all local utilities (phone, internet, electric, water).
F194: Contractor mobilization shall consist of preparatory Work and operations, including but not limited to, those necessary for the movement of personnel, equipment, supplies and incidentals to the Project Site; for the establishment of facilities necessary for Work on the Project, and for all other Work and operations which must be performed or costs incurred before beginning production Work on the various Agreement items. Contractor mobilization cost for subcontracted Work will be considered to be included in the contract unit price for mobilization by the prime Contractor.
F195: Include all costs for surveying for construction activites, included staking, surveying for ROW clearing, grading, and ROW access.
F196: Include all costs for mangement of all materials delivered to the job site.
F197: Contractor shall perform all Transmission Facilities testing and commissioning in accordance with Owner's procedures and acceptance criteria. Contractor shall use an Owner-approved third party testing and commissioning firm to complete testing. The Owner will dictate which testing and commissioning firm the Contractor uses. Once the testing and commissioning firm is identified by Owner, it will be the Contractor's responsibility to contract with, and manage, that entity.
F198: Include all costs for Project mangement, including construction mangement staff, scheduling, document control, project adminstation & support services and home office management & support staff.
F199: Include all costs for bonding.
F200: Include all costs to support permitting activities during construction.
F201: includes all sales taxes.

## Erection Crew Standby
Erection Crew Standby Summary
Summary of Crew Schedule Changes - EWT Fire Restriction Claim |  | Unrestricted | [13 empty] | A001 to D030 Fire Restrictions | [20 empty] | Only A001 to B100 Restrictions | [7 empty] | Unrestricted | [11 empty] | SUM CREW DAYS | ACTUAL DELTA
|  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Program | Shift Schedule | time axis 2021-07-07 to 2021-08-30
Erection Crew 1 | Original | [55 empty] | 39 | 0 | bar: 2021-07-15 to 2021-08-03; 2021-08-12 to 2021-08-30
| Actual | [55 empty] | 39 | bar: 2021-07-15 to 2021-08-03; 2021-08-12 to 2021-08-30
Erection Crew 2 | Original | [55 empty] | 41 | -9 | bar: 2021-07-08 to 2021-07-27; 2021-08-04 to 2021-08-24
| Actual | [55 empty] | 32 | bar: 2021-07-08 to 2021-07-20; 2021-08-12 to 2021-08-30
Erection Crew 3 | Original | [55 empty] | 38 | -4 | bar: 2021-07-07 to 2021-07-20; 2021-07-30 to 2021-08-17; 2021-08-26 to 2021-08-30
| Actual | [55 empty] | 34 | bar: 2021-07-07 to 2021-07-20; 2021-08-05 to 2021-08-24
Erection Crew 4 | Original | [55 empty] | 39 | -12 | bar: 2021-07-07 to 2021-07-13; 2021-07-22 to 2021-08-10; 2021-08-19 to 2021-08-30
| Actual | [55 empty] | 27 | bar: 2021-07-07 to 2021-07-13; 2021-08-05 to 2021-08-24
[57 empty] | SUM: | -25
Total Crew Days Standby | 25
Weekly Standby Rate per B-2.3A | 548060
Total Standby | 1957357.1429

## Equipment Standby
Equipment Standy Summary
Unit Number of Equipment in Restricted Fire Zone - Erection Equipment | Equipment Category | Equipment Title | FA Rate (Standby) | Fire Restriction in Effect Day | Current Day | Days on Standby | Hours Per Day | Standby Cost
675569029 | Wheel Loaders | JD 644K 4WD Wheel loader | 36.75 | 2021-07-19 | 2021-08-18 | 30 | 11 | 12127.5
6757038 | Wheel Loaders | 2014 JD 644K Wheel Loader | 36.75 |  |  |  |  | 12127.5
6757045 | Dozers | 2014 JD 650K LGP Crawler Dozer | 87.95 |  |  |  |  | 29023.5
6757074 | Production Excavators | 2012 John Deere 290G Excavator | 86.63 |  |  |  |  | 28587.9
67572843 | Excavators | Caterpillar 336EL | 86.63 |  |  |  |  | 28587.9
67572844 | Excavators | Caterpillar 336EL | 86.63 |  |  |  |  | 28587.9
67572854 | Excavators | Hydraulic Excavator | 86.63 |  |  |  |  | 28587.9
67576364 | Forklifts/Manlifts | Boom 135' Telescopic With JIB | 45.1 |  |  |  |  | 14883
67576372 | Forklifts/Manlifts | Boom 135' Telescopic With JIB | 45.1 |  |  |  |  | 14883
67576374 | Forklifts/Manlifts | Boom 135' Telescopic With JIB | 45.1 |  |  |  |  | 14883
67576375 | Forklifts/Manlifts | Boom 135' Telescopic With JIB | 45.1 |  |  |  |  | 14883
6757681 | Wheel Loaders | JD 544 loader and grapple | 36.75 |  |  |  |  | 12127.5
6757698 | Dozers | John Deere 750k Dozer | 87.95 |  |  |  |  | 29023.5
67577238 | Forklifts/Manlifts | Forklift Variable Reach 12000# | 45.1 |  |  |  |  | 14883
67576363 | Forklifts/Manlifts | Boom 84-86' Telescopic 4WD | 45.1 |  |  |  |  | 14883
Notes:
1. Only activity affected by forest fires in scheduled work were Erection (Drew)
***Includes Equipment stranded in the fire Restricted Zone only

## Direct Activity Supervision
Supervision Summary
Right-of-Way Supervision
| MONTH: | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
CONTRACT | ROW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fires Supervision/Mitigation | ROW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 2 | 2 | 0 | 0 | 0 | 0 | 0
TOTAL | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 2 | 2 | 0 | 0 | 0 | 0 | 0
(Hrly Force Acct Staff) | 150.59 | 49694.7 | [19 empty] | Note: 2 included in Sep-Oct'21 are actually for Sep-Oct'22 when reclamation of the All Season access roads.
(Hrly Force Acct Pickup) | 27.07 | 4466.55 | *1 truck for every 2 people |  |  | Mandays | 390
(Round Trip Flight/Month) | 1375 | 1833.3333
| Supervision | 727929.5833
Foundations' Supervision
| MONTH: | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
CONTRACT | FDN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fires Supervision/Mitigation | FDN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(Hrly Force Acct Staff) | 150.59 | 49694.7
(Hrly Force Acct Pickup) | 27.07 | 8933.1 |  |  |  | Mandays | 120
(Round Trip Flight/Month) | 1375 | 1833.3333
| Supervision | 241844.5333
Assembly Supervision
| MONTH: | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
CONTRACT | ASSY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fires Supervision/Mitigation | ASSY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(Hrly Force Acct Staff) | 150.59 | 49694.7
(Hrly Force Acct Pickup) | 27.07 | 8933.1 |  |  |  | Mandays | 120
(Round Trip Flight/Month) | 1375 | 1833.3333
| Supervision | 241844.5333
Erection Supervision
| MONTH: | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
CONTRACT | ERECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fires Supervision/Mitigation | ERECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(Hrly Force Acct Staff) | 150.59 | 49694.7
(Hrly Force Acct Pickup) | 27.07 | 8933.1 |  |  |  | Mandays | 120
(Round Trip Flight/Month) | 1375 | 1833.3333
| Supervision | 241844.5333
Stringing Supervision
| MONTH: | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
CONTRACT | STRING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fires Supervision/Mitigation | STRING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
= | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(Hrly Force Acct Staff) | 150.59 | 49694.7
(Hrly Force Acct Pickup) | 27.07 | 8933.1 |  |  |  | Mandays | 120
(Round Trip Flight/Month) | 1375 | 1833.3333
| Supervision | 241844.5333

## Fire Mitigation - Summary
Fire Mitigation Summary |  | Comments
Fire Mitigation Labour & Equipment | 286320.3925 | Labour & Equipment charges for the placement of additional fire caches for fire mitigation. Labour & Equipment charges to move a 200 ton crane, which was on standby due to the fires, to an area away from potential fire impacts. Actual costs supported via invoices and timesheets.
Fire Mitigation Training & Supplies | 0 | Fire suppression training and mitigation steps provided to personnel to limit spread of forest fires. Obtained supplies including Fire Caches, Hoses, and other fire mitigation supplies to assist in prevention measures.
TOTAL | 286320.3925
Additional Lodging For Fire Mitigation
Number of Manhours | 1870.25 | Refer to 'Fire Mitigation - All Labour' Tab for source data
Working Manhours/Day | 11
Number of Mandays | 170 | This manday addition is included in the 'Camps Mandays' tab for additional accomodation nights for the additional labour involved in this fire mitigation.
Fire Mitigation Labour & Eqipment Breakdown
Sum of Labour Cost
Activity | Total
FORFIRES - Forest Fires | 198069.4775 | Refer to 'Fire Mitigation - All Labour' Tab for source data
Grand Total | 198069.4775
Sum of Equipment Cost
Activity | Total
FORFIRES - Forest Fires | 88250.915 | Refer to 'Fire Mitigation - All Equip' Tab for source data
Grand Total | 88250.915

## Fire Mitigation - 3rd Party
|  | Forest Fires 3rd Party Fire Watch & Mitigation |  |  |  | Date Retrieved: April 6, 2022
Project: Ontario East West Tie Line
Project Number: VC-7556
Invoice Number | Vendor | Service / Good | Activity (assumed) | Date | Cost | Markup (15%) | Claim
14802 | Valley Fire Protection and Services Limited | Fire Mitigation/Suppression Training | Fire Watch & Mitigation | 2021-06-25 | 21150 | 3172.5 | 24322.5
INV/2021/2429 | WFR Wholesale Fire & Rescue | Fire Mitigation Supplies | Fire Watch & Mitigation | 2021-07-15 | 33228.23 | 4984.2345 | 38212.4645
VC-2021-01 | FIRE 1 | Fire Mitigation/Suppression Training | Fire Watch & Mitigation | 2021-07-19 | 22950 | 3442.5 | 26392.5
ESI10336 | Northern Mat & Bridge | Delivery of Fire Cache | Fire Watch & Mitigation | 2021-07-22 | 14633.99 | 2195.0985 | 16829.0885
31597 | Taranis Contracting Group | Equipment Rental - Water Truck | Fire Watch & Mitigation | 2021-09-10 | 9717.5 | 1457.625 | 11175.125
TOTAL

## Fire Mitigation - All Labour
[5 empty] | Forest Fires Fire Watch & Mitigation Labour Timesheets | [9 empty] | Date Retrieved: April 6, 2022
Project: Ontario East West Tie Line
Project Number: VC-7556
Code | Employee | Role | Company | Date | Activity | Notes | Cost Code | Hours | Rate | Labour Cost | Lodging Cost | Total Cost | Facility | Structures | Activity Tags | Timesheet Tags
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6.5 | 146.89 | 954.785 | 124.0909 | 1078.8759 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6.5 | 81.03 | 526.695 | 124.0909 | 650.7859 |  |  |  | mVolts
203987 | Antonio Teixeira | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 57010138 | 5.5 | 81.03 | 445.665 | 105 | 550.665 |  |  |  | mVolts
197247 | Nathaniel McNutt | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 57010138 | 5.5 | 111.7 | 614.35 | 105 | 719.35 |  |  |  | mVolts
196261 | Cristian Sinisterra Mosquera | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
117745 | Bradley Eagle | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Got shut down due to dry forest conditions and had to walk bucket hoe unit #7679 from C069 to lay down on Antler Road | 57010138 | 4.5 | 111.7 | 502.65 | 85.9091 | 588.5591 |  |  |  | mVolts
118960 | Barry Skinner | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Got shut down due to dry forest conditions and had to walk bucket hoe unit #7679 from C069 to lay down on Antler Road | 57010138 | 4.5 | 81.03 | 364.635 | 85.9091 | 450.5441 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Demoved equipment | 57010138 | 3 | 111.7 | 335.1 | 57.2727 | 392.3727 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Demoved equipment | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 132.15 | 1189.35 | 171.8182 | 1361.1682 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 146.89 | 1322.01 | 171.8182 | 1493.8282 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 132.15 | 1189.35 | 171.8182 | 1361.1682 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 132.15 | 1189.35 | 171.8182 | 1361.1682 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 111.7 | 1005.3 | 171.8182 | 1177.1182 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 111.7 | 1005.3 | 171.8182 | 1177.1182 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 111.7 | 1005.3 | 171.8182 | 1177.1182 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 146.89 | 1322.01 | 171.8182 | 1493.8282 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 146.89 | 1322.01 | 171.8182 | 1493.8282 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 70.81 | 637.29 | 171.8182 | 809.1082 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Get all equipment moved off ROW to laydowns for hauling. | 57010138 | 9 | 150.59 | 1355.31 | 171.8182 | 1527.1282 |  |  |  | mVolts
117459 | Mark Byrd | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 81.03 | 121.545 | 28.6364 | 150.1814 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 111.7 | 167.55 | 28.6364 | 196.1864 |  |  |  | mVolts
117569 | Samuel Clarke | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 146.89 | 220.335 | 28.6364 | 248.9714 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 81.03 | 121.545 | 28.6364 | 150.1814 |  |  |  | mVolts
205779 | Craig Marshall | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
119196 | Joseph Wells Jr | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 146.89 | 881.34 | 114.5455 | 995.8855 |  |  |  | mVolts
116660 | Richard Hickey | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 111.7 | 670.2 | 114.5455 | 784.7455 |  |  |  | mVolts
204132 | Ian Day | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
204116 | Stephen Bustard | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
185748 | Steven Wray | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117873 | Kevin Genaille | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
205229 | Ashton Kenney | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
176481 | Dylan Berlingeri | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
185005 | Michael Mischke | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
117570 | Terence Clarke | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mob Gear/crews out | 57010138 | 2 | 146.89 | 293.78 | 38.1818 | 331.9618 |  |  |  | mVolts
118615 | Gary O'Brien | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 146.89 | 440.67 | 57.2727 | 497.9427 |  |  |  | mVolts
205842 | Shane Moores | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
118036 | Keith Hickey | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 111.7 | 335.1 | 57.2727 | 392.3727 |  |  |  | mVolts
118239 | Trevor Labour | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117815 | Keith Foote | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
116488 | Perry Abbott | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
118238 | Lee Labour | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
174876 | Matt Michano | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
196449 | Denzil Bouchard | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
205918 | Norman Edwards | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117550 | Barry Clarke | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 146.89 | 440.67 | 57.2727 | 497.9427 |  |  |  | mVolts
175342 | Patrick Bananish | Apprentice - 2nd Year | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
118960 | Barry Skinner | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Shut down due to extreme fire conditions. Cleaned truck. Got drills ready on Cooks rd and Antler rd for floats to move gear. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117745 | Bradley Eagle | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Shut down due to extreme fire conditions. Cleaned truck. Got drills ready on Cooks rd and Antler rd for floats to move gear. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
119254 | David Wood | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11.5 | 127.04 | 1460.96 | 210 | 1670.96 |  |  |  | mVolts
118054 | Robert Hinsperger | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Meeting in the morning at Marathon. Clean grout,truck demoved equipment , move it to Marathon. Organized crews | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Meeting in the morning at Marathon. Clean grout,truck demoved equipment , move it to Marathon. Organized crews | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Move equipment | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Move equipment | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
117459 | Mark Byrd | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117569 | Samuel Clarke | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
205229 | Ashton Kenney | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117873 | Kevin Genaille | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
185748 | Steven Wray | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
204116 | Stephen Bustard | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
204132 | Ian Day | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
116660 | Richard Hickey | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
205779 | Craig Marshall | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
119196 | Joseph Wells Jr | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 111.7 | 446.8 | 76.3636 | 523.1636 |  |  |  | mVolts
117813 | Craig Foote | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
117967 | Leeland Halleran | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 146.89 | 587.56 | 76.3636 | 663.9236 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
176481 | Dylan Berlingeri | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
175345 | Gabriel Oskaboose-Eccleston | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
176490 | Ward Bolt | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
185005 | Michael Mischke | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
153100 | Axel Beaulieu | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Moving equipment from Thunder Bay to white lake laydown. | 57010138 | 12 | 150.59 | 1807.08 | 210 | 2017.08 |  |  |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 13 | 127.04 | 1651.52 | 210 | 1861.52 |  |  |  | mVolts
117248 | Wayne Ashley | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 13 | 111.7 | 1452.1 | 210 | 1662.1 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 70.81 | 849.72 | 210 | 1059.72 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
205842 | Shane Moores | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Getting equipment ready for float | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
118615 | Gary O'Brien | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Getting equipment ready for float | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
117438 | Bobby Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 6 | 127.04 | 762.24 | 114.5455 | 876.7855 |  |  |  | mVolts
205842 | Shane Moores | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Mobe to Wawa from Schrieber | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
118615 | Gary O'Brien | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Mobe to Wawa from Schrieber | 57010138 | 4 | 146.89 | 587.56 | 76.3636 | 663.9236 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Organized moving equipment to wawa due to forest fires. | 57010138 | 5 | 146.89 | 734.45 | 95.4545 | 829.9045 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Organized moving equipment to wawa due to forest fires. | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Moving cranes around and hauling equipment. | 57010138 | 12 | 150.59 | 1807.08 | 210 | 2017.08 |  |  |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 13.5 | 127.04 | 1715.04 | 210 | 1925.04 |  |  |  | mVolts
117248 | Wayne Ashley | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 13.5 | 111.7 | 1507.95 | 210 | 1717.95 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 70.81 | 849.72 | 210 | 1059.72 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
117248 | Wayne Ashley | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 70.81 | 778.91 | 210 | 988.91 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 150.59 | 1656.49 | 210 | 1866.49 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Poured STR C061 with mixer on legs A,B and C Stripped STR C059. Get material to formed STR C070 | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Poured STR C061 with mixer on legs A,B and C Stripped STR C059. Get material to formed STR C070 | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
119254 | David Wood | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
118054 | Robert Hinsperger | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
155244 | Craig Greenslade | Surveyor | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Travel from Thunderbay to White River | 57010138 | 7.5 | 132.15 | 991.125 | 143.1818 | 1134.3068 |  |  |  | mVolts
138222 | Trent Linton | Surveyor | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Travel from Thunderbay to White River | 57010138 | 7.5 | 132.15 | 991.125 | 143.1818 | 1134.3068 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Poured grout pad with mixer at STR C070 and C072. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Poured grout pad with mixer at STR C070 and C072. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
117438 | Bobby Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 7 | 127.04 | 889.28 | 133.6364 | 1022.9164 |  |  |  | mVolts
119254 | David Wood | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
176227 | Craig McKay | Surveyor | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Travel from Thunder Bay to Wawa. | 57010138 | 10 | 132.15 | 1321.5 | 190.9091 | 1512.4091 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Fire Watch Monitoring as per MNRF approval | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
117438 | Bobby Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 4 | 127.04 | 508.16 | 76.3636 | 584.5236 |  |  |  | mVolts
206244 | Bryan Lavigne | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
206248 | Joshua Hewitt | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
203233 | Eric Marsh | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Hauling water totes back to marathon from access | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
118625 | Joseph O'Donnell | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
119017 | Frank Stone | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
116651 | Sheldon Hardiman | Foreman | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 146.89 | 734.45 | 95.4545 | 829.9045 |  |  |  | mVolts
116651 | Sheldon Hardiman | Foreman | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 146.89 | 881.34 | 114.5455 | 995.8855 |  |  |  | mVolts
119017 | Frank Stone | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
118625 | Joseph O'Donnell | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 3.75 | 81.03 | 303.8625 | 71.5909 | 375.4534 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire Watch monitoring as required by MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
206244 | Bryan Lavigne | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 14 | 81.03 | 1134.42 | 210 | 1344.42 |  |  |  | mVolts
118625 | Joseph O'Donnell | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
119017 | Frank Stone | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
116651 | Sheldon Hardiman | Foreman | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
203233 | Eric Marsh | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Loaded plywood,2x4 at nipigon yard and then loaded rebar at cooks road and went back to marathon for to deliver to Wawa | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 0.5 | 81.03 | 40.515 | 9.5455 | 50.0605 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Monitoring compliance to Fire Watch as required by MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 14 | 81.03 | 1134.42 | 210 | 1344.42 |  |  |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 14 | 81.03 | 1134.42 | 210 | 1344.42 |  |  |  | mVolts
196172 | Dwayne Hollmer | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Ongoing monitoring of Fire Watch requirements as per MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Moved crane from Thunder Bay to 600rd due to fire ban. | 57010138 | 11 | 150.59 | 1656.49 | 210 | 1866.49 |  |  |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-29 | FORFIRES - Forest Fires | Monitoring site for compliance to fire watch as required by MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-29 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 13.5 | 81.03 | 1093.905 | 210 | 1303.905 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-30 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-30 | FORFIRES - Forest Fires | Monitoring site for Fire watch compliance. Weekly Safety Meeting | 57010138 | 11 | 91.26 | 1003.86 | 210 | 1213.86 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-31 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-02 | FORFIRES - Forest Fires | Preparation for upcoming work in restricted fire zone | 57010138 | 2 | 91.26 | 182.52 | 38.1818 | 220.7018 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-03 | FORFIRES - Forest Fires | Crossover discussion with Kim to ensure compliance for fire restricted zone | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-04 | FORFIRES - Forest Fires | preparation fire watch | 57010138 | 1 | 111.7 | 111.7 | 19.0909 | 130.7909 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-05 | FORFIRES - Forest Fires | fire | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-06 | FORFIRES - Forest Fires | Fire | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-07 | FORFIRES - Forest Fires | fire C 006 | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-08 | FORFIRES - Forest Fires | fire C006 | 57010138 | 6 | 111.7 | 670.2 | 114.5455 | 784.7455 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 70.81 | 354.05 | 95.4545 | 449.5045 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 146.89 | 734.45 | 95.4545 | 829.9045 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 150.59 | 752.95 | 95.4545 | 848.4045 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-15 | FORFIRES - Forest Fires | Monitoring of sites and fire cache (with tote) inspection | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-16 | FORFIRES - Forest Fires | Inspection of Fire Cache and Fire Equipment | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-19 | FORFIRES - Forest Fires | Working on improving fire response | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-20 | FORFIRES - Forest Fires | Working on IOP protocol communication | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-21 | FORFIRES - Forest Fires | Ongoing communication of IOP requirements with crews | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Incident Investigation information | 57010138 | 3 | 91.26 | 273.78 | 57.2727 | 331.0527 |  |  |  | mVolts
119036 | Junior Stuckey | Equipment Operator | 00677 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 4 | 111.7 | 446.8 | 76.3636 | 523.1636 |  |  |  | mVolts
191544 | Neil Burnet | Labourer | 00677 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-23 | FORFIRES - Forest Fires | Ongoing monitoring, coaching for I.O.P compliance | 57010138 | 2 | 91.26 | 182.52 | 38.1818 | 220.7018 |  |  |  | mVolts
[10 empty] | TOTAL | TOTAL | TOTAL

## Fire Mitigation - All Equip
|  |  |  | Forest Fires Fire Watch & Mitigation Equipment Timesheets | [8 empty] | Date Retrieved: April 6, 2022
Project: Ontario East West Tie Line
Project Number: VC-7556
Equipment | Description | Company | Date | Activity | Notes | Cost Code | Hours | Rate | Equipment Cost | Facility | Structures | Activity Tags | Timesheet Tags | Unit Number
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Get all equipment moved off ROW to laydowns for hauling. | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 10624
72861 - John Deere 210G Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 138.54 | 138.54 |  |  |  | mVolts | 72861
2824 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 31.95 | 31.95 |  |  |  | mVolts | 2824
72863 - Komatsu Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 2 | 138.54 | 277.08 |  |  |  | mVolts | 72863
10547 - Ford Super Duty F350 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 27.07 | 81.21 |  |  |  | mVolts | 10547
10622 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 31.95 | 95.85 |  |  |  | mVolts | 10622
2214 - 2017 F350 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 27.07 | 162.42 |  |  |  | mVolts | 2214
021471 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 31.95 | 47.925 |  |  |  | mVolts | 21471
10577 - Ford Super Duty F250 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 27.07 | 81.21 |  |  |  | mVolts | 10577
10544 - Ford Super Duty F350 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 27.07 | 81.21 |  |  |  | mVolts | 10544
2963 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 31.95 | 95.85 |  |  |  | mVolts | 2963
7002 - John Deere 210G Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 138.54 | 415.62 |  |  |  | mVolts | 7002
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 2 | 90.19 | 180.38 |  |  |  | mVolts | 76373
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 173.26 | 173.26 |  |  |  | mVolts | 72853
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 73.49 | 73.49 |  |  |  | mVolts | 569028
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 335 | 335 |  |  |  | mVolts | 7955
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 431.32 | 431.32 |  |  |  | mVolts | 7975
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 27.07 | 243.63 |  |  |  | mVolts | 2619
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 27.07 | 243.63 |  |  |  | mVolts | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2050
7596 - 2012 JD 250G LC Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 138.54 | 415.62 |  |  |  | mVolts | 7596
2767 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 31.95 | 95.85 |  |  |  | mVolts | 2767
932042 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 11.5 | 126.5 |  |  |  | mVolts | 932042
3292 - 2015 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 137.22 | 1509.42 |  |  |  | mVolts | 3292
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 5.5 | 11.5 | 63.25 |  |  |  | mVolts | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 5.5 | 137.22 | 754.71 |  |  |  | mVolts | TT10
7649 - John Deere 225D LC Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6 | 138.54 | 831.24 |  |  |  | mVolts | 7649
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6.5 | 31.95 | 207.675 |  |  |  | mVolts | 2990
021458 - 2020 F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mob Gear/crews out | 57010138 | 2 | 31.95 | 63.9 |  |  |  | mVolts | 21458
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Moving equipment from Thunder Bay to white lake laydown. | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 10624
2826 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Move equipment | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2826
10547 - Ford Super Duty F350 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 27.07 | 297.77 |  |  |  | mVolts | 10547
10622 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 10622
2214 - 2017 F350 | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 27.07 | 297.77 |  |  |  | mVolts | 2214
10582 - Ford Super Duty F250 SRW XLT 4 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 10582
10580 - Ford Super Duty F250 SRW XLT 4 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 10580
021471 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 21471
2824 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 31.95 | 127.8 |  |  |  | mVolts | 2824
2570 - F350 pickup | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 27.07 | 108.28 |  |  |  | mVolts | 2570
10583 - Ford Super Duty F350 SRW XLT 4 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 31.95 | 127.8 |  |  |  | mVolts | 10583
932042 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 11.5 | 126.5 |  |  |  | mVolts | 932042
3292 - 2015 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 137.22 | 1509.42 |  |  |  | mVolts | 3292
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11.5 | 11.5 | 132.25 |  |  |  | mVolts | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11.5 | 137.22 | 1578.03 |  |  |  | mVolts | TT10
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Meeting in the morning at Marathon. Clean grout,truck demoved equipment , move it to Marathon. Organized crews | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2990
76369 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 2 | 90.19 | 180.38 |  |  |  | mVolts | 76369
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 4 | 90.19 | 360.76 |  |  |  | mVolts | 76373
72869 - Hydraulic Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 2 | 138.54 | 277.08 |  |  |  | mVolts | 72869
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 4 | 173.26 | 693.04 |  |  |  | mVolts | 72853
7029 - 2013 JD 450J Dozer | Crawler Tractors 750 JD | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 2 | 175.9 | 351.8 |  |  |  | mVolts | 7029
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 4 | 73.49 | 293.96 |  |  |  | mVolts | 569028
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 335 | 4020 |  |  |  | mVolts | 7955
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 431.32 | 5175.84 |  |  |  | mVolts | 7975
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  | mVolts | 2619
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  | mVolts | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2050
2767 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Getting equipment ready for float | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2767
2184 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Shut down due to extreme fire conditions. Cleaned truck. Got drills ready on Cooks rd and Antler rd for floats to move gear. | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2184
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Moving cranes around and hauling equipment. | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 10624
7948 - 2013 Liebherr LTM 1200-5.1 | 200T All-Tr. Crane | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 431.32 | 5175.84 |  |  |  | mVolts | 7948
76369 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 4 | 90.19 | 360.76 |  |  |  | mVolts | 76369
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 4 | 90.19 | 360.76 |  |  |  |  | 76373
72869 - Hydraulic Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 138.54 | 277.08 |  |  |  |  | 72869
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 173.26 | 346.52 |  |  |  |  | 72853
7029 - 2013 JD 450J Dozer | Crawler Tractors 750 JD | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 175.9 | 351.8 |  |  |  |  | 7029
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 73.49 | 146.98 |  |  |  |  | 569028
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 10 | 335 | 3350 |  |  |  |  | 7955
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 10 | 431.32 | 4313.2 |  |  |  |  | 7975
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 2619
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2050
2767 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Mobe to Wawa from Schrieber | 57010138 | 4 | 31.95 | 127.8 |  |  |  |  | 2767
932044 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 6 | 11.5 | 69 |  |  |  |  | 932044
3293 - 2016 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 6 | 137.22 | 823.32 |  |  |  |  | 3293
7948 - 2013 Liebherr LTM 1200-5.1 | 200T All-Tr. Crane | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 431.32 | 4744.52 |  |  |  |  | 7948
76369 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 90.19 | 992.09 |  |  |  |  | 76369
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 90.19 | 992.09 |  |  |  |  | 76373
72869 - Hydraulic Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 138.54 | 1523.94 |  |  |  |  | 72869
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 173.26 | 1905.86 |  |  |  |  | 72853
7029 - 2013 JD 450J Dozer | Crawler Tractors 750 JD | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 175.9 | 1934.9 |  |  |  |  | 7029
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 73.49 | 808.39 |  |  |  |  | 569028
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 431.32 | 4744.52 |  |  |  |  | 7975
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2050
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 10624
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 11.5 | 126.5 |  |  |  |  | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | TT10
932042 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 12 | 11.5 | 138 |  |  |  |  | 932042
3292 - 2015 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 12 | 137.22 | 1646.64 |  |  |  |  | 3292
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Poured STR C061 with mixer on legs A,B and C Stripped STR C059. Get material to formed STR C070 | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2990
2981 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Travel from Thunderbay to White River | 57010138 | 7.5 | 31.95 | 239.625 |  |  |  |  | 2981
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 11.5 | 126.5 |  |  |  |  | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | TT10
932044 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 7 | 11.5 | 80.5 |  |  |  |  | 932044
3293 - 2016 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 7 | 137.22 | 960.54 |  |  |  |  | 3293
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Poured grout pad with mixer at STR C070 and C072. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2990
2983 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Travel from Thunder Bay to Wawa. | 57010138 | 10 | 31.95 | 319.5 |  |  |  |  | 2983
9198 - Trimble TSC7 w/Access Data Col | Survey Equipment | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Travel from Thunder Bay to Wawa. | 57010138 | 10 | 55 | 550 |  |  |  |  | 9198
2826 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2826
041855 - F350 FLAT DECK (Lineman Truck) | Pickup | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 27.07 | 135.35 |  |  |  |  | 41855
041855 - F350 FLAT DECK (Lineman Truck) | Pickup | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 27.07 | 162.42 |  |  |  |  | 41855
3340 - Kenworth T800BT/A w/ 1996 Hiab | Tractor Trailer | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Hauling water totes back to marathon from access | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | 3340
932044 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 4 | 11.5 | 46 |  |  |  |  | 932044
3293 - 2016 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 4 | 137.22 | 548.88 |  |  |  |  | 3293
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Fire Watch Monitoring as per MNRF approval | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
2826 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2826
041855 - F350 FLAT DECK (Lineman Truck) | Pickup | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 41855
3340 - Kenworth T800BT/A w/ 1996 Hiab | Tractor Trailer | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Loaded plywood,2x4 at nipigon yard and then loaded rebar at cooks road and went back to marathon for to deliver to Wawa | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | 3340
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire Watch monitoring as required by MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
2794 - 2015 Ford Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 14 | 31.95 | 447.3 |  |  |  |  | 2794
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Monitoring compliance to Fire Watch as required by MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
2794 - 2015 Ford Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2794
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 2619
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2091
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 335 | 3685 |  |  |  |  | 7955
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Moved crane from Thunder Bay to 600rd due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 10624
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Ongoing monitoring of Fire Watch requirements as per MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-29 | FORFIRES - Forest Fires | Monitoring site for compliance to fire watch as required by MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-30 | FORFIRES - Forest Fires | Monitoring site for Fire watch compliance. Weekly Safety Meeting | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 1508
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 31.95 | 159.75 |  |  |  |  | 10624
2769 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 4 | 31.95 | 127.8 |  |  |  |  | 2769
TOTAL

## Camps - Mandays
Additional Mandays Due To Acceleration
Activity | Additional Mandays
Fire Mitigation | 170 | Calculation included on 'Fire Mitigation - Summary' Tab
ROW | 390 | See 'Direct Activity Supervision' Tab
Foundations | 120 | See 'Direct Activity Supervision' Tab
Assembly | 120 | See 'Direct Activity Supervision' Tab
Erection | 120 | See 'Direct Activity Supervision' Tab
Stringing | 120 | See 'Direct Activity Supervision' Tab
Total | 1040
Additional Camp Operating Costs | 109200
Nipigon | Camp Operational Extension
| Current planned closure date | 2021-09-30 | 61
| Updated closure date | 2021-11-30
| Total Extension in Days | 61
| Total # Rooms | 136
| Rate per Night | 105 |  | **50% of camp force account rate considered operational/facility costs excluding catering/cleaning.
|  | Total | 980280

## All Season Access - Summary
Ontario East-West Tie Line WF6-7 All-Season Access Construction & Reclamation Pricing
WF6-7 All-Season Access Pricing
COST TYPE | AMOUNT | RELATED TABS
Direct Construction Activities | #REF! | All Season Access - Detail
Maintenance Activities | 2452911.5684
Gravel Procurement + Hauling | 842521.5683
Access Material Procurement | 740405
Bridge Rentals | 346361.656
Seedlings | 448376.2
Markup @ 15% | 1079978.0898
Mobilization/Demobilization | 1898950 | All Season Access - Detail

## All Season Access - Detail
All Season Access Detail
Cost Type | Actuals ($) T&M Scope | Actuals ($) Non-T&M Scope | Remaining Forecast ($) | Credits for 3rd Winter Season | Total ($) | Supporting Tabs | Comments
Direct Construction Activities | 2277908.7413 | 0 | #REF! | -618594.1804 | #REF! | Removal | Includes the actual cost of constructing all-season roads (including mat handling) with credit given based on the submitted forecast. An additional forecast is added to remove 42km of built access.
Credits
Maintenance Activities | 2332445.3167 | 0 | 120466.2517 |  | 2452911.5684 | Removal | Actuals include T&M scope relating to all-season and winter access maintenance within 42km of built access as well as impacts on WF10. WF10 additional maintenance was required as construction moved to WF10 due to the Fire ban on Westside. In other words, the access on WF10 was not ready to support increased foot traffic, thus requiring high maintenance costs. Under forecast, $120k forecasted includes 20 days of Grader time and the ability to re-install 19 bridge tops to regain access to all-season road headings within WF6/WF7
Gravel (Procurement/Hauling) | 622842.2483 | 219679.32 | 0 |  | 842521.5683 |  | All-season access development required imported gravel which would not have been required for winter roads. See additional "Backup" below.
Procurement (Mats) | 0 | 740405 | 0 |  | 740405 |  | Matting purchase required for all-season construction. Matting was required to support work in wetlands or wet conditions, both of which would not have been present if work had been performed in winter as originally planned.
Bridge Rentals | 0 | 157836.16 | 188525.496 |  | 346361.656 | Bx Rental | Bridge rental increase is attibuted to increase in project duration out of winter season into non-frozen season. See durations on 'Bx Rental' Tab.
Seedlings | 0 | 0 | 448376.2 |  | 448376.2 | Seedlings | Off ROW seeding within WF6/WF7. Additional detail included on the 'Seedlings' Tab.
Total (w/o markup) | 5233196.3063 | 1117920.48 | #REF! | -618594.1804 | #REF!
|  |  |  | 15% Markup | #REF! | Markup
|  |  |  | Subtotal w/Markup | #REF! | Subtotal w/Markup - Excluding mobilization
Mobilization | Crew | Schedule B2 Mob/Demb Rate | Number of Crews | Number of Mobs | Cost
| Access Crews | 0 | 5 | 1 | 0
|  |  |  | Total Cost | #REF! | Total including Mobilization & Markup.
Backup
The following table shows the breakdown of hourly costs into respective categories within the Fire Claim. The pivot table is constructed from hourly LEM export (see 'LEM Backup' Tab)
All Season Access - LEM Backup |  | Maintenance Activities |  |  | Gravel (Hauling) | Direct Construction Activities
Sum of SubTotal |  | Net
Company | InvoiceNumber | WF6/WF7 - All Season Access Maintenance | WF6/WF7 - Winter Maintenance | WF10-All Season Maintenance | Gravel Hauling | New All Season Development | Rig/Access Mat Handling | Wetland Access Development | Grand Total
Corbiere and Sons Contracting | INV #144 |  |  | 468613.395 |  |  |  |  | 468613.395
Corbiere and Sons Contracting | INV #148 |  |  | 212176.51 | 77475.86 | 116452.055 | 1749.12 |  | 407853.545
Corbiere and Sons Contracting | INV #149 |  |  |  | 225128.62 | 941242.03 | 4613.71 |  | 1170984.36
Corbiere and Sons Contracting | INV #150 | 1565.7 |  |  | 271537.15 | 823649.845 | 6047.26 |  | 1102799.955
Corbiere and Sons Contracting | INV #151 | 202078.125 |  |  | 18628.3 | 95962.36 | 1171.95 |  | 317840.735
Corbiere and Sons Contracting | INV #155 | 37291.51 | 2870.45 |  |  |  | 2037.705 |  | 42199.665
Corbiere and Sons Contracting | INV #162 |  | 70425.925 | [5 empty] | 70425.925
Corbiere and Sons Contracting | INV #164 |  | 270815.455 | [5 empty] | 270815.455
Corbiere and Sons Contracting | INV #165 | 1563.86 | 171715.315 |  |  | 2865.2 |  |  | 176144.375
Corbiere and Sons Contracting | INV# 157 | 2763.81 | 43230.98 |  |  |  | 1171.95 |  | 47166.74
Corbiere and Sons Contracting | INV# 169 |  | 60145.35 | [5 empty] | 60145.35
Corbiere and Sons Contracting | Inv#142-R01 |  |  | 422684.74 |  |  |  |  | 422684.74
KABI LAKE FOREST PRODUCTS LTD | OEWT-PA19-Lem-R1 |  |  | 7172.4546 |  |  |  |  | 7172.4546
KABI LAKE FOREST PRODUCTS LTD | OEWT-PA20-Lem |  |  | 49762.58 |  |  |  |  | 49762.58
KABI LAKE FOREST PRODUCTS LTD | OEWT-PA21-LEM |  |  | 205814.6819 | 30072.3183 |  |  | 28017.7275 | 263904.7277
KABI LAKE FOREST PRODUCTS LTD | OEWT-PA22-Lem | 10600.9092 |  | 91153.566 |  |  | 10667.8182 | 69742.1368 | 182164.4302
Northern Mat & Bridge | ESI10895 | [5 empty] | 122365.7156 |  | 122365.7156
Northern Mat & Bridge | ESI10897 | [5 empty] | 7808.285 |  | 7808.285
Northern Mat & Bridge | ESI11123 | [5 empty] | 42343.8732 |  | 42343.8732
Grand Total |  | 255863.9142 | 619203.475 | 1457377.9275 | 622842.2483 | 1980171.49 | 199977.387 | 97759.8643 | 5233196.3063
Gravel Procurement (all invoices associated with the purchase of gravel for all-season access build)
Invoice | Total Amount Invoiced | Invoice Date | Company
472 | 83050 | 2021-10-13 | North Shore Forest Products
3461 | 6315.32 | 2021-10-26 | Cress Contracting Inc
3334 | 130314 | 2021-09-30 | Cress Contracting Inc
219679.32
Procurement (all invoices associated with the purchase of mats for all-season access build)
Invoice | Actual Amount ($) | Invoice Date | Company
1353 | 157250 | 2021-10-28 | Dan Blizzard Services Integres
001355 | 157250 | 2021-11-02 | Dan Blizzard Services Integres
ESI11149A | 8875 | 2021-09-19 | Northern Mat and Bridge East L
ESI11150A | 127985 | 2021-09-21 | Northern Mat and Bridge East L
ESI11152 | 87725 | 2021-09-23 | Northern Mat and Bridge East L
ESI11187 | 35090 | 2021-09-30 | Northern Mat and Bridge East L
ESI11147A | 61805 | 2021-09-17 | Northern Mat and Bridge East L
ESI11146A | 104425 | 2021-09-16 | Northern Mat and Bridge East L
740405
Bridge Rentals (Bridge rental payments starting Aug 2021 and associated with crossings installed within 42 km of all-season access built)
Invoice | Invoice Date | Claim Related Cost | Total Invoice Cost | WF
ESI10682 | 2021-08-31 | 15736 | 39508.66 | 6
ESI11010 | 2021-09-30 | 15736 | 41031.02 | 6
ESI11391 | 2021-10-31 | 15736 | 41380.93 | 6
ESI11630 | 2021-11-30 | 15736 | 38684.04 | 6
ESI11839 | 2021-12-31 | 15736 | 39265.42 | 6
ESI12052 | 2022-01-31 | 15736 | 39325 | 6
ESI12205A | 2022-02-28 | 15736 | 39324.98 | 6
ESI10678 | 2021-08-31 | 901 | 29965.5 | 6
ESI11013 | 2021-09-30 | 901 | 10370 | 6
ESI11344 | 2021-10-31 | 901 | 10370 | 6
ESI11592 | 2021-11-30 | 901 | 10002.8 | 6
ESI11843 | 2021-12-31 | 901 | 6698 | 6
ESI12039 | 2022-01-31 | 901 | 6698 | 6
ESI10678 | 2021-08-31 | 7046.36 | 29965 | 7
ESI11088 | 2021-09-30 | 7046.36 | 29965 | 7
ESI11341A | 2021-10-31 | 7046.36 | 29965 | 7
ESI11620 | 2021-11-30 | 7046.36 | 29965 | 7
ESI11835 | 2021-12-31 | 7046.36 | 29965 | 7
ESI12050 | 2022-01-31 | 7046.36 | 29965 | 7
|  | 157836.16 | See 'All Season Access - Bx Rental' Tab for addiitional detail

## All Season Access - Roads Built
GIS Raw data export showing all the roads that were built as all-season. The same dataset is visually shown within Figure 1.
wkt_geom | RID | ROAD_TYPE | SECTION | TYPE | WORKFRONT | STRUCTURE | Length_KM | BUFFDIST | Rd_Width | RoadID | ROADGROUP | HONIROW | SFL | MOC | RID All-season Roads _WORKFRONT | RID All-season Roads _STRUCTURE | RID All-season Roads _ROAD_TYPE | RID All-season Roads _Not Required | RID All-season Roads _RoadID | RID All-season Roads _Planned KM | RID All-season Roads _Sum of All-season Progress (km) | RID All-season Roads _Type | Standard Access | Wetland | Note | Tag | RID | ROAD_TYPE | Length_KM
LineStringZ (-86.77101808506094471 48.80867593596073561 0, -86.77100982914356564 48.80866267755599353 0, -86.77096532129561979 48.80857135783646328 0, -86.77091435978182687 48.80848020519155739 0, -86.77085702667608302 48.80839064383120984 0, -86.77080472421226887 48.80829974215441069 0, -86.77078043476761593 48.80825072812324095 0) | R4455 | ANWIN | C | Temp | WF6 | C188 | 0.050411 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.05 | 0.05 | All-season | 0.049175 | 0.0012369 | To C134 | 1 | R1769 | ANWIN | 0.1241
LineStringZ (-86.76765580174297554 48.8080838754399764 0, -86.76757776266809685 48.80849222861385073 0) | R4456 | ANWIN | C | Temp | WF6 | C188 | 0.045754 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.05 | 0.05 | All-season | 0.045754 | 0 | C186-C188 | 4 | R1729 | ANWIN | 0.039728
LineStringZ (-86.76547619331455508 48.80837995716802169 0, -86.76538087570210678 48.80831767960761169 0, -86.76528951343175322 48.80821835489247462 0) | R4457 | ANWIN | C | Temp | WF6 | C188 | 0.022763 | 4 | 8 | Del Lake Rd W - ML - WF6 - BR1 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - BR1 | 0.02 | 0.02 | All-season | 0.022763 | 0 | C186-C188 | 4 | R1817 | ANWIN | 0.24963
LineStringZ (-86.76042716315338055 48.80810763459314927 0, -86.76031745088135949 48.80804992074197912 0, -86.76020806649017914 48.80799376196434025 0, -86.76009591707591539 48.80793827382166938 0, -86.75998393427836675 48.80788416859051182 0, -86.75985787133637928 48.80782872231218761 0, -86.75972250335888702 48.80781070115757814 0, -86.75958411845607543 48.80781866369189714 0, -86.75944841422304421 48.80779494259263629 0, -86.75929653531190411 48.80778035801100145 0, -86.75915404207728443 48.80775433292453869 0, -86.75902982256413054 48.80770383195412876 0, -86.75889269456294528 48.80768857689155027 0, -86.75875766159465741 48.80765907199934617 0, -86.75861072775650484 48.80765827592806971 0, -86.75848030520022292 48.80762424641632435 0, -86.75837029374332587 48.80758328139994262 0) | R4458 | ANWIN | C | Temp | WF6 | C189 | 0.16656 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.17 | 0.17 | All-season | 0.16634 | 0.00022017 | C186-C188 | 4 | R1818 | ANWIN | 0.29042
LineStringZ (-86.75267175087040528 48.80726636044393274 0, -86.75263535058140008 48.8072789953885362 0, -86.75248984019579268 48.80729777061452523 0, -86.75234407889061572 48.80732488614493292 0, -86.75220007799133271 48.80736038318570991 0, -86.75206873360279758 48.80740028109038064 0, -86.75192062522881997 48.80742571959305565 0, -86.75177486366045798 48.80743812605599175 0, -86.75163706534767982 48.80745191417476292 0, -86.75152181430260612 48.80750287603931525 0, -86.75140706605708374 48.80755291589014178 0, -86.75130414400223344 48.80760146892527729 0) | R4459 | ANWIN | C | Temp | WF6 | C191 | 0.10875 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.11 | 0.11 | All-season | 0.10862 | 0.00012853 | C186-C188 | 4 | R2003 | ANWIN | 0.010184
LineStringZ (-86.74671981032487622 48.80734127995312832 0, -86.74671009692504242 48.80731855827701793 0, -86.74674924060462899 48.80722581256397774 0, -86.74677572736091236 48.80713365255574843 0, -86.74669391987272604 48.8070535223741544 0, -86.74663482740535869 48.80696521888035733 0, -86.74660167144229206 48.80692187556741146 0) | R4460 | ANWIN | C | Temp | WF6 | C193 | 0.050629 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd W - ML - WF6 | 0.05 | 0.05 | All-season | 0.050629 | 0 | C186-C188 | 4 | R2008 | ANWIN | 0.10247
LineStringZ (-86.6846827029317808 48.81163498839284642 0, -86.68478373976178375 48.81158566385239084 0, -86.68492371642182093 48.81155351993895408 0, -86.68504416480199382 48.81150792216292444 0, -86.68517844324242105 48.81148692542227963 0, -86.68523466525603283 48.81146993540648538 0) | R4461 | AU2 | C | Temp | WF6 | C203 | 0.044968 | 4 | 8 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.04 | 0.04 | All-season | 0.044968 | 0 | C186-C188 | 4 | R2009 | ANWIN | 0.0038076
LineStringZ (-86.66222819606257133 48.80209999969869727 0, -86.66224889947704924 48.8021718228439525 0, -86.66229516847911896 48.80226268344576823 0, -86.662284019702156 48.80235836227495128 0, -86.66229868854377116 48.80245014413010551 0, -86.66231603340906986 48.80251778779747696 0) | R4462 | ANWIN | C | Temp | WF6 | C211 | 0.047337 | 4 | 8 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C211 | ANWIN | Required | Middleton Road - ML - WF6 | 0.05 | 0.05 | All-season | 0.047337 | 0 | C189-C195 | 5 | R2009 | ANWIN | 0.0081273
LineStringZ (-86.64419099189700546 48.80147180477517566 0, -86.64423366973609575 48.80143937205696858 0, -86.64430357448424047 48.80135349922709764 0, -86.64435671578125664 48.80127026712288085 0, -86.64436736084587665 48.80117781438040225 0, -86.64433844299206555 48.801086954200386 0, -86.6443467556290301 48.80106861191285361 0) | R4463 | ANWIN | C | Temp | WF6 | C213 | 0.048414 | 4 | 8 | Little Pie River Rd - ML - WF6 | Little Pie River Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | 0 | Little Pie River Rd - ML - WF6 | 0.05 | 0.05 | All-season | 0.048414 | 0 | C189-C195 | 5 | R2013 | ANWIN | 0.041151
LineStringZ (-86.60953570915241073 48.79707269625555455 0, -86.60956736360647312 48.79713924766475941 0, -86.60963643107075427 48.79722394558710619 0, -86.60970859897429364 48.79731149578935145 0, -86.60978554458969825 48.79738596759555946 0, -86.60985620369990556 48.79746744121960944 0, -86.60994195130369633 48.7975423178422858 0) | R4464 | ANWIN | C | Temp | WF6 | C221 | 0.06043 | 4 | 8 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C221 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.06 | 0.06 | All-season | 0.06043 | 0 | C189-C195 | 5 | R2015 | ANWIN | 0.022863
LineStringZ (-86.60769480699396183 48.79725982187483169 0, -86.6077007130973584 48.79725713868878501 0, -86.60784303848366505 48.79721837270245999 0, -86.60796390510141407 48.79717277489137928 0, -86.60809592042765814 48.79712881164265781 0, -86.60821821249528796 48.79707881398728375 0, -86.60834109111829093 48.7970345990011225 0, -86.60844393681956888 48.79697303458856794 0, -86.60846844586143334 48.79693852656238562 0) | R4465 | ANWIN | C | Temp | WF6 | C221 | 0.068178 | 4 | 8 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C221 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.07 | 0.07 | All-season | 0.068178 | 0 | C189-C195 | 5 | R4455 | ANWIN | 0.0012369
LineStringZ (-86.60657393618475908 48.79670033710605281 0, -86.60658047217440014 48.79671809855638998 0, -86.60665766833415091 48.79679621758288732 0, -86.60673888910788776 48.79686868013130407 0, -86.60682513975838503 48.79694432635766077 0, -86.60692806869430171 48.79701418921442979 0, -86.60700157855805514 48.79709054841895721 0, -86.60707081372039795 48.79717256585825425 0, -86.60709475098680343 48.7971843790905524 0) | R4466 | ANWIN | C | Temp | WF6 | C221 | 0.066484 | 4 | 8 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C221 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.07 | 0.07 | All-season | 0.066484 | 0 | C189-C195 | 5 | R4458 | ANWIN | 0.00022017
LineStringZ (-86.4965131449296365 48.78282220859374974 0, -86.49658010936904873 48.78285707633855139 0, -86.49668882174655948 48.78291348556868456 0, -86.49680457634448771 48.78296444867381609 0, -86.49692116880065385 48.78301482428174296 0, -86.49703197725824566 48.78307760430829632 0, -86.49711361785273311 48.78312031013024352 0, -86.49720866156066279 48.78313593612082144 0) | R4473 | ANWIN | C | Temp | WF6 | C243 | 0.062433 | 4 | 8 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C243 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.06 | 0.06 | All-season | -4.2e-10 | 0.062433 | C189-C195 | 5 | R4459 | ANWIN | 0.00012853
LineStringZ (-86.46297134084474578 48.7795297477542249 0, -86.462977163980824 48.77952631142093054 0, -86.4630584359528882 48.77947833289188395 0, -86.46318114666250665 48.77943726194493479 0, -86.46332724406356363 48.77944061413715104 0, -86.4634555712027435 48.77948034516896314 0, -86.46357358810973892 48.77952933714790618 0, -86.46369873058091571 48.7795776163922099 0, -86.46377211470976931 48.77961631774204676 0) | R4474 | ANWIN | C | Temp | WF6 | C251 | 0.067617 | 4 | 8 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C251 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.07 | 0.07 | All-season | 0.067617 | 0 | C189-C195 | 5 | R2011 | ANWIN | 0.11265
LineStringZ (-86.40815719801834405 48.77431635867688442 0, -86.40817363178199173 48.77430406182458711 0, -86.40828930169131183 48.77425427344884667 0, -86.40839223173986738 48.77417565024404666 0, -86.40844168477543974 48.77407762420750714 0, -86.40847370387918147 48.7739839985914827 0, -86.40852240312635502 48.77388534342427562 0, -86.40854531530578697 48.77385126078286248 0) | R4478 | AU2 | C | Temp | WF6 | C264 | 0.061363 | 4 | 8 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.06 | 0.06 | All-season | 0.061363 | 0 | C189-C195 | 5 | R2017 | ANWIN | 0.015396
LineStringZ (-86.43168539221284163 48.77620872089368476 0, -86.43178596448983342 48.77616547089441923 0, -86.43192024176470056 48.77614912673173109 0, -86.43204823429458372 48.77618252825555345 0, -86.43216180889672273 48.77624053110413627 0, -86.43218665193565187 48.77626189671590851 0) | R4384 | ANWIN | C | Temp | WF6 | C258 | 0.042498 | 4 | 8 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C258 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.04 | 0.04 | All-season | 0.042498 | 0 | C189-C195 | 5 | R5837 | ANWIN | 0.08129
LineStringZ (-86.41979165743080671 48.77486247904511174 0, -86.41979271425459785 48.77486053492552998 0, -86.41973554981187533 48.77477105868258178 0, -86.41967419349745683 48.77468866456880647 0, -86.41962884747104567 48.77460073842041055 0, -86.41957176637296811 48.77451034041800426 0, -86.41952499633524098 48.77441952112713608 0, -86.41952123040336176 48.77441207143762369 0) | R4385 | ANWIN | C | Temp | WF6 | C261 | 0.053988 | 4 | 8 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C261 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.05 | 0.05 | All-season | 0.053988 | 0 | C197-C202 | 6 | R1823 | ANWIN | 0.0059395
LineStringZ (-86.41761695007245692 48.77400488227622333 0, -86.41755114040896046 48.77400981419138049 0, -86.41743303977894186 48.77405972821047442 0, -86.41729716942120376 48.77409866257041671 0, -86.41715710754661472 48.77411060636724471 0, -86.4170242541650282 48.77413286082540367 0, -86.41699144388441312 48.77413584976632421 0) | R4386 | ANWIN | C | Temp | WF6 | C261 | 0.048927 | 4 | 8 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C261 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.05 | 0.05 | All-season | 0.040398 | 0.0085281 | C197-C202 | 6 | R1828 | ANWIN | 0.034336
LineStringZ (-86.40237326769093329 48.76557233908462052 0, -86.4024829037092843 48.76562732376160625 0, -86.40260946965788946 48.76566914941016506 0, -86.40272539147514408 48.76572577043305046 0, -86.40284315817858385 48.7657812997814446 0, -86.40295016035118181 48.7658149524274549 0, -86.40297735190179651 48.76582350279866773 0, -86.40307583913754286 48.76588749806886369 0, -86.40319427524555351 48.76594344704021466 0, -86.40332612275341262 48.76596964072663809 0, -86.40345260624008006 48.76601511291541158 0, -86.40358612995618159 48.76604998177268158 0, -86.40370448281947802 48.76610396145091642 0, -86.40382234024711749 48.76615578568967635 0) | R4388 | ANWIN | C | Temp | WF6 | C265 | 0.12572 | 4 | 8 | Hare Lake Creek Rd - ML - WF6 - BR1 | Hare Lake Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corp. |  | WF6 | C265 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR1 | 0.13 | 0.13 | All-season | -1.2e-10 | 0.12572 | C197-C202 | 6 | R4346 | ANWIN | 0.03135
LineStringZ (-86.47348008422427768 48.78063506804903682 0, -86.47347169713295045 48.78062275557660143 0, -86.47344202471749952 48.78052921443338619 0, -86.47337279001891375 48.7804502135938165 0, -86.47329727003111088 48.78037427411879889 0, -86.47321730654368821 48.78029644941073428 0, -86.47312854163338613 48.7802160241471725 0, -86.4730765380131885 48.7801760519253591 0) | R4502 | ANWIN | C | Temp | WF6 | C250 | 0.059759 | 4 | 8 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C250 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.06 | 0.06 | All-season | 0.059759 | 0 | C197-C202 | 6 | R4350 | ANWIN | 0.018177
LineStringZ (-86.47148050137707287 48.78000887694204835 0, -86.47140631166288927 48.78002864639975655 0, -86.47131218317031198 48.78009762969663399 0, -86.47120883328008745 48.78015743425875428 0, -86.47114622160725617 48.78023928417344734 0, -86.47107204177765993 48.78032595230641277 0, -86.47102461930140294 48.7803779079403057 0) | R4503 | ANWIN | C | Temp | WF6 | C250 | 0.054303 | 4 | 8 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C250 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.05 | 0.05 | All-season | 0.054303 | 0 | C197-C202 | 6 | R1829 | ANWIN | 0.13216
LineStringZ (-86.75641941511710797 48.80760114725502063 0, -86.75631022868677178 48.8076041712139741 0, -86.75592373969796256 48.80750304440717713 0, -86.75564738871923964 48.80746733613153765 0, -86.75551956456257585 48.80742966002609506 0) | R4504 | ANWIN | C | Temp | WF6 | C191 | 0.0695 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.07 | 0.07 | All-season | 0.0695 | 0 | C203-C207 | 7 | R1833 | ANWIN | 0.070791
LineStringZ (-86.75668473228847688 48.80748410018512118 0, -86.75644702185624624 48.80759780062668796 0, -86.75641941511710797 48.80760114725502063 0) | R4505 | ANWIN | C | Temp | WF6 | C191 | 0.02361 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.02 | 0.02 | All-season | 0.02361 | 0 | C203-C207 | 7 | R4351 | ANWIN | 0.0026648
LineStringZ (-86.75628929469476702 48.80788115212229172 0, -86.75630302081721368 48.80778806966917216 0, -86.75639105342293078 48.80768021642244747 0, -86.75641941511710797 48.80760114725502063 0) | R4506 | ANWIN | C | Temp | WF6 | C191 | 0.03305 | 4 | 8 | Del Lake Rd W - ML - WF6 - SP1 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - SP1 | 0.03 | 0.03 | All-season | 0.03305 | 0 | C203-C207 | 7 | R1832 | ANWIN | 0.021657
LineStringZ (-86.73890543984650492 48.80689734006991642 0, -86.73892288765728154 48.80686480441532638 0, -86.73894800572641373 48.80677352289498572 0) | R4508 | ANWIN | C | Temp | WF6 | C195 | 0.01415 | 4 | 8 | Del Lake Rd E - ML - WF6 - BR2 | Del Lake Rd E - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR2 | 0.01 | 0.01 | All-season | 0.01415 | 0 | C203-C207 | 7 | R5809 | ANWIN | 0.041673
LineStringZ (-86.47819607386777818 48.78603775894247008 0, -86.47812734393845346 48.78600657798609319 0, -86.478027934819508 48.78594224722668571 0, -86.47792927957470965 48.78587862868025127 0, -86.47783037207813095 48.7858015571831487 0, -86.47776097049717237 48.78571379890277626 0, -86.47774408217752296 48.78569403822736206 0) | R4509 | ANWIN | C | Temp | WF6 | C249 | 0.051234 | 4 | 8 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.05 | 0.05 | All-season | 0.051234 | 0 | C208-C209 | 8 | R1739 | ANWIN | 0.082294
LineStringZ (-86.49324634725003591 48.78282764791057247 0, -86.49329540762630586 48.78278402877354836 0, -86.49339288964216621 48.78270720860012943 0, -86.49347654073307012 48.78263281855526401 0, -86.493563629253714 48.78255486764107474 0, -86.49367142040885881 48.78249824717617145 0, -86.49368674270655788 48.78246471530822248 0) | R4510 | ANWIN | C | Temp | WF6 | C246 | 0.052269 | 4 | 8 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C246 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.05 | 0.05 | All-season | 0.052269 | 0 | C208-C209 | 8 | R1953 | ANWIN | 0.069839
LineStringZ (-86.65369302434615406 48.80160873000490795 0, -86.65370748663563916 48.80162218011810182 0, -86.65381083572222565 48.80168931966755963 0, -86.65392650553644671 48.80174296440607407 0, -86.6540575986486914 48.80177334770933584 0, -86.65419087044067226 48.80181844217926823 0, -86.65431014537408316 48.80186261561513561 0, -86.65444425564618314 48.80189752619158838 0, -86.65458356394105977 48.80190628476920978 0, -86.65472731252687311 48.80190699700721524 0, -86.65486796190604935 48.80193704637402874 0, -86.65500291039052172 48.80195724683319014 0, -86.65513417115637651 48.8019905647902732 0, -86.65526979029790766 48.80201348911743509 0, -86.65539685974765405 48.80205296816022553 0, -86.65552275590148668 48.80209835659383089 0, -86.65566130921732224 48.80210372103856287 0, -86.65580556091472886 48.80209010018822369 0, -86.65595735825984036 48.80209420840601808 0, -86.65609783786088371 48.80211700592799673 0, -86.65631417585090901 48.8020812148632146 0, -86.65642640974752453 48.8020209491278294 0, -86.65656010068435933 48.8019743445922245 0, -86.65666378483312826 48.80191345132217862 0, -86.65673586872730993 48.80186902720248554 0, -86.65678314055956832 48.80178666610941463 0) | R4511 | ANWIN | C | Temp | WF6 | C212 | 0.25596 | 4 | 8 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 | 0.26 | 0.26 | All-season | 0.25596 | 0 | C210-C214 | 10 | R1740 | ANWIN | 0.055841
LineStringZ (-86.65610884709774098 48.80212033938670402 0, -86.65623940818498738 48.80216235217937282 0, -86.65624260603070184 48.80216828464897816 0) | R4512 | ANWIN | C | Temp | WF6 | C212 | 0.011364 | 4 | 8 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 | 0.01 | 0.01 | All-season | 0.011364 | 0 | C210-C214 | 10 | R1842 | ANWIN | 0.076515
LineStringZ (-86.74389029545409358 48.80676789765851709 0, -86.74390215872193721 48.806849045736314 0, -86.7438950345618025 48.80693915115936932 0, -86.74394406825724957 48.80702372469475137 0, -86.743964687539588 48.80711424978017732 0, -86.74392160149676556 48.80718237292449402 0) | R4513 | ANWIN | C | Temp | WF6 | C194 | 0.047543 | 4 | 8 | Del Lake Rd W - ML - WF6 - SP2 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C194 | ANWIN | Required | Del Lake Rd W - ML - WF6 - SP2 | 0.05 | 0.05 | All-season | 0.047543 | 0 | C210-C214 | 10 | R5843 | ANWIN | 0.013387
LineStringZ (-86.76822816201446642 48.80751459400621428 0, -86.76820859550858245 48.80752596689976741 0, -86.76812083734287739 48.80759935101657021 0, -86.76802821699536139 48.80767503903435767 0, -86.76794255405221179 48.80775793592692935 0, -86.76782445385019571 48.80780877340617252 0, -86.76774398667599542 48.80788538256454956 0, -86.76768531421264186 48.80797008244933721 0, -86.7676551386950905 48.8080578830670504 0, -86.7676612575792916 48.8080553261628225 0, -86.76765580174297554 48.8080838754399764 0) | R5836 | ANWIN | C | Temp | WF6 | C188 | 0.079092 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.08 | 0.08 | All-season | 0.079092 | 0 | C244-C247 | 14 | R2045 | ANWIN | 0.062463
LineStringZ (-86.76264236383248374 48.80944721729875369 0, -86.7625271734104615 48.80940049630537203 0, -86.76238836914728836 48.8093897264247758 0, -86.76228275588277938 48.80932790907106522 0, -86.76214940042127921 48.80929542857338532 0, -86.76202040338242227 48.80925377117788599 0, -86.76188059295530763 48.80922577590567357 0, -86.76176542542837922 48.80917246557891787 0, -86.76163257183972632 48.80912678579518627 0, -86.7615396160395278 48.80905398831204423 0, -86.76144632600083639 48.8089853830630247 0, -86.76134934711167546 48.80891350817735486 0, -86.76126292988287503 48.80884238735151825 0, -86.76116385527140551 48.80877197970123405 0, -86.76106461408404869 48.8087025773642651 0, -86.76097056874759517 48.80863497770383219 0, -86.76093217944018932 48.80854223193782815 0, -86.76087459646475963 48.80845996258413777 0, -86.76082983702777085 48.80837304282396616 0, -86.76076118921615432 48.80829173820627886 0, -86.76065834336228022 48.80821940255587776 0, -86.76053940353249061 48.80816705741981565 0, -86.76043169669247845 48.80811001894031165 0, -86.76042716315338055 48.80810763459314927 0) | R5837 | ANWIN | C | Temp | WF6 | C189 | 0.23016 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.23 | 0.23 | All-season | 0.14887 | 0.08129 | C244-C247 | 14 | R2046 | ANWIN | 0.026596
LineStringZ (-86.7448286660554686 48.80518893431890604 0, -86.74472760787058689 48.80521046723776379 0, -86.74459031339188186 48.80524466612516932 0, -86.74445947158486092 48.80527131986952583 0, -86.74431739798478702 48.80530040534284808 0, -86.74417909609073263 48.80533255043255281 0, -86.74403995739928064 48.80533908656975939 0, -86.74391883870576692 48.80538585910764482 0, -86.74378053642308828 48.80540702328015357 0, -86.74364357629528399 48.80542642706832623 0, -86.74350711847402806 48.8054418502107481 0, -86.74338180943790633 48.80549964367496329 0, -86.74325096867858065 48.80552583635715536 0) | R5838 | ANWIN | C | Temp | WF6 | C193 | 0.12299 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd W - ML - WF6 | 0.12 | 0.12 | All-season | 0.12299 | 0 | C244-C247 | 14 | R4375 | ANWIN | 0.00091259
LineStringZ (-86.68443774826563697 48.81249671027102011 0, -86.68444527826133594 48.81246865458692241 0, -86.684461203224771 48.81237519808195202 0, -86.68451853581019861 48.8122853858054242 0, -86.68454133420725327 48.81219314275669774 0, -86.68453068988500831 48.81210081628246655 0, -86.68452901282944367 48.81200903431121674 0, -86.68457192863729688 48.8119203124369534 0, -86.68460906005560673 48.81181935194851462 0, -86.68461467596459613 48.81172769517957022 0, -86.68467376901770649 48.81163935037127288 0, -86.6846827029317808 48.81163498839284642 0) | R5839 | AU2 | C | Temp | WF6 | C203 | 0.098995 | 7.5 | 15 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.1 | 0.1 | All-season | 0.098995 | 0 | C244-C247 | 14 | R4472 | ANWIN | 0.035232
LineStringZ (-86.68363932311983433 48.81501577997767782 0, -86.68367464602854966 48.81496499685277968 0, -86.68375544714156433 48.81488000373639125 0, -86.68381101892094875 48.81479727490801679 0, -86.6838748059000892 48.81470800695193191 0, -86.68396943685084466 48.81463135484705873 0, -86.68406465647322534 48.81455830624603465 0, -86.68416247269182406 48.81449188028426533 0, -86.68426431308476765 48.814417323047536 0, -86.68433983431238232 48.81433488698881007 0, -86.68439934593075691 48.81424813398495388 0, -86.68440269743754811 48.81415232934041626 0, -86.68439867467952809 48.81406167896278703 0, -86.68437134928373666 48.81396310774026404 0, -86.68436791382008266 48.81386700923359001 0, -86.68433421820660101 48.81376600694939327 0, -86.68429071599589975 48.81367489580704699 0, -86.6843044615152678 48.81358546085103001 0, -86.68431410101767653 48.8134874343314209 0, -86.68433933026535954 48.81339846082142486 0, -86.68438199411322387 48.81330542120231542 0, -86.68441292422946276 48.81321569323040421 0, -86.68444351847071516 48.81312412106363752 0, -86.68442901711794946 48.81302412490286713 0, -86.68442935197613508 48.81292714610663097 0, -86.68443077782724515 48.81283603474167165 0, -86.68442214402632828 48.81274609679314835 0, -86.6844080629740148 48.81265620060410271 0, -86.68442113873813071 48.81255859368174299 0, -86.68443774826563697 48.81249671027102011 0) | R5840 | AU2 | C | Temp | WF6 | C203 | 0.3 | 7.5 | 15 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0 | C244-C247 | 14 | R4473 | ANWIN | 0.062433
LineStringZ (-86.68536758841318601 48.80651597413443454 0, -86.68536711952926055 48.80650602064732624 0, -86.68537005264555262 48.80641008966163952 0) | R5841 | AU2 | C | Temp | WF6 | C203 | 0.011773 | 7.5 | 15 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.01 | 0.01 | All-season | 0.011773 | 0 | C244-C247 | 14 | R1751 | ANWIN | 0.087782
LineStringZ (-86.6862915134519767 48.80905189290877644 0, -86.68627060531206041 48.80900257066911507 0, -86.68620413625758658 48.80892151809143087 0, -86.68614856384208167 48.80883602236337993 0, -86.68613708117933925 48.80873493615936098 0, -86.68614169140170134 48.80863762258512395 0, -86.68609089655869582 48.8085515820846183 0, -86.68606156078791969 48.80845623793372567 0, -86.68599433744981297 48.80837204179161404 0, -86.68601906451823425 48.80827447625100035 0, -86.68602442775558359 48.80818114362720905 0, -86.6860066581108839 48.80809191940831226 0, -86.68604479668302076 48.80799996876850599 0, -86.68605795628309352 48.80790349440100329 0, -86.68606373968994205 48.80781112457940907 0, -86.68604429345300844 48.80770991320633811 0, -86.68601319652101722 48.80761708399416676 0, -86.68594454816967243 48.80753728833938965 0, -86.68589610167765613 48.80745229586314338 0, -86.68587129101682365 48.80736223199624391 0, -86.68586760310492423 48.80726646918565592 0, -86.68583223168072038 48.80717493807716778 0, -86.6858137071544661 48.80708043203902946 0, -86.68576785852897615 48.80698781262922381 0, -86.68567817196297653 48.80691262744707615 0, -86.68563601119713269 48.80682055059727276 0, -86.68555026341535097 48.80674695844017208 0, -86.68546283999569368 48.80666934226056952 0, -86.68537156194928173 48.80660031740936233 0, -86.68536758841318601 48.80651597413443454 0) | R5842 | AU2 | C | Temp | WF6 | C203 | 0.3 | 7.5 | 15 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0 | C248-C256 | 16 | R1756 | ANWIN | 0.10194
LineStringZ (-86.6599912706109734 48.80094238065368017 0, -86.66009902420812239 48.80095485467014527 0, -86.66023841614220657 48.80092618890557077 0, -86.66037713689168243 48.80091562714478925 0, -86.660496578731113 48.80087199959464073 0, -86.66063169529985544 48.80082803664166136 0, -86.66077997146281575 48.80080108941586303 0, -86.66091751787847386 48.80079174339990544 0, -86.66105783040299571 48.80076596795207422 0, -86.66118984636582923 48.80081244591443834 0, -86.66131121643984159 48.80085909125600097 0, -86.66144457250288724 48.80089186483357366 0, -86.66165068361145529 48.80096667311052983 0, -86.66173056272087649 48.80103959572940653 0, -86.66180038435450683 48.80111792413692484 0, -86.66186316426919234 48.80120174366331298 0, -86.66196257433539074 48.80126946887479278 0, -86.66203943597480475 48.80135039691784726 0, -86.66208620721974398 48.80143484407810917 0, -86.66210087543289831 48.80152541061897864 0, -86.6621206570381446 48.80162067093822742 0, -86.66211353169789788 48.80171236915289512 0, -86.66213004442529666 48.80180934800724657 0, -86.66217178620048855 48.80189920134242243 0, -86.66220464416295499 48.80199060741664852 0, -86.66222299927139261 48.80208196918394492 0, -86.66222819606257133 48.80209999969869727 0) | R5843 | ANWIN | C | Temp | WF6 | C211 | 0.2679 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C211 | ANWIN | Required | Middleton Road - ML - WF6 | 0.27 | 0.27 | All-season | 0.25452 | 0.013387 | C248-C256 | 16 | R2049 | ANWIN | 0.00793
LineStringZ (-86.64422708394096162 48.7985976026974555 0, -86.6442282214377002 48.79856961708933483 0, -86.64422830532870989 48.79847938610603819 0, -86.64429167157723555 48.79839267532865676 0, -86.64434523306448455 48.79830831099528154 0, -86.64443416460765945 48.79823551479677235 0, -86.64455821636758515 48.79819402391044747 0, -86.6446714555166011 48.79814084079946213 0, -86.64475334759910652 48.79806670294593829 0, -86.64482249840412464 48.79798267430145842 0, -86.6448184741106644 48.79789189808988681 0, -86.64481746939362949 48.79779408104932514 0, -86.64485317596538039 48.79770628077237404 0, -86.64496440343265249 48.79765334935594723 0, -86.64503288371084011 48.797568692395906 0, -86.64512810223541805 48.79750385844572946 0, -86.64518803305014671 48.79742079344315187 0, -86.64521569292328707 48.79733081374758541 0, -86.64523421766963907 48.79724095975956288 0, -86.64524922117081474 48.79715089611942602 0, -86.64526170971967645 48.79706062322676274 0, -86.64524150919579881 48.79696775245058404 0, -86.6451629712891247 48.7968896740735687 0, -86.64514277046883706 48.79680074170710213 0, -86.64511393605725686 48.79671210301096096 0, -86.64503165964201514 48.79652305057027206 0) | R5844 | ANWIN | C | Temp | WF6 | C213 | 0.26098 | 10 | 20 | Little Pie River Rd - ML - WF6 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | 0 | Little Pie River Rd - ML - WF6 | 0.26 | 0.26 | All-season | 0.26098 | 0 | C248-C256 | 16 | R1899 | ANWIN | 0.020195
LineStringZ (-86.40779600289720008 48.77452024260064434 0, -86.40785897480999722 48.77449495894336451 0, -86.40798344662606212 48.77444026737904181 0, -86.40807975413608233 48.77437430204150814 0, -86.40815719801834405 48.77431635867688442 0) | R5847 | AU2 | C | Temp | WF6 | C264 | 0.03518 | 7.5 | 15 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.04 | 0.04 | All-season | 0.03518 | 0 | C248-C256 | 16 | R1908 | ANWIN | 0.032691
LineStringZ (-86.40729314515344583 48.76977049173473944 0, -86.40738665444078492 48.76975947655595434 0, -86.40753082358909865 48.76972900871651007 0, -86.40766267025142611 48.76969313371607484 0, -86.40779569120402925 48.76965968993163614 0, -86.40794438592755 48.76964615378882684 0, -86.40809056635987417 48.76966543199583981 0, -86.40823423190360586 48.76967637036835157 0, -86.40838250891239625 48.76969015879021185 0, -86.40850538755616128 48.7696509307446604 0, -86.4086368986127269 48.76960508169555908 0, -86.40876857852254034 48.76957520043639249 0, -86.40888953024089858 48.76951677893719506 0, -86.40899254383414529 48.76944624481357238 0, -86.40908927064566569 48.76937608858320772 0, -86.40919831896906089 48.76931150641053847 0, -86.40927970772186484 48.76922869222570966 0, -86.40937115448750205 48.76915774043164475 0, -86.40947735266904317 48.76909265400240656 0, -86.40951716582355857 48.7690746041242349 0) | R5848 | AU2 | C | Temp | WF6 | C264 | 0.19258 | 7.5 | 15 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.19 | 0.19 | All-season | 0.19258 | 0 | C248-C256 | 16 | R5822 | ANWIN | 0.0026
LineStringZ (-86.40855346862123554 48.77160543400572124 0, -86.40849298180795302 48.77152910615819792 0, -86.40843464445789834 48.77143514538020952 0, -86.40838644874085617 48.77133452018873072 0, -86.40833699519778577 48.77124517045017882 0, -86.4082602169412155 48.77117010914347617 0, -86.40812116035924362 48.77112748704166023 0, -86.40798319506428982 48.77110967605567993 0, -86.40782670405057786 48.77109546888928548 0, -86.40770164639148732 48.77104144735800162 0, -86.40766417986608872 48.77094983255210536 0, -86.40765718803828577 48.77069534183524269 0, -86.40759371991421744 48.77058076590738978 0, -86.40711759466219632 48.77037110455963642 0, -86.40700418824613394 48.77031775392958934 0, -86.40689790515527591 48.77025459457870227 0, -86.40679137090373274 48.77018770857550578 0, -86.40672364615845424 48.77009584234185979 0, -86.40669363840899564 48.77000644983696276 0, -86.40673529609219372 48.76991307486820659 0, -86.4068563315913849 48.76986907029093032 0, -86.4069783714669768 48.76982770569505732 0, -86.40711767844562985 48.76979815973724186 0, -86.40725002926801324 48.76977556955789339 0, -86.40729314515344583 48.76977049173473944 0) | R5849 | AU2 | C | Temp | WF6 | C264 | 0.3 | 7.5 | 15 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0 | C257-C261 | 17 | R1920 | ANWIN | 0.046332
LineStringZ (-86.42134782645106839 48.7756196008827132 0, -86.42122392498619377 48.77564416042805107 0, -86.42108964610723376 48.77562731206872826 0, -86.42094472290435192 48.77562613873188724 0, -86.4206148113806023 48.77557031472152715 0, -86.4204733246152017 48.77555464117382655 0, -86.42033410185371167 48.77555619184234104 0, -86.42019186095194527 48.77556252024388783 0, -86.42007300499872713 48.77560820142396381 0, -86.41994476168402173 48.7756474714448558 0, -86.41981090300953383 48.77561356543847637 0, -86.41970051334872949 48.77555715512913537 0, -86.41965189751496723 48.77546612780164992 0, -86.41965365770602148 48.7753757706436204 0) | R5853 | ANWIN | C | Temp | WF6 | C259 | 0.14851 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C259 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.15 | 0.15 | All-season | 0.14851 | 0 | C257-C261 | 17 | R4386 | ANWIN | 0.0085281
LineStringZ (-86.42464447504367797 48.77636752641830498 0, -86.4246286545376563 48.77635825529891633 0, -86.42453067069506289 48.77629451143111794 0, -86.42445003629669031 48.77622037284763934 0, -86.42433998212742097 48.77615738357857822 0, -86.42424040491266624 48.77609259156161414 0, -86.42415910052388028 48.77601723765913277 0, -86.42407771162291397 48.7759432245835427 0, -86.42399188061715165 48.77587311061755315 0, -86.42390864840578502 48.77580119417802251 0, -86.42378610575650555 48.775758949763798 0, -86.42366875930956382 48.7757076101292455 0, -86.42354412014211107 48.77566746094306893 0, -86.42343901042801235 48.7756081587182635 0, -86.42332660930658506 48.77555719701637571 0, -86.42319065497598274 48.77555028243469337 0, -86.42304724045743569 48.77557639165398484 0, -86.42294389113349951 48.77564382395073039 0, -86.4228892417485639 48.77572693090988309 0, -86.42275647227791069 48.77576427243519674 0, -86.42261825476452941 48.77577022365930759 0, -86.4224881669891829 48.77580727244503578 0, -86.42234735134253754 48.77580987010004776 0, -86.42223050698626707 48.7757573566350473 0, -86.42210544912336445 48.77571796215844557 0, -86.42198106210300068 48.77567290970888791 0, -86.42188467050000611 48.77560698642842141 0, -86.42174787762523636 48.77559416094486267 0, -86.42161326390532849 48.77561012903068871 0, -86.42148703212555461 48.77565011075214585 0, -86.42135946040713179 48.77561729513633537 0, -86.42134782645106839 48.7756196008827132 0) | R5854 | ANWIN | C | Temp | WF6 | C259 | 0.3 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C259 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.3 | 0.3 | All-season | 0.3 | 0 | C263 | 18 | R1922 | ANWIN | 0.1338
LineStringZ (-86.41174952872360393 48.76999228392547536 0, -86.41176200957957576 48.76992497718357811 0, -86.4117506097984176 48.76983239922184055 0, -86.41177340851118061 48.76974267123179629 0, -86.41174256329006198 48.76965000841009612 0, -86.41164474632985559 48.76958659977822208 0, -86.41156679489409953 48.76950877378171612 0, -86.41151247904660693 48.76942617007738079 0, -86.41146939661443582 48.76933237686024825 0, -86.41137543584264336 48.76926247185436125 0, -86.41130762623508588 48.76918284339089382 0, -86.41124157574411413 48.76910200041107402 0, -86.41120117586557114 48.76901466015817022 0, -86.41109279701332468 48.76895896157205357 0, -86.41097888814316264 48.76890473156162642 0, -86.41091912435960865 48.76881588255869104 0, -86.41080605310057194 48.76875268400431196 0, -86.41065978800057223 48.76875054716402502 0, -86.41052190611203798 48.76873353128164723 0, -86.41041059355502796 48.76867372744333551 0, -86.4103136155098781 48.768603947362692 0, -86.41024563776370826 48.76851216644708131 0) | R5800 | ANWIN | C | Temp | WF6 | C263 | 0.21638 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C263 | ANWIN | Required | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.22 | 0.22 | All-season | 0.089356 | 0.12702 | C263 | 18 | R2055 | AU2 | 0.059783
LineStringZ (-86.40895448006685342 48.76844484767726584 0, -86.40905423425579102 48.76848232575611775 0, -86.40917434623771953 48.76852561880263437 0, -86.40928037830036601 48.76858412383303687 0, -86.40936059270806879 48.76865922639569817 0, -86.40938833655370388 48.76874773940207319 0, -86.40942161312109704 48.76883922695598272 0, -86.40944416041969589 48.76893662479627523 0, -86.4094957098338341 48.76902258163161719 0, -86.40951716582355857 48.7690746041242349 0) | R5801 | ANWIN | C | Temp | WF6 | C264 | 0.086587 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR1 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR1 | 0.09 | 0.09 | All-season | 0.032616 | 0.053971 | C263 | 18 | R2056 | AU2 | 0.0058641
LineStringZ (-86.73090842520687715 48.80514425610509477 0, -86.73100927874016008 48.80519135762215654 0, -86.73112997825667492 48.80523636880754879 0, -86.73123735013298585 48.80529215021339695 0, -86.73136777285294841 48.80532131858558387 0, -86.73160523250443532 48.80524919265138806 0) | R5806 | ANWIN | C | Temp | WF6 | C197 | 0.058579 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | Required | Ripple Lake RD - ML - WF6 | 0.06 | 0.06 | All-season | 0.058579 | 0 | C263 | 18 | R1759 | ANWIN | 0.06213
LineStringZ (-86.71535364247191069 48.80586952261793954 0, -86.71548255294331398 48.80584879307469492 0, -86.71562378712948771 48.80585554039338092 0, -86.71577097414413515 48.80586182723165933 0, -86.71590927529526027 48.80586174445007686 0, -86.71603366301503968 48.80582188767812113 0, -86.7161655104994793 48.80585042815507535 0, -86.71630314117319926 48.805863210138277 0, -86.71644236454662291 48.80587347791231423 0, -86.71658628103988065 48.8058644256886538 0, -86.71672408060454984 48.80587360381222339 0, -86.71686137634594616 48.80587624408593683 0, -86.71686950727205101 48.80587401057510988 0) | R5807 | ANWIN | C | Temp | WF6 | C200 | 0.11347 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C200 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.11 | 0.11 | All-season | 0.11347 | 0 | C263 | 18 | R5800 | ANWIN | 0.12702
LineStringZ (-86.7100949720162788 48.80564283484395105 0, -86.71017672229037032 48.80565077242118832 0, -86.71031493973860904 48.80566015896832965 0, -86.71045634268416791 48.80567168358913221 0, -86.71059699122305631 48.80566095559044726 0, -86.71074132771326504 48.80565709967530097 0, -86.71087904187436379 48.80564176074783234 0, -86.71102304348239898 48.80563928811483976 0, -86.71115178884795682 48.8055998514491165 0, -86.71127961324623357 48.80556707832253949 0, -86.71141799898070701 48.80557537635981191 0, -86.71143117585846483 48.80557577008413972 0) | R5808 | ANWIN | C | Temp | WF6 | C201 | 0.10023 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C201 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.1 | 0.1 | All-season | 0.10023 | 0 | C262 | 19 | R1921 | ANWIN | 0.045705
LineStringZ (-86.69428978667822605 48.80457225924814679 0, -86.69420500084500247 48.80456456143013355 0, -86.69407089021021307 48.80454260092951557 0, -86.69393409669892492 48.80454147044776647 0, -86.69379370012670449 48.80454339694893662 0, -86.69373022861843481 48.80453019140897908 0) | R5809 | ANWIN | C | Temp | WF6 | C203 | 0.041673 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 5e-11 | 0.041673 | C266 | 20 | R1925 | ANWIN | 0.10519
LineStringZ (-86.61854514513554193 48.7992296181770655 0, -86.6186072494412258 48.79922839422289371 0, -86.61874286807774581 48.7992013206335784 0, -86.61887781771038419 48.79917877323836706 0, -86.61899080530544381 48.7991260094349002 0, -86.61912173129098846 48.79908845758831148 0, -86.6192098253424092 48.79901599742247953 0, -86.61928895022084873 48.79893875769887757 0, -86.6193776301155367 48.79886223136549717 0, -86.61948215274655638 48.79879676831763646 0, -86.61950626098966666 48.79874415316886882 0) | R5810 | ANWIN | C | Temp | WF6 | C219 | 0.093932 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C219 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.09 | 0.09 | All-season | 0.093932 | 0 | C266 | 20 | R4388 | ANWIN | 0.12572
LineStringZ (-86.60188528229737415 48.79678730440690515 0, -86.60192692070691578 48.79680778539010078 0, -86.6020445187382677 48.79686369295827575 0, -86.60217075053303404 48.7969045547668685 0, -86.6023108125807255 48.79690740402715221 0, -86.60241600605100132 48.79685015585619823 0, -86.60240648929645602 48.79681501267941002 0) | R5811 | ANWIN | C | Temp | WF6 | C222 | 0.049045 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.05 | 0.05 | All-season | 0.049045 | 0 | C266 | 20 | R1760 | ANWIN | 0.20721
LineStringZ (-86.60579296965458695 48.79538044903003424 0, -86.60584630045039489 48.79544321094871151 0, -86.60593875209838188 48.79551001533870647 0, -86.60606716367104241 48.79554635087287551 0, -86.6061486352910066 48.79561910528219926 0, -86.60626631819863519 48.79568041901701747 0, -86.60637067171505521 48.79574998858961976 0, -86.60641551553153761 48.7958372442596513 0, -86.60645256325588548 48.7959296549694912 0, -86.60646672864984907 48.79602432829533143 0, -86.60653361698038566 48.79610944706752207 0, -86.60660285099747568 48.79618785921680058 0, -86.60667175054172162 48.79626832575990392 0, -86.60674073388541672 48.79635604239452817 0, -86.60672514362872221 48.79644740529823821 0, -86.60664241404182917 48.79652011806255985 0, -86.60658038771509837 48.79660108775907901 0, -86.60654794965851977 48.79662971194921539 0) | R5812 | ANWIN | C | Temp | WF6 | C222 | 0.16814 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.17 | 0.17 | All-season | 0.16814 | 0 | C266 | 20 | R5801 | ANWIN | 0.053971
LineStringZ (-86.59753488757031903 48.79673756401155771 0, -86.59756900008318325 48.79674504721110395 0, -86.5976975791035386 48.79678238940172008 0, -86.59782590600546825 48.79682182572921789 0, -86.59794484605673404 48.79686616615782668 0, -86.59805459225115953 48.79689381207698062 0) | R5813 | ANWIN | C | Temp | WF6 | C224 | 0.042004 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C224 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 0.042004 | 0 | To D014 | 24 | R338 | AN | 0.071119
LineStringZ (-86.59220110835723005 48.79550363202505991 0, -86.59223953308813293 48.79551747601770018 0, -86.59236844666746435 48.79554794433431653 0, -86.59250599482102473 48.79556139657209002 0, -86.59263323192197959 48.7955958042969371 0, -86.59275787070144759 48.79563700185354236 0, -86.59289633908640837 48.79564278511480069 0, -86.59302433168745949 48.79567727693865464 0, -86.59315802296188735 48.79570334421911326 0, -86.59329473175623093 48.79568544880115155 0, -86.59343311722402348 48.79569831544942815 0, -86.59357233956151845 48.79568968182049105 0, -86.59369370995230497 48.79573611778565834 0, -86.59382362919322418 48.79577375240589987 0, -86.59396226633967331 48.79578804336691888 0, -86.59402716408349931 48.79578965643747779 0, -86.59402903052735212 48.79578970169379915 0) | R5814 | ANWIN | C | Temp | WF6 | C225 | 0.14109 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C225 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.14 | 0.14 | All-season | 0.14109 | 0 | To D014 | 24 | R339 | AN | 0.1145
LineStringZ (-86.48104110980415271 48.78914131971603751 0, -86.48095598586257893 48.78915067278475703 0, -86.48081843832457594 48.78915465385172467 0, -86.48068122641170419 48.78915025289742857 0, -86.48055549792182717 48.78910805017716967 0, -86.48041560495354929 48.7891162231229174 0, -86.48026825023775643 48.78911446305800581 0, -86.48012835627582717 48.78911073304724511 0, -86.47998402065948653 48.78909572883553381 0, -86.4798949145745155 48.78908450730175161 0, -86.47936842592611129 48.78959869758956813 0) | R5818 | ANWIN | C | Temp | WF6 | C247 | 0.15473 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C247 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 | 0.15 | 0.15 | All-season | 0.15473 | 0 | To D014 | 24 | R5711 | AN | 0.043665
LineStringZ (-86.48231278659623911 48.78766069986393461 0, -86.4823118426460411 48.78766074690139476 0, -86.48217437883650405 48.78764813234163 0, -86.48203666496287667 48.7876141851816314 0, -86.481904313961806 48.78757864628152419 0, -86.48176986901796681 48.78755542863014938 0, -86.48164782819604568 48.78750576529294136 0, -86.4815238596133895 48.78745480312787208 0, -86.48139695728572462 48.78741918020106993 0, -86.48128707048203978 48.78735816063962005 0, -86.48117265771305995 48.78730501908710693 0, -86.48107081790396933 48.78724500440903 0, -86.48098305867034696 48.78717212399499914 0, -86.48087652536275982 48.78710707993523954 0, -86.48075557432710525 48.78705134105890551 0, -86.48067921563942662 48.78697628076094617 0, -86.48057259741743508 48.78691492529431883 0, -86.48043186437608654 48.78690180723538106 0, -86.48029993357728529 48.78687200962700388 0, -86.48017185866311252 48.78691362691385791 0, -86.4800661442333336 48.78693907116338124 0) | R5819 | ANWIN | C | Temp | WF6 | C248 | 0.19569 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.2 | 0.2 | All-season | 0.19569 | 0 | To D014 | 24 | R5712 | AN | 0.075923
LineStringZ (-86.48466756317129978 48.78353180597167693 0, -86.48461829134531342 48.78349569430109511 0, -86.48449516120064118 48.78345298927474261 0, -86.48435786488742849 48.78344037444944803 0, -86.48426834706120303 48.78350994395592011 0, -86.48415435227227022 48.78356015059728179 0, -86.48408486697270803 48.78363982126900567 0, -86.48404656080839459 48.78372615537798396 0, -86.48403122238741503 48.78382061942814829 0, -86.48400423253337976 48.78390909035231005 0, -86.4839696988676252 48.78400280005233469 0, -86.48395377389786631 48.7840932402480405 0, -86.48399903621984208 48.78418078959168014 0, -86.48402191893191571 48.78427160773479443 0, -86.48406064348206712 48.78435911428943683 0, -86.48414890433552671 48.78443228881034344 0) | R5820 | ANWIN | C | Temp | WF6 | C248 | 0.14873 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.15 | 0.15 | All-season | 0.14873 | 0 | D31 and D018-D028 | 25 | R449 | AN | 0.077234
LineStringZ (-86.45941988996902694 48.78079380617614902 0, -86.45943225593175896 48.78077664940291669 0, -86.45947466821127136 48.78068687828058358 0, -86.45950299978501619 48.78059761055814647 0, -86.45958564493267318 48.78052477233965334 0, -86.45970081308014699 48.78047456486816458 0, -86.45977893200208086 48.7803957328379596 0, -86.45989745164671092 48.78034280069226725 0, -86.46000591434869875 48.78028110956613261 0, -86.46011018427034855 48.78021560597779427 0, -86.46021784042956426 48.78017601857910535 0, -86.46032769446671296 48.78012554179981919 0, -86.46132028070928754 48.77972119937303574 0, -86.46140376445062259 48.77964898898655832 0, -86.46148708035939023 48.77964232542017697 0, -86.46161406656564452 48.77960523526386538 0, -86.46175060752779018 48.77959660170380118 0, -86.46189108805766921 48.77961328227014803 0, -86.46202897042252289 48.77962216628603187 0, -86.46216299687833384 48.77964312188807128 0, -86.46230146687558715 48.77965141908096314 0, -86.46243817479724214 48.77963964317726919 0, -86.46249669835471252 48.77960753316575193 0) | R5821 | ANWIN | C | Temp | WF6 | C252 | 0.28283 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C252 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.28 | 0.28 | All-season | 0.28283 | 0 | D31 and D018-D028 | 25 | R343 | AN | 0.14291
LineStringZ (-86.67980235481164186 48.80494757700836317 0, -86.67985366864533603 48.80496458872480758 0, -86.67999180266615156 48.8049844116142495 0, -86.68013513340061138 48.80500364872899155 0, -86.68027301584933753 48.80500737864216632 0, -86.68041274147905995 48.80502410004226022 0, -86.68055557020109347 48.80504501298526776 0, -86.68070233670862024 48.80506885944014073 0, -86.68083326190549087 48.80510020764337042 0, -86.68096401955111219 48.80513029940041747 0, -86.68110969702443924 48.80516294664992927 0, -86.68125403328183154 48.80518419484720738 0, -86.68139040774242687 48.8051953840857351 0, -86.68152300872034743 48.80522610372150183 0, -86.68165426946538332 48.80525192031345938 0, -86.681792152497394 48.80529077036459284 0, -86.68193137619610411 48.80532073595975362 0, -86.68205308058738012 48.8053735414387404 0, -86.68217897761408608 48.80540924896799737 0, -86.6823000954430114 48.8054543016650868 0, -86.68243227819124286 48.8055011982997371 0, -86.68254878691391241 48.80556192515823 0, -86.68265917640526652 48.80562013687956124 0, -86.68277602010675764 48.80567491271463609 0, -86.68289571372214652 48.80573392166375157 0) | R5826 | ANWIN | C | Temp | WF6 | C207 | 0.24724 | 10 | 20 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C207 | ANWIN | Required | Dead Horse Creek RD - ML - WF6 | 0.25 | 0.25 | All-season | 0.24724 | 0 | D31 and D018-D028 | 25 | R345 | AN | 0.3
LineStringZ (-86.30939940662027254 48.7213833227586548 0, -86.30936973019178993 48.72138428559483003 0, -86.30922866249632364 48.72138575286774653 0, -86.30909178561566364 48.7213722998123373 0, -86.30895122130424113 48.72136471425069004 0, -86.30880227486230183 48.7213687381302023 0, -86.30866011708124574 48.72136978524491013 0, -86.30852424619500596 48.72138541756975627 0, -86.30839835022621287 48.72142271743359032 0, -86.30825535567844042 48.72144094794893476 0, -86.30815612271365467 48.72144091800956289 0) | R5711 | AN | D | Temp | WF7 | D011 | 0.092834 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D011 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.09 | 0.09 | All-season | 0.049169 | 0.043665 | D31 and D018-D028 | 25 | R346 | AN | 0.29079
LineStringZ (-86.3042876473453191 48.72171139843549525 0, -86.30425425221027069 48.72172052668632602 0, -86.3041131013867755 48.72173217712218474 0, -86.3039820914386695 48.72175757357047843 0, -86.30384647239476692 48.72174039208253049 0, -86.3037094288536224 48.72173569656455783 0, -86.3035728032396463 48.72172446591501682 0, -86.30343416639456677 48.72171532984051368 0, -86.30329636810752447 48.72171449131102605 0, -86.30315354042552656 48.72171956235069956 0, -86.30301859163115807 48.7216993621378478 0, -86.30288325207217781 48.72166573086470009 0, -86.30275763542464063 48.72163771338514238 0, -86.30263830500550171 48.72160209069438253 0, -86.30259247942343848 48.72159826255695236 0) | R5712 | AN | D | Temp | WF7 | D012 | 0.12803 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D012 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.13 | 0.13 | All-season | 0.052103 | 0.075923 | D31 and D018-D028 | 25 | R443 | AN | 0.045214
LineStringZ (-86.29224392796082554 48.72133816859717825 0, -86.29236611146458813 48.72138152118665033 0, -86.29250005458990813 48.72141198960986941 0, -86.29252033262892496 48.72141196388657391 0) | R5713 | AN | D | Temp | WF7 | D015 | 0.022107 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D015 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.02 | 0.02 | All-season | 0.022107 | 0 | D31 and D018-D028 | 25 | R5715 | AN | 0.060936
LineStringZ (-86.28827949062453229 48.72045193680775554 0, -86.28832287573673909 48.72044771031539057 0, -86.2884493859874766 48.72045950743221709 0, -86.28854086037235049 48.72048692129372682 0, -86.28856305712440644 48.72050256230708953 0) | R5714 | AN | D | Temp | WF7 | D016 | 0.022394 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D016 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.02 | 0.02 | All-season | 0.022394 | 0 | D31 and D018-D028 | 25 | R5716 | AN | 0.060006
LineStringZ (-86.2582927488951583 48.71152382200396858 0, -86.25829240492303995 48.71151836901222509 0, -86.25830204440671878 48.71142541340097409 0, -86.25833084994469857 48.71134140640516819 0, -86.25832140665383463 48.7112393776611583 0, -86.2582457178169193 48.71115794738906146 0, -86.25814144746814804 48.7110963818949827 0, -86.25798439775887516 48.71111309301348768 0, -86.2578707120346877 48.71116536531236818 0, -86.25773551189212185 48.71119172667630437 0, -86.25759444470260462 48.71117798024765477 0, -86.25746896652776741 48.71114790081480095 0, -86.25737877705915935 48.71110317174134963 0, -86.25727584776942081 48.71106029194869791 0, -86.25714919779157697 48.71103117080076572 0, -86.25701114677225689 48.71102412995482922 0, -86.25687720399824343 48.71104504314444483 0, -86.25677083861826588 48.71110665011814689 0, -86.25663186554048423 48.71111909666595352 0, -86.25654806638610239 48.71111714356639055 0) | R5715 | AN | D | Temp | WF7 | D022 | 0.17967 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D022 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.18 | 0.18 | All-season | 0.11874 | 0.060936 | D31 and D018-D028 | 25 | R5717 | AN | 0.011474
LineStringZ (-86.24161437504055527 48.70536520328619901 0, -86.24159036789637867 48.70536127495696377 0, -86.24145139583635 48.70534669036160125 0, -86.24132742725116429 48.70531200257400428 0, -86.24120505067314468 48.7052834488379176 0, -86.24107898804237493 48.7052492921591309 0, -86.24098904940089483 48.70518068675558254 0, -86.24088265166263056 48.7051568637786545 0) | R5716 | AN | D | Temp | WF7 | D026 | 0.060006 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D026 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.06 | 0.06 | All-season | 4e-10 | 0.060006 | D028-D029 | 26 | R347 | AN | 0.034504
LineStringZ (-86.23758028952262578 48.70375269959922093 0, -86.23755255163190725 48.70374109358295556 0, -86.2374180227745768 48.7037068129782682 0, -86.23729279688082272 48.70366880101148155 0, -86.23715885323329644 48.70364843297803503 0, -86.23704687125110979 48.70359424333189224 0, -86.23679315092905995 48.70355900799126658 0) | R5717 | AN | D | Temp | WF7 | D027 | 0.062551 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D027 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.06 | 0.06 | All-season | 0.051077 | 0.011474 | D028-D029 | 26 | R450 | AN | 0.017698
LineStringZ (-86.2362429421235106 48.70323464426479632 0, -86.23634170192345039 48.70325335156700675 0, -86.23647136905962896 48.7032906509213035 0, -86.23655803798392583 48.70336022060509862 0, -86.23660506172967644 48.7034446267346226 0, -86.23666753465113288 48.70351504987684876 0, -86.23677211309083646 48.70354638282108084 0) | R5718 | AN | D | Temp | WF7 | D028 | 0.05551 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D028 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.06 | 0.06 | All-season | 0.05551 | 0 | D028-D029 | 26 | R667 | AU2 | 0.13393
LineStringZ (-86.29644722282669989 48.7214792360757798 0, -86.29649378133076709 48.72147580405015788 0, -86.29666901932658618 48.72143481060366099 0, -86.29677482638899733 48.72138596324479209 0, -86.29690415883695209 48.72135459311152772 0, -86.29704514348539135 48.72134476591359942 0, -86.29717967282464031 48.72136165459265555 0, -86.29730540090311308 48.72139975181975302 0, -86.29744417750437435 48.72143805441820774 0, -86.29758208730619629 48.72144371356385051 0, -86.29771879679948654 48.72142699272442457 0, -86.29785676233835545 48.72140989344254081 0, -86.29800244003793352 48.7214085941259043 0, -86.29811620771991443 48.72143147439192745 0, -86.29813872968264832 48.72143600440014666 0, -86.29827577418276974 48.72145343789137684 0, -86.29840384948441567 48.7214948021169576 0, -86.29850711472764146 48.72155842094255007 0, -86.29861465438361279 48.72161504060765935 0, -86.29874524450468698 48.72164152844810303 0, -86.29888128331299413 48.72163306240425129 0, -86.29901891435125094 48.72161529218200116 0, -86.2991187706494145 48.72159495032671117 0, -86.29925553589814058 48.72155561260517942 0, -86.29935796171299955 48.72149631128903735 0, -86.29948355027173079 48.72146754596834484 0, -86.29962693797806139 48.72144228924518927 0) | R5723 | AN | D | Temp | WF7 | D014 | 0.25137 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D014 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.25 | 0.25 | All-season | 0.25137 | 0 | D028-D029 | 26 | R5729 | AN | 0.10494
LineStringZ (-86.27304199578513533 48.71297150273750987 0, -86.27303986571372718 48.71301055692460835 0, -86.27300885322378576 48.71309906968733827 0, -86.27297205642864242 48.71318615783369665 0, -86.27297566099295523 48.7132812079192874 0, -86.27295177181818531 48.71337734757487681 0, -86.27296199794484721 48.71347269313304906 0, -86.27292296635476987 48.71355663559349125 0, -86.27288781830534958 48.71363861259747807 0, -86.27287516145111113 48.71373043658874735 0, -86.27285940397074171 48.71382016469549825 0, -86.27285563233441223 48.713915760170309 0, -86.2728915067934139 48.71400385385689447 0, -86.27295621437596651 48.71408322957699255 0, -86.27301614598118817 48.71416650464678355 0, -86.2730923373674301 48.71424709705743084 0, -86.27317724571008739 48.71432014535037069 0, -86.27318655008397741 48.71441062803172883 0, -86.273209097323587 48.71450769037334538 0, -86.27323910408212271 48.71460031067874041 0, -86.27316525923939139 48.71467989627497275 0, -86.27314690271215625 48.71477490584773307 0, -86.27310667063089511 48.71486484301574649 0, -86.27308202695810735 48.7149564159613746 0, -86.27301229055767351 48.7150357502945468 0, -86.27294188163622835 48.71512107807905778 0, -86.27282897788461469 48.71517170483923564 0, -86.27276471683806847 48.7152800825853376 0, -86.2727481767430362 48.71536001609618438 0, -86.27277749286673725 48.71550090372796404 0) | R5725 | AN | D | Temp | WF7 | D017 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D017 | AN | Required | Pic River RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0 | D028-D029 | 26 | R5735 | AU2 | 0.11905
LineStringZ (-86.27560318663194039 48.71640478034286303 0, -86.2754996766436193 48.71638290488558454 0, -86.27538160332174755 48.71633834030473764 0, -86.27524883467272332 48.71631700839679979 0, -86.27511137146878184 48.71629550825944222 0, -86.27497530419708482 48.71626817014070809 0, -86.27485303997545429 48.71622627389259463 0, -86.27472982665568679 48.716181849917497 0, -86.27455106786818817 48.71614635742641752 0, -86.27437314804711832 48.71610860290991241 0, -86.27420780096265673 48.71605800703913758 0, -86.27409911570475742 48.7160036009065962 0, -86.27398291499235938 48.71593684687047698 0, -86.27386934048371359 48.71590508722080415 0, -86.27374168352882577 48.71586744516896772 0, -86.27361025478056433 48.71582721169313146 0, -86.27347907788141868 48.71579527680968624 0, -86.27334077728799855 48.71575315728119904 0, -86.27322829181817099 48.71570219527264811 0, -86.27312242821612642 48.71564050473053697 0, -86.27299552614449851 48.71560471442134599 0, -86.27286510353459903 48.71557814440541989 0, -86.27273174702631309 48.71555479973662273 0, -86.27267408014012062 48.7155440712508252 0) | R5726 | AN | D | Temp | WF7 | D018 | 0.23819 | 10 | 20 | Pic River RD - ML - WF7 - BR1 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D018 | AN | 0 | Pic River RD - ML - WF7 - BR1 | 0.24 | 0.24 | All-season | 0.23819 | 0
LineStringZ (-86.50514650769849823 48.78157636301063604 0, -86.50514566190102528 48.7815863791285409 0, -86.50512856267998529 48.78167933428893122 0, -86.50509922587744427 48.78177254186391565 0, -86.50506821350482767 48.78186143135000208 0, -86.5050628489731821 48.78195153657466676 0, -86.50500870214717963 48.78203455935853583 0, -86.50497903047669013 48.78212453859312348 0, -86.50494918972326275 48.7822134285761706 0, -86.50488800234445819 48.78229737463582438 0, -86.50486864030837353 48.78238794058375305 0, -86.50487199301565511 48.78247942904144452 0, -86.5048219537054166 48.78256479934061929 0, -86.50478817336970394 48.78265239041984813 0, -86.50472430402415114 48.78273185025220471 0, -86.50472572849062658 48.78282614707136133 0, -86.50468901574231495 48.78291482842688254 0, -86.50463679713632814 48.78300245986551431 0, -86.50459480362719944 48.78309528993858635 0, -86.50450536805492163 48.78316356027661271 0, -86.50440813796078032 48.78324117716066155 0, -86.50438927927689292 48.78333082128946785 0) | R5793 | ANWIN | C | Temp | WF6 | C244 | 0.20685 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.21 | 0.21 | All-season | 0.20685 | 0
LineStringZ (-86.67438670893582753 48.80369418226344891 0, -86.67443560519517121 48.80373726881188645 0, -86.67450928144273803 48.80381366982577873 0, -86.6746013989456543 48.80388458044919275 0, -86.67464624182387922 48.80397032772577859 0, -86.6746887389330567 48.80405682942035384 0, -86.67478026922367462 48.80412388437781601 0, -86.67490490790676461 48.80417031858019783 0, -86.67501336951791302 48.80422555635006887 0, -86.67512132814552217 48.80428385301961924 0) | R5796 | ANWIN | C | Temp | WF6 | C208 | 0.087476 | 10 | 20 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C208 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 | 0.09 | 0.09 | All-season | 0.087476 | 0
LineStringZ (-86.652216882936969 48.80302233707478621 0, -86.65231734788126516 48.80295599276001894 0, -86.65240795563036613 48.80288629732950767 0, -86.65251004772522947 48.80281655998235379 0, -86.6526454157472017 48.80280184938620636 0, -86.65296980596711762 48.802740291104584 0) | R5797 | ANWIN | C | Temp | WF6 | C213 | 0.066286 | 10 | 20 | C214 - ML - WF6 | C214 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | Required | C214 - ML - WF6 | 0.07 | 0.07 | All-season | 0.066286 | 0
LineStringZ (-86.61357905015788106 48.79831948759883176 0, -86.61362445749988126 48.7983670287346456 0, -86.61368891452882224 48.79845172764134986 0, -86.61381556496468193 48.79848982441475869 0, -86.61395428633848326 48.7985078024284249 0, -86.61408596624328027 48.79848177634934814 0, -86.61422585890329628 48.79851056840324475 0, -86.61436868782621445 48.79853915060903091 0, -86.6145027144605848 48.7985181957312335 0, -86.61459457969799303 48.7985976565807249 0, -86.61462215559809863 48.79864283473258268 0) | R5798 | ANWIN | C | Temp | WF6 | C220 | 0.095847 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C220 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.1 | 0.1 | All-season | 0.095847 | 0
LineStringZ (-86.26886893734337036 48.71482140218139278 0, -86.26884455528421825 48.71479560930554698 0, -86.26877079403872983 48.71471753133942428 0, -86.26873391420180326 48.71462788714860181 0, -86.26867607833077045 48.71454406808769733 0, -86.26856158214596348 48.71449193273233647 0, -86.26842914755695801 48.71446037543078944 0, -86.26829143307352865 48.7144529994086497 0, -86.26815807708926798 48.71447776719612932 0, -86.26802346276055289 48.71448075073115547 0, -86.26790821234254736 48.71449105227734577 0, -86.26777091685121945 48.71447588132370043 0, -86.26762884320103808 48.71446284790889791 0, -86.26748769205886447 48.71444423986577021 0, -86.26735726932885484 48.71441293341921153 0, -86.26722449956042738 48.71438757815089104 0, -86.26710170469024774 48.71434281759007234 0, -86.26697086341019372 48.71431574523381869 0, -86.26684823669874902 48.71427534411123617 0, -86.26674094771014722 48.71421855680541313 0, -86.26661463288223786 48.71418238894423069 0, -86.26649907392496175 48.71414567678054652 0, -86.26638237007124133 48.7141099278963452 0, -86.26624809208885836 48.71408264481453187 0, -86.26610660473339465 48.7140502481175659 0, -86.26598246960372762 48.71401102125592075 0, -86.26588498728062859 48.71394782198595408 0, -86.26580955085846369 48.71387054018550344 0) | R5727 | AN | D | Temp | WF7 | D020 | 0.26666 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D020 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.27 | 0.27 | All-season | 0.26666 | 0
LineStringZ (-86.26223534455853326 48.71280401741707067 0, -86.26214146116792847 48.71276459057248331 0, -86.26202344330663152 48.71271501163199247 0, -86.26188589674923435 48.71269254784871094 0, -86.26174575036141334 48.71269401503106877 0, -86.26161147251998784 48.7126774607532198 0, -86.26147853572520319 48.71265696559857616 0) | R5728 | AN | D | Temp | WF7 | D021 | 0.059286 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D021 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.06 | 0.06 | All-season | 0.059286 | 0
LineStringZ (-86.2315400343636469 48.70139883714031726 0, -86.23159150698280939 48.70142102590261857 0, -86.23171103364906287 48.70146431834042033 0, -86.23183793515997309 48.70149751032496965 0, -86.23195025288207205 48.70154834723108195 0, -86.23203843137119406 48.70161921596871935 0, -86.23215619600692605 48.70166510689056594 0, -86.23229156391090555 48.70169394036924615 0, -86.23241746065777136 48.70173392343710361 0, -86.23252290478870918 48.70179184166604358 0, -86.23261032837099549 48.7018615786095026 0, -86.23271300657354743 48.70192293457467514 0, -86.2327449323513946 48.70195252424522181 0) | R5729 | AN | D | Temp | WF7 | D029 | 0.10997 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D029 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.11 | 0.11 | All-season | 0.0050371 | 0.10494
LineStringZ (-86.2758721508762676 48.70918383455222056 0, -86.27584713361770241 48.70923056892974046 0, -86.27581528159872448 48.70931908171648672 0, -86.27583623640639132 48.70941497131095588 0, -86.27582894489525245 48.70950809426781092 0, -86.27581586837578698 48.70959882836402954 0, -86.27579130962847387 48.70969941035512107 0, -86.27573640790623699 48.70979383264633356 0, -86.27568226121405814 48.70987702344702086 0, -86.27561780411210179 48.7099676737901035 0, -86.27554689347991257 48.7100518278699397 0, -86.27547514435914877 48.7101413464429811 0, -86.27540389837257351 48.71022269332004839 0, -86.27533457956177187 48.71030688966374811 0, -86.2752749015324838 48.71038953359527568 0, -86.27519720020924865 48.71047063012603218 0, -86.27511304677746296 48.71055260541781706 0) | R5731 | AU2 | D | Temp | WF7 | D018 | 0.16563 | 7.5 | 15 | Pic River RD - ML - WF7 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D018 | AU2 | Required | Pic River RD - ML - WF7 | 0.17 | 0.17 | All-season | 0.16563 | 0
LineStringZ (-86.22798143362966528 48.69897944094972075 0, -86.22803330390854626 48.69906512462087989 0, -86.22808158471524109 48.69915074643309083 0, -86.22810170030224697 48.69924902338546957 0, -86.22812617609329777 48.6993395478377451 0, -86.22810111342461425 48.69943325789745359 0, -86.22806934719876892 48.69953145171852071 0, -86.22806026424106562 48.69959697940520726 0) | R5734 | AU2 | D | Temp | WF7 | D030 | 0.070725 | 7.5 | 15 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D030 | AU2 | 0 | Pic River RD - ML - WF7 - BR2 | 0.07 | 0.07 | All-season | 0.070725 | 0
LineStringZ (-86.22839376119739541 48.69663440306089086 0, -86.22831300802788235 48.69666739640992859 0, -86.22821720318526673 48.69673885197105534 0, -86.22812232043675351 48.69681211017061884 0, -86.22800539183698731 48.69686307192841213 0, -86.22786667213763678 48.69690121008169115 0, -86.22779970011991679 48.69698117371685697 0, -86.22771244508888344 48.69705082664891904 0, -86.22761420922978459 48.69712722771230062 0, -86.22753357460091195 48.69720647885404219 0, -86.22745796980066757 48.69728250344531517 0, -86.22745193485513937 48.69737386523561895 0, -86.22745562355773075 48.69746380335764968 0, -86.22743349433794435 48.69755487279815043 0, -86.22744028390047788 48.6976608197518317 0, -86.22745838875016489 48.69775503237367786 0, -86.22744891754896912 48.69785096367219523 0, -86.22744372100041232 48.69794605640002061 0, -86.22743709957696012 48.69804047835074101 0, -86.22742201212281543 48.69813787614472744 0, -86.22744531312032734 48.69823187890914085 0, -86.22750759139391619 48.69831448305540533 0, -86.22756794027355909 48.69840622156174703 0, -86.22775351672186162 48.69869510457537842 0, -86.22784269955614889 48.69880293787532821 0, -86.22792241156477644 48.69888189642296794 0, -86.22798142037080993 48.69897941927001028 0, -86.22798143362966528 48.69897944094972075 0) | R5735 | AU2 | D | Temp | WF7 | D030 | 0.3 | 7.5 | 15 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D030 | AU2 | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.18095 | 0.11905
LineStringZ (-86.31708284010086629 48.72133926591324382 0, -86.31711653802497608 48.72133931719860556 0, -86.31732994196691777 48.72127708074640395 0, -86.31743127909793145 48.72124778604441531 0, -86.31753554921643001 48.72122469436926195 0, -86.31764107829680199 48.72119858465467956 0, -86.3177608552288973 48.72118521497255017 0, -86.31786638372750531 48.7211657693864737 0, -86.3179755999688183 48.7211723317734311 0, -86.31808020589242858 48.72119356555950276 0, -86.31815857759141863 48.7212215512425999 0, -86.31823334332563036 48.72127712287991841 0, -86.31829226879412431 48.72133998657866272 0, -86.31831590508481611 48.72141068941530051 0, -86.31831791751065452 48.72148331813396283 0, -86.31838983319751435 48.72153784184768455 0, -86.31845437410613897 48.72159580339840801 0, -86.31851992114830807 48.72166222992967022 0, -86.31860575227061361 48.72171461556173711 0, -86.31869049263936233 48.72176582967995273 0, -86.31879845105029858 48.72178368299319828 0, -86.31896298872487705 48.72182680792654708 0, -86.31903373177814842 48.72187924889402666 0, -86.31912135033803679 48.72192378118064227 0) | R5736 | AN | D | Temp | WF7 | D010 | 0.19545 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D010 | AN | Required | Three Finger Lake RD - ML - WF7 | 0.2 | 0.2 | All-season | 0.19545 | 0
LineStringZ (-86.71143117585846483 48.80557577008413972 0, -86.71156384334672396 48.80557973468167887 0, -86.71170549743916922 48.8055674128668997 0, -86.71185427640210719 48.80558941559583985 0, -86.71200841964039796 48.80558413516126848 0, -86.71215745014933418 48.80556887965268231 0, -86.71228913022645202 48.80559737826904865 0, -86.71252575141473073 48.80558618843247132 0, -86.71267570292872051 48.80557608832340577 0, -86.71280855715927771 48.8056127171022851 0, -86.71293721832640244 48.80564528081686149 0, -86.71308046585929219 48.80562529044497211 0, -86.71322471866459125 48.80562172807801602 0, -86.71335145297946667 48.8055847632336679 0, -86.71348941837150903 48.80561049636322934 0, -86.71362084757969058 48.80558346541076276 0, -86.7137542028048216 48.80560852556854456 0, -86.71389652801650527 48.80559809097534441 0, -86.71401714427135232 48.80564205385908139 0, -86.71414563780321316 48.80567742523950159 0, -86.71426332019812833 48.80573350081542117 0, -86.71438888056741234 48.80577415156535892 0, -86.71450790420105648 48.80582172005719599 0, -86.71464880464230873 48.80583060517870564 0, -86.7147867696078265 48.80584368036901566 0, -86.71492876016426976 48.80584527304021236 0, -86.71506689398522383 48.80586342022193946 0, -86.7152103083223551 48.80586660474803296 0, -86.71534676537264374 48.80587062832884726 0, -86.71535364247191069 48.80586952261793954 0) | R1830 | ANWIN | C | Temp | WF6 | C200 | 0.3 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C200 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.70610978402851288 48.80535741911702985 0, -86.70616715339409097 48.8053439940945637 0, -86.70630780239241631 48.80533971871904697 0, -86.70643956580049405 48.80536750455834749 0, -86.70657719650506579 48.8053765990276176 0, -86.70670694885326668 48.80541532390049753 0, -86.70684164603659383 48.80543309256999152 0, -86.70696268077600166 48.80547563175133519 0, -86.70709813144510747 48.80550203543815968 0, -86.70723752273359253 48.80549583240077283 0, -86.70737825465697313 48.80551364365665279 0, -86.70751613799856727 48.8055332565960498 0, -86.70765971890192247 48.80554901466702233 0, -86.70779349517933099 48.80556976024219296 0, -86.70792592912341945 48.80560169500684253 0, -86.70806196769545693 48.80557881300440215 0, -86.70820227999172403 48.80559369041480267 0, -86.70833999455879848 48.80559012840481614 0, -86.70848022430580215 48.80560211487303945 0, -86.70862565068431138 48.80561112495611553 0, -86.7087635322977377 48.8056234047089319 0, -86.70890518683205528 48.8056059703462779 0, -86.70904189583450261 48.80563073856415457 0, -86.70918153867820877 48.80561166961995667 0, -86.70932654542536966 48.80561154418435876 0, -86.70946979257001885 48.80562533264639313 0, -86.70961899002004714 48.80563132564664386 0, -86.70975913557343517 48.80563484606885538 0, -86.7099043101448359 48.80566112340601137 0, -86.71003900725315816 48.8056374017716692 0, -86.7100949720162788 48.80564283484395105 0) | R1831 | ANWIN | C | Temp | WF6 | C201 | 0.3 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C201 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.69803281418971608 48.80487726318787622 0, -86.69799397183651024 48.80486502320778186 0, -86.6978221180450106 48.80486100234455904 0, -86.69770329986945967 48.80484569457745891 0, -86.69764828690722425 48.80480554085065137 0, -86.6975083094052934 48.80480901937774263 0, -86.6973755399562549 48.80484560642563707 0, -86.6972392496242179 48.80483403959986077 0, -86.69711662310163547 48.80479330319571574 0, -86.69702241057622416 48.80472461359450165 0, -86.69689324553684173 48.8046918823456366 0, -86.69676667897111599 48.80465533721127969 0, -86.6963780096922676 48.80458631201186392 0, -86.69623945613224691 48.80459628691821905 0, -86.69610467595880721 48.80457160304928976 0, -86.69596302177987468 48.8045896244145041 0, -86.69582849103848332 48.80462595944749893 0, -86.69570276356930094 48.80466292298954301 0, -86.69557225694931901 48.80469045772179015 0, -86.69546513564986867 48.80474758056621454 0, -86.69506255254233906 48.80482578311851682 0, -86.69492223986391366 48.80481061173264123 0, -86.6947805859614391 48.80478756157818765 0, -86.69468134429165218 48.80472541028802169 0, -86.6945665963464478 48.80467562142931826 0, -86.69446802443194144 48.80461292477541235 0, -86.69434254797373285 48.80457705006464408 0, -86.69428978667822605 48.80457225924814679 0) | R1832 | ANWIN | C | Temp | WF6 | C203 | 0.3 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.27834 | 0.021657
LineStringZ (-86.61494695964212553 48.79892814125572897 0, -86.61495491760872767 48.79893792035892375 0, -86.61495818665451907 48.79902835956450247 0, -86.61506614622645372 48.79909432587532336 0, -86.61513680491532341 48.79917336731919164 0, -86.61524191395592709 48.79924230880503444 0, -86.61537292286735124 48.79927713578234005 0, -86.61550217227004111 48.79930701706015128 0, -86.61564860502815577 48.79929276823934003 0, -86.61578866610477689 48.79927210636574131 0, -86.61591861325896957 48.79924647813783167 0, -86.61604448179197391 48.79920748167643296 0, -86.61616845013901411 48.79915497041776007 0, -86.61631580408906927 48.79913644533872485 0, -86.61644413054636971 48.79909076362842058 0, -86.61657899643900294 48.7990491058298943 0, -86.61670640041371882 48.79899843699729445 0, -86.61684528859359489 48.79900627543587888 0, -86.61698484835810063 48.7990024607737567 0, -86.61713278832299068 48.79899629974443087 0, -86.61727176083492452 48.7989932402441795 0, -86.61740863656481793 48.79898548672206715 0, -86.61753914329891302 48.79901733820605614 0, -86.617662608101611 48.79906431897813945 0, -86.61778708049622821 48.79911134164103714 0, -86.61792001738925251 48.79914046867794752 0, -86.6180604973385897 48.79916884240487462 0, -86.61819846395505351 48.79920023117723815 0, -86.6183334128982807 48.79921531901063503 0, -86.61846903194302172 48.79923111868504293 0, -86.61854514513554193 48.7992296181770655 0) | R1851 | ANWIN | C | Temp | WF6 | C219 | 0.3 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C219 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.59805459225115953 48.79689381207698062 0, -86.59813117507196978 48.79691310466932919 0, -86.59822765105626274 48.79698212967682025 0, -86.59836217989742124 48.7970091204140104 0, -86.59850031433262529 48.79701498663372661 0, -86.59864297442285874 48.79701222062504229 0, -86.59878077287714859 48.79701565732779756 0, -86.59890918368638779 48.79704662843517582 0, -86.59904362901322372 48.79706485871469823 0, -86.59918042274269112 48.79707718035739106 0, -86.59931201825420999 48.79710396007436657 0, -86.59944470351591406 48.79707956898279519 0, -86.59958577094229781 48.79707282185540151 0, -86.59972817985601523 48.79705953644859306 0, -86.59986681586561019 48.79704843008544657 0, -86.6000084704440809 48.79705002283871096 0, -86.60014467725872578 48.79704352713965676 0, -86.60026369968852578 48.79699847435535531 0, -86.60039613333862007 48.79696469490645683 0, -86.6005314177231611 48.79694914741123313 0, -86.60066360053139078 48.79692274257726581 0, -86.60079871612114744 48.79689583767755323 0, -86.60091681739315561 48.79684680301249244 0, -86.60101086334576337 48.79678075365695378 0, -86.60114581200960515 48.79675611115714418 0, -86.60126181644497478 48.79670594528629834 0, -86.60141143433308741 48.79670171288741898 0, -86.60155417835646574 48.79669835972837433 0, -86.6016915572259478 48.7967074121805453 0, -86.60181343041693935 48.7967519620598722 0, -86.60188528229737415 48.79678730440690515 0) | R1855 | ANWIN | C | Temp | WF6 | C222 | 0.3 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.60254404703032094 48.79619356271864206 0, -86.60256998131922046 48.796132162016292 0, -86.60262354067364754 48.79604817501828506 0, -86.60270794673645867 48.79597554557346939 0, -86.60281364230489487 48.79591389703665527 0, -86.60293241418003163 48.79586423469375944 0, -86.60307105133631467 48.79585333768588384 0, -86.60320943653444203 48.79584537502768171 0, -86.60335176079273367 48.79583121044529292 0, -86.60349106856358503 48.79582815072649993 0, -86.60362869953929987 48.7958142782191544 0, -86.60376616315490139 48.79578879657747592 0, -86.60390136222541457 48.79577559458021341 0, -86.60400613688588578 48.79571566541179095 0, -86.60408291537638092 48.79564094058069657 0, -86.6041435165268183 48.79555733060014688 0, -86.60425549823251856 48.79549731620340225 0, -86.6043746058341668 48.7954507130536328 0, -86.60447678003642125 48.79537431191040042 0, -86.60459613941586099 48.79532783443899291 0, -86.60469580020136959 48.79525931214226375 0, -86.60483845999205244 48.79523094044416354 0, -86.60497215093732848 48.79520876933899842 0, -86.60510550762505488 48.79515977725738196 0, -86.60524037248191576 48.79513945133725628 0, -86.60537372884559204 48.79511405356623754 0, -86.60550775517401689 48.79514611427528337 0, -86.60560305746930965 48.795217905263776 0, -86.60568905570630704 48.79528852275647921 0, -86.6057749701335382 48.79535926674049051 0, -86.60579296965458695 48.79538044903003424 0) | R1858 | ANWIN | C | Temp | WF6 | C222 | 0.3 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.59402903052735212 48.79578970169379915 0, -86.59410065207308094 48.79579148144009082 0, -86.59422051340936832 48.79574739141097695 0, -86.59435948435101693 48.79576993866874801 0, -86.59449284121490109 48.79580078368010021 0, -86.59462468908563437 48.79582475660800611 0, -86.59475846388308184 48.79585480573860679 0, -86.59488603670484963 48.79589176970674913 0, -86.59501318960823824 48.79593288279719587 0, -86.59511846606031327 48.79599046608822022 0, -86.59519616745721748 48.79606741342013976 0, -86.59527093406484255 48.796152907357353 0, -86.59530831649043137 48.79624385109536178 0, -86.59536891864455299 48.79632591005265851 0, -86.59545877261206215 48.79639740782454282 0, -86.59559061882119124 48.79642607373281038 0, -86.59573344687740359 48.79643051678492327 0, -86.59586403781509034 48.79646224200364912 0, -86.59599630432845174 48.79648541778306736 0, -86.59610769858285551 48.79653906158134902 0, -86.5962381211966914 48.79651140161420386 0, -86.59637524902719008 48.79650624679801751 0, -86.59650910849728689 48.79652422609893847 0, -86.5966383580402379 48.79655725105837405 0, -86.59677246778717574 48.79657699143945848 0, -86.59691395503098477 48.7965957238271244 0, -86.59704546701871664 48.79662514436071774 0, -86.59717840393678046 48.79665280471520816 0, -86.59731377218038517 48.7966769865737362 0, -86.5974390814188979 48.79671654862983132 0, -86.59753488757031903 48.79673756401155771 0) | R1861 | ANWIN | C | Temp | WF6 | C224 | 0.3 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C224 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.58824146355460982 48.7951010345917382 0, -86.58826776786358437 48.79508916031660704 0, -86.58840078736756141 48.79506636191629809 0, -86.5885394240840327 48.79505647104018351 0, -86.58867085334540548 48.79508509570958097 0, -86.58881443446138348 48.7951088166950413 0, -86.58894888088327946 48.79512633459101068 0, -86.5890923792231888 48.79512637664385721 0, -86.58923026082976548 48.79511925210393031 0, -86.58936864700102376 48.79513521915100682 0, -86.58949010015932402 48.79517771511364543 0, -86.58963385001204927 48.79520353173918323 0, -86.58977005627011181 48.79521836784593347 0, -86.58991104027246877 48.79523123358026027 0, -86.59005931540391998 48.79524816516273233 0, -86.59020080295846356 48.79527880117116467 0, -86.59034430103861268 48.79527943000047685 0, -86.59049232472987967 48.7952863026386936 0, -86.5906366614900378 48.79529464272933126 0, -86.59077152637499353 48.79531207722106956 0, -86.59090915689785106 48.79532012418149378 0, -86.59105005646490838 48.79531664524586887 0, -86.59118693340043649 48.79531991414074099 0, -86.59132657547691281 48.7953089763474992 0, -86.59146596768437121 48.79531605912358572 0, -86.59160150286916746 48.79533902484148911 0, -86.59173561320805845 48.79535972826460011 0, -86.59187072894729909 48.79538709570650212 0, -86.59199771509887 48.79543084915763984 0, -86.59211774488061053 48.79547359639254012 0, -86.59220110835723005 48.79550363202505991 0) | R1863 | ANWIN | C | Temp | WF6 | C225 | 0.3 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C225 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.47994496011885701 48.78722128401753366 0, -86.48003640613137577 48.78729441575074333 0, -86.48011586675048079 48.7873680511023835 0, -86.48023237541988806 48.78741813282126571 0, -86.48032357018195171 48.78748824773136761 0, -86.48042918290228442 48.78754805157682739 0, -86.4805523963270133 48.7875872798336232 0, -86.48061475806991893 48.78766862561138851 0, -86.48065733896424945 48.78775625859084641 0, -86.48077929463693181 48.78779896418646445 0, -86.48089052358703555 48.78785713494181664 0, -86.48100166683261136 48.78790964761956417 0, -86.48111784038341909 48.78795784316537265 0, -86.48123434933700082 48.7880091824052613 0, -86.48135697647302322 48.78804945789078573 0, -86.48148630870504405 48.78808248204829567 0, -86.48153500748514944 48.78816663557707045 0, -86.48163056200594667 48.78823159635276596 0, -86.48168009868227557 48.78831876814488311 0, -86.4817386044116887 48.78840107832408535 0, -86.48178822514837805 48.78848950808523455 0, -86.48176978526267078 48.78858355299841065 0, -86.48173600539668371 48.78867076664177915 0, -86.48166417359411184 48.78874746106293259 0, -86.48158848453903147 48.7888266695633348 0, -86.48145713985645955 48.788865352561686 0, -86.48139268274327662 48.78894623793894425 0, -86.48129235127504444 48.78900859921150612 0, -86.48118539822563378 48.78906903243606052 0, -86.48109177280312565 48.78913575259191759 0, -86.48104110980415271 48.78914131971603751 0) | R1898 | ANWIN | C | Temp | WF6 | C247 | 0.3 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C247 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.4854017746873609 48.78715923903005347 0, -86.48540359247664355 48.78717438741202983 0, -86.48547869455516945 48.78725376333692765 0, -86.4855787749025211 48.78736708644537856 0, -86.48564683527013131 48.78744629588928206 0, -86.48563007124951696 48.787540423574562 0, -86.48555128204262132 48.78761724500744634 0, -86.48543292893792511 48.78766510526888567 0, -86.48529907045322318 48.78768899380273893 0, -86.48500318847487733 48.7876926820198662 0, -86.48486555829860833 48.78771154242704 0, -86.48472574797436607 48.78770118921460153 0, -86.48458778113700873 48.78769561555352396 0, -86.4844518269333804 48.78767365462307737 0, -86.48431897415643732 48.78770085434609882 0, -86.48418151083197358 48.78771443313259937 0, -86.48404077914058519 48.78772570674333764 0, -86.48390775759816052 48.78770294955872799 0, -86.48377096532831843 48.78770776965758671 0, -86.48362914244313515 48.78770676373834903 0, -86.48349251860979336 48.78769569912731185 0, -86.48335522284881449 48.78769532218700533 0, -86.48321641822559513 48.78770638662567904 0, -86.48308264323564742 48.78767776241782883 0, -86.48294082162539098 48.78766577604091026 0, -86.4827229758428615 48.78767918677744575 0, -86.48258727159713999 48.78766795519564425 0, -86.48244871960181968 48.78765391561002929 0, -86.48231278659623911 48.78766069986393461 0) | R1899 | ANWIN | C | Temp | WF6 | C248 | 0.3 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.27981 | 0.020195
LineStringZ (-86.48499069919387239 48.78214784292464401 0, -86.48505591008898818 48.78222684215264593 0, -86.48512346815608964 48.7823075592697819 0, -86.48518021397143229 48.78239012171083289 0, -86.48527509718172723 48.78246128378209789 0, -86.48536637673173288 48.78253144012288089 0, -86.48546997706542072 48.78259631586180234 0, -86.48556368599001587 48.78266177887776678 0, -86.48564649898908385 48.78273327629162281 0, -86.48570684886621507 48.78281483260323625 0, -86.48572352971778798 48.78290414201140379 0, -86.48575714008055115 48.78299181681025232 0, -86.48581170720029832 48.78307634832925999 0, -86.48587121879297968 48.7831602091844303 0, -86.48589099992655349 48.78325056603286214 0, -86.48587842649847346 48.78334016863076528 0, -86.48586057292833118 48.783431196029305 0, -86.48585889649609726 48.78352121786612372 0, -86.48583601414432565 48.78361077806746948 0, -86.48577734134794071 48.7836951417273923 0, -86.48570441853182444 48.78377133367354901 0, -86.48558547965971854 48.78382652864120672 0, -86.48545857710965379 48.78386797712459355 0, -86.48532941180690159 48.78389957643459951 0, -86.48519261882624676 48.78387966999405023 0, -86.48507594371240259 48.7838311380252776 0, -86.48496169842543679 48.78378051173061891 0, -86.48487092246965346 48.78371073157079252 0, -86.48478685092001683 48.78363965259788415 0, -86.48471024133529284 48.78356308517563633 0, -86.48466756317129978 48.78353180597167693 0) | R1901 | ANWIN | C | Temp | WF6 | C248 | 0.3 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.45729491056630422 48.78119374218305637 0, -86.45729386430659247 48.78126300835945273 0, -86.45735228629061453 48.78134661800449123 0, -86.45747206363368775 48.78139732835061437 0, -86.45761111992061387 48.78139833456658891 0, -86.4577551204872492 48.78140311341438462 0, -86.45789308734555334 48.78142767112453271 0, -86.45813448610509511 48.78143634674266593 0, -86.45826432136469464 48.78146530620994525 0, -86.45837898598261972 48.78151408892324525 0, -86.45849750633101394 48.78156890617031394 0, -86.45858526446758674 48.7816394819454473 0, -86.45866941851286924 48.78171395489027162 0, -86.45876731939041804 48.78177736425946165 0, -86.45887955409097003 48.78183930612172503 0, -86.45896657830343202 48.78187947163547733 0, -86.45912313140374295 48.78186156037853038 0, -86.45922388268657244 48.78179986979568383 0, -86.45927233025336989 48.78171571540214302 0, -86.4593576578194245 48.78164174475103465 0, -86.45934340810204333 48.78155189140615278 0, -86.45927308360523966 48.78147083758015157 0, -86.45922354663586873 48.78138500720559279 0, -86.45920971653032439 48.78129008205732475 0, -86.45919588691188551 48.78119498958223943 0, -86.45922664834060356 48.78110211783828731 0, -86.45930082842926367 48.78102617786846906 0, -86.45930049211753499 48.78093481457717218 0, -86.45937341491092809 48.78085828841764027 0, -86.45941988996902694 48.78079380617614902 0) | R1905 | ANWIN | C | Temp | WF6 | C252 | 0.3 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C252 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.67589313401991546 48.80442131566746156 0, -86.67603436961020691 48.80444268943043795 0, -86.67618054927318383 48.80444306688362843 0, -86.6762951306040037 48.80450123711953125 0, -86.67640945922201468 48.8045561805862036 0, -86.67654876741983117 48.80458384096957758 0, -86.67668136871793649 48.80461422523578108 0, -86.67682536967153339 48.80461166758053082 0, -86.67696752684399542 48.80460504740819516 0, -86.67710675018804523 48.80459444443494021 0, -86.67724588993890222 48.80460471164705183 0, -86.67738209619244572 48.80461095559176954 0, -86.67752651615461446 48.80461950642355617 0, -86.67765660418768903 48.80464775319673265 0, -86.67780219716019019 48.8046562601842453 0, -86.67794360064374359 48.80468056835105273 0, -86.67809916800007386 48.80469016525101011 0, -86.67824308599321625 48.80471677763571137 0, -86.67837359135026531 48.80475483124065761 0, -86.67850761893762979 48.80477197265757638 0, -86.67863804052338139 48.80480805741668604 0, -86.67877516844176 48.80483642960354729 0, -86.67891523096008655 48.80486124021137329 0, -86.67903626551461116 48.80490352626228656 0, -86.67916962169563533 48.80493592305669637 0, -86.67931102427205303 48.80494992019171718 0, -86.67944890623610377 48.80492335005764915 0, -86.67959416498398184 48.80491052537202279 0, -86.67973028745906561 48.80492368508719636 0, -86.67980235481164186 48.80494757700836317 0) | R1953 | ANWIN | C | Temp | WF6 | C207 | 0.3 | 10 | 20 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C207 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.23016 | 0.069839
LineStringZ (-86.77078043476761593 48.80825072812324095 0, -86.77075803610338767 48.80820552942132906 0, -86.77071168396146561 48.80811563358229677 0, -86.77067505555201876 48.8080220498457038 0, -86.77064923954833375 48.80793332741832558 0, -86.77062912244943504 48.80783944996167634 0, -86.77062099237738835 48.80774729118600419 0, -86.77057665239078688 48.80766070619247898 0, -86.77054278894298989 48.80757198391156493 0, -86.77051093783403246 48.8074762622946281 0, -86.77044614513656029 48.80739550277285588 0, -86.77033475065714185 48.80732790227987294 0, -86.77020734484396769 48.80729500394502907 0, -86.7700758325526067 48.80724580205166063 0, -86.76996670070393236 48.80718096656467253 0, -86.76988095331741135 48.80710163303849924 0, -86.76978749593052953 48.80702326190760942 0, -86.76964039264218798 48.80701731139442501 0, -86.76951374232604053 48.80696693560794586 0, -86.76938323621186555 48.80700515738097067 0, -86.7692488737964851 48.80702804042294218 0, -86.76911845242916854 48.80707531377024111 0, -86.76899515399129825 48.80711898398067916 0, -86.76891091587172866 48.80719408588350205 0, -86.76881083642767578 48.8072636135620499 0, -86.76870078205840287 48.80732153258214367 0, -86.76858980544108135 48.80738062541328048 0, -86.76844136201675894 48.80741411063439017 0, -86.76831898610059568 48.80746180315318838 0, -86.76822816201446642 48.80751459400621428 0) | R2011 | ANWIN | C | Temp | WF6 | C188 | 0.3 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.3 | 0.3 | All-season | 0.18735 | 0.11265
LineStringZ (-86.76646574595413597 48.80914212381492945 0, -86.76637044452625958 48.8091496681023429 0, -86.76623650135992705 48.80913122658699166 0, -86.76609618856211625 48.80911827659921443 0, -86.76595612664358725 48.80910440576702314 0, -86.76582017203209318 48.80914447099199549 0, -86.76569544955690105 48.80918805740307675 0, -86.76556930199190276 48.80924337776649935 0, -86.7654278992484933 48.8092576266324869 0, -86.76530418184896121 48.80921500489917975 0, -86.76516319797305243 48.8092238477412792 0, -86.76502464594813091 48.80922787085246028 0, -86.76487703971365306 48.80924346118410995 0, -86.76473639130891513 48.80925800400772374 0, -86.7646002697377412 48.80927233730292158 0, -86.76450639167651957 48.80933763230793687 0, -86.76438259143560572 48.80938083955374651 0, -86.76427798567566185 48.80944701563535659 0, -86.76414479625562137 48.80949001541035415 0, -86.76400791995550321 48.8095036357834644 0, -86.76387280446587624 48.80952454900013748 0, -86.76374338698180111 48.80955862128312361 0, -86.76361036650182257 48.80959449601267863 0, -86.76345965968934593 48.80957978528821428 0, -86.76333083003015645 48.80953951058024387 0, -86.76319948524020731 48.80951247886238775 0, -86.7630668832563714 48.80948838068113105 0, -86.76293252236196452 48.80946298331650013 0, -86.76279304671730586 48.80944232242089953 0, -86.76265457808644044 48.80945217131613845 0, -86.76264236383248374 48.80944721729875369 0) | R2012 | ANWIN | C | Temp | WF6 | C189 | 0.3 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.74660167144229206 48.80692187556741146 0, -86.74657112551879834 48.80688194474230812 0, -86.74648319882109604 48.80680520861317007 0, -86.74640222943507695 48.80673165698888027 0, -86.74632159571632428 48.80665613683570569 0, -86.74623895003087171 48.80658317243833011 0, -86.74622872457757694 48.80649222803561571 0, -86.74618756887488757 48.80640606343982313 0, -86.74617751110574204 48.80631214264465711 0, -86.74619896835260136 48.80621927179571173 0, -86.74627298017377086 48.8061418645926608 0, -86.74635076509112253 48.80606483537645346 0, -86.74637607735232336 48.80597523220009037 0, -86.74639493778812493 48.80588164941516993 0, -86.74638177767954517 48.80578630404492912 0, -86.74627574711588807 48.80572675062479249 0, -86.74621849746462487 48.80564129726570854 0, -86.74614632984116724 48.80555798084487407 0, -86.746059744322352 48.80548539445285883 0, -86.74602923513462827 48.80539151673437459 0, -86.74597181917793876 48.80530220722343415 0, -86.74593066370000827 48.80521277159591165 0, -86.74581717200958053 48.80515342889919594 0, -86.74568188781432809 48.80513310376012726 0, -86.74553730004593888 48.80513712611381294 0, -86.7453985806526191 48.80513926310543127 0, -86.74526136774305485 48.80518410606298829 0, -86.74512348536264028 48.80521373615044212 0, -86.74500060709222282 48.8051576194269856 0, -86.7448609641893853 48.80518205285240185 0, -86.7448286660554686 48.80518893431890604 0) | R2017 | ANWIN | C | Temp | WF6 | C193 | 0.3 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd W - ML - WF6 | 0.3 | 0.3 | All-season | 0.2846 | 0.015396
LineStringZ (-86.68184479196985137 48.81704492409649276 0, -86.681800284145055 48.81695326863484041 0, -86.68178779506561682 48.81685754722523285 0, -86.68181059475402606 48.81676622597151294 0, -86.68181897538640612 48.81667469579129914 0, -86.68182811185872083 48.81657909973848319 0, -86.68186666951488917 48.81648924601549311 0, -86.68188083406519695 48.81639876362064001 0, -86.6819064834264168 48.81630157496674371 0, -86.68193380851768381 48.81621100833096705 0, -86.68194805753228138 48.81611704743269797 0, -86.6819830093716206 48.81602518212223885 0, -86.68203397220632667 48.81593180736707893 0, -86.68208837015966139 48.81583780425027896 0, -86.68211988598886819 48.81574359137743357 0, -86.68215743658902284 48.81565189330206067 0, -86.682250812275214 48.81557410926860996 0, -86.68237100834669207 48.8155248657667542 0, -86.68252104480674802 48.81551409533524577 0, -86.68266227980822691 48.81553295464799191 0, -86.6828054429607846 48.81551782529091099 0, -86.68294374381544287 48.81547708897586091 0, -86.68306980769555992 48.8154344665915545 0, -86.68320861217367224 48.81541317693515225 0, -86.68332503678510648 48.8153643106977313 0, -86.68342151274524099 48.81529524318565194 0, -86.68348261651007647 48.81521133955190805 0, -86.68355537084225659 48.81512978521725898 0, -86.6836168113761687 48.81504814491005106 0, -86.68363932311983433 48.81501577997767782 0) | R2023 | AU2 | C | Temp | WF6 | C203 | 0.3 | 7.5 | 15 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.50615847415572546 48.78186173496581546 0, -86.5059053146749477 48.78181910283819178 0, -86.50579020300175159 48.78180278444134643 0, -86.50573046733936167 48.78173159569757189 0, -86.50571001603576349 48.78164270574034589 0, -86.50570666258798269 48.78155058757178608 0, -86.50564329627013649 48.78146781704631252 0, -86.50556970337324003 48.78138986585499737 0, -86.50552594862762135 48.78130353241013495 0, -86.50552678707019538 48.78120986421084382 0, -86.50547842354136208 48.78112323659428284 0, -86.50546735917363605 48.78103346656779848 0, -86.50545179643089 48.78096415304409561 0, -86.50545358485015868 48.78087106915823767 0, -86.50547968148185873 48.78077861493673595 0, -86.5054158942702287 48.78069559237899 0, -86.50530500161573855 48.78064140311985852 0, -86.50516737047442462 48.7806258546514897 0, -86.50503812245905522 48.78065607141465421 0, -86.5049202729323099 48.78070334574252342 0, -86.5048774412798025 48.78079085301491347 0, -86.50490811924862555 48.78087848534244841 0, -86.50497676626423527 48.7809618439120527 0, -86.50502320228122244 48.78105085910092242 0, -86.50507977971776086 48.78113392377979096 0, -86.50512546104008038 48.7812206767869796 0, -86.50517181374577547 48.7813075550027051 0, -86.50518488991110644 48.78139812174066492 0, -86.50515345790887523 48.78149401104359129 0, -86.50514650769849823 48.78157636301063604 0) | R1716 | ANWIN | C | Temp | WF6 | C244 | 0.3 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.67051899076689381 48.80327965909110333 0, -86.67065578455429886 48.80331197122357167 0, -86.67079861174967448 48.80331469566667835 0, -86.67094060187535831 48.80330715137008468 0, -86.67107982505032737 48.80331100676199441 0, -86.67121728755985544 48.80331733534686833 0, -86.67134796176661382 48.80327961735617492 0, -86.67148793945814589 48.80328032942382066 0, -86.67162749874938754 48.80327337198549031 0, -86.67176739268872154 48.80328858583912677 0, -86.67191114199938795 48.80329629708253236 0, -86.67204961106742189 48.80329822492393532 0, -86.67217743570461153 48.80332986742134693 0, -86.67228648330636531 48.80338451660201571 0, -86.67242478534478778 48.8033899654302914 0, -86.67256224838453704 48.80338267345076986 0, -86.67270004730940514 48.80339847215395821 0, -86.67283256476289921 48.80342060144209171 0, -86.67295988686164776 48.8034567684039402 0, -86.67309475105255956 48.80347219127399683 0, -86.67322223988337271 48.80350936506461323 0, -86.67336095993147183 48.80351845911120279 0, -86.67349808879627915 48.80352177038831485 0, -86.67363856973098279 48.80349855205543719 0, -86.67377754073750395 48.80349205633842047 0, -86.67388748087201122 48.80347679094247582 0, -86.67402229325801954 48.80350425185367413 0, -86.67415187778378538 48.80353463590463292 0, -86.67425581216772912 48.803594859744166 0, -86.67435270815411741 48.8036642205777369 0, -86.67438670893582753 48.80369418226344891 0) | R1739 | ANWIN | C | Temp | WF6 | C208 | 0.3 | 10 | 20 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C208 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.21771 | 0.082294
LineStringZ (-86.64832052023616882 48.80289690027465355 0, -86.64845982713700323 48.80292032784398515 0, -86.64858991438275382 48.80295138269099198 0, -86.6487237732792579 48.80297845558299485 0, -86.6488574649602441 48.80301253025648833 0, -86.64899241274468977 48.80302782595811806 0, -86.64912694301558815 48.80299639257398781 0, -86.64925702972170996 48.80296550685930157 0, -86.6493902190631502 48.80294274927872067 0, -86.64954084153788472 48.80292833341506054 0, -86.64967931094909659 48.80291274243317901 0, -86.64981920417670835 48.80291307843986459 0, -86.64995599647443214 48.80290050466957297 0, -86.65008993927072822 48.80287468814676544 0, -86.65022840930136283 48.80286660002819588 0, -86.65036436281862109 48.80285809209583192 0, -86.65050291601261279 48.80284233395375537 0, -86.65064021186499588 48.80282720514923511 0, -86.65078320679076285 48.80281660221650952 0, -86.6509133778435654 48.80285851100601491 0, -86.65103357515666005 48.80290452759074782 0, -86.65115385483375121 48.80294891063461193 0, -86.65128402617915526 48.8029822278741463 0, -86.65141017332611284 48.80301713857365087 0, -86.65152609617410917 48.80307128574860798 0, -86.65166188250960033 48.80309601221140525 0, -86.65179859094159553 48.80309437777334125 0, -86.65193873713100459 48.80308834284006991 0, -86.65208634249374597 48.80306432935752525 0, -86.65221517146730434 48.80302346719980022 0, -86.652216882936969 48.80302233707478621 0) | R1742 | ANWIN | C | Temp | WF6 | C213 | 0.3 | 10 | 20 | C214 - ML - WF6 | C214 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | 0 | C214 - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.60994195130369633 48.7975423178422858 0, -86.60994480108922744 48.7975448058734429 0, -86.61001453900846059 48.79762309260948427 0, -86.61011118130828379 48.79769278830535484 0, -86.61024604637124469 48.79771470697061631 0, -86.61039759181660713 48.79772279569133531 0, -86.61054502895383678 48.79774303827049664 0, -86.61068391699254221 48.79775929896089082 0, -86.61082071025306561 48.79778725255940941 0, -86.61094669040208771 48.79782383980735716 0, -86.6110662994662448 48.79786763457521204 0, -86.61120862548034438 48.79787061020123673 0, -86.61133317928630504 48.79791034080150069 0, -86.61146896672262585 48.79792052501262845 0, -86.61161439263686646 48.79794248486866337 0, -86.61174238489364541 48.79797802459775369 0, -86.61175371549018109 48.79797997890206318 0, -86.6119285470885103 48.79801012657090808 0, -86.61204857586534445 48.79796134428988807 0, -86.612195509882838 48.79793892241361419 0, -86.61233607546527935 48.7979263502007683 0, -86.61246641304271066 48.797961888916916 0, -86.61260437946474156 48.79794927435339247 0, -86.61273354499492427 48.79798833434536931 0, -86.61287293616473448 48.79800132585390315 0, -86.61300645940548293 48.79803862527158032 0, -86.61313587594302987 48.79806884262446687 0, -86.61327510054005074 48.7980792773345371 0, -86.61337593373345101 48.7981481351250963 0, -86.61343653577580426 48.79823132521813989 0, -86.61354684198242637 48.79828576621260794 0, -86.61357905015788106 48.79831948759883176 0) | R1744 | ANWIN | C | Temp | WF6 | C220 | 0.3 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C220 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.414383289692978 48.77190453833179618 0, -86.41431438284099897 48.77183533881195387 0, -86.41418714570866655 48.77179242336541876 0, -86.4140895802301543 48.77172666655486211 0, -86.41400324686541978 48.77165579944760765 0, -86.41390719087638672 48.77159159297590918 0, -86.41378758009381045 48.77153841000758661 0, -86.4136991512233692 48.77146686990236901 0, -86.41358205670091763 48.77142064356098672 0, -86.41347451690428727 48.77135849236127285 0, -86.41334803337434778 48.77132219910227207 0, -86.41326513604177251 48.77125070121049788 0, -86.41314083338737362 48.77121147442241522 0, -86.41305474996642033 48.77114060427001618 0, -86.41295902919881655 48.77107304678313682 0, -86.41283824557572757 48.77102703028905495 0, -86.41271008611718685 48.7709864618665847 0, -86.41262048370785465 48.77091563462692392 0, -86.41252073944343692 48.77085415288151893 0, -86.4124274491807256 48.77078776872619414 0, -86.4123421213813856 48.77071643859057559 0, -86.41226023013898327 48.77064150411077748 0, -86.41223424554485177 48.77055227932159909 0, -86.412219829395994 48.77046070618509077 0, -86.41213382991431047 48.77038321557527922 0, -86.41201757385518079 48.77033615167771785 0, -86.41190106557364459 48.77027819037203216 0, -86.41184901347708092 48.77018598972026098 0, -86.41175982999777716 48.77010527189096933 0, -86.41174516121853344 48.77001583665574458 0, -86.41174952872360393 48.76999228392547536 0) | R1759 | ANWIN | C | Temp | WF6 | C263 | 0.3 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C263 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.3 | 0.3 | All-season | 0.23787 | 0.06213
LineStringZ (-86.40577640610882781 48.76717931726132349 0, -86.40584262313211639 48.76721313834322302 0, -86.40597212365806001 48.76725203010289533 0, -86.40610153995821463 48.76729611919758867 0, -86.40619474721626148 48.76736506028164797 0, -86.40633019828413808 48.76739770755495584 0, -86.40643094848572048 48.76746476304726485 0, -86.40655936010816163 48.76750642111689871 0, -86.40668936307376669 48.76753454189037029 0, -86.40677678670770945 48.76760369291893227 0, -86.40689773771809712 48.76764866143467003 0, -86.4070113959931092 48.76770980767025776 0, -86.40713536425698749 48.76775364536378987 0, -86.40726201451940369 48.76780284666488541 0, -86.40740450680992524 48.76778071868467634 0, -86.40752344654769956 48.76772338667603179 0, -86.40762645957937593 48.7676554104267268 0, -86.40775612843677322 48.76768969056809766 0, -86.40789375962582142 48.76771173456921815 0, -86.40801688908810263 48.76775058589432632 0, -86.40807749020888195 48.76783364997309178 0, -86.40813666666588233 48.76791671479863055 0, -86.40821202018719305 48.76799839630558608 0, -86.40830640046966948 48.76806897267453422 0, -86.40840195484531705 48.76813728529010916 0, -86.40848845588114102 48.7682110038616301 0, -86.40858560181710857 48.76828162118116694 0, -86.40871384546125 48.76832365740989417 0, -86.40883077188050265 48.76837730061345866 0, -86.40893521158682233 48.76843760869928701 0, -86.40895448006685342 48.76844484767726584 0) | R1760 | ANWIN | C | Temp | WF6 | C264 | 0.3 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR1 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.092789 | 0.20721
LineStringZ (-86.72731614300548131 48.80582524758625595 0, -86.72739667661238627 48.80577201480080873 0, -86.72749290170074232 48.80570449842445413 0, -86.72757043371974817 48.80562704855811518 0, -86.72765919778538546 48.80555752180848117 0, -86.72772868456914352 48.80547680259448384 0, -86.72778635187648888 48.80539369669232741 0, -86.7279088956102413 48.80534533328893332 0, -86.72802414682269045 48.80529483220692555 0, -86.72815792133182811 48.80526088583523858 0, -86.72830100105848317 48.80526155601433658 0, -86.72843284832258348 48.80522052677818579 0, -86.72856721035036287 48.80520405682169383 0, -86.7287064334082487 48.80521122327752437 0, -86.72884121482421449 48.80517782093745183 0, -86.72897809128531321 48.80517589295058656 0, -86.72910926757816696 48.80513767169361472 0, -86.72923449387241135 48.80510167180150916 0, -86.72937489098744379 48.8050915716081235 0, -86.7295103415789157 48.8050792079537672 0, -86.72963875293926606 48.80503863976279888 0, -86.72977554551049195 48.80503780093993527 0, -86.72992038446807328 48.80502522941543475 0, -86.73006136873564742 48.80503050921489461 0, -86.73020914166403372 48.80502418108105189 0, -86.73035456827345513 48.80503889056411282 0, -86.73049161128913909 48.80506349198589788 0, -86.73063645131630039 48.80506646724133191 0, -86.73076327002533503 48.80510699424307575 0, -86.73089235147561737 48.80513674925561673 0, -86.73090842520687715 48.80514425610509477 0) | R1825 | ANWIN | C | Temp | WF6 | C197 | 0.3 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | Required | Ripple Lake RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.68523466525603283 48.81146993540648538 0, -86.68530324955337107 48.81144920711832214 0, -86.68543400720399461 48.81140310631788992 0, -86.68556308930310195 48.81136484345149285 0, -86.68568043567799464 48.81130021824972687 0, -86.68575822016106258 48.81121782427598532 0, -86.68580001738591534 48.81116074387373516 0, -86.68585964107319342 48.81108425833414088 0, -86.6858483254042369 48.81098501676196832 0, -86.68584069702011163 48.81089512121425145 0, -86.68582804004711306 48.8108043447519151 0, -86.68586886021968496 48.8107158739505067 0, -86.68586190385130408 48.81062589387032347 0, -86.68586860973772446 48.810535537206583 0, -86.6858825228689085 48.81044593424872602 0, -86.68592652834985302 48.81035922360946699 0, -86.68596977914550905 48.81026836377120048 0, -86.68602057237805525 48.81018475359114461 0, -86.68610154268377244 48.81010722225412479 0, -86.68616717260094617 48.81002570797812723 0, -86.68623079161766043 48.80994184744836417 0, -86.68628921349072414 48.80985375274642024 0, -86.68631980689454508 48.80976536458990012 0, -86.68635434077529567 48.80967496665875416 0, -86.68635668731364774 48.80958502899637352 0, -86.68636791950648046 48.8094802551246616 0, -86.68636574008816353 48.80938834762968526 0, -86.68636884081804794 48.80928579521637545 0, -86.68633397271119634 48.80919137257224349 0, -86.68631134110530922 48.80909866905315653 0, -86.6862915134519767 48.80905189290877644 0) | R2024 | AU2 | C | Temp | WF6 | C203 | 0.3 | 7.5 | 15 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | AU2 | Required | Dead Horse Creek RD - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.65678314055956832 48.80178666610941463 0, -86.65680124852099198 48.80175511725286697 0, -86.6568230404347446 48.80166304201582506 0, -86.65686210033572934 48.80157448701655198 0, -86.65697617837950872 48.80151711303186346 0, -86.65710400206928909 48.80146753433327689 0, -86.65724322618744679 48.80144636981648887 0, -86.65736845157208279 48.80139192888341171 0, -86.65749300694982082 48.80133924902943221 0, -86.65761496387413843 48.80129775858191721 0, -86.65772686218004139 48.80123929426564189 0, -86.65784630364585439 48.80119537259461993 0, -86.65798401824537223 48.80119457763048985 0, -86.65810882480839439 48.80115706772682671 0, -86.65824268414198173 48.8011265995706367 0, -86.65838836155371894 48.80112450442749861 0, -86.65850813875420044 48.80106289702633404 0, -86.65859053386043342 48.80097995823854973 0, -86.65867535812635936 48.80090644894282548 0, -86.65871642962605392 48.80081206898685764 0, -86.65878306611489279 48.80073285990034293 0, -86.65905237587359977 48.80068080827290089 0, -86.65919042665377958 48.80072083199111432 0, -86.65932202276134433 48.8007522219442933 0, -86.65945956913817838 48.80076160993664303 0, -86.6595973678155076 48.80078604333831294 0, -86.65971597161727402 48.80083495187015785 0, -86.65983608472998867 48.800892284043762 0, -86.65995384962934622 48.80093804756839404 0, -86.6599912706109734 48.80094238065368017 0) | R2026 | ANWIN | C | Temp | WF6 | C211 | 0.3 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C211 | ANWIN | Required | Middleton Road - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.6443467556290301 48.80106861191285361 0, -86.64438060379163176 48.80099391499813777 0, -86.64442645330424853 48.80090263597094946 0, -86.64446316645803847 48.80080616056948628 0, -86.64451094295262124 48.80071945019687973 0, -86.64457120908194554 48.80063625974909769 0, -86.6446040655852272 48.80054783008203856 0, -86.64462954706240794 48.80044951090602012 0, -86.64471303115006151 48.80036510463733634 0, -86.64469551289973026 48.80027051486331402 0, -86.64461135865136043 48.80019864044804478 0, -86.64448001364509366 48.80015094728975811 0, -86.64434858491962643 48.80012437622276877 0, -86.64425051652840182 48.80005237584735767 0, -86.64425286427979245 48.79996243794547439 0, -86.64421087010711631 48.79986835098922882 0, -86.64417675575798228 48.7997732169223255 0, -86.64416233936039191 48.7996834467686682 0, -86.64415714319515871 48.79959350896385217 0, -86.64414767116409166 48.79950030142153139 0, -86.64412562610651491 48.79940826861458447 0, -86.64415387331517593 48.79931615177791571 0, -86.64418723411382928 48.79922051440768627 0, -86.64423635186413719 48.79913539605207262 0, -86.64420651208777713 48.79903799829808264 0, -86.64421346934639701 48.79894324018236773 0, -86.64421464183057253 48.79885062143985408 0, -86.64421229609261843 48.79875389327897039 0, -86.64422453331249585 48.79866039289692026 0, -86.64422708394096162 48.7985976026974555 0) | R2028 | ANWIN | C | Temp | WF6 | C213 | 0.3 | 10 | 20 | Little Pie River Rd - ML - WF6 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | 0 | Little Pie River Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.40425569039207687 48.77520559744737483 0, -86.40470821667985035 48.77509661156600629 0, -86.40483201818551606 48.77504250738404323 0, -86.40494492236915391 48.7749735663223376 0, -86.40507366742230033 48.77493345914422918 0, -86.40521624401903011 48.77494158886838704 0, -86.40536393397042048 48.77496426259749285 0, -86.405503576342511 48.77498056501691792 0, -86.40563818893235748 48.77495956806203026 0, -86.40578487307487876 48.77497038109119387 0, -86.40591261327207917 48.77500914771738394 0, -86.40604538175789173 48.77505654662014933 0, -86.40618460557665514 48.7751012222446434 0, -86.40633053503468375 48.77510901791843878 0, -86.4064806549936435 48.77508370439603169 0, -86.40661635835419929 48.77506010936382808 0, -86.40676765189178354 48.77503936429804554 0, -86.40691760294492951 48.77505273318005408 0, -86.40705892210905859 48.77505223055554495 0, -86.40717082036663044 48.77499309591439669 0, -86.40727819347139871 48.77491979612790374 0, -86.40736947256576173 48.77485160959513166 0, -86.40746318117908231 48.7747831709968267 0, -86.40754624598233136 48.77469876542352978 0, -86.4076345084208981 48.77461389891900012 0, -86.40773685042616137 48.77454399313563727 0, -86.40779600289720008 48.77452024260064434 0) | R2053 | AU2 | C | Temp | WF6 | C264 | 0.3 | 7.5 | 15 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.40854531530578697 48.77385126078286248 0, -86.4085830884919659 48.77379507017526805 0, -86.40858325570060572 48.773694277658457 0, -86.4085653186921121 48.77359796941902914 0, -86.40855375084234424 48.7735081997931772 0, -86.40858535152263187 48.7734066950616878 0, -86.40861887822245535 48.77331721800676689 0, -86.40868828114962241 48.77323080014667767 0, -86.40880302863627094 48.77315557292459403 0, -86.40893395511001529 48.77311726732952479 0, -86.40901601319721692 48.77303956655865846 0, -86.40908608592388873 48.77295675390357133 0, -86.40917233652716334 48.77286690017973569 0, -86.40922715382910724 48.77278123665173126 0, -86.40928775524744765 48.77269058745250874 0, -86.40933016645958276 48.77259842811997714 0, -86.40934391295265016 48.77250350222301023 0, -86.40935112164184773 48.77240644044377404 0, -86.40935489380109402 48.77230833010500533 0, -86.40936436547291066 48.77220862698783321 0, -86.40937258002128374 48.77211039097672796 0, -86.40934877476846054 48.77202057938602309 0, -86.40925615507848079 48.77194187333880393 0, -86.40913025878350595 48.7718931324443048 0, -86.40898533540450899 48.77186044262828801 0, -86.40885566676917051 48.77182075459189292 0, -86.40873027379041105 48.77176166230010068 0, -86.40863463670419264 48.77169200827444939 0, -86.40856163064482587 48.77161573317438581 0, -86.40855346862123554 48.77160543400572124 0) | R2054 | AU2 | C | Temp | WF6 | C264 | 0.3 | 7.5 | 15 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.42840964835988871 48.77628843369573985 0, -86.4282703411021771 48.77629798920310122 0, -86.42813631417213571 48.77633109805125144 0, -86.42801192733902838 48.77637707302515935 0, -86.42790706923693733 48.77643985312315777 0, -86.42779693091895865 48.77649534171945334 0, -86.42766483221168983 48.77652614491456973 0, -86.42755444278277821 48.77658368672434364 0, -86.42741555415145172 48.77659835482064921 0, -86.427295609402222 48.7766430727537994 0, -86.42717038355466741 48.77668070693136571 0, -86.42702856255039023 48.77669885404378647 0, -86.42689277506588041 48.77666620703227807 0, -86.42675330045150872 48.77663846234808176 0, -86.42661080786920991 48.77665510057104825 0, -86.4264637889600067 48.77663653443234182 0, -86.42632221824301553 48.77662362673731877 0, -86.42619439463963715 48.77658590789904736 0, -86.42605869154502329 48.77657291574261933 0, -86.42591326561840503 48.77654957274643976 0, -86.42577580278899063 48.77652870176676458 0, -86.42563079543380411 48.7765474349178163 0, -86.42549266211759118 48.77656922841535447 0, -86.4253666811072776 48.77660673722343176 0, -86.42524262934774981 48.77656847388254846 0, -86.42511170331356141 48.7765376698094002 0, -86.42498740012487701 48.77649785582285347 0, -86.42486100071100452 48.77646307171525564 0, -86.42473594240942703 48.77642111983067963 0, -86.42464447504367797 48.77636752641830498 0) | R2089 | ANWIN | C | Temp | WF6 | C259 | 0.3 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C259 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.32458959765516227 48.72178064174293155 0, -86.32456891885090045 48.72178723434109315 0, -86.3244076229549222 48.72189499440315785 0, -86.32427904483523662 48.72197516785318783 0, -86.32413646865435908 48.722037277578508 0, -86.32399431085798369 48.72200534219713575 0, -86.32385181945696218 48.72192152307638224 0, -86.32373790820346926 48.72186276742593236 0, -86.32361511357926531 48.72182223965990033 0, -86.32350044920775645 48.72175124460888185 0, -86.32336348883522703 48.72168649497290005 0, -86.32324111354934359 48.72164567509498312 0, -86.323106081010053 48.72157652386990634 0, -86.32296979039125517 48.7215194855858087 0, -86.32282998034916943 48.72147011635206582 0, -86.32267206611145127 48.72146009937333133 0, -86.32252680691534863 48.72147765957171828 0, -86.32236595795079381 48.72148692162834038 0, -86.32216948660068567 48.72152388621515229 0, -86.32198793478686127 48.72160087390408023 0, -86.32189129169657349 48.72166759357068599 0, -86.32177838747581688 48.72172739837022704 0, -86.32166204667807108 48.72178703619006512 0, -86.32154520213896376 48.72186591006024514 0, -86.32142751968744676 48.72193275644206523 0, -86.32133079303433476 48.72199901544194489 0, -86.32123088072684425 48.72207323606481566 0, -86.32111423285282115 48.72211547569535384 0, -86.32098034564920397 48.7221198397458366 0, -86.32084003196607114 48.72213920190066005 0, -86.32069561285787529 48.72213962080957117 0, -86.32056169676094726 48.72213199055649824 0) | R639 | AU1 | D | Temp | WF7 | D009 | 0.35266 | 7.5 | 15 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D009 | AU1 | Required | Three Finger Lake RD - ML - WF7 | 0.35 | 0.35 | All-season | 0.35266 | 0
LineStringZ (-86.32603898795161967 48.72145173404629048 0, -86.32561361199206829 48.72151043234850931 0, -86.32539224502437492 48.72154090094407053 0, -86.32523223533979717 48.72158268484537302 0, -86.32506493267058545 48.72162006807720758 0, -86.32489025300961316 48.72167446631333831 0, -86.32473108027907926 48.721735528640572 0, -86.32458959765516227 48.72178064174293155 0) | R640 | AU1 | D | Temp | WF7 | D009 | 0.11352 | 7.5 | 15 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D009 | AU1 | Required | Three Finger Lake RD - ML - WF7 | 0.11 | 0.11 | All-season | 0.11352 | 0
LineStringZ (-86.32056169676094726 48.72213199055649824 0, -86.32041004103639636 48.72211145761814777 0, -86.32027148742807299 48.72209796298281503 0, -86.32012815763415858 48.72208404866697151 0, -86.31999932759136129 48.7220474199412763 0, -86.31986027097850922 48.72203434466067051 0, -86.31972887153105489 48.72203289964295436 0, -86.31959923143520541 48.72203407914142304 0, -86.31945975600729071 48.72202051331351669 0, -86.31928764699877377 48.72198099499436807 0, -86.31912135033803679 48.72192378118064227 0) | R337 | AN | D | Temp | WF7 | D010 | 0.10974 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D010 | AN | Required | Three Finger Lake RD - ML - WF7 | 0.11 | 0.11 | All-season | 0.10974 | 0
LineStringZ (-86.30259247942343848 48.72159826255695236 0, -86.30250184684688008 48.7215906906598093 0, -86.30231426028372255 48.72155012306661348 0, -86.30218090364728312 48.72152988023365339 0, -86.30204436253099232 48.72150238775829934 0, -86.301905558998385 48.72147627941370729 0, -86.30175180632615195 48.72148170264312483 0, -86.30162644131800675 48.72150050136722399 0, -86.30149886830427874 48.72154039961124994 0, -86.30138831152559931 48.72159999538096997 0, -86.30126694056744441 48.72164697584953785 0, -86.30113936894785809 48.72166219189366387 0, -86.30100978488478347 48.72165288470453248 0, -86.30087240507154434 48.72161470643431613 0, -86.30074424496868346 48.72156977837223479 0, -86.3006156674308329 48.72153859733433023 0, -86.30047895873771324 48.72152736610804169 0, -86.30033688468920161 48.72153075955132095 0, -86.30019556536537095 48.72153365271980618 0, -86.30005927677466104 48.72153134771839689 0, -86.29993614541567126 48.72148809559737259 0, -86.29981913507728564 48.72144182815001301 0, -86.29968661698597998 48.72141827514438006 0, -86.29962693797806139 48.72144228924518927 0) | R340 | AN | D | Temp | WF7 | D013 | 0.23175 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D013 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.23 | 0.23 | All-season | 0.23175 | 0
LineStringZ (-86.77620307553644352 48.80573098218682304 0, -86.77630090729871881 48.80578290768175265 0, -86.77637190138118228 48.80586609766741191 0, -86.77644281181615327 48.80594916240236358 0, -86.7765446522319337 48.80601215236107748 0, -86.77665437181443053 48.80607049040646928 0, -86.77676400710997484 48.80612547629971942 0, -86.77686953596023045 48.80619408207473953 0, -86.77699300111389391 48.80623423144134421 0, -86.77707137172386354 48.80631528433222854 0, -86.77717748620553095 48.80637638834937775 0, -86.7772920676478634 48.80643296658132613 0, -86.77739893715992991 48.80649499213549802 0, -86.77751536139039956 48.80655320466473057 0, -86.77764603450980019 48.80657935607938214 0, -86.77773572159823345 48.80664716584242768 0, -86.77785005098186843 48.80670466511332251 0, -86.77797435484333732 48.80674934089288541 0, -86.77809932823444683 48.80680591944164348 0, -86.77820703626811394 48.80686844782881195 0, -86.77829814711873269 48.80694723762228904 0, -86.77837517753297902 48.80702686568087501 0, -86.77843385099222928 48.80710917607483879 0, -86.77845748788845981 48.80720741206953051 0, -86.77849746878780479 48.8073021278716439 0, -86.7784689713484596 48.80739210706278897 0, -86.77846369062960719 48.80749269028706294 0, -86.77846369045097674 48.80759352474860435 0, -86.77846729488436495 48.80768736010685416 0, -86.7784954579777974 48.807783416972363 0, -86.77858346782748811 48.80786233190861623 0, -86.77869318699154633 48.80792469366862463 0, -86.77880868890410682 48.80798127124300123 0, -86.77893165217875548 48.80804275229691314 0, -86.77906458946813473 48.80807540059683447 0, -86.77919174262619606 48.80812728445059179 0, -86.77930355717674615 48.80819165843045226 0, -86.7794170482974323 48.80824492373987056 0, -86.77950271130598026 48.80831755341944955 0, -86.77959055342603278 48.80838900873449404 0, -86.77966322526320653 48.80846561933866212 0, -86.77974176294321751 48.80854575041508525 0, -86.7798205537611409 48.80863158173934835 0, -86.77984628616638929 48.8087198431426188 0, -86.77984206819209589 48.80873413141328143 0) | R2004 | ANWIN | C | Temp | WF6 | C186 | 0.45478 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C186 | ANWIN | Not Required | Del Lake Rd W - ML - WF6 | 0.45 | 0.45 | All-season | 0.45478 | 0
LineStringZ (-86.62811467822183431 48.80063567370567768 0, -86.62818139780065962 48.80072121107608041 0, -86.62822280485235638 48.80080804764796909 0, -86.62825608029349667 48.80089827914100908 0, -86.62822087724019582 48.80098926404100723 0, -86.6281501331325785 48.80107966289381949 0, -86.62808291087958423 48.80116520085640985 0, -86.62807972490813313 48.8012588681481958 0, -86.62810705094516095 48.80135220117758621 0, -86.62813521301870878 48.80144058822170905 0, -86.62814510416190217 48.80153060935627707 0, -86.62812783755441615 48.8016218463917113 0, -86.62809246625548099 48.8017189092646575 0, -86.62806732033983792 48.80181048160378765 0, -86.62806815891592294 48.8019108971406439 0, -86.62809238273084134 48.8020098030414573 0, -86.62815410335943511 48.80219999668683784 0) | R1743 | AU1 | C | Temp | WF6 | C218 | 0.18025 | 7.5 | 15 | C218 - ML - WF6 | C218 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C218 | AU1 | Required | C218 - ML - WF6 | 0.18 | 0.18 | All-season | 0.18025 | 0
LineStringZ (-86.77984206819209589 48.80873413141328143 0, -86.77981988336672714 48.80880927789364421 0, -86.779736901233548 48.80896262494948701 0, -86.77969197496145171 48.80905205935633262 0, -86.77961284947902243 48.80913013668006784 0, -86.77960400017424547 48.80913395742327765 0) | R4454 | ANWIN | C | Temp | WF6 | C186 | 0.048308 | 4 | 8 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C186 | ANWIN | Not Required | Del Lake Rd W - ML - WF6 | 0.05 | 0.05 | All-season | 0.048308 | 0
LineStringZ (-86.50439552679777933 48.78423744082018487 0, -86.50439967236704319 48.78426284715703787 0, -86.5043696651535754 48.78435140159243133 0, -86.50434434569889675 48.78446752372828854 0) | R1714 | ANWIN | C | Temp | WF6 | C244 | 0.02597 | 10 | 20 | Mink Creek Rd - ML - WF6 - SP1 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 - SP1 | 0.03 | 0.03 | All-season | 0.02597 | 0
LineStringZ (-86.50438927927689292 48.78333082128946785 0, -86.50440805407960454 48.78343731302101105 0, -86.50440000762422699 48.78352729331012938 0, -86.50439045262706372 48.78362171563310312 0, -86.50440327640889393 48.78371211401340446 0, -86.50438659720775547 48.78380242871219252 0, -86.5043858421675651 48.78381758642551347 0) | R1715 | ANWIN | C | Temp | WF6 | C244 | 0.054351 | 10 | 20 | Mink Creek Rd - ML - WF6 - SP1 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 - SP1 | 0.05 | 0.05 | All-season | 0.054351 | 0
LineStringZ (-86.77109616274465509 48.80883651989368133 0, -86.77057546614302908 48.80893371758327959 0) | R1729 | ANWIN | C | Temp | WF6 | C188 | 0.039728 | 10 | 20 | Del Lake Rd W - ML - WF6 - SP1 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - SP1 | 0.04 | 0.04 | All-season | 4.7e-10 | 0.039728
LineStringZ (-86.76559672704756565 48.80848573356040987 0, -86.76575856483687232 48.80851109280279587 0, -86.76590306919094076 48.80852467243495596 0, -86.76603893965383918 48.80855648080337517 0, -86.76617673768338079 48.80856071320584277 0, -86.76631311257285972 48.8085379565743267 0, -86.76645091059835124 48.8085234141476505 0, -86.76657596862399657 48.80856138377696851 0, -86.76669172198508306 48.80860899336621372 0, -86.76675752122410756 48.80869553600374644 0) | R1730 | ANWIN | C | Temp | WF6 | C189 | 0.095098 | 10 | 20 | Del Lake Rd W - ML - WF6 - BR1 - SP1 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - BR1 - SP1 | 0.1 | 0.1 | All-season | 0.095098 | 0
LineStringZ (-86.68289571372214652 48.80573392166375157 0, -86.68293762311515138 48.8057754956362615 0, -86.68305153387328232 48.80582725398092236 0, -86.68316167185838594 48.80588190393289949 0, -86.68328496908871728 48.80592138319796192 0, -86.68342050455594006 48.80590311142015025 0, -86.68354858049212908 48.80593747584100583 0, -86.68371722407030688 48.80602033160027275 0, -86.68385837537935856 48.80604162086829234 0, -86.68400011436446562 48.80605046389229784 0, -86.68412408269712444 48.806105994653457 0, -86.68425961741431252 48.80612648809061227 0, -86.6843968292981657 48.80612627820653415 0, -86.6845150987104347 48.80617137294605357 0, -86.68465222660820757 48.80619283104773132 0, -86.68478834827114099 48.80617950343435041 0, -86.68493025423552467 48.80619417244076175 0, -86.68505447433791744 48.80623733886799442 0, -86.68516503095334258 48.80629043804341194 0, -86.68527969637365516 48.80634207029734029 0, -86.68537005264555262 48.80641008966163952 0) | R1731 | ANWIN | C | Temp | WF6 | C203 | 0.2056 | 10 | 20 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C203 | ANWIN | Required | Dead Horse Creek RD - ML - WF6 | 0.21 | 0.21 | All-season | 0.2056 | 0
LineStringZ (-86.68289571372214652 48.80573392166375157 0, -86.68288682963516578 48.80563807426435119 0, -86.68287333448206766 48.80554520262874263 0, -86.68289420521337263 48.80544914741228979 0, -86.68288154797436107 48.80535925033853317 0, -86.68284382996269244 48.80526922943807477 0, -86.68280125040502071 48.80517916456001615 0, -86.6827824749260003 48.80508767634528766 0, -86.68280334583261038 48.80499828443214483 0, -86.68282329380367912 48.80490859760626421 0, -86.68278758716621724 48.80482125760756418 0, -86.68270879760588343 48.8047470779268906 0, -86.6826205359584776 48.80467340107345109 0, -86.68248617384445254 48.8046503927658577 0, -86.68235105747336888 48.80462348697999175 0, -86.68223547148775765 48.8045701364278699 0, -86.68215140084124926 48.80449826095791366 0, -86.68206791682590051 48.80442626110040294 0, -86.6821455337020268 48.80433192239474494 0) | R1732 | ANWIN | C | Temp | WF6 | C206 | 0.18673 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C206 | ANWIN | Required | Dead Horse Creek RD - ML - WF6 - BR1 | 0.19 | 0.19 | All-season | 0.18673 | 0
LineStringZ (-86.22811038971536846 48.69939783276433332 0, -86.22805752801002654 48.69945685255914469 0, -86.22792677106995995 48.69948803429802098 0, -86.22778771460276914 48.69947734595280764 0, -86.22767196071129092 48.69942755786653521 0, -86.22758110081717575 48.69934472442074735 0) | R348 | AN | D | Temp | WF7 | D030 | 0.049693 | 10 | 20 | Swede Creek RD - ML - WF7 | Swede Creek RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D030 | AN | 0 | Swede Creek RD - ML - WF7 | 0.05 | 0.05 | All-season | 0.049693 | 0
LineStringZ (-86.27511304677746296 48.71055260541781706 0, -86.27504753593369458 48.71063008291868357 0) | R441 | AN | D | Temp | WF7 | D017 | 0.0098694 | 10 | 20 | Pic River RD - ML - WF7 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D017 | AN | Required | Pic River RD - ML - WF7 | 0.01 | 0.01 | All-season | 0.0098694 | 0
LineStringZ (-86.25654806638610239 48.71111714356639055 0, -86.2564880330042314 48.71111574410384293 0, -86.25635274822761289 48.71110141093402035 0, -86.25621545236170107 48.71107513390455068 0, -86.25611688170590696 48.71100296629904136 0, -86.2560216627850167 48.71092522373479738 0, -86.25591999029188628 48.71085095961294797 0, -86.25584983477554601 48.7107683975863921 0, -86.25572050127827595 48.71072694987352492 0, -86.25558647472745122 48.71069145234576325 0, -86.25548664621528872 48.71062016398860806 0, -86.25537608901746012 48.71054682345007336 0, -86.25525731703852728 48.71048798190765439 0, -86.25515061488948731 48.7104188312952715 0, -86.25500759286751418 48.71040307460452823 0, -86.25490829491060651 48.71042704511033605 0, -86.25477410067843209 48.71044561162722886 0, -86.25465507666697818 48.71049187907363631 0, -86.25451426175509084 48.71051534855148901 0, -86.25439247227784278 48.710523722161291 0, -86.25426456444886014 48.71052528102612911 0, -86.25412659791963677 48.71050390726908574 0, -86.25399785147818932 48.71046987696028907 0, -86.25389819142084491 48.71040613159895116 0, -86.25377765980218214 48.71036015784738282 0, -86.25371878974037543 48.71028154135361632 0, -86.25372012050681292 48.71018824799673297 0) | R446 | AN | D | Temp | WF7 | D023 | 0.263 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D023 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.26 | 0.26 | All-season | 0.263 | 0
LineStringZ (-86.25278683456997442 48.70991679673532815 0, -86.25288775265265429 48.70997033157495082 0, -86.25300845188201038 48.71000468159886054 0, -86.25312068599950521 48.71005597758380645 0, -86.2532476709433098 48.71009658895471972 0, -86.25337583132686348 48.71012768535613446 0, -86.25346803147174057 48.71019666898762068 0, -86.2536105245502398 48.71021401918608973 0, -86.25372012050681292 48.71018824799673297 0) | R447 | AN | D | Temp | WF7 | D024 | 0.079087 | 10 | 20 | Pic River RD - ML - WF7 - BR2 - SP1 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D024 | AN | 0 | Pic River RD - ML - WF7 - BR2 - SP1 | 0.08 | 0.08 | All-season | 0.079087 | 0
LineStringZ (-86.25372012050681292 48.71018824799673297 0, -86.25374170030038101 48.71018317359314409 0, -86.25380734196755839 48.71015942063566939 0, -86.2538089242837458 48.71006859295622604 0, -86.25378243681984713 48.70997488372707807 0, -86.25373283554259274 48.70994541486947327 0) | R448 | AN | D | Temp | WF7 | D024 | 0.032788 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D024 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.03 | 0.03 | All-season | 0.032788 | 0
LineStringZ (-86.25233053046513021 48.70949169299097292 0, -86.25223790337561525 48.70948198593757894 0, -86.25212030475448444 48.70943353843500034 0, -86.25199139086487321 48.70939787377879782 0, -86.25186851190380821 48.70935784993672968 0, -86.2517302949648581 48.7093748232532846 0, -86.25161780905699516 48.70932264534193479 0, -86.25151094046898947 48.70926585818978793 0, -86.25140096998622141 48.70921238206574344 0, -86.25126099259082935 48.70918623012560289 0, -86.25113652113331852 48.70913945971646086 0, -86.25100366775680527 48.70911791842474514 0, -86.25086285179959589 48.70908904190502398 0, -86.25080711196628158 48.70900480365028784 0, -86.25070208695130702 48.70894315540328279 0, -86.25057099327666776 48.70890623260356023 0, -86.25044258264381369 48.70887299844753215 0, -86.25031886530175029 48.70881839009237524 0, -86.25022012701535346 48.70875598704751042 0, -86.25009464960203331 48.70871768155565462 0, -86.24995928202132234 48.70870489935782643 0, -86.24983439186216572 48.70866286399277811 0, -86.24969575468088578 48.70863696356703088 0, -86.24955183739035647 48.70862061940265875 0, -86.24941152486078977 48.70860008383515805 0, -86.24927624025674788 48.70858394940002967 0, -86.2492150743766075 48.70856167303777795 0) | R449 | AN | D | Temp | WF7 | D024 | 0.26002 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D024 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.26 | 0.26 | All-season | 0.18278 | 0.077234
LineStringZ (-86.22455246710036647 48.69897786902626535 0, -86.22445062603335941 48.69904077491010241 0, -86.22439522166325787 48.69912668983346293 0, -86.22439874250086689 48.6992188903469625 0, -86.22448800998081708 48.69929860201080629 0, -86.22460887688923492 48.69934000907637994 0, -86.22473762289257593 48.69937324291476699 0, -86.22487676191478556 48.69938141566481704 0, -86.2249995571302037 48.69934000913140437 0, -86.22509276470879058 48.69927307917355819 0, -86.22517482267583944 48.69919781025035377 0, -86.22525570806578799 48.69912312713171332 0, -86.22529854013400552 48.69903993856761559 0, -86.22535712933419916 48.69895892596063902 0, -86.22545168582931296 48.69888823807286116 0) | R451 | AN | D | Temp | WF7 | D031 | 0.14342 | 10 | 20 | Swede Creek RD - ML - WF7 | Swede Creek RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D031 | AN | 0 | Swede Creek RD - ML - WF7 | 0.14 | 0.14 | All-season | 0.14342 | 0
LineStringZ (-86.22573077206106973 48.69867921084156848 0, -86.22579357555386537 48.69865457759898675 0, -86.22591352019817634 48.69860525137493568 0, -86.22604050557706046 48.69857189109275453 0, -86.22617914290304952 48.69857515957562555 0, -86.22631484617274111 48.69858693658090942 0, -86.22645800893421608 48.69860449678677128 0, -86.22658097136185518 48.69864431093692048 0, -86.22671323753601769 48.6986821974447821 0, -86.22682882512566493 48.69873663732105484 0, -86.226929407823107 48.69879782519858935 0, -86.2270194288716425 48.69886714395583027 0, -86.22711531831606635 48.69893700669679504 0, -86.22722495377912821 48.69899760821753176 0, -86.22733676844993056 48.69906013683896617 0, -86.2274330757527423 48.69912459360249102 0, -86.22749350989792561 48.69920983655401159 0, -86.22758110081717575 48.69934472442074735 0) | R668 | AU2 | D | Temp | WF7 | D031 | 0.17678 | 7.5 | 15 | Swede Creek RD - ML - WF7 | Swede Creek RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D031 | AU2 | 0 | Swede Creek RD - ML - WF7 | 0.18 | 0.18 | All-season | 0.17678 | 0
LineStringZ (-86.4800661442333336 48.78693907116338124 0, -86.4799635672456759 48.78683953004698992 0, -86.47988041947438376 48.7867682825749327 0, -86.47977916593590919 48.78670567134780356 0, -86.47967631929628851 48.78663823817936418 0, -86.47954430430783646 48.7866065546612333 0, -86.47943148441891026 48.78653966727520697 0, -86.47929343454332241 48.78649616515355092 0, -86.47918195448025358 48.78643799530186698 0, -86.47908229486822052 48.78637634603507678 0, -86.47894432870808146 48.78634415994175555 0, -86.47878331230762683 48.78634110015703129 0, -86.47868750614240696 48.78627668640909576 0, -86.47855465368010641 48.78624018240626015 0, -86.47843554671905508 48.78619559007331219 0, -86.47833404212748576 48.7861263553739164 0, -86.47824133785476874 48.78605829481763578 0, -86.47819607386777818 48.78603775894247008 0) | R2106 | ANWIN | C | Temp | WF6 | C249 | 0.17554 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.18 | 0.18 | All-season | 0.17554 | 0
LineStringZ (-86.47774408217752296 48.78569403822736206 0, -86.47769123295837801 48.78563220041885273 0, -86.47762006998918594 48.78554590941312341 0, -86.47750917860832942 48.78548099089663737 0, -86.47743742877764817 48.78540446407559728 0, -86.47733374413584784 48.78533149965096527 0, -86.47722151158509973 48.78527035399360301 0, -86.47708681439898726 48.78521796737292249 0, -86.47697122787205615 48.7851595869182546 0, -86.47687081214024829 48.78508146780288968 0, -86.47680509724581555 48.78500049875734845 0, -86.4767361142581592 48.78491177557395986 0) | R2107 | ANWIN | C | Temp | WF6 | C249 | 0.11638 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.12 | 0.12 | All-season | 0.11638 | 0
LineStringZ (-86.46753913327508201 48.78096355668358086 0, -86.46749397325397979 48.78096067263109603 0, -86.46736204178253615 48.78093171297635422 0, -86.46722265067836588 48.78090199900717039 0, -86.46708250520590866 48.78089521041673038 0, -86.46694655067784652 48.78087727159004316 0, -86.46680892042621736 48.78088594764923158 0, -86.46667145736969928 48.78087421326566897 0, -86.46654254369633463 48.78083993110102767 0, -86.46641916181037857 48.78078963990894579 0, -86.46630072576122927 48.7807383009605644 0, -86.4661770914651413 48.78069748114035775 0, -86.4660474245048789 48.78066550420756187 0, -86.46591155315167043 48.78065418830767186 0, -86.46578590899063954 48.78061412341421743 0, -86.46566043154767556 48.78057183624143534 0, -86.46558700539725351 48.78049451332601194 0) | R2108 | ANWIN | C | Temp | WF6 | C251 | 0.15754 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C251 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.16 | 0.16 | All-season | 0.15754 | 0
LineStringZ (-86.49194935718207944 48.78307416811392017 0, -86.49208623381856853 48.78308380696327617 0, -86.49220668194155337 48.78313221261951327 0, -86.49231824445992345 48.78319080206963321 0, -86.49244221298394564 48.78323317317219932 0, -86.49259568635963547 48.78324599711826437 0, -86.49273038288474424 48.78320672782601264 0, -86.49284764649348745 48.78314407302438838 0, -86.4928983571610388 48.78305778157827888 0, -86.4929941625871237 48.78298075195799299 0, -86.4931074854980011 48.78292555703430367 0, -86.49320848702690512 48.78286131001886616 0, -86.49324634725003591 48.78282764791057247 0) | R2109 | ANWIN | C | Temp | WF6 | C246 | 0.12112 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C246 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.12 | 0.12 | All-season | 0.12112 | 0
LineStringZ (-86.49368674270655788 48.78246471530822248 0, -86.4937112335729239 48.78241111764221927 0, -86.49381047616823537 48.78234900791603224 0, -86.49388641557325741 48.78227260637989104 0, -86.49395280062728375 48.78219180517935172 0, -86.4940363683148945 48.78211796041453852 0, -86.49413007809498311 48.78205107263343621 0, -86.49425924232063778 48.78201733590076117 0, -86.49439670619835852 48.78201800556988843 0, -86.4945420480018754 48.78209470067885434 0, -86.49472301430783716 48.78223057097266491 0, -86.49482242307117019 48.78224289224878873 0, -86.49495544357692722 48.78225802174467418 0, -86.49509441600112325 48.78224679007921338 0, -86.49522752075056076 48.78222583575520588 0, -86.4953623012777939 48.78225035262368436 0, -86.4954903768873038 48.78229029242272929 0, -86.49562247650669633 48.78232725671776393 0, -86.49574366855711105 48.78236094267524692 0) | R2110 | ANWIN | C | Temp | WF6 | C246 | 0.18967 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C246 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.19 | 0.19 | All-season | 0.18967 | 0
LineStringZ (-86.65212732980914723 48.7997943394467697 0, -86.65228004756161795 48.7997997866927733 0, -86.65241985818886405 48.79983230862067956 0, -86.65255279453199933 48.7998636986580081 0, -86.65268874881492422 48.79989408289146269 0, -86.65278690173376219 48.79995988082300329 0, -86.6528240338766409 48.80004711037517495 0, -86.65284389821303535 48.80013900268870231 0, -86.65285563293535631 48.80023128702705293 0, -86.65287600186620409 48.80032072225782969 0, -86.65291011500883656 48.80040781044447584 0, -86.65289167565448736 48.80049795733385309 0, -86.65291330080374621 48.80058751778194903 0, -86.65292847146928068 48.80067783334196463 0, -86.65297675164784152 48.8007645017668068 0, -86.65297113581667077 48.80085745712183609 0, -86.65300080795307736 48.80094781542535998 0, -86.65305688316475141 48.80103016673109551 0, -86.65309611030627934 48.80111729633187423 0, -86.65313726529372218 48.80120312730617371 0, -86.65320909817936013 48.80128707055457227 0, -86.6533051548477431 48.80135915618674147 0, -86.65340439680741724 48.80142277443101761 0, -86.65351017583982696 48.80148023292046133 0, -86.65362190780444962 48.80154259400153904 0, -86.65369302434615406 48.80160873000490795 0) | R2112 | ANWIN | C | Temp | WF6 | C212 | 0.25673 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 | 0.26 | 0.26 | All-season | 0.25673 | 0
LineStringZ (-86.6563268808392877 48.80233106305473711 0, -86.65632712826216277 48.80234567591230643 0, -86.65628119590664369 48.80243092040858244 0) | R2113 | ANWIN | C | Temp | WF6 | C212 | 0.011683 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 | 0.01 | 0.01 | All-season | 0.011683 | 0
LineStringZ (-86.65624260603070184 48.80216828464897816 0, -86.65628743782332322 48.80225145184731161 0, -86.6563268808392877 48.80233106305473711 0) | R2114 | ANWIN | C | Temp | WF6 | C212 | 0.019125 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 | 0.02 | 0.02 | All-season | 0.019125 | 0
LineStringZ (-86.6563268808392877 48.80233106305473711 0, -86.65639874842557333 48.80239578815127288 0, -86.65650779775363333 48.80245156958287822 0, -86.65662388687024986 48.80250311859692403 0) | R2115 | ANWIN | C | Temp | WF6 | C212 | 0.029322 | 10 | 20 | Middleton Road - ML - WF6 - SP2 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 - SP2 | 0.03 | 0.03 | All-season | 0.029322 | 0
LineStringZ (-86.65452882959682768 48.80308377501746975 0, -86.65442397149907094 48.80305355817453972 0, -86.65434467963547149 48.8030018834020396 0, -86.65429430416212142 48.80293667273608094 0) | R2117 | ANWIN | C | Temp | WF6 | C213 | 0.024718 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | Required | Middleton Road - ML - WF6 | 0.02 | 0.02 | All-season | 0.024718 | 0
LineStringZ (-86.73160523250443532 48.80524919265138806 0, -86.73169751675101224 48.80518289243180163 0, -86.73175635762089541 48.80510162964229437 0, -86.7318198081927676 48.8050219176505351 0, -86.7319086571184954 48.80495356269180718 0, -86.73204444336552399 48.80492632205950088 0, -86.73216790877630444 48.80488214927579094 0, -86.73229715785977589 48.8048523104231009 0, -86.73243663323748365 48.80484908265342625 0, -86.73256387092423836 48.80488474724358383 0, -86.7327018367562772 48.80487292902929397 0, -86.7328419821301253 48.80487330609492602 0, -86.73297852388459717 48.80487934118314541 0, -86.73310073090658534 48.8049266153773047 0, -86.73320651085309407 48.80499216175167732 0, -86.73328362471799835 48.80508620740034331 0, -86.73336325249189827 48.80517442584572763 0, -86.73343961246246181 48.80525304880956838 0, -86.73353055503076803 48.80532848578686611 0) | R2118 | ANWIN | C | Temp | WF6 | C197 | 0.18725 | 10 | 20 | Highway 17 - ML - WF6 | Highway 17 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | Required | Highway 17 - ML - WF6 | 0.19 | 0.19 | All-season | 0.18725 | 0
LineStringZ (-86.74392160149676556 48.80718237292449402 0, -86.74391196578325491 48.80719760771950888 0, -86.74379579189832157 48.80725452141929566 0, -86.74369328164590343 48.80731822312682056 0, -86.74357291682136406 48.8073625212835509 0, -86.74344165739017853 48.80739990508335779 0, -86.74330519872040668 48.80738561442011303 0) | R2119 | ANWIN | C | Temp | WF6 | C194 | 0.053547 | 10 | 20 | Del Lake Rd W - ML - WF6 - SP2 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C194 | ANWIN | Required | Del Lake Rd W - ML - WF6 - SP2 | 0.05 | 0.05 | All-season | 0.053547 | 0
LineStringZ (-86.74325096867858065 48.80552583635715536 0, -86.74342556325920839 48.80561950484641898 0, -86.74354517236554329 48.80567000520733956 0, -86.74368112756332039 48.80566166520080884 0, -86.74381993149299319 48.8056790579379296 0, -86.74394901309860018 48.80571459710122895 0, -86.74405898419568928 48.80577109110005551 0, -86.74413861195137088 48.80584824697761803 0, -86.74414783189418188 48.80594011232899021 0, -86.74413425347798068 48.80603838975486042 0, -86.74407231183491263 48.80611902403914115 0, -86.74403526360531202 48.80620866901944765 0, -86.74400475265554178 48.80629747479040503 0, -86.74393375865217592 48.80638221622746897 0, -86.74391531809624212 48.80647638697119106 0, -86.74392931575307841 48.80656657620654215 0, -86.74390316416688052 48.80666309394678848 0, -86.74388824499682471 48.80675386934357363 0, -86.74389029545409358 48.80676789765851709 0) | R2120 | ANWIN | C | Temp | WF6 | C194 | 0.18394 | 10 | 20 | Del Lake Rd W - ML - WF6 - SP2 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C194 | ANWIN | Required | Del Lake Rd W - ML - WF6 - SP2 | 0.18 | 0.18 | All-season | 0.18394 | 0
LineStringZ (-86.74011888905718592 48.80458764298520435 0, -86.73989057820435278 48.80450399928331251 0, -86.73982167930060427 48.80441665967454412 0, -86.7398101960404091 48.80432056074957359 0, -86.73983726944425143 48.80422693457094852 0, -86.7399219266059589 48.80407296043380683 0) | R2121 | ANWIN | C | Temp | WF6 | C195 | 0.06964 | 10 | 20 | Del Lake Rd E - ML - WF6 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 | 0.07 | 0.07 | All-season | 0.06964 | 0
LineStringZ (-86.77960400017424547 48.80913395742327765 0, -86.77948415714814701 48.80918569409661245 0) | R2003 | ANWIN | C | Temp | WF6 | C186 | 0.010512 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C186 | ANWIN | Not Required | Del Lake Rd W - ML - WF6 | 0.01 | 0.01 | All-season | 0.00032786 | 0.010184
LineStringZ (-86.76757776266809685 48.80849222861385073 0, -86.76756545225542538 48.80855664792002102 0, -86.7675532148074069 48.80865978764281721 0, -86.76749915185405371 48.80875529902640153 0, -86.76742706673954331 48.80883522096529248 0, -86.76734995322919985 48.80891007070158594 0, -86.76729245442527372 48.80900269095582189 0, -86.76723394831550706 48.80909573015542691 0, -86.76685123069319161 48.8092212496450486 0, -86.76671376778912759 48.80921366324775335 0, -86.76660237118700536 48.80914585405749051 0, -86.76646574595413597 48.80914212381492945 0) | R2006 | ANWIN | C | Temp | WF6 | C188 | 0.13545 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.14 | 0.14 | All-season | 0.13545 | 0
LineStringZ (-86.76646574595413597 48.80914212381492945 0, -86.76636155925606886 48.80908332492406743 0, -86.76627103522704942 48.80901538859069433 0, -86.76613265009598308 48.80898542406041685 0, -86.76599912598742037 48.8089464067343286 0, -86.76586677538416836 48.80891954243570297 0, -86.76574004114465311 48.80888316541027905 0, -86.76565085768041286 48.80880693166856332 0, -86.76557776775315745 48.8087295251312554 0, -86.76558271287574087 48.80863929343867369 0, -86.7656025772295294 48.80854407505292158 0, -86.76559672704756565 48.80848573356040987 0) | R2007 | ANWIN | C | Temp | WF6 | C188 | 0.10992 | 10 | 20 | Del Lake Rd W - ML - WF6 - BR1 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - BR1 | 0.11 | 0.11 | All-season | 0.10992 | 0
LineStringZ (-86.77236577727583722 48.80902046205226696 0, -86.77222864254835599 48.80902154955502681 0, -86.77209126206916778 48.80900864144574314 0, -86.77195187103704654 48.80901622731369116 0, -86.77181398948756907 48.80902791994279255 0, -86.77167895612601001 48.80904464227332795 0, -86.77153571045556646 48.80903244695655019 0, -86.77139925247594476 48.80901438338566578 0, -86.77126665095005364 48.80898152630705056 0, -86.77118417238965264 48.80890525078243769 0, -86.77109616274465509 48.80883651989368133 0) | R2008 | ANWIN | C | Temp | WF6 | C188 | 0.10247 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.1 | 0.1 | All-season | -3.5e-10 | 0.10247
LineStringZ (-86.77109616274465509 48.80883651989368133 0, -86.77106162946118673 48.80874587042602997 0, -86.77101808506094471 48.80867593596073561 0) | R2009 | ANWIN | C | Temp | WF6 | C188 | 0.018797 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.02 | 0.02 | All-season | 0.0068618 | 0.011935
LineStringZ (-86.76559672704756565 48.80848573356040987 0, -86.7655935254076951 48.8084538023007255 0, -86.76548171022513145 48.8083835613656305 0, -86.76547619331455508 48.80837995716802169 0) | R2010 | ANWIN | C | Temp | WF6 | C188 | 0.015457 | 10 | 20 | Del Lake Rd W - ML - WF6 - BR1 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C188 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - BR1 | 0.02 | 0.02 | All-season | 0.015457 | 0
LineStringZ (-86.4800661442333336 48.78693907116338124 0, -86.48004336302530248 48.78694455491206128 0, -86.47992367059366359 48.78699677464006612 0, -86.47988486137113284 48.78708579036189263 0, -86.47993548873438385 48.78717438741595913 0, -86.47994496011885701 48.78722128401753366 0) | R1900 | ANWIN | C | Temp | WF6 | C248 | 0.038401 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 0.038401 | 0
LineStringZ (-86.47777555435787633 48.78177660837472729 0, -86.47774378635325832 48.78166169245102424 0, -86.47770045202784672 48.78157326322904908 0, -86.47756768370803115 48.78154342356961592 0, -86.47743868590954719 48.78150168203944048 0, -86.47730247949215254 48.78148638472757881 0, -86.47715445520830713 48.78147838068607456 0, -86.47700349659169206 48.78148185913975965 0, -86.47686502801761321 48.78151999633720237 0, -86.47674332278506881 48.78157099999945245 0, -86.47661063644405033 48.7815944699599271 0, -86.47647459905834921 48.7816095150770721 0, -86.47633437015430502 48.78160180357642872 0, -86.47619204454235842 48.78160498913787535 0, -86.47605483334716325 48.78160750328130746 0, -86.47591812368587227 48.78160603700861486 0, -86.47578057733217349 48.78161119142951918 0, -86.47563976146811626 48.78160704243209977 0, -86.47550095687691396 48.78157892175294563 0, -86.4753625714168237 48.78155004535012296 0, -86.47523139444987805 48.78152125377843618 0, -86.47510549824134785 48.7814772909465475 0, -86.47496635814135857 48.78145046891728498 0, -86.47483400798748221 48.78141752798589437 0, -86.47471255484902031 48.78137649877564996 0, -86.47459705244371264 48.78131924976962353 0, -86.47446143192955503 48.78128433956751309 0, -86.47433981049513818 48.78123471890535967 0, -86.47422833127015451 48.78117734483980428 0, -86.47409673550031073 48.78113472229505021 0) | R1902 | ANWIN | C | Temp | WF6 | C249 | 0.30551 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.31 | 0.31 | All-season | 0.30551 | 0
LineStringZ (-86.47409673550031073 48.78113472229505021 0, -86.47395214350459014 48.78100019821250299 0) | R1903 | ANWIN | C | Temp | WF6 | C249 | 0.018343 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.02 | 0.02 | All-season | 0.018343 | 0
LineStringZ (-86.47858650329007446 48.78145172585800537 0, -86.47845339954122323 48.78147565574701616 0, -86.47830973321183023 48.78150251985018571 0, -86.47817973009456693 48.78153328243245568 0, -86.47809021127271478 48.78160297760624076 0, -86.47797403756167967 48.78165624402192435 0, -86.47785409275708446 48.78170020755599978 0, -86.47777555435787633 48.78177660837472729 0) | R1904 | ANWIN | C | Temp | WF6 | C249 | 0.07214 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 - SP1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 - SP1 | 0.07 | 0.07 | All-season | 0.07214 | 0
LineStringZ (-86.46249669835471252 48.77960753316575193 0, -86.46249706941310365 48.77960732978707625 0, -86.4625483976111866 48.77957916782914083 0, -86.46268661426566382 48.77958721418852406 0, -86.46281133805268837 48.77955029208681026 0, -86.46294754414086015 48.77954379570017096 0, -86.46297134084474578 48.7795297477542249 0) | R1907 | ANWIN | C | Temp | WF6 | C252 | 0.037547 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C252 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.04 | 0.04 | All-season | 0.037547 | 0
LineStringZ (-86.43744903144079217 48.77706233482452092 0, -86.43730846714936433 48.7770559640618373 0, -86.43717963617247335 48.77701925196101485 0, -86.43704183774832472 48.77703102856463602 0, -86.43689875929921129 48.77705449742766319 0, -86.43678543569780004 48.77710675755971437 0, -86.43666817253817669 48.77715319498970814 0, -86.43652601539223213 48.77716459432951268 0, -86.43638293627930125 48.77716727633625027 0, -86.43624052867056662 48.77717599328406095 0, -86.4360912463943265 48.77718575864183492 0, -86.43594707684776779 48.77720424078639638 0, -86.43580743440081449 48.77720474296836528 0, -86.4356642715525112 48.77721949543771984 0, -86.43552102566492579 48.77722817140800515 0, -86.43538071221551888 48.77724237792798334 0, -86.43524182372865994 48.77724749088180545 0, -86.43509790636264256 48.77724539569479845 0, -86.43496480253618586 48.77728059958052143 0, -86.43482717174443053 48.77728194077010926 0, -86.43468928846827737 48.77727255279823027 0, -86.4345504002569669 48.77727435528301214 0, -86.43440681866920272 48.77727762431005232 0, -86.43426742780634697 48.77728805927070965 0, -86.43414949337932285 48.77724065961368183 0, -86.43409769320064129 48.77715654794398148 0, -86.43406227663358266 48.77711280899413282 0) | R1914 | ANWIN | C | Temp | WF6 | C257 | 0.2656 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C257 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.27 | 0.27 | All-season | 0.2656 | 0
LineStringZ (-86.43406227663358266 48.77711280899413282 0, -86.43403348805561848 48.77707725477808509 0, -86.43389451649311184 48.77705504297423289 0, -86.43375504145224397 48.77706078457510586 0) | R1915 | ANWIN | C | Temp | WF6 | C257 | 0.025254 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C257 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.03 | 0.03 | All-season | 0.025254 | 0
LineStringZ (-86.43218665193565187 48.77626189671590851 0, -86.43225283676861181 48.77631881856564178 0, -86.43237085356889793 48.7763670140307255 0, -86.43251669888073252 48.77645347335578663 0, -86.43254804652522694 48.77649806536881982 0, -86.43264443938291208 48.77657287407915732 0, -86.43273840009041464 48.77664793342087535 0, -86.43280553917095688 48.77672802261076868 0, -86.43291098302202613 48.77679038375566023 0, -86.43302061841296791 48.77684775823547625 0, -86.43311600533267836 48.77691435272392084 0, -86.43324215262479981 48.77696246493344745 0, -86.43336704308080698 48.77701656937444596 0, -86.43349872243859977 48.77704787603762071 0, -86.43363777864485087 48.77705081025414557 0, -86.43375504145224397 48.77706078457510586 0) | R1916 | ANWIN | C | Temp | WF6 | C258 | 0.15169 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C258 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.15 | 0.15 | All-season | 0.15169 | 0
LineStringZ (-86.42890433438765285 48.77624989919164022 0, -86.42897961854444588 48.77627250858874675 0, -86.42911708166641915 48.77630109074120668 0, -86.42924163618127409 48.7763437127746613 0, -86.42935286448449972 48.77640804357477577 0, -86.42948135857062653 48.77646495704941998 0, -86.42960876450246133 48.77650657264950951 0, -86.42973013462945175 48.77655246374163056 0, -86.42990573430954271 48.77657593318367901 0, -86.43004671891176827 48.77657924381362164 0, -86.43018099727434844 48.77659818769470945 0, -86.43032474665453435 48.77660376155964883 0, -86.43045877259743293 48.77662060869472072 0, -86.43060009202361016 48.77662333286157548 0, -86.43073830925746392 48.77661704640649987 0, -86.43086831234535339 48.7765826804103142 0, -86.43099127583239749 48.77653431678118068 0, -86.43108012380082528 48.77646319740107117 0, -86.43119193876087536 48.7764042720660953 0, -86.43131439865526033 48.77635427372706545 0, -86.43143099071042457 48.7763058260128588 0, -86.43153366855290187 48.77624610500140534 0, -86.43166735973274228 48.77621647560955154 0, -86.43168539221284163 48.77620872089368476 0) | R1917 | ANWIN | C | Temp | WF6 | C258 | 0.22893 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C258 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.23 | 0.23 | All-season | 0.22893 | 0
LineStringZ (-86.41969311790687414 48.77510173884541445 0, -86.41969400769234255 48.7750990544120242 0, -86.41971367213353972 48.77503969865623645 0, -86.41974560796822402 48.77494716344593684 0, -86.41979165743080671 48.77486247904511174 0) | R1918 | ANWIN | C | Temp | WF6 | C261 | 0.027614 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C261 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.03 | 0.03 | All-season | 0.027614 | 0
LineStringZ (-86.41952123040336176 48.77441207143762369 0, -86.41947864355354625 48.77432782320585858 0, -86.41938510147492991 48.77425678712619828 0, -86.41934193488076232 48.77416253233300836 0, -86.41927881839237102 48.77407615558301046 0, -86.41920665092349907 48.77399510381770398 0, -86.41911386258175298 48.77392524079521507 0, -86.41902627243555912 48.77385336539959582 0, -86.41889392250637059 48.7738094866177363 0, -86.41886148343462537 48.77371866823231272 0, -86.41876240991211944 48.77364746430743736 0, -86.41865386454212228 48.77358656965217421 0, -86.41854538953383269 48.77356875185404306 0) | R1919 | ANWIN | C | Temp | WF6 | C261 | 0.12368 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C261 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.12 | 0.12 | All-season | 0.12368 | 0
LineStringZ (-86.41699144388441312 48.77413584976632421 0, -86.4168885508305209 48.77414522396716734 0, -86.41673952038919992 48.77414920537164988 0, -86.41660297967048621 48.77414279281774867 0, -86.4164842081041229 48.77409593844227231 0, -86.41637809292750205 48.77403349313841829 0, -86.41626829017849332 48.77397968144354934 0) | R1920 | ANWIN | C | Temp | WF6 | C261 | 0.059293 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C261 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.06 | 0.06 | All-season | 0.012962 | 0.046332
LineStringZ (-86.41726221609546599 48.77486116403979821 0, -86.41723934881045466 48.77482469275451393 0, -86.41720790183856593 48.77477453739766133 0, -86.41720262133212316 48.77467889997210193 0, -86.41712626186429702 48.77459981743329109 0, -86.41702140356865414 48.7745335152901518 0, -86.41689953123182022 48.77448527736630979 0, -86.41679794277135329 48.77441474363466511 0, -86.41670666314765015 48.77434739530399099 0, -86.41662711929856755 48.77426814427921187 0, -86.41651639479498215 48.77421135676862463 0, -86.41641673337289831 48.77414845119235309 0, -86.41626829017849332 48.77397968144354934 0) | R1921 | ANWIN | C | Temp | WF6 | C262 | 0.12616 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 - SP1 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C262 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 - SP1 | 0.13 | 0.06 | All-season | 0.080457 | 0.045705
LineStringZ (-86.41626829017849332 48.77397968144354934 0, -86.41624079702387462 48.77388739672517914 0, -86.41621623782590689 48.77379879994041545 0, -86.41626141688058738 48.77371213069271505 0, -86.41623744492096648 48.77362277941801239 0, -86.41621364033626662 48.77353120786394669 0, -86.41611154778782122 48.77346976774828136 0, -86.41602328704269098 48.77339982080862768 0, -86.41595329809176462 48.77331746910491006 0, -86.41590778419754315 48.77323071639352037 0, -86.41585221223412816 48.77314421495097463 0, -86.4157331894468399 48.77308889414776161 0, -86.4156010895456177 48.77304711071566601 0, -86.41546505166461145 48.77303868694544065 0, -86.41534452039218195 48.77299577171654477 0, -86.41528676790984775 48.77291044371268214 0, -86.41520764293015588 48.77283383324502353 0, -86.41515827340292333 48.77274791888638106 0, -86.41511393321304979 48.77265659732275793 0, -86.41506330720594065 48.77257085106700885 0, -86.41499239547314914 48.77248908512085279 0, -86.41486406958739508 48.7724569826355463 0, -86.41474856688446948 48.77240384132426954 0, -86.41466240038883484 48.77233049985983371 0, -86.41457304967489961 48.772260762160208 0, -86.4145218354339022 48.77217644034215738 0, -86.41449208018998718 48.77208662838671671 0, -86.41443743054186655 48.77200130041094184 0, -86.41439334169483288 48.77191463168355057 0, -86.414383289692978 48.77190453833179618 0) | R1922 | ANWIN | C | Temp | WF6 | C262 | 0.28937 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C262 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.29 | 0.29 | All-season | 0.15557 | 0.1338
LineStringZ (-86.40382234024711749 48.76615578568967635 0, -86.40382476218979946 48.76615685075599771 0, -86.40395082620604228 48.76619368941731381 0, -86.40406917855125357 48.76624800426871786 0, -86.40416490100407998 48.76631237743175973 0, -86.40428803086012977 48.76636493104107473 0, -86.40441954349151388 48.76640692509785424 0, -86.40454225406909927 48.76645964719223514 0, -86.40460679411295075 48.76654572915830954 0, -86.40472078838124048 48.76660356436343591 0, -86.40482355051864261 48.76667359496447318 0, -86.40489102487710227 48.76675464783762237 0, -86.40496327745120198 48.76683385686155248 0, -86.40503863055339195 48.76691189256784753 0, -86.40513854227064883 48.76697551107940143 0, -86.40524742422307725 48.76703263387102538 0, -86.40537943895917294 48.76707173538768814 0, -86.40551614709646344 48.76709277441234747 0, -86.40565411390058159 48.76713170840287148 0, -86.40577640610882781 48.76717931726132349 0) | R1925 | ANWIN | C | Temp | WF6 | C265 | 0.18897 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR1 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C265 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR1 | 0.19 | 0.19 | All-season | 0.083778 | 0.10519
LineStringZ (-86.40577640610882781 48.76717931726132349 0, -86.40589936790577497 48.76715576442236966 0, -86.406031299100448 48.76712378700266726 0, -86.40616725456860081 48.76709097194483888 0, -86.40625788209537461 48.76706311662966442 0) | R1926 | ANWIN | C | Temp | WF6 | C265 | 0.037714 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR1 - SP1 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C265 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR1 - SP1 | 0.04 | 0.04 | All-season | 0.037714 | 0
LineStringZ (-86.75837029374332587 48.80758328139994262 0, -86.75835289999139377 48.80757680385314501 0, -86.75826380044165376 48.80750660531545293 0, -86.75813681477144712 48.80747114956948707 0, -86.75799507553864487 48.80745346385759831 0, -86.75786104960062062 48.80742069090637614 0, -86.75772467547177769 48.80740778307476546 0, -86.75747988203329442 48.80741178967896587 0) | R2071 | ANWIN | C | Temp | WF6 | C189 | 0.070951 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.07 | 0.07 | All-season | 0.070951 | 0
LineStringZ (-86.7399219266059589 48.80407296043380683 0, -86.73991907587020478 48.80397979477452708 0, -86.73990591687478968 48.80388696479300847 0, -86.73987481954750933 48.80379124441678584 0, -86.74013365327623148 48.80338220717908371 0) | R2072 | ANWIN | C | Temp | WF6 | C193 | 0.080887 | 10 | 20 | Del Lake Rd E - ML - WF6 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd E - ML - WF6 | 0.08 | 0.08 | All-season | 0.080887 | 0
LineStringZ (-86.4767361142581592 48.78491177557395986 0, -86.47665194969253832 48.78483693801631915 0, -86.47660108284989633 48.78475800999230927 0, -86.47662094692300627 48.78460726059048369 0) | R2076 | ANWIN | C | Temp | WF6 | C249 | 0.036723 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.04 | 0.04 | All-season | 0.036723 | 0
LineStringZ (-86.46868965183921318 48.7806969364437677 0, -86.46880004187917734 48.7806910688947184 0, -86.46892954182774815 48.78066227659626009 0, -86.46906205955102109 48.78063864017450157 0, -86.46919809848918703 48.78063206006324748 0, -86.46933899788754729 48.78065251179661033 0, -86.46947964740161297 48.78065406158611239 0, -86.46961359017066684 48.78062615078734154 0, -86.4697518068633002 48.78061454137781539 0, -86.46988851563368428 48.78061194336908812 0, -86.47011105592839897 48.78067849455873528 0, -86.47032303417812216 48.78071717841131516 0) | R2077 | ANWIN | C | Temp | WF6 | C251 | 0.12391 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C251 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.12 | 0.12 | All-season | 0.12391 | 0
LineStringZ (-86.46753913327508201 48.78096355668358086 0, -86.46760461510181983 48.78094277702317783 0, -86.4677252303969226 48.78089143791491011 0, -86.46780058331829366 48.7808132767865672 0, -86.46794383013292418 48.78079940508540346 0, -86.46805908168373378 48.78085032462413295 0, -86.468194867657445 48.78083502829305473 0, -86.46832596084087186 48.78080573305063439 0, -86.46841740838949875 48.78073771409855652 0, -86.46855881017515344 48.78072824206916636 0, -86.46868965183921318 48.7806969364437677 0) | R2078 | ANWIN | C | Temp | WF6 | C251 | 0.098063 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C251 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.1 | 0.1 | All-season | 0.098063 | 0
LineStringZ (-86.46377211470976931 48.77961631774204676 0, -86.46380895164881508 48.77963574508959965 0, -86.46392864601688188 48.77968591128980336 0, -86.46404448387241359 48.77973356213815492 0, -86.46417884587354763 48.77975698905941471 0, -86.46428479227682828 48.77982471506494022 0, -86.46438705195066632 48.77988791503692312 0, -86.46452107842861778 48.77990723511745585 0, -86.46465762011234801 48.77993145875711178 0, -86.46478670104073672 48.77996234602155567 0, -86.46492391318871285 48.77997973818682453 0, -86.4650553414268046 48.7800075243259883 0, -86.46519280513828676 48.77998677963725527 0, -86.46529833227792494 48.7800476316056546 0, -86.46537494313257355 48.7801297742555775 0, -86.46541827806782976 48.78021765940419385 0, -86.46543043233538128 48.78032008591198831 0, -86.46558700539725351 48.78049451332601194 0) | R2079 | ANWIN | C | Temp | WF6 | C251 | 0.18179 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C251 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.18 | 0.18 | All-season | 0.18179 | 0
LineStringZ (-86.42840964835988871 48.77628843369573985 0, -86.42858667391641347 48.77627284337695102 0, -86.42872707195358828 48.77627510557683621 0, -86.42884844137797984 48.77623311361215741 0, -86.42890433438765285 48.77624989919164022 0) | R2080 | ANWIN | C | Temp | WF6 | C259 | 0.038015 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C259 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.04 | 0.04 | All-season | 0.038015 | 0
LineStringZ (-86.41965365770602148 48.7753757706436204 0, -86.41964804237622388 48.77530900891660792 0, -86.4196762893124486 48.77522066259748357 0, -86.41968399993288585 48.77512925857198667 0, -86.41969311790687414 48.77510173884541445 0) | R2081 | ANWIN | C | Temp | WF6 | C260 | 0.030779 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C260 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.03 | 0.03 | All-season | 0.030779 | 0
LineStringZ (-86.47409673550031073 48.78113472229505021 0, -86.47381837240439495 48.78100635258454076 0, -86.47370479822629363 48.78095338008874648 0, -86.4736452859298339 48.78086968741489926 0, -86.47357680634246435 48.78079181915120444 0, -86.4735292807387026 48.78070728695864489 0, -86.47348008422427768 48.78063506804903682 0) | R2098 | ANWIN | C | Temp | WF6 | C250 | 0.074269 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C250 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.07 | 0.07 | All-season | 0.074269 | 0
LineStringZ (-86.47102461930140294 48.7803779079403057 0, -86.47099576530679599 48.78040952063727786 0, -86.47093499770987535 48.78049937455376295 0, -86.47084790944100519 48.78057443420455996 0, -86.4708062508708224 48.78066294721398322 0, -86.4707287180173978 48.78074240741431566 0, -86.47058983017737432 48.78078352093107384 0, -86.47046108347706195 48.78074529916739266 0, -86.47032303417812216 48.78071717841131516 0) | R2099 | ANWIN | C | Temp | WF6 | C250 | 0.078535 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C250 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.08 | 0.08 | All-season | 0.078535 | 0
LineStringZ (-86.4730765380131885 48.7801760519253591 0, -86.47303416115674679 48.78014347883442525 0, -86.47293894259409797 48.78007390908989294 0, -86.4728252006975282 48.78001540330055263 0, -86.47271556516122359 48.77996138180498065 0, -86.47260316347346532 48.77990752836667099 0, -86.47246863490384783 48.77987672478313641 0, -86.47233519461154572 48.77985132723063799 0, -86.47219446251928332 48.77987395822920291 0, -86.47205775265965144 48.77988049742069165 0, -86.47192976183822566 48.77992085642632958 0, -86.47179422674400939 48.7799360683459966 0, -86.47165718251356736 48.77995019186766967 0, -86.47153480656706392 48.77999440667579023 0, -86.47148050137707287 48.78000887694204835 0) | R2100 | ANWIN | C | Temp | WF6 | C250 | 0.13267 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C250 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.13 | 0.13 | All-season | 0.13267 | 0
LineStringZ (-86.75747988203329442 48.80741178967896587 0, -86.75733039052207118 48.80741423682392366 0, -86.75709961520873037 48.80742368138298559 0, -86.75696887868620877 48.80742903098199292 0, -86.75668473228847688 48.80748410018512118 0) | R2101 | ANWIN | C | Temp | WF6 | C191 | 0.059317 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.06 | 0.06 | All-season | 0.059317 | 0
LineStringZ (-86.7565952139994323 48.80809807502441089 0, -86.75643780162202745 48.80808680078794737 0, -86.75635322845521102 48.80801488402364896 0, -86.75628516711138616 48.80790914682535941 0, -86.75628929469476702 48.80788115212229172 0) | R2103 | ANWIN | C | Temp | WF6 | C191 | 0.037647 | 10 | 20 | Del Lake Rd W - ML - WF6 - SP1 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - SP1 | 0.04 | 0.04 | All-season | 0.037647 | 0
LineStringZ (-86.73733258864946549 48.80708876897183757 0, -86.7373459158505824 48.80718671196918024 0, -86.73741020442810168 48.80725754307419351 0, -86.73749335349471323 48.80727461871962447 0, -86.73760634096623789 48.80726700992103417 0, -86.73781069203583627 48.80725468897820463 0, -86.73800925960820507 48.80724509109134601 0, -86.73811981750566247 48.80723402722709636 0, -86.73827010471089238 48.80718972893729557 0, -86.73841335194602209 48.80716215230794575 0, -86.73850429505178283 48.80712799598307328 0, -86.73861149985981456 48.80709484622311578 0, -86.73874150272635575 48.8070337832793868 0, -86.7388832405253396 48.80693873314924502 0, -86.73890543984650492 48.80689734006991642 0) | R2104 | ANWIN | C | Temp | WF6 | C195 | 0.14358 | 10 | 20 | Del Lake Rd E - ML - WF6 - BR2 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR2 | 0.14 | 0.14 | All-season | 0.14358 | 0
LineStringZ (-86.47662094692300627 48.78460726059048369 0, -86.47672303894803747 48.78454745630281053 0, -86.47682404062994976 48.78448107179529813 0, -86.47692965257554931 48.78442021907384429 0, -86.47706166779677517 48.78438736197242065 0, -86.47711254572860184 48.78430119606792914 0, -86.47715814364477183 48.78421469492668905 0, -86.47714288846336217 48.78412048343032126 0, -86.47719938224722114 48.78403607559014432 0, -86.47725269101682954 48.78395120977276633 0, -86.47729644507568025 48.78386353522673602 0) | R2105 | ANWIN | C | Temp | WF6 | C249 | 0.10288 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.1 | 0.1 | All-season | 0.10288 | 0
LineStringZ (-86.75130414400223344 48.80760146892527729 0, -86.75128837797213066 48.80760890693009202 0, -86.75115049525327038 48.80763715434378014 0, -86.75101730699768154 48.8076643124295444 0, -86.75088604607825005 48.80769113358068978 0, -86.75077193201963155 48.80771549798397757 0) | R2013 | ANWIN | C | Temp | WF6 | C191 | 0.041151 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.04 | 0.04 | All-season | -4.6e-10 | 0.041151
LineStringZ (-86.75551956456257585 48.80742966002609506 0, -86.75542283740257687 48.8073657897403308 0, -86.75541784312056848 48.80723752775804769 0, -86.75539380227198194 48.80701709712835168 0, -86.75531169352817074 48.80678895517239368 0, -86.7552082602228154 48.80679758037085492 0, -86.75506920365376118 48.80679426955442324 0, -86.75492587369691933 48.80679535929065338 0, -86.754787404279881 48.80679062442702332 0, -86.75464524785667209 48.80680604593008098 0, -86.75451356722699359 48.80684074715814091 0, -86.75437995951754999 48.80688571658367891 0, -86.75425724822952134 48.80692599161741185 0, -86.75410888861183878 48.80693898292749111 0, -86.75397075548610815 48.80697707922897877 0, -86.75383899199884752 48.80700960069446381 0, -86.7537133466496897 48.80704870211081925 0, -86.75357722464700316 48.80707342888574374 0, -86.75343808592684525 48.80709618613520462 0, -86.75329978313652646 48.80710481959456359 0, -86.75316424905011559 48.80713428169854495 0, -86.75302267860591598 48.80715016574563236 0, -86.75288446075497006 48.80718055015056933 0, -86.75276694599358507 48.80723331389209108 0, -86.75267175087040528 48.80726636044393274 0) | R2014 | ANWIN | C | Temp | WF6 | C191 | 0.27922 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C191 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.28 | 0.28 | All-season | 0.27922 | 0
LineStringZ (-86.75077193201963155 48.80771549798397757 0, -86.75075570752460408 48.80771896142210409 0, -86.75073760422905877 48.80772475523929188 0, -86.75062671038477902 48.80776024273313141 0, -86.7504894987726658 48.80778647841800932 0, -86.75035446652354665 48.80781703040873509 0, -86.75021834427938927 48.80783639164084065 0, -86.75008096418817161 48.80783450609560248 0, -86.74995003914199287 48.80786124414622407 0, -86.74981441922979286 48.80784473201995866 0, -86.74968173464968402 48.80781422214329268 0, -86.74954519347558346 48.80780525258640523 0, -86.74946615146085094 48.80773153459585245 0, -86.74932634157114819 48.80771196316778315 0, -86.74918108244796144 48.80769788162464096 0, -86.74904219443951092 48.80771577631045233 0, -86.74890992829850234 48.80775056161864001 0, -86.74876617926203437 48.80775781219350051 0, -86.74863106241630817 48.80777348631087875 0, -86.7484900791173601 48.80777344417397501 0, -86.74835932111086834 48.80774679083440759 0, -86.74822311484466297 48.80775751883164304 0, -86.74808757938944836 48.80774008457374435 0, -86.74795221118422717 48.80772679944533365 0, -86.74781675975006578 48.80771464476432442 0, -86.74767468670279413 48.80771032797811415 0, -86.74753529574698518 48.80770810844480678 0, -86.74739355748161529 48.80769897112596567 0, -86.74725500481464735 48.80769255918774263 0, -86.74711796050861778 48.80767139436652968 0, -86.74698460443053705 48.80764239302583718 0, -86.74687144901211866 48.80758066011566854 0, -86.74679727078959957 48.80751260941092085 0) | R2015 | ANWIN | C | Temp | WF6 | C192 | 0.30922 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C192 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.31 | 0.31 | All-season | 0.28636 | 0.022863
LineStringZ (-86.74679727078959957 48.80751260941092085 0, -86.74678670722916252 48.80750291828005771 0, -86.74674999513682394 48.80741189056597307 0, -86.74671981032487622 48.80734127995312832 0) | R2016 | ANWIN | C | Temp | WF6 | C193 | 0.019955 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd W - ML - WF6 | 0.02 | 0.02 | All-season | 0.019955 | 0
LineStringZ (-86.74325096867858065 48.80552583635715536 0, -86.7431392379131978 48.80557897831506864 0, -86.74301401232980879 48.80563308323131366 0, -86.74288928857149017 48.80569020636684741 0, -86.74274889217102213 48.80572327344814454 0, -86.74261872149365615 48.80576019455916992 0, -86.74247639561775713 48.80578035323213015 0, -86.74234538742943812 48.80581559891953702 0, -86.74219736321909124 48.80581207890688233 0, -86.7420852129583011 48.80586568129420044 0, -86.74194137965339735 48.80589711323673896 0, -86.74182386471146344 48.80595197268568342 0, -86.74168615049023856 48.80598571017816312 0, -86.74154768058632214 48.80600930559494088 0, -86.74140032739498452 48.80603675456639934 0) | R2018 | ANWIN | C | Temp | WF6 | C193 | 0.14992 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd W - ML - WF6 | 0.15 | 0.15 | All-season | 0.14992 | 0
LineStringZ (-86.74140032739498452 48.80603675456639934 0, -86.74126160725089107 48.80604010822670347 0, -86.74111576206756524 48.80605129826937372 0, -86.7410027734248672 48.80599920539067682 0, -86.74097007883358401 48.80594059358498527 0) | R2019 | ANWIN | C | Temp | WF6 | C193 | 0.038034 | 10 | 20 | Del Lake Rd E - ML - WF6 - BR1 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 0.038034 | 0
LineStringZ (-86.74097007883358401 48.80594059358498527 0, -86.74095466133651655 48.80591295491531412 0, -86.74094016012814734 48.80581874299134881 0, -86.74091853467591307 48.80572218330591738 0, -86.74086480683253342 48.80563375394580561 0, -86.7408328717550603 48.80553882901519813 0, -86.74078593296400186 48.80544729868704934 0, -86.74074083827609627 48.80535287669428612 0, -86.74072826584695406 48.80525606564850705 0, -86.74072642166171931 48.80515887841126244 0, -86.74068526683544178 48.80506269485326953 0, -86.74060094480914529 48.80498545584448067 0, -86.74052123275950521 48.80491249122357544 0, -86.74047454552581371 48.80482205073214175 0, -86.74038594903072408 48.80474380518910493 0, -86.7402870426141277 48.80468048039780626 0, -86.7401546916848929 48.80463978587870599 0, -86.74011888905718592 48.80458764298520435 0) | R2020 | ANWIN | C | Temp | WF6 | C193 | 0.16979 | 10 | 20 | Del Lake Rd E - ML - WF6 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C193 | ANWIN | Required | Del Lake Rd E - ML - WF6 | 0.17 | 0.17 | All-season | 0.16979 | 0
LineStringZ (-86.74097007883358401 48.80594059358498527 0, -86.74083094393019167 48.80594757205597034 0, -86.74071837596004286 48.80600075566225371 0, -86.74059331714863674 48.80604769395997522 0, -86.74046264394381467 48.80607912668359916 0, -86.74031646252404926 48.80607862384223239 0, -86.74019173986324915 48.80603348727743196 0, -86.74004924841612763 48.8060126157233185 0, -86.73991429856917534 48.80602745237769113 0, -86.73977130325982898 48.80602686517458011 0, -86.73966250646671483 48.80609031612583237 0, -86.73952009761039506 48.80606429033370119 0, -86.73937752250037647 48.80603042763129906 0, -86.73923586697402754 48.80602544018292122 0, -86.73912103559966624 48.80607929540283152 0, -86.73897678284633628 48.80608059441415492 0, -86.73886421349160969 48.80614069138107425 0, -86.73871342308068222 48.80613050723581381 0, -86.73858434181907739 48.80616038874063634 0, -86.7384658218543052 48.80621231520978398 0, -86.738342692091706 48.80626361217284881 0, -86.73819869107670399 48.80628159194236559 0, -86.73806675941594335 48.80631315043232377 0, -86.73797361130128536 48.80632087944686504 0) | R2021 | ANWIN | C | Temp | WF6 | C195 | 0.23849 | 10 | 20 | Del Lake Rd E - ML - WF6 - BR1 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR1 | 0.24 | 0.24 | All-season | 0.23849 | 0
LineStringZ (-86.66231603340906986 48.80251778779747696 0, -86.66232173849574849 48.80254003979481325 0, -86.66237546705900741 48.80262272780154831 0) | R2025 | ANWIN | C | Temp | WF6 | C211 | 0.012512 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C211 | ANWIN | Required | Middleton Road - ML - WF6 | 0.01 | 0.01 | All-season | 0.012512 | 0
LineStringZ (-86.64342791741432848 48.80207413309664588 0, -86.64354048664847596 48.8020196509374955 0, -86.64363629091374719 48.80195087714835722 0, -86.64369949028210272 48.80186772862571587 0, -86.64379336886572958 48.80180197319112523 0, -86.64388950904999831 48.80172796098539578 0, -86.64396687338135905 48.80164862627658806 0, -86.64402697223242455 48.80156761442819402 0, -86.64413660772883929 48.80151313341855257 0, -86.64419099189700546 48.80147180477517566 0) | R2027 | ANWIN | C | Temp | WF6 | C213 | 0.088549 | 10 | 20 | Little Pie River Rd - ML - WF6 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | 0 | Little Pie River Rd - ML - WF6 | 0.09 | 0.09 | All-season | 0.088549 | 0
LineStringZ (-86.60709475098680343 48.7971843790905524 0, -86.60718673466396922 48.7972297722666255 0, -86.60732302465615362 48.79725722273317245 0, -86.60744607082496316 48.79730512523825325 0, -86.60758688722542331 48.79730885495825277 0, -86.60769480699396183 48.79725982187483169 0) | R2030 | ANWIN | C | Temp | WF6 | C221 | 0.049353 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C221 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.05 | 0.05 | All-season | 0.049353 | 0
LineStringZ (-86.60846844586143334 48.79693852656238562 0, -86.60850495740992017 48.79688711989724936 0, -86.60845801827193213 48.79679504420186475 0, -86.6084266694272884 48.7967062384054131 0, -86.60842256307431342 48.79661625941658798 0, -86.60842046735149324 48.79652460231253031 0, -86.60847436360381835 48.79644179042561092 0, -86.60855994300042937 48.79636681274522658 0, -86.60862607517088918 48.79628743741445618 0, -86.60867678612893883 48.79620022278455593 0, -86.60879932905578471 48.79615734926305493 0, -86.6089342781448579 48.79618081886301439 0, -86.60907325032506776 48.79621769873988057 0, -86.6091992304984899 48.79625939941899304 0, -86.60933107831489508 48.79629460317033818 0, -86.60944523920109361 48.7963537372818621 0, -86.60949368734942766 48.7964436748547854 0, -86.60952662784337974 48.79653394759973395 0, -86.60953257864358079 48.79662531097876155 0, -86.60956585471122082 48.79671956556030921 0, -86.60962880344723658 48.79689466389797303 0, -86.60951816149781735 48.79695459357887444 0, -86.60952277193764814 48.79704549541612835 0, -86.60953570915241073 48.79707269625555455 0) | R2031 | ANWIN | C | Temp | WF6 | C221 | 0.23689 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C221 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.24 | 0.24 | All-season | 0.23689 | 0
LineStringZ (-86.60654794965851977 48.79662971194921539 0, -86.60657393618475908 48.79670033710605281 0) | R2032 | ANWIN | C | Temp | WF6 | C221 | 0.0080795 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C221 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.01 | 0.01 | All-season | 0.0080795 | 0
LineStringZ (-86.49574366855711105 48.78236094267524692 0, -86.49586169634717692 48.78239946620966805 0, -86.49599547069986727 48.78244120888189883 0, -86.49608968364927364 48.78250960542574433 0, -86.4961957983594516 48.78257883926715976 0, -86.49629353171243906 48.78264727711861326 0, -86.49635773712434172 48.78273050984677894 0, -86.49646460631787193 48.78279693638249626 0, -86.4965131449296365 48.78282220859374974 0) | R2046 | ANWIN | C | Temp | WF6 | C243 | 0.077937 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C243 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.08 | 0.08 | All-season | 0.051341 | 0.026596
LineStringZ (-86.47729171392960268 48.78384313961716146 0, -86.47736526078740837 48.78381965531195874 0, -86.47742770609281138 48.78373860286516361 0, -86.47750146597485355 48.78366257916641757 0, -86.47760883925637643 48.78359481137471931 0, -86.47768595166760974 48.78351497315157559 0, -86.47777169899927685 48.78343299876640771 0, -86.47784126877844812 48.78334310291195663 0, -86.47786281020488275 48.78324834481004046 0, -86.47792081298156575 48.78315434200397505 0, -86.47796314139888807 48.78306100944561052 0, -86.47800597269265666 48.78297023311419167 0, -86.47808551775622732 48.78288800729858821 0, -86.47815441691193428 48.78280699626620986 0, -86.47823781608795457 48.78273533021444308 0, -86.47818987222773046 48.78264044728287274 0, -86.4781433519339231 48.78255231058395935 0, -86.47809280949651622 48.78246782242450763 0, -86.47804779882352477 48.78238287170899667 0, -86.47797437302138235 48.78230697360543644 0, -86.47790522272684655 48.78222902214093892 0, -86.477835401312106 48.78213954460641588 0, -86.47778871451285454 48.78205010977685419 0, -86.47774646873162396 48.78195853780720626 0, -86.4777406018669268 48.78186654592769855 0, -86.47777555435787633 48.78177660837472729 0) | R2048 | ANWIN | C | Temp | WF6 | C249 | 0.25902 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C249 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 -BR2 | 0.26 | 0.26 | All-season | 0.25902 | 0
LineStringZ (-86.40951716582355857 48.7690746041242349 0, -86.40959780041772831 48.76903804619568206 0, -86.4096919292208554 48.76896659061285533 0, -86.40978496873813697 48.76889341742727169 0, -86.40987926485775006 48.76882145786914435 0, -86.40997951305438107 48.76874778077420558 0, -86.41009652368254024 48.7686833662543151 0, -86.41018369537225396 48.76860285792329108 0, -86.41024563776370826 48.76851216644708131 0) | R2055 | AU2 | C | Temp | WF6 | C264 | 0.083198 | 7.5 | 15 | Hare Lake Creek Rd - ML - WF6 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corp. |  | WF6 | C264 | AU2 | Required | Hare Lake Creek Rd - ML - WF6 | 0.08 | 0.08 | All-season | 0.023415 | 0.059783
LineStringZ (-86.62739559379286902 48.800010216061807 0, -86.62750589962843151 48.80006947629295411 0, -86.62762911389746989 48.80011088156349075 0, -86.62771343551926861 48.80018573310427143 0, -86.62780236800657008 48.80025639296155759 0, -86.62788400713088777 48.80033312936230772 0, -86.62791736810369514 48.80042051041904472 0, -86.62790119120320753 48.80051170507626779 0, -86.6279940623885949 48.80058278411263473 0, -86.62811467822183431 48.80063567370567768 0) | R2061 | ANWIN | C | Temp | WF6 | C218 | 0.092899 | 10 | 20 | C218 - ML - WF6 | C218 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C218 | ANWIN | Required | C218 - ML - WF6 | 0.09 | 0.09 | All-season | 0.092899 | 0
LineStringZ (-86.6821455337020268 48.80433192239474494 0, -86.68201268013694971 48.8042925693659555 0, -86.68188619746121049 48.80425711371566422 0, -86.68176289941581558 48.80421771929847807 0, -86.68162526784482225 48.8041923224309997 0, -86.68151244829383018 48.80414110812918693 0, -86.68139451404137219 48.80408469791635895 0, -86.68133634435754686 48.80400222064360349 0, -86.68125252528210467 48.80392774717651605 0, -86.68116610683553347 48.80385432168186099 0, -86.68104708301690664 48.80380023894542063 0, -86.68104574272814489 48.8037996298098733 0) | R1733 | ANWIN | C | Temp | WF6 | C206 | 0.10357 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 - SP1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C206 | ANWIN | Required | Dead Horse Creek RD - ML - WF6 - BR1 - SP1 | 0.1 | 0.1 | All-season | 0.10357 | 0
LineStringZ (-86.6838529278258676 48.80426972844883693 0, -86.68372258908920003 48.80423980483958957 0, -86.6836081758023056 48.80418331119788888 0, -86.68347347904315825 48.80414869385582932 0, -86.68334079305256523 48.80412308681866307 0, -86.68325621982084783 48.80405238563897541 0, -86.68312018158070487 48.80403235291773001 0, -86.68297584508934506 48.80401651091372628 0, -86.68284475109626896 48.80404262086236855 0, -86.68272069983939332 48.80408654222312492 0, -86.68258566702213841 48.80411265183061431 0, -86.6824889403826262 48.80418000074847384 0, -86.68236287652850081 48.804230250223263 0, -86.68225944272346339 48.80429470716122609 0, -86.6821455337020268 48.80433192239474494 0) | R1734 | ANWIN | C | Temp | WF6 | C206 | 0.144 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C206 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.14 | 0.14 | All-season | 0.144 | 0
LineStringZ (-86.68311095711099767 48.804028337858675 0, -86.68383734910939609 48.80399397356558211 0) | R1735 | ANWIN | C | Temp | WF6 | C206 | 0.053475 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 - SP2 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C206 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 - SP2 | 0.05 | 0.05 | All-season | 0.053475 | 0
LineStringZ (-86.67524688932920185 48.80361380298231211 0, -86.67519592771182602 48.8036972865980232 0, -86.67517530822144067 48.80379149969706276 0, -86.6751982739604756 48.80388227591463846 0, -86.6751794150841306 48.80397166944743503 0, -86.67514722833409735 48.80405904990730903 0, -86.67513079996922443 48.80414848356403468 0, -86.67510171488295612 48.80423804527040232 0, -86.67512132814552217 48.80428385301961924 0) | R1737 | ANWIN | C | Temp | WF6 | C208 | 0.076338 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - SP1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C208 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - SP1 | 0.08 | 0.08 | All-season | 0.076338 | 0
LineStringZ (-86.67512132814552217 48.80428385301961924 0, -86.67525904337415454 48.80431080069442373 0, -86.67536406858378939 48.80437190460178698 0, -86.67549071855960108 48.80440735978537248 0, -86.67562063917974058 48.80443870838917064 0, -86.67575701254781961 48.80444977205264223 0, -86.67589313401991546 48.80442131566746156 0) | R1738 | ANWIN | C | Temp | WF6 | C208 | 0.061653 | 10 | 20 | Dead Horse Creek RD - ML - WF6 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C208 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 | 0.06 | 0.06 | All-season | 0.061653 | 0
LineStringZ (-86.66311590756967576 48.80285649572169859 0, -86.66314601598500644 48.80284962534571491 0, -86.66328054578151807 48.8028201212702939 0, -86.66341188924978667 48.80279501844685797 0, -86.66354138942838858 48.80275595827860258 0, -86.66365069051984449 48.80269372214117141 0, -86.66376057671985222 48.80263844327296852 0, -86.6638951066016574 48.80265545922377868 0, -86.66402904894430037 48.80267930572707513 0, -86.66416357886443222 48.80269879345075168 0, -86.66429517459846465 48.80273127341518347 0, -86.66439919476948717 48.8028035672758449 0, -86.6645416866373921 48.80282976082688862 0, -86.66467361804377845 48.80285528386949778 0, -86.66481577511819978 48.80287862709089808 0, -86.66494628096648967 48.80290741930092224 0, -86.66508692947873271 48.8029217519601346 0, -86.66521617900269803 48.80288910419336901 0, -86.66535280336835001 48.80288193802133634 0, -86.66549311662052446 48.80290901107093759 0, -86.66562932256277918 48.80292074564059845 0, -86.6657694688889535 48.80292686540936842 0, -86.66590525562402547 48.8029453471966761 0, -86.66617554308292881 48.80298365326002141 0) | R1740 | ANWIN | C | Temp | WF6 | C210 | 0.23985 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C210 | ANWIN | 0 | Middleton Road - ML - WF6 | 0.24 | 0.24 | All-season | 0.18401 | 0.055841
LineStringZ (-86.65628483865958742 48.80242416091957836 0, -86.65624737161739688 48.80250098074840537 0, -86.65620630030173288 48.80259225979771998 0, -86.65617101192601979 48.80268282740870944 0, -86.6561470396618887 48.80277506962513456 0, -86.65611644688429749 48.80286978486176963 0, -86.65606674200864745 48.80296131517455649 0, -86.6560080682468481 48.8030486130942549 0, -86.6559558486833339 48.80313482014670257 0, -86.65590681470641243 48.80321897481241677 0, -86.6558217392048391 48.80329181379726577 0, -86.65571160018663477 48.80335488742764483 0, -86.65559106798048106 48.80339797059133389 0, -86.65545243170882372 48.80342169241458805 0, -86.65532142277965022 48.80337986541768913 0, -86.65519125142178325 48.80334462041288646 0, -86.65507507852781544 48.80329449557086718 0, -86.65498882829921001 48.8032245071629518 0, -86.65491464838579816 48.80314219709133994 0, -86.65481247283510413 48.80308180542850494 0, -86.65466889191687017 48.80306332320576956 0, -86.65452530897488259 48.80308084078285447 0) | R1741 | ANWIN | C | Temp | WF6 | C213 | 0.21782 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | Required | Middleton Road - ML - WF6 | 0.22 | 0.22 | All-season | 0.21782 | 0
LineStringZ (-86.61593308635697497 48.79862640608352109 0, -86.61583853878184414 48.79870230479009763 0, -86.61572873544453444 48.79875825259818356 0, -86.61560585603658069 48.79881445356281233 0, -86.61548079924430965 48.79885422680742835 0, -86.61535498681894296 48.79890179419297169 0, -86.61522942505507672 48.79894433173706147 0, -86.61509212966734594 48.79896863923352868 0, -86.61496396968369993 48.79893356056807363 0, -86.61494695964212553 48.79892814125572897 0) | R1745 | ANWIN | C | Temp | WF6 | C220 | 0.085299 | 10 | 20 | Neys Rd - ML - WF6 - BR1 - SP4 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C220 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 - SP4 | 0.09 | 0.09 | All-season | 0.085299 | 0
LineStringZ (-86.4681543829393604 48.78032767059606556 0, -86.46820928469772127 48.78041031660633564 0, -86.46822244483661279 48.78050105083575971 0, -86.4683042519506273 48.78057451815620738 0, -86.46840701441313115 48.78063365156766196 0, -86.46853936394872164 48.78065548711394683 0, -86.46868965183921318 48.7806969364437677 0) | R1753 | ANWIN | C | Temp | WF6 | C251 | 0.062301 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - SP1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C251 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 - SP1 | 0.06 | 0.06 | All-season | 0.062301 | 0
LineStringZ (-86.46280480034863558 48.77978511067901479 0, -86.46268041213910749 48.77974743398595336 0, -86.462555354320898 48.77970925475698039 0, -86.46249669835471252 48.77960753316575193 0) | R1754 | ANWIN | C | Temp | WF6 | C252 | 0.032274 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C252 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 | 0.03 | 0.03 | All-season | 0.032274 | 0
LineStringZ (-86.45729491056630422 48.78119374218305637 0, -86.45729595975463155 48.78112433028417172 0, -86.45730241378458913 48.78103288380893332 0, -86.45735505240725161 48.78094001211319153 0, -86.45739260304759455 48.78085116344741579 0, -86.45741917380797759 48.78076231525673734 0, -86.45749503047341022 48.78068713010457458 0, -86.45750668033747388 48.78059526456431882 0, -86.45757046772628485 48.78051567837646729 0, -86.457548338958361 48.78042326792324701 0, -86.45751715829781858 48.78033425133714474 0, -86.45746234128715457 48.78025106085147655 0, -86.45742696909344716 48.7801595730933002 0, -86.45738111990137043 48.78007147877304561 0, -86.45733543795297749 48.77998594188805725 0, -86.45725832466852978 48.77990694191628762 0, -86.45720325537936901 48.77981402901774999 0, -86.45712932804521245 48.77973033544628834 0, -86.45704475410410339 48.7796592148811925 0, -86.45700033041882193 48.77957422264513809 0, -86.45690963755450298 48.77950708357449372 0, -86.4568370502000505 48.77942556956170961 0, -86.45682539950868772 48.77933387133610665 0, -86.45683660391991054 48.77927895757882482 0, -86.45677107144791762 48.77918854642224744 0, -86.45663183290984932 48.77914218940574642 0, -86.45647076449466795 48.77910056103628023 0) | R1757 | ANWIN | C | Temp | WF6 | C253 | 0.2657 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - SP3 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C253 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 - SP3 | 0.27 | 0.27 | All-season | 0.2657 | 0
LineStringZ (-86.43408193549642249 48.77674918724803632 0, -86.4340943411502991 48.776841430429144 0, -86.43413683697059469 48.77692717688141499 0, -86.43420976038734693 48.77700705615067989 0, -86.43420355742458128 48.77710118528922578 0, -86.43406227663358266 48.77711280899413282 0) | R1758 | ANWIN | C | Temp | WF6 | C258 | 0.051629 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 - SP3 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C258 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 - SP3 | 0.05 | 0.05 | All-season | 0.051629 | 0
LineStringZ (-86.60654794965851977 48.79662971194921539 0, -86.60653836226795477 48.79669586433252704 0) | R1857 | ANWIN | C | Temp | WF6 | C222 | 0.0073873 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.01 | 0.01 | All-season | 0.0073873 | 0
LineStringZ (-86.60240648929645602 48.79681501267941002 0, -86.602628139324068 48.79686443618369651 0) | R1859 | ANWIN | C | Temp | WF6 | C223 | 0.01718 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C223 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.02 | 0.02 | All-season | 0.01718 | 0
LineStringZ (-86.59805459225115953 48.79689381207698062 0, -86.59821164093189338 48.79689290406513891 0, -86.59834943985143241 48.79685820289089548 0, -86.59841825551444572 48.79678046113512124 0, -86.59848447236252866 48.79670125203883657 0, -86.59855488080060582 48.796621455671783 0, -86.59863870001584019 48.79654643783621992 0, -86.59871137026209453 48.79646349886024836 0, -86.59879770403567534 48.7963935939726241 0) | R1862 | ANWIN | C | Temp | WF6 | C224 | 0.083749 | 10 | 20 | Neys Rd - ML - WF6 - BR1 - SP1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C224 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 - SP1 | 0.08 | 0.08 | All-season | 0.083749 | 0
LineStringZ (-86.58424545804545858 48.79462601862206128 0, -86.58441317947543325 48.79464747611999798 0, -86.58455139811856327 48.79465552290017882 0, -86.58470126656411026 48.79467266413439575 0, -86.58484392650585448 48.79468108820347538 0, -86.58498750870248273 48.79469177520431344 0, -86.58513067121509721 48.79469441541920105 0, -86.58527995360799423 48.7947075325924331 0, -86.58541213533449366 48.79474018038979466 0, -86.58554859299768225 48.7947613861420848 0, -86.58565412158996821 48.79482295162718941 0, -86.585761996240592 48.79488388763176943 0, -86.5858605675560824 48.79495421158822666 0, -86.58597523266362828 48.79500660042852189 0, -86.58610490067482601 48.79503643885379205 0, -86.58623557433926976 48.79506338673936483 0, -86.58629661017393175 48.79511689704644084 0) | R1864 | ANWIN | C | Temp | WF6 | C226 | 0.16652 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C226 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.17 | 0.17 | All-season | 0.16652 | 0
LineStringZ (-86.50368455983273464 48.78414757461727902 0, -86.5036189545428158 48.78420901995095704 0, -86.50355511141914633 48.78426666123158384 0, -86.50347590262890662 48.78434281032494368 0, -86.50337959514139641 48.78440848271624475 0, -86.50330424151874809 48.78448500994026915 0, -86.50317331609385008 48.78452226843896256 0, -86.50303166151286405 48.78453211559608604 0, -86.5028947017057277 48.78454917333019836 0, -86.5027547242837187 48.7845347561728957 0, -86.50265212890823818 48.78446623358629353 0, -86.502552048817833 48.7843902101029343 0, -86.50247300782284299 48.78431259419914312 0, -86.50236094231169659 48.78425786002205911 0, -86.50221995894170846 48.78424201830144824 0, -86.50208224342922847 48.78422873279517802 0, -86.50195852671431851 48.78418254896774187 0, -86.50182273938789024 48.78416276737439006 0, -86.50168301297064488 48.78417483692275169 0, -86.50156231387275341 48.78412861083998564 0, -86.5014354116864439 48.78409349124883931 0, -86.50132368153009566 48.7840340633968168 0, -86.50121421329826887 48.78397815636335366 0, -86.50108219828888423 48.78394169544196757 0, -86.50097518900413718 48.78393508791448596 0, -86.50085379162702282 48.7839113525643171 0, -86.50072529657472842 48.78387744784729563 0, -86.50057484207295033 48.78387443006511859 0, -86.50043762922052792 48.78388004626787477 0, -86.50029882517756619 48.78385108557477423 0, -86.50016898935058407 48.78380611743835971 0, -86.50008424774480886 48.78380428806588753 0) | R1893 | ANWIN | C | Temp | WF6 | C244 | 0.31052 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.31 | 0.31 | All-season | 0.31052 | 0
LineStringZ (-86.50438927927689292 48.78333082128946785 0, -86.50430780706930989 48.78340554616046632 0, -86.50425827012438162 48.78349334638435408 0, -86.50416715933469902 48.78356199427990703 0, -86.50411267612672361 48.78364539390739196 0, -86.50404260362297748 48.78372996787655325 0, -86.50403383245195243 48.78377309294607045 0) | R1894 | ANWIN | C | Temp | WF6 | C244 | 0.056458 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.06 | 0.06 | All-season | 0.056458 | 0
LineStringZ (-86.4976508337560972 48.78338472527451586 0, -86.49770336826472317 48.78343421274379921 0, -86.49778953442418583 48.78350508179897105 0, -86.49786740174540967 48.78358173414819277 0, -86.49798625730569768 48.78363202587129877 0, -86.49812011615371432 48.78366852895909034 0, -86.49825590333919934 48.78364857957765111 0, -86.49839445647684499 48.78362796017677283 0, -86.49852898630908271 48.78360097012802754 0, -86.49866787475572494 48.78360310814424139 0, -86.49880659459790877 48.78362423042259621 0, -86.49894942251802377 48.78364116206271461 0, -86.49908428734919141 48.78365503356278055 0, -86.499220996446752 48.78369069943524039 0, -86.49936130902068498 48.78371022757652753 0, -86.499497180600315 48.78372049556922008 0, -86.4996379121209884 48.78370721137694943 0, -86.49976682633517555 48.78373717618012506 0, -86.49990294770719856 48.78375259858771784 0, -86.50002725203366083 48.78380305757892188 0, -86.50008424774480886 48.78380428806588753 0) | R1896 | ANWIN | C | Temp | WF6 | C245 | 0.19733 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C245 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.2 | 0.2 | All-season | 0.19733 | 0
LineStringZ (-86.48910396645695187 48.78258150357426359 0, -86.48920478642529019 48.7825877663462748 0, -86.48934015357977501 48.78261102621996059 0, -86.48947971321257455 48.78262573670922819 0, -86.48962681505230421 48.78262414368182931 0, -86.48976302041509712 48.78260113581740143 0, -86.48990341786227987 48.78260088374821635 0, -86.4900393721948717 48.78257213409538195 0, -86.49016644200733595 48.78261655807111907 0, -86.49030658733170185 48.78263462116150606 0, -86.49038160514852791 48.78271018377218127 0, -86.49050263989499854 48.78275431440931698 0, -86.49057598252559842 48.78283323039362074 0, -86.49066348879854615 48.78290389031599261 0, -86.49080179070884355 48.78292409020312448 0, -86.4909349796321294 48.78295183478043384 0, -86.49107126943269463 48.78295699043459877 0, -86.49120009893098882 48.78298993043947007 0, -86.49133471283607832 48.78300602382224582 0, -86.49146781686557972 48.78302861269780522 0, -86.4915984075354487 48.78306297869691122 0, -86.49172757214284957 48.78309353025041872 0, -86.49194935718207944 48.78307416811392017 0) | R1897 | ANWIN | C | Temp | WF6 | C246 | 0.22955 | 10 | 20 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C246 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.23 | 0.23 | All-season | 0.22955 | 0
LineStringZ (-86.77948415714814701 48.80918569409661245 0, -86.77946926818231077 48.80919212109012761 0, -86.77936357134862533 48.80925393764652398 0, -86.77923700566803689 48.80929278802523186 0, -86.77909928986770183 48.80930292979139296 0, -86.77895721694677889 48.80931617382935173 0, -86.77881740710247982 48.80933293764216785 0, -86.77867868649971683 48.80935502356706479 0, -86.77853803854273451 48.80932174739512419 0, -86.77840325687063228 48.80930393642903198 0, -86.77826579301418519 48.80931898136289959 0, -86.77813520301164374 48.80934794076667771 0, -86.77799866196046708 48.80934148689586038 0, -86.77785457712590755 48.80932694358312318 0, -86.77771644377260429 48.8093344039060284 0, -86.77757495693765577 48.80933482367861842 0, -86.77743003376122033 48.80933432085755896 0, -86.77728377003406024 48.80932220872099947 0, -86.77714748020689228 48.80932887218610716 0, -86.77700884328632469 48.80931717926134894 0, -86.77686853059738326 48.80931881398849725 0, -86.7767319885969215 48.809321831325164 0, -86.77659243004244161 48.80932539410418514 0, -86.77644826150654467 48.80933008755808089 0, -86.77631004343722054 48.80933327296673951 0, -86.77618020846256286 48.80929882293883537 0) | R1817 | ANWIN | C | Temp | WF6 | C186 | 0.24963 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C186 | ANWIN | Not Required | Del Lake Rd W - ML - WF6 | 0.25 | 0.25 | All-season | -4.4e-10 | 0.24963
LineStringZ (-86.77618020846256286 48.80929882293883537 0, -86.77604634860647081 48.80925741559229181 0, -86.77590846582035056 48.80923797011991638 0, -86.77578667670755408 48.80919404908459569 0, -86.77565943965066708 48.80914711087938684 0, -86.7754306135327198 48.80911647499851824 0, -86.77528678051704958 48.80909313094976909 0, -86.77514948502199843 48.80907318194161348 0, -86.7750048137984038 48.80908533742926636 0, -86.77498470589279123 48.80908854660967222 0, -86.77487120579885982 48.80910666769700157 0, -86.77473240076875527 48.80912971757065577 0, -86.77460264967017167 48.80916534059480938 0, -86.77446124685847906 48.80915410968409418 0, -86.77433468015192375 48.80919786285779338 0, -86.7741930256546965 48.80918231488005432 0, -86.7740458387973348 48.80917192134495508 0, -86.77390317901631533 48.80913977625521483 0, -86.77376806288232558 48.80912079244036761 0, -86.77363051541648531 48.8091039861042475 0, -86.77350638020131157 48.80906467476000188 0, -86.77336128909755075 48.80905809514260341 0, -86.77321678476195643 48.80903617664306893 0, -86.7730723653905045 48.80902473478554526 0, -86.77293263826354064 48.80904011614806848 0, -86.77279257707031945 48.8090453123943675 0, -86.77265243080503865 48.80903768640867213 0, -86.77251329172186445 48.8090254059485531 0, -86.77236593799803188 48.80902046057047272 0, -86.77236577727583722 48.80902046205226696 0) | R1818 | ANWIN | C | Temp | WF6 | C187 | 0.29042 | 10 | 20 | Del Lake Rd W - ML - WF6 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C187 | ANWIN | 0 | Del Lake Rd W - ML - WF6 | 0.29 | 0.29 | All-season | 4.8e-10 | 0.29042
LineStringZ (-86.7633561275331715 48.80826665766284123 0, -86.76325740411556353 48.80829312158495981 0, -86.76312639486791056 48.80832769638296043 0, -86.76299035626037437 48.80835636296083635 0, -86.76286605356037285 48.8083945838073916 0, -86.76276211744990974 48.80845971187662968 0) | R1819 | ANWIN | C | Temp | WF6 | C189 | 0.049252 | 10 | 20 | Del Lake Rd W - ML - WF6 - BR1 | Del Lake Rd W - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - BR1 | 0.05 | 0.05 | All-season | 0.049252 | 0
LineStringZ (-86.73836438372728708 48.80645388132695217 0, -86.73848434604192903 48.80640652367245735 0, -86.73860730839790278 48.80635786558658396 0, -86.73874418533787889 48.80635665107537591 0, -86.7388630411304149 48.8064074037697111 0, -86.73897887871196133 48.80646532286401396 0, -86.73901028431589566 48.80649060057918831 0) | R1820 | ANWIN | C | Temp | WF6 | C195 | 0.055532 | 10 | 20 | Del Lake Rd E - ML - WF6 - BR2 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR2 | 0.06 | 0.06 | All-season | 0.055532 | 0
LineStringZ (-86.73797361130128536 48.80632087944686504 0, -86.73795863259775274 48.80639621423079433 0, -86.73805586932834899 48.80643634299098466 0) | R1821 | ANWIN | C | Temp | WF6 | C195 | 0.016865 | 10 | 20 | Del Lake Rd E - ML - WF6 - BR2 | Del Lake Rd E - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR2 | 0.02 | 0.02 | All-season | 0.016865 | 0
LineStringZ (-86.73213739874138639 48.80671636126671586 0, -86.73226228963633844 48.80667692356699661 0, -86.73237251198345632 48.80662193908869284 0, -86.73248742701987624 48.8065734082828655 0, -86.73252374200123427 48.80653439262505344 0) | R1822 | ANWIN | C | Temp | WF6 | C197 | 0.035412 | 10 | 20 | C197 SP - ML - WF6 | C197 SP - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | 0 | C197 SP - ML - WF6 | 0.04 | 0.04 | All-season | 0.035412 | 0
LineStringZ (-86.73236900771654234 48.80611288521546243 0, -86.73221096942158681 48.80604869023145653 0) | R1823 | ANWIN | C | Temp | WF6 | C197 | 0.013623 | 10 | 20 | C197 SP - ML - WF6 | C197 SP - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | 0 | C197 SP - ML - WF6 | 0.01 | 0.01 | All-season | 0.0076833 | 0.0059395
LineStringZ (-86.72665760618359343 48.80620045027300336 0, -86.7267621671080633 48.80626772058145235 0, -86.72678563653074946 48.80635908315012017 0, -86.7267912664132723 48.80643686095235267 0, -86.72679242558061219 48.80645287556389178 0) | R1826 | ANWIN | C | Temp | WF6 | C198 | 0.031457 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C198 | ANWIN | Required | Ripple Lake RD - ML - WF6 | 0.03 | 0.03 | All-season | 0.031457 | 0
LineStringZ (-86.72235358929464155 48.806221926834084 0, -86.72244422820732268 48.80616139555824162 0, -86.72256299917525268 48.8061131160170163 0, -86.72270540816496975 48.80609358665440567 0, -86.72283851319498638 48.80606848155477451 0, -86.72297497023446056 48.80607024262267402 0, -86.72311276838506444 48.80605599398489858 0, -86.72324118029609963 48.80608973035764109 0, -86.72335726850815263 48.80613805270863992 0, -86.72344209343162902 48.80621076528703384 0, -86.72352842752879098 48.80628448356875992 0, -86.72366061027122441 48.80630728316194933 0, -86.72379413372846102 48.80633297441068663 0, -86.723930507217176 48.80634537903680581 0, -86.72406889284276588 48.80634403803117749 0, -86.72419973407042448 48.80631277272227209 0, -86.72431733293086609 48.80626067969209458 0, -86.72445135915663172 48.80623565859631441 0, -86.72458873881518571 48.80622073969573194 0, -86.72472578305733748 48.80624693305381356 0, -86.72486299507458796 48.80626264908349299 0, -86.72499928421095206 48.80623519845189406 0, -86.72513934555614412 48.80624814840284387 0, -86.72527773110692806 48.80626646296385474 0, -86.72541024890033157 48.80623825799499116 0, -86.72555072965721479 48.80622203912532342 0, -86.72568785837606242 48.80620087423892528 0, -86.72582003999120559 48.80616156341640277 0, -86.72588814786698208 48.80615662469724469 0) | R1827 | ANWIN | C | Temp | WF6 | C198 | 0.28179 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C198 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.28 | 0.28 | All-season | 0.28179 | 0
LineStringZ (-86.72012686732627174 48.80582831793465459 0, -86.72016828922764375 48.8059082214469413 0, -86.72025889779240515 48.80597594687376528 0, -86.72036694095601206 48.80603721855781174 0, -86.72047657617679306 48.80609413097143801 0, -86.72057841632587838 48.80615858816795338 0, -86.72066810222776212 48.80622832612267104 0, -86.72077882778158653 48.80628326897954139 0, -86.72089567124234577 48.80633037578959943 0, -86.72103874944404822 48.80635149734121825 0, -86.72117344708041742 48.80633590762199248 0, -86.72132130459917221 48.80631545577193009 0, -86.72145390612750759 48.80629370473888429 0, -86.72158064082407236 48.80632895022466755 0, -86.72171827174243219 48.80635669407724464 0, -86.72185707493756013 48.80636088563681341 0, -86.72200308781758338 48.80636834644720778 0, -86.72214843000492124 48.80636532789015547 0, -86.72225957410192621 48.80630388811698595 0, -86.72234758423867618 48.80622593715170865 0, -86.72235358929464155 48.806221926834084 0) | R1828 | ANWIN | C | Temp | WF6 | C199 | 0.19718 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C199 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.2 | 0.2 | All-season | 0.16285 | 0.034336
LineStringZ (-86.69373022861843481 48.80453019140897908 0, -86.69371653325472948 48.80452734109011459 0, -86.69366277463016957 48.80451615572034996 0, -86.69352480905099867 48.8045207664460392 0, -86.69340293618195403 48.80447810205937742 0, -86.69328089446281638 48.8044370311749276 0, -86.69315248400006624 48.80439386424571069 0, -86.69302633620414156 48.8043544284179589 0, -86.69292458089491049 48.80429382611232114 0, -86.6928754819678602 48.80427143664761047 0) | R1833 | ANWIN | C | Temp | WF6 | C204 | 0.070791 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C204 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.07 | 0.07 | All-season | 2.5e-10 | 0.070791
LineStringZ (-86.68939490754682708 48.80407211902640796 0, -86.68933838140829096 48.80408876302407606 0, -86.68920913285549545 48.80412417619125165 0, -86.68920027984066223 48.80412366024372517 0) | R1834 | ANWIN | C | Temp | WF6 | C204 | 0.015472 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C204 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.02 | 0.02 | All-season | 0.015472 | 0
LineStringZ (-86.6922826737554999 48.80382477514277184 0, -86.69227657466876735 48.80381865601378166 0, -86.69220499392829993 48.80373768673688772 0, -86.6921324067191108 48.80366099229691912 0, -86.69209343076158802 48.80357285659597721 0, -86.69204196552338715 48.80348782170138833 0, -86.69196317499559257 48.80340702012290421 0, -86.69191179419757987 48.80332315936372822 0, -86.69182763989812202 48.80324835084499568 0, -86.6917180052537617 48.80319474862846363 0, -86.69158221812737963 48.80315824599465913 0, -86.69144182041355862 48.80312878277920419 0, -86.69130175986018116 48.803110091138727 0, -86.69116622365450553 48.80308293457189706 0, -86.69102465332387908 48.80308104836991134 0, -86.69088777742979346 48.80307580920024435 0, -86.69074360838074256 48.80306667304996182 0, -86.69061997496949346 48.80310506343270305 0, -86.69055434488487322 48.80318460662135038 0, -86.69048033206250636 48.80326222282187132 0, -86.69040296745174601 48.80333807936113999 0, -86.69027614887561128 48.80338690420971659 0, -86.69019626932656308 48.80346217361314842 0, -86.69006844562510139 48.80349855144289961 0, -86.68998940472444303 48.80357532887757088 0, -86.6899143024834018 48.80365667599628665 0, -86.68989866714341019 48.80368825107642294 0) | R1835 | ANWIN | C | Temp | WF6 | C204 | 0.25266 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C204 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.25 | 0.25 | All-season | 0.25266 | 0
LineStringZ (-86.6886706097653672 48.80403062882751897 0, -86.68870152498854509 48.80408306330777179 0, -86.68875961118440898 48.80416889391512569 0, -86.68883203140292437 48.80424655259000133 0, -86.68892649495417402 48.80431343959241985 0, -86.68906915522364898 48.80430258495853479 0) | R1836 | ANWIN | C | Temp | WF6 | C205 | 0.047559 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 - SP3 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 - SP3 | 0.05 | 0.05 | All-season | 0.047559 | 0
LineStringZ (-86.6848178823282467 48.80380985081004752 0, -86.68477879231612349 48.80383646816983401 0, -86.68465021482914779 48.80386739718415612 0, -86.68453588490119444 48.80391852675504794 0, -86.68444225967830619 48.80398432500384587 0, -86.68439775072917541 48.80407015578818175 0, -86.68433849154530435 48.8041535550412604 0, -86.68426012062302277 48.80422878307726364 0, -86.68412651338961439 48.80424915088590154 0, -86.68398988799744131 48.80426000515262075 0, -86.6838529278258676 48.80426972844883693 0) | R1837 | ANWIN | C | Temp | WF6 | C205 | 0.095112 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.1 | 0.1 | All-season | 0.095112 | 0
LineStringZ (-86.68920027984066223 48.80412366024372517 0, -86.68906957432680827 48.80411604623197519 0, -86.68894091238024657 48.80408365016695171 0, -86.68884337559805431 48.8040405257562 0) | R1838 | ANWIN | C | Temp | WF6 | C205 | 0.028364 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.03 | 0.03 | All-season | 0.028364 | 0
LineStringZ (-86.68707629637233936 48.8039392832783534 0, -86.68704869657724998 48.80395641309146271 0, -86.68695884290470133 48.80402438984419433 0, -86.68685851186366165 48.80408826020361346 0, -86.68672523922623441 48.80410783219366522 0, -86.68658760779307215 48.80410435356956356 0, -86.68647428505724406 48.80405355927048561 0, -86.68635048334117243 48.80401428983631007 0, -86.6862299522153279 48.80396990778113775 0, -86.68609416530750877 48.80394065481429777 0, -86.68597572842344334 48.80389354882634478 0, -86.68588207631319165 48.80387084698282507 0) | R1839 | ANWIN | C | Temp | WF6 | C205 | 0.10142 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.1 | 0.1 | All-season | 0.10142 | 0
LineStringZ (-86.68826192032263123 48.80359449129809235 0, -86.68821168635199115 48.80356539659423731 0, -86.68808243754234866 48.80353132473385358 0, -86.68794287829190637 48.80352931244723891 0, -86.68780147534984337 48.80355051892561136 0, -86.68775095621373339 48.80356521640015188 0) | R1840 | ANWIN | C | Temp | WF6 | C205 | 0.040076 | 10 | 20 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 0.040076 | 0
LineStringZ (-86.66237546705900741 48.80262272780154831 0, -86.66240606050008921 48.80271077978145655 0, -86.66250169834079031 48.80277519464593894 0, -86.66262533121658862 48.80282037257243388 0, -86.66275969290349224 48.80284786603583314 0, -86.66289455815012843 48.80283072472342809 0, -86.6630154252006264 48.80287942325231398 0, -86.66311590756967576 48.80285649572169859 0) | R1841 | ANWIN | C | Temp | WF6 | C211 | 0.069063 | 10 | 20 | Middleton Road - ML - WF6 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C211 | ANWIN | Required | Middleton Road - ML - WF6 | 0.07 | 0.07 | All-season | 0.069063 | 0
LineStringZ (-86.65866831699965189 48.80258831982454382 0, -86.65864250313975958 48.80258197230776318 0, -86.6585403258980449 48.80255684625920054 0, -86.65840344872049172 48.80253404709977616 0, -86.65827612781606604 48.80256673702947978 0, -86.65814059284741688 48.80255064441809054 0, -86.6580058120360377 48.80252859856685177 0, -86.65786885166696152 48.80254050129631338 0, -86.65773205805520263 48.80252968868874319 0, -86.65760113304577317 48.80250060368800291 0, -86.65745964611134866 48.80251028487979426 0, -86.65733148758314996 48.80247814017499763 0, -86.65719804744760779 48.80251003257403397 0, -86.65706351847831002 48.80248987461902743 0, -86.6569212762458676 48.80248249838356145 0, -86.65678599293428874 48.80246175312262125 0, -86.65665464912970606 48.80249951469394887 0, -86.65662388687024986 48.80250311859692403 0) | R1842 | ANWIN | C | Temp | WF6 | C212 | 0.15569 | 10 | 20 | Middleton Road - ML - WF6 - SP2 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C212 | ANWIN | Required | Middleton Road - ML - WF6 - SP2 | 0.16 | 0.16 | All-season | 0.079172 | 0.076515
LineStringZ (-86.65403186614531705 48.80225803162490195 0, -86.65404572925064031 48.80229171628361939 0, -86.65406765712225479 48.80234499403189119 0, -86.65410152051650527 48.80243245891330872 0, -86.65414736838633303 48.80252264863080569 0, -86.65415306885196856 48.80261258743978914 0, -86.65429430416212142 48.80293667273608094 0) | R1843 | ANWIN | C | Temp | WF6 | C213 | 0.078125 | 10 | 20 | Middleton Road - ML - WF6 - SP1 | Middleton Road - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C213 | ANWIN | Required | Middleton Road - ML - WF6 - SP1 | 0.08 | 0.08 | All-season | 0.078125 | 0
LineStringZ (-86.6445033160917859 48.80328640778908778 0, -86.64449621224464693 48.80328088755649674 0, -86.64441195354834235 48.80321541333228907 0, -86.64431975196015401 48.80314370643264965 0, -86.64433592867545997 48.80304517693511457 0, -86.64437264157413665 48.80294937179461812 0, -86.64442678854280189 48.8028658881973314 0, -86.64449870576768831 48.80278395540590708 0, -86.64448582739817084 48.80272281339733809 0) | R1844 | ANWIN | C | Temp | WF6 | C215 | 0.070306 | 10 | 20 | Little Pie River Rd - ML - WF6 - BR2 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C215 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR2 | 0.07 | 0.07 | All-season | 0.070306 | 0
LineStringZ (-86.64392054121793763 48.80259968441807672 0, -86.64387651661319012 48.80262289740264237 0, -86.64378104724309537 48.80268789861800371 0, -86.64364442223750018 48.80271266678556685 0, -86.64350285131354212 48.80271874390292908 0, -86.64335817965456954 48.80272037804878238 0, -86.64322591399850637 48.80268479728292874 0, -86.64311032741933616 48.8026239857880384 0, -86.64302600528093024 48.80255135676509326 0, -86.64298024009511323 48.80246594511377367 0, -86.6429940506219225 48.80239625127925507 0) | R1845 | ANWIN | C | Temp | WF6 | C215 | 0.095048 | 10 | 20 | Little Pie River Rd - ML - WF6 - BR2 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C215 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR2 | 0.1 | 0.1 | All-season | 0.095048 | 0
LineStringZ (-86.64327294710797389 48.80217328377003128 0, -86.64342791741432848 48.80207413309664588 0) | R1846 | ANWIN | C | Temp | WF6 | C215 | 0.015842 | 10 | 20 | Little Pie River Rd - ML - WF6 - BR2 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C215 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR2 | 0.02 | 0.02 | All-season | 0.015842 | 0
LineStringZ (-86.63933913931711572 48.80213557333676277 0, -86.63946436527123751 48.80218070914263961 0, -86.63959160313380892 48.80221763240141541 0, -86.63973124555433003 48.80223464666737954 0, -86.6398700491984215 48.80224214942317928 0, -86.63999510750473121 48.80228531581321505 0, -86.64013248723814797 48.80232550689098048 0, -86.6402639157144705 48.80234993991624037 0, -86.64039794180727938 48.80233087107873757 0, -86.6405384230489517 48.80232320209351826 0, -86.64068108238899413 48.80231926225115302 0, -86.64081577979948179 48.80233640282349228 0, -86.64095684715711343 48.8023248363095874 0, -86.64109297032418056 48.80231871657025522 0, -86.64123370252696077 48.80230333619000049 0, -86.64137082957795144 48.80229583477019162 0, -86.64149286980394038 48.80225287730360861 0, -86.64161323400584536 48.8022033402557085 0, -86.64170727914689962 48.80213226233591683 0, -86.64173757747956017 48.80211877172204993 0) | R1847 | ANWIN | C | Temp | WF6 | C216 | 0.18851 | 10 | 20 | Little Pie River Rd - ML - WF6 - BR1 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C216 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR1 | 0.19 | 0.19 | All-season | 0.18851 | 0
LineStringZ (-86.64210937866256756 48.80191632492342535 0, -86.6421443956535029 48.80190184310533397 0, -86.64223500400277089 48.80182707743723824 0, -86.6423659294691646 48.80185364844291485 0, -86.64249509423517281 48.80188654608914334 0, -86.64262811586087309 48.80191483522720119 0, -86.64276105211226309 48.80194538732828136 0, -86.6428942412017733 48.80197334112872909 0, -86.64302080835513209 48.80201659167381933 0, -86.64315617535122271 48.80204492344851275 0, -86.64329129176574895 48.80206252391819532 0, -86.64342791741432848 48.80207413309664588 0) | R1848 | ANWIN | C | Temp | WF6 | C216 | 0.10588 | 10 | 20 | Little Pie River Rd - ML - WF6 - BR1 | Little Pie River Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C216 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR1 | 0.11 | 0.11 | All-season | 0.10588 | 0
LineStringZ (-86.63415727769263697 48.80094798319398564 0, -86.63428459920386615 48.80098180358775295 0, -86.63440697402612045 48.80102773559689666 0, -86.6345467854872453 48.80101872599520618 0, -86.63467905178437434 48.80098658170616233 0, -86.63481332893682918 48.80097061386296531 0, -86.63493444842337965 48.80092744720742814 0, -86.63504265894590617 48.8008625718991027 0, -86.63514064234763623 48.80079974937958553 0, -86.63527760340758732 48.80079761177415065 0, -86.63541598848559033 48.80079890956689326 0, -86.63552382566884091 48.80075498959988778 0) | R1849 | ANWIN | C | Temp | WF6 | C217 | 0.11149 | 10 | 20 | C217 - ML - WF6 | C217 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C217 | ANWIN | Required | C217 - ML - WF6 | 0.11 | 0.11 | All-season | 0.11149 | 0
LineStringZ (-86.63594452770337284 48.80038924455426752 0, -86.63594480232096373 48.80038874344733557 0, -86.6359496645649898 48.80029700276492832 0, -86.63592476988876001 48.8002078605872498 0, -86.63592929652713792 48.80011733599550894 0, -86.635997692724942 48.80003821127545649 0, -86.63609433630273315 48.79996989887344228 0, -86.63612400732637298 48.79987975141513346 0, -86.63616583390756887 48.79979383713037322 0, -86.63619915919326786 48.79955706440699004 0) | R1850 | ANWIN | C | Temp | WF6 | C217 | 0.097652 | 10 | 20 | C217 - ML - WF6 | C217 - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C217 | ANWIN | Required | C217 - ML - WF6 | 0.1 | 0.1 | All-season | 0.097652 | 0
LineStringZ (-86.62088309036886358 48.79891709323957372 0, -86.62088486524798725 48.7989197303951201 0, -86.62095585985399282 48.79900723816780328 0, -86.62101838885769212 48.79908841639316108 0, -86.62106004666154035 48.79917973728442604 0) | R1852 | ANWIN | C | Temp | WF6 | C219 | 0.032085 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C219 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.03 | 0.03 | All-season | 0.032085 | 0
LineStringZ (-86.61462215559809863 48.79864283473258268 0, -86.61473355138957686 48.79870695698210881 0, -86.61483572733547476 48.7987719578071335 0, -86.61488861659101701 48.79885644825706947 0, -86.61494695964212553 48.79892814125572897 0) | R1853 | ANWIN | C | Temp | WF6 | C219 | 0.040479 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C219 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 0.040479 | 0
LineStringZ (-86.60642945907883927 48.79710073013603022 0, -86.60642272399191199 48.7971500194140404 0, -86.60640311015681903 48.79724020804445672 0, -86.60631898642317594 48.79729717916862342 0) | R1854 | ANWIN | C | Temp | WF6 | C222 | 0.024477 | 10 | 20 | Neys Rd - ML - WF6 - BR1 - SP3 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 - SP3 | 0.02 | 0.02 | All-season | 0.024477 | 0
LineStringZ (-86.60240648929645602 48.79681501267941002 0, -86.60239144614027396 48.79675946378312545 0, -86.60239027352153585 48.7966685204284758 0, -86.60242994638477398 48.79659777356565797 0) | R1856 | ANWIN | C | Temp | WF6 | C222 | 0.02477 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.02 | 0.02 | All-season | 0.02477 | 0
LineStringZ (-86.5043858421675651 48.78381758642551347 0, -86.50438181911613356 48.78389836040877725 0, -86.504358936719143 48.78398821391971296 0, -86.50437150929499808 48.78407924183712652 0, -86.50438441771706266 48.78416934730663712 0, -86.50439552679777933 48.78423744082018487 0) | R4297 | ANWIN | C | Temp | WF6 | C244 | 0.046948 | 4 | 8 | Mink Creek Rd - ML - WF6 - SP1 | Mink Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 - SP1 | 0.05 | 0.05 | All-season | 0.046948 | 0
LineStringZ (-86.6928754819678602 48.80427143664761047 0, -86.69281025175811806 48.804241689574269 0, -86.69272542680783999 48.80416918739653909 0, -86.69262190908449384 48.8041062807605428 0, -86.69252970878426368 48.80403444785894607 0, -86.69245242781974525 48.80395951330564941 0, -86.69235360520237066 48.80389593706008355 0, -86.6922826737554999 48.80382477514277184 0) | R4351 | ANWIN | C | Temp | WF6 | C204 | 0.066483 | 4 | 8 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C204 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.07 | 0.07 | All-season | 0.063819 | 0.0026648
LineStringZ (-86.68989866714341019 48.80368825107642294 0, -86.68987138728667219 48.80374334440537609 0, -86.68977893452598948 48.8038171889150405 0, -86.68969578562244749 48.80389656571166057 0, -86.68963451463281444 48.80398390519014384 0, -86.68951943109105684 48.80403545418294442 0, -86.68939490754682708 48.80407211902640796 0) | R4352 | ANWIN | C | Temp | WF6 | C204 | 0.058748 | 4 | 8 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C204 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.06 | 0.06 | All-season | 0.058748 | 0
LineStringZ (-86.68862899018816393 48.80390738894606528 0, -86.68864938869509729 48.80399463541937877 0, -86.6886706097653672 48.80403062882751897 0) | R4353 | ANWIN | C | Temp | WF6 | C205 | 0.014107 | 4 | 8 | Dead Horse Creek RD - ML - WF6 - BR1 - SP3 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 - SP3 | 0.01 | 0.01 | All-season | 0.014107 | 0
LineStringZ (-86.68884337559805431 48.8040405257562 0, -86.68882431943467282 48.80403210089241384 0, -86.6887024469827594 48.80397237972112379 0, -86.68865464075035732 48.8039373166637489 0, -86.68864712624053936 48.80392451942964982 0, -86.68856498388791465 48.80384585560883437 0, -86.68849667137452286 48.80376346160117151 0, -86.68842249117878396 48.80368387461851398 0, -86.68831595660824973 48.80362578857241118 0, -86.68826192032263123 48.80359449129809235 0) | R4354 | ANWIN | C | Temp | WF6 | C205 | 0.066473 | 4 | 8 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.07 | 0.07 | All-season | 0.066473 | 0
LineStringZ (-86.68775095621373339 48.80356521640015188 0, -86.68766937707353293 48.80358894978618167 0, -86.68755798067398644 48.80364460626662293 0, -86.68747324061452275 48.80371916342240013 0, -86.6873722376177227 48.80378135556595964 0, -86.68725497552142656 48.80383034874141401 0, -86.68714944775480546 48.8038938841011074 0, -86.68707629637233936 48.8039392832783534 0) | R4355 | ANWIN | C | Temp | WF6 | C205 | 0.065348 | 4 | 8 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.07 | 0.07 | All-season | 0.065348 | 0
LineStringZ (-86.68588207631319165 48.80387084698282507 0, -86.68584606068797882 48.80386211632669813 0, -86.68575084231912342 48.8037947677398094 0, -86.68567481822185528 48.80372000118303077 0, -86.68554741343216108 48.80368307889491319 0, -86.6854088599069712 48.80366958386188969 0, -86.68527273871957561 48.80368198922698042 0, -86.68513133518997904 48.80370042977443745 0, -86.68500099640208134 48.80372716765726437 0, -86.68487375933131034 48.80377180140589388 0, -86.6848178823282467 48.80380985081004752 0) | R4356 | ANWIN | C | Temp | WF6 | C205 | 0.09074 | 4 | 8 | Dead Horse Creek RD - ML - WF6 - BR1 | Dead Horse Creek RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C205 | ANWIN | 0 | Dead Horse Creek RD - ML - WF6 - BR1 | 0.09 | 0.09 | All-season | 0.09074 | 0
LineStringZ (-86.64448582739817084 48.80272281339733809 0, -86.64447925911159132 48.80269162757069523 0, -86.64436710962596067 48.80263697756940644 0, -86.64425730668004633 48.80258350057526684 0, -86.64412395104629638 48.80254833938543158 0, -86.64398414013213312 48.80256615144720911 0, -86.64392054121793763 48.80259968441807672 0) | R4357 | ANWIN | C | Temp | WF6 | C215 | 0.050726 | 4 | 8 | Little Pie River Rd - ML - WF6 - BR2 | Little Pie River Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C215 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR2 | 0.05 | 0.05 | All-season | 0.050726 | 0
LineStringZ (-86.6429940506219225 48.80239625127925507 0, -86.64299834433396086 48.80237458343687251 0, -86.64307897788764024 48.80229738519933846 0, -86.64327294710797389 48.80217328377003128 0) | R4358 | ANWIN | C | Temp | WF6 | C215 | 0.032684 | 4 | 8 | Little Pie River Rd - ML - WF6 - BR2 | Little Pie River Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C215 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR2 | 0.03 | 0.03 | All-season | 0.032684 | 0
LineStringZ (-86.64173757747956017 48.80211877172204993 0, -86.64182135751804026 48.80208146768880084 0, -86.64191112799738903 48.8020129869438577 0, -86.64202805471745705 48.80194995565089044 0, -86.64210937866256756 48.80191632492342535 0) | R4359 | ANWIN | C | Temp | WF6 | C216 | 0.035617 | 4 | 8 | Little Pie River Rd - ML - WF6 - BR1 | Little Pie River Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C216 | ANWIN | 0 | Little Pie River Rd - ML - WF6 - BR1 | 0.04 | 0.04 | All-season | 0.035617 | 0
LineStringZ (-86.63552382566884091 48.80075498959988778 0, -86.63553216117209388 48.80075159479470415 0, -86.63565889655178864 48.80071391827228666 0, -86.63574497871840663 48.80063412273654677 0, -86.63580608183634979 48.80054678337391749 0, -86.63589702544088311 48.80047595585624975 0, -86.63594452770337284 48.80038924455426752 0) | R4360 | ANWIN | C | Temp | WF6 | C217 | 0.053088 | 4 | 8 | C217 - ML - WF6 | C217 - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C217 | ANWIN | Required | C217 - ML - WF6 | 0.05 | 0.05 | All-season | 0.053088 | 0
LineStringZ (-86.61950626098966666 48.79874415316886882 0, -86.61952372737933104 48.79870603467032453 0, -86.61959597961282498 48.79862435233224716 0, -86.61966496269459981 48.79854367660416159 0, -86.619714583472458 48.79845956437112164 0, -86.6198437474949543 48.79841899584067733 0, -86.61998481541566264 48.79840780583419502 0, -86.62012638600062076 48.79842327144093161 0, -86.62026259227316416 48.79844296799345926 0, -86.62039754006561054 48.79846794626634932 0, -86.62053827243012449 48.79850503579285004 0, -86.62062829452524682 48.7985791736447041 0, -86.6207022236524864 48.79865662295992479 0, -86.62077154108368404 48.79874433943560064 0, -86.62082376120508798 48.79882895359577333 0, -86.62088309036886358 48.79891709323957372 0) | R4361 | ANWIN | C | Temp | WF6 | C219 | 0.15104 | 4 | 8 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C219 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.15 | 0.15 | All-season | 0.15104 | 0
LineStringZ (-86.60653836226795477 48.79669586433252704 0, -86.60653831044930939 48.7966962221950098 0, -86.60653504131867919 48.79678829732463896 0, -86.60649053309620626 48.79687509227974829 0, -86.60644694823854195 48.79696741838897367 0, -86.60643496210626324 48.79706045780304891 0, -86.60642945907883927 48.79710073013603022 0) | R4362 | ANWIN | C | Temp | WF6 | C222 | 0.046091 | 4 | 8 | Neys Rd - ML - WF6 - BR1 - SP3 | Neys Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 - SP3 | 0.05 | 0.05 | All-season | 0.046091 | 0
LineStringZ (-86.60242994638477398 48.79659777356565797 0, -86.60243763094273106 48.79658407222769512 0, -86.60247124216172665 48.79649463781468199 0, -86.60250812194975367 48.79640683663475897 0, -86.60250870910303433 48.7963099422160127 0, -86.60253326811682939 48.79621908218977211 0, -86.60254404703032094 48.79619356271864206 0) | R4363 | ANWIN | C | Temp | WF6 | C222 | 0.045973 | 4 | 8 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C222 | ANWIN | 0 | Neys Rd - ML - WF6 - BR1 | 0.05 | 0.05 | All-season | 0.045973 | 0
LineStringZ (-86.50403383245195243 48.78377309294607045 0, -86.50402441456100178 48.78381940341430578 0, -86.50396247310781916 48.78390284464056492 0, -86.5038539270679081 48.78396344589147304 0, -86.50377270629377335 48.78404009840344457 0, -86.50371017699943366 48.78412358194076859 0, -86.50368455983273464 48.78414757461727902 0) | R4374 | ANWIN | C | Temp | WF6 | C244 | 0.049985 | 4 | 8 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C244 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.05 | 0.05 | All-season | 0.049985 | 0
LineStringZ (-86.49720866156066279 48.78313593612082144 0, -86.4972494879869771 48.78314264800798838 0, -86.49739147731841626 48.78315584908101954 0, -86.49747311659628224 48.78322109142793295 0, -86.49754914161088948 48.78327533321874654 0, -86.49761812413494511 48.78335391443364699 0, -86.4976508337560972 48.78338472527451586 0) | R4375 | ANWIN | C | Temp | WF6 | C245 | 0.045536 | 4 | 8 | Mink Creek Rd - ML - WF6 | Mink Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C245 | ANWIN | 0 | Mink Creek Rd - ML - WF6 | 0.05 | 0.05 | All-season | 0.044624 | 0.00091259
LineStringZ (-86.48541246445716979 48.78688429255606707 0, -86.48539604817058546 48.78690071792588867 0, -86.48537853087431415 48.78699086508934357 0, -86.48539252899043106 48.78708218570216815 0, -86.4854017746873609 48.78715923903005347 0) | R4376 | ANWIN | C | Temp | WF6 | C248 | 0.031087 | 4 | 8 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | Required | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.03 | 0.03 | All-season | 0.031087 | 0
LineStringZ (-86.76528951343175322 48.80821835489247462 0, -86.76522245887365159 48.80813969018463183 0, -86.76516847926569653 48.80805289456485951 0, -86.76503931313003193 48.80800851442743493 0, -86.76490117986497808 48.80799388698386565 0, -86.76476455511215136 48.80800268785170459 0, -86.76461829023345729 48.80800801083861984 0, -86.7644708531159381 48.80801672810752478 0, -86.76433573581567771 48.80804589743035393 0, -86.76419114894159179 48.80806743756780008 0, -86.76404605830356331 48.80808688403969597 0, -86.76391454605285958 48.80811307809739219 0, -86.76378085443293742 48.8081407383734529 0, -86.76363744038431491 48.80816735032492915 0, -86.76351263268489333 48.8082068716453108 0, -86.76338388690820125 48.80825921743907969 0, -86.7633561275331715 48.80826665766284123 0) | R4343 | ANWIN | C | Temp | WF6 | C189 | 0.16009 | 4 | 8 | Del Lake Rd W - ML - WF6 - BR1 | Del Lake Rd W - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C189 | ANWIN | 0 | Del Lake Rd W - ML - WF6 - BR1 | 0.16 | 0.16 | All-season | 0.16009 | 0
LineStringZ (-86.73901028431589566 48.80649060057918831 0, -86.73907208521704604 48.80654033956457027 0, -86.73902430803977381 48.80663417594002595 0, -86.73897451949493131 48.80672268934404912 0, -86.73895096486552347 48.80677411433196511 0) | R4344 | ANWIN | C | Temp | WF6 | C195 | 0.034627 | 4 | 8 | Del Lake Rd E - ML - WF6 - BR2 | Del Lake Rd E - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR2 | 0.03 | 0.03 | All-season | 0.034627 | 0
LineStringZ (-86.73805586932834899 48.80643634299098466 0, -86.73808151104222475 48.80644692469883239 0, -86.73821813634785372 48.80645459372484396 0, -86.73836406574231717 48.80645400744785434 0, -86.73836438372728708 48.80645388132695217 0) | R4345 | ANWIN | C | Temp | WF6 | C195 | 0.02303 | 4 | 8 | Del Lake Rd E - ML - WF6 - BR2 | Del Lake Rd E - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C195 | ANWIN | Required | Del Lake Rd E - ML - WF6 - BR2 | 0.02 | 0.02 | All-season | 0.02303 | 0
LineStringZ (-86.73252374200123427 48.80653439262505344 0, -86.73256009939417766 48.80649533027511922 0, -86.73260871385745929 48.80641096673326018 0, -86.73260066697041282 48.80632014940373153 0, -86.73255347676577287 48.80623452727314771 0, -86.73247770446859306 48.80615703678824246 0, -86.73236900771654234 48.80611288521546243 0) | R4346 | ANWIN | C | Temp | WF6 | C197 | 0.054997 | 4 | 8 | C197 SP - ML - WF6 | C197 SP - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | 0 | C197 SP - ML - WF6 | 0.05 | 0.05 | All-season | 0.023647 | 0.03135
LineStringZ (-86.72665663852077955 48.80619982725888661 0, -86.7267635084562869 48.80614014790728561 0, -86.72687750138251772 48.80608289894264828 0, -86.72699669234906139 48.8060362117089781 0, -86.72710817179346066 48.805980514658728 0, -86.72721277749823798 48.80591501005794441 0, -86.72729517205574723 48.8058391110906058 0, -86.72731614300548131 48.80582524758625595 0) | R4347 | ANWIN | C | Temp | WF6 | C197 | 0.064373 | 4 | 8 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C197 | ANWIN | Required | Ripple Lake RD - ML - WF6 | 0.06 | 0.06 | All-season | 0.064373 | 0
LineStringZ (-86.72588814786698208 48.80615662469724469 0, -86.72596337183959747 48.80615117029569205 0, -86.72610301336730743 48.8061534327060329 0, -86.72624014173283058 48.80617153801740926 0, -86.72638330507014359 48.80617183114543423 0, -86.72652194183034169 48.80618331419555034 0, -86.72665663852077955 48.80619982725888661 0, -86.72665760618359343 48.80620045027300336 0) | R4349 | ANWIN | C | Temp | WF6 | C198 | 0.057011 | 4 | 8 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C198 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.06 | 0.06 | All-season | 0.057011 | 0
LineStringZ (-86.71963762458923952 48.805800424617793 0, -86.71971005013998024 48.80578638986495577 0, -86.71984734633197434 48.80577377487273338 0, -86.71998397095046585 48.80580667392557359 0, -86.72012344615720281 48.80582171920530499 0, -86.72012686732627174 48.80582831793465459 0) | R4350 | ANWIN | C | Temp | WF6 | C199 | 0.03755 | 4 | 8 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 | YES | Nawiinginokiima Forest Management Corporation |  | WF6 | C199 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.04 | 0.04 | All-season | 0.019374 | 0.018177
LineStringZ (-86.27504753593369458 48.71063008291868357 0, -86.27501187644799074 48.7106722565586594 0, -86.27495018643040225 48.71075682992952238 0, -86.27491322134464724 48.71084387628224732 0, -86.27489116628690624 48.7108933171369074 0) | R3755 | AN | D | Temp | WF7 | D017 | 0.031594 | 4 | 8 | Pic River RD - ML - WF7 | Pic River RD - ML - WF7 | YES | Nawiinginokiima Forest Management Corp. |  | WF7 | D017 | AN | Required | Pic River RD - ML - WF7 | 0.03 | 0.03 | All-season | 0.031594 | 0
LineStringZ (-86.25373283554259274 48.70994541486947327 0, -86.25367288557200141 48.70990979844337687 0, -86.25354573227181731 48.70985493831410196 0, -86.25342335544489458 48.70980691009964403 0, -86.25331422303194984 48.70975188310541881 0, -86.25320106849829926 48.70968574935279349 0, -86.25311037509341361 48.7096122196063277 0, -86.2530460026751058 48.70956384100117731 0, -86.25292588947718286 48.70953873118138944 0, -86.25278792319382148 48.70951039997473941 0, -86.25264995704822013 48.70948399738254153 0, -86.25251534470808679 48.70950080340377042 0, -86.25237586953757329 48.70949644480698026 0, -86.25233053046513021 48.70949169299097292 0) | R3756 | AN | D | Temp | WF7 | D024 | 0.12067 | 4 | 8 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 | YES | Nawiinginokiima Forest Management Corp. |  | WF7 | D024 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.12 | 0.12 | All-season | 0.12067 | 0
LineStringZ (-86.2280562711070786 48.69962578994660163 0, -86.22812139871577131 48.69974380745009768 0, -86.22814796831379169 48.69983642673713575 0, -86.22818065895896211 48.69993244170350977 0, -86.22819649703204448 48.69996962831277187 0) | R3757 | AN | D | Temp | WF7 | D029 | 0.039683 | 4 | 8 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 | YES | Nawiinginokiima Forest Management Corporation |  | WF7 | D029 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.04 | 0.04 | All-season | 0.039683 | 0
LineStringZ (-86.22545168582931296 48.69888823807286116 0, -86.22545209688694001 48.69888793136732374 0, -86.22554647587135435 48.69880461244971315 0, -86.22566994148769481 48.69870306834386042 0) | R3758 | AN | D | Temp | WF7 | D031 | 0.026112 | 4 | 8 | Swede Creek RD - ML - WF7 | Swede Creek RD - ML - WF7 | YES | Nawiinginokiima Forest Management Corporation |  | WF7 | D031 | AN | 0 | Swede Creek RD - ML - WF7 | 0.03 | 0.03 | All-season | 0.026112 | 0
LineStringZ (-86.22566994148769481 48.69870306834386042 0, -86.22573077206106973 48.69867921084156848 0) | R3826 | AU2 | D | Temp | WF7 | D031 | 0.0052029 | 4 | 8 | Swede Creek RD - ML - WF7 | Swede Creek RD - ML - WF7 | YES | Nawiinginokiima Forest Management Corporation |  | WF7 | D031 | AU2 | 0 | Swede Creek RD - ML - WF7 | 0.01 | 0.01 | All-season | 0.0052029 | 0
LineStringZ (-86.41854538953383269 48.77356875185404306 0, -86.41851480771777005 48.77356372890916703 0, -86.41837600456558732 48.77356783599613976 0, -86.41829000614733047 48.7736456620596357 0, -86.41818858405953563 48.77370794061958748 0, -86.41811096780541845 48.77379695584684072 0, -86.41805397153319745 48.77388182271510431 0, -86.41796503847747601 48.77395109917886629 0, -86.41782657026416814 48.77397322724965534 0, -86.41769430331002866 48.77399908565450204 0, -86.41761695007245692 48.77400488227622333 0) | R5111 | ANWIN | C | Temp | WF6 | C261 | 0.091573 | 10 | 20 | Hare Lake Creek Rd - ML - WF6 - BR2 | Hare Lake Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C261 | ANWIN | 0 | Hare Lake Creek Rd - ML - WF6 - BR2 | 0.09 | 0.09 | All-season | 0.091573 | 0
LineStringZ (-86.48414890433552671 48.78443228881034344 0, -86.48417706774939973 48.78452021494781121 0, -86.48418620396718381 48.78460998466984222 0, -86.48424177577430783 48.7846937621429646 0, -86.48433473080291378 48.78475968605265933 0, -86.48436021187292511 48.78484824065448322 0, -86.48444679817222891 48.78491982235252777 0, -86.48446473545739366 48.78501084857163761 0, -86.48452793483329515 48.78509990738483992 0, -86.48461032864072706 48.78517270355799695 0, -86.48469062709001776 48.78525166156040882 0, -86.48471359325202457 48.78534486835919637 0, -86.48478676835365775 48.78542114422333498 0, -86.48483597000446821 48.7855080640118004 0, -86.48491375301330208 48.78558308205637672 0, -86.48493353456161969 48.78567624668593794 0, -86.48495784277008624 48.785767945398824 0, -86.48502062297859538 48.78585264439233526 0, -86.48507761983466935 48.7859343254433 0, -86.48515221890683335 48.78601047518657197 0, -86.48523327213155198 48.7860837336038955 0, -86.48534701380116019 48.78614274162727327 0, -86.4854138185610708 48.78622459134483336 0, -86.48550342030060278 48.78629348958939005 0, -86.48555639463232581 48.78637818859026964 0, -86.48556100436515237 48.78646888164863071 0, -86.48558514423213239 48.78655735259856385 0, -86.48556561455657743 48.78665009875421532 0, -86.48552202825631241 48.78673877928794411 0, -86.48547333046496988 48.78682339418402591 0, -86.48541246445716979 48.78688429255606707 0) | R5112 | ANWIN | C | Temp | WF6 | C248 | 0.3049 | 10 | 20 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | Little Red Sucker Creek Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C248 | ANWIN | 0 | Little Red Sucker Creek Rd - ML - WF6 - BR1 | 0.3 | 0.3 | All-season | 0.3049 | 0
LineStringZ (-86.58629661017393175 48.79511689704644084 0, -86.58632190786815386 48.79513907474517964 0, -86.58640262543308097 48.79521669196063982 0, -86.58653430546340246 48.79525248255685455 0, -86.58665802238904519 48.79529728359704421 0, -86.58681434541655619 48.79530059413147569 0, -86.58695624987745987 48.79529183507179368 0, -86.58709597713881578 48.7952779214442387 0, -86.58723075772820721 48.79529502063001445 0, -86.58736210168646608 48.79532041783183161 0, -86.58748146065822482 48.79527557464449217 0, -86.58762202452673762 48.79526522307851621 0, -86.5877499328018132 48.79522968324418031 0, -86.58789426942662715 48.79521618815387285 0, -86.5880197469516304 48.79517947615062923 0, -86.58815117431403507 48.79514179931160811 0, -86.58820311746217158 48.7951183479849746 0, -86.58824146355460982 48.7951010345917382 0) | R5113 | ANWIN | C | Temp | WF6 | C226 | 0.15684 | 10 | 20 | Neys Rd - ML - WF6 - BR1 | Neys Rd - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C226 | ANWIN | Required | Neys Rd - ML - WF6 - BR1 | 0.16 | 0.16 | All-season | 0.15684 | 0
LineStringZ (-86.71686950727205101 48.80587401057510988 0, -86.71698802690039543 48.80584145925381989 0, -86.71712230446817671 48.80581627187265781 0, -86.71726496485347013 48.80580239929473407 0, -86.71740703797165395 48.80581304442560509 0, -86.71754626132121757 48.80581023617202874 0, -86.71768255058218244 48.80583881908194144 0, -86.71782035020153501 48.80582737720845188 0, -86.71796015961243143 48.80582352186299033 0, -86.71810198112814305 48.80583219721064125 0, -86.71823190059562592 48.80586354543686411 0, -86.71836684952290852 48.80587766869061994 0, -86.71850833700696626 48.80589837208815851 0, -86.718650660987592 48.80589518684532635 0, -86.7187819217801632 48.8059264099824901 0, -86.71892055803134269 48.80592561372645122 0, -86.71905433417495601 48.80594422138791089 0, -86.71919548450013338 48.80592343386176424 0, -86.71932414716096105 48.80588852362321006 0, -86.71945741999942925 48.80586723441304997 0, -86.71957099473195285 48.80581333723788617 0, -86.71963762458923952 48.805800424617793 0) | R1829 | ANWIN | C | Temp | WF6 | C199 | 0.21043 | 10 | 20 | Ripple Lake RD - ML - WF6 | Ripple Lake RD - ML - WF6 |  | Nawiinginokiima Forest Management Corporation |  | WF6 | C199 | ANWIN | 0 | Ripple Lake RD - ML - WF6 | 0.21 | 0.21 | All-season | 0.078278 | 0.13216
LineStringZ (-86.24495627338032477 48.70677097659424959 0, -86.24494220825826574 48.7067675900178827 0, -86.24486685518603224 48.7066832265956009 0, -86.24480524724890529 48.70659794024997069 0, -86.24467851306172861 48.70655142057665188 0, -86.24458664746637737 48.70648403065438714 0, -86.24444775961737264 48.70646709863351731 0, -86.24433326313372561 48.70641278357683746 0, -86.24420744989194532 48.70637162934591657 0, -86.244123882378247 48.70630067612267311 0, -86.24397719884260027 48.70628944544370853 0, -86.24385457226965457 48.70624828924603378 0, -86.24371970662474496 48.70621316907986653 0, -86.24358199282438875 48.706184628753185 0, -86.24347621279541443 48.70612381814942893 0, -86.24334889120325442 48.70608626773710625 0, -86.24322232411095968 48.70605144078483306 0, -86.24311721622629534 48.7059878220583542 0, -86.24300255113938363 48.70592860344474673 0, -86.24288872492667224 48.7058766357515367 0, -86.24277104221675927 48.70582135719363492 0, -86.24265403132376662 48.70577458611986543 0, -86.24251933386788949 48.70574307041726314 0, -86.24242981474023395 48.70567358458221463 0, -86.24229729786627274 48.70564261283210783 0, -86.24218330296686474 48.70559165090010367 0, -86.24205271287272012 48.70555422598648931 0, -86.24194944827033282 48.70549492388368407 0, -86.2418418243974827 48.70543746600586843 0, -86.2417286686719109 48.7053839056484037 0, -86.24161437504055527 48.70536520328619901 0) | R345 | AN | D | Temp | WF7 | D026 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D026 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 3.8e-10 | 0.3
LineStringZ (-86.24088265166263056 48.7051568637786545 0, -86.24085820848719663 48.70515139137770433 0, -86.24074572333557853 48.70509682599614365 0, -86.24060859433467385 48.70508022928665781 0, -86.24047029383638119 48.70508756442885101 0, -86.24034230109990062 48.70505194043423103 0, -86.24021481282105128 48.70501225244999688 0, -86.2400864023577185 48.70498237037683253 0, -86.24000409161068603 48.70490756216391759 0, -86.23993343169593118 48.70483061679315284 0, -86.23982974825347014 48.7047688837435615 0, -86.23971944153154823 48.70470580964344265 0, -86.23958885224868709 48.70467852692503641 0, -86.239468208841771 48.70461783401919575 0, -86.23933068937594726 48.70457459101294972 0, -86.23925332382390252 48.70449328637595698 0, -86.23919230462615815 48.70440951042540689 0, -86.23907621486873154 48.70435066890188125 0, -86.23893917014805766 48.70434199369412198 0, -86.23881553747899886 48.70429522263688682 0, -86.23871989998681897 48.70423097512612998 0, -86.23862124440788079 48.70416588983675155 0, -86.23850037778962019 48.70411978894160399 0, -86.23841362562384916 48.70405042889532155 0, -86.23827596620813551 48.70401806188220206 0, -86.23815437192796196 48.70397203857574908 0, -86.23802830798753405 48.70392247526849872 0, -86.23792806128099642 48.70386564994802825 0, -86.23779956594435703 48.70383203943236339 0, -86.23766813862596337 48.70378945816941041 0, -86.23758028952262578 48.70375269959922093 0) | R346 | AN | D | Temp | WF7 | D027 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D027 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.0092135 | 0.29079
LineStringZ (-86.2327449323513946 48.70195252424522181 0, -86.23279204844268975 48.70199619244068145 0, -86.23291140613932271 48.7020427112317833 0, -86.23304520934574668 48.70204876315145981 0, -86.23317191621099198 48.70206584558910379 0, -86.2333071157439548 48.70209853521423327 0, -86.23343728733959779 48.70213449372700154 0, -86.23356594947260589 48.70216747600744611 0, -86.23369025324980441 48.70222300598691589 0, -86.23381229392731484 48.70226961005736399 0, -86.23393458504762066 48.70230913026590258 0, -86.23402326634530368 48.70237991534835231 0, -86.23414002683240653 48.70242718926487413 0, -86.23426181575183591 48.70248041417537621 0, -86.23437737429124184 48.70250812574931132 0, -86.23448603192231587 48.70256402408732299 0, -86.23460564162708408 48.70261544660999675 0, -86.23472860376662652 48.70265903310681921 0, -86.23485223717348447 48.70270999540507972 0, -86.23497014153134899 48.70274296763756894 0, -86.23508424830745867 48.70279326907879636 0, -86.23519812967553833 48.70283029593681334 0, -86.23529991476844714 48.70287683682695246 0, -86.23540879560455608 48.70293337269980327 0, -86.23552446627697066 48.70298798065915236 0, -86.2356347720862999 48.7030439716069381 0, -86.23577265431458727 48.70307946944061683 0, -86.23590757473034785 48.70308814962803012 0, -86.2360079334309404 48.70310490845236018 0, -86.23609502192753951 48.70317560939208335 0, -86.2362085128941942 48.70322812228976517 0, -86.2362429421235106 48.70323464426479632 0) | R347 | AN | D | Temp | WF7 | D028 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D028 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.2655 | 0.034504
LineStringZ (-86.29252033262892496 48.72141196388657391 0, -86.29264391527429723 48.72141180683079398 0, -86.29276534154537615 48.72136102770624433 0, -86.29289350086555999 48.72132758395890306 0, -86.29303289174183078 48.72132946936475406 0, -86.29318183843361112 48.72133948636020762 0, -86.29332475066651398 48.72133177433860141 0, -86.2934664605277959 48.72132981859548551 0, -86.29360696905618511 48.72132762591139965 0, -86.29374954463847303 48.72132724855294583 0, -86.29387013285943908 48.72130652103982129 0, -86.29399521863130929 48.72126626964214324 0, -86.2941316758435164 48.72125528925158022 0, -86.29426846874925161 48.72126316756992281 0, -86.29439852860308235 48.72129059539304308 0, -86.29452495460988359 48.7213297632760387 0, -86.29466082625576462 48.72135813589641629 0, -86.29479577491547104 48.72137561197740752 0, -86.29493063931180075 48.72139124407498656 0, -86.29507514376454935 48.72138030641208672 0, -86.2952163780582282 48.72135205887972376 0, -86.29535551846308294 48.72132205131822502 0, -86.29549957485676259 48.72131153500103551 0, -86.2956320372761212 48.72133638433184899 0, -86.2957746134553787 48.72136274640270415 0, -86.2959129155989757 48.72139413621194848 0, -86.2960319381610077 48.72144891138430012 0, -86.29616697042651197 48.72147506314743026 0, -86.29630200375174809 48.72148994079372386 0, -86.29644722282669989 48.7214792360757798 0) | R439 | AN | D | Temp | WF7 | D014 | 0.3 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D014 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.27489116628690624 48.7108933171369074 0, -86.27487282074189068 48.71093444278962181 0, -86.27481682943506769 48.71101687757894894 0, -86.27474809763791086 48.71109545915212635 0, -86.27467224230959175 48.71117131498179731 0, -86.27466729648263311 48.71126175555777138 0, -86.27461272998615982 48.71134838332935146 0, -86.27452941372023076 48.71142122155607979 0, -86.27440678643228011 48.7114664836177127 0, -86.27426991081034657 48.71149221599348067 0, -86.27414141618538679 48.71153718532391252 0, -86.2740479580777162 48.71160377984364942 0, -86.27391158476987698 48.71164841319740191 0, -86.27379675206981346 48.71170465586710918 0, -86.27369893534927314 48.71177217172572682 0, -86.27359128297831603 48.71183224503848663 0, -86.27349785320991771 48.7118862077777095 0, -86.2733620667911083 48.71191114438529723 0, -86.27323885174122609 48.71195100020047164 0, -86.27314505836838521 48.71202082059362937 0, -86.2730807697950155 48.71210350895415075 0, -86.27302150955964066 48.71218590334419218 0, -86.27302000038486085 48.71227659492436146 0, -86.27297306255188403 48.7123682512187699 0, -86.27297951682854205 48.71246430797772575 0, -86.27303676447493785 48.71254682844151063 0, -86.27307641157955231 48.71263655620861499 0, -86.27310172492758511 48.7127264940018847 0, -86.27307356180435249 48.71282087406628847 0, -86.2730450627907004 48.7129152547019828 0, -86.27304199578513533 48.71297150273750987 0) | R440 | AN | D | Temp | WF7 | D017 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D017 | AN | Required | Pic River RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.2789345259904934 48.71768547916258996 0, -86.27893286819447383 48.71768503967135899 0, -86.27881622936979511 48.71765411407792357 0, -86.27868902038261467 48.7176307878149899 0, -86.27854711476391003 48.71761488657308803 0, -86.27841375859766515 48.71760312655088399 0, -86.27827730014121244 48.71760656393323075 0, -86.27815282878820824 48.71758804737567061 0, -86.27804285886566049 48.71755685960786053 0, -86.27796993619413968 48.71747999743388391 0, -86.27793045721148246 48.71739332938952316 0, -86.27788586607640298 48.7173064079854683 0, -86.27784001711330575 48.71721999056003227 0, -86.27774848607633373 48.71715243237834159 0, -86.27761546579321816 48.71712946612717587 0, -86.27748808775172051 48.71711997355704682 0, -86.27735654805343302 48.71708743088968419 0, -86.2772382793443029 48.71704061795801266 0, -86.27710551010660822 48.71701999798884941 0, -86.27698380495174035 48.7169789693516222 0, -86.2768791991313293 48.71691258429030569 0, -86.27677802864300816 48.71684452312206304 0, -86.27667224965817638 48.71678585010621987 0, -86.27657032599707065 48.71673271134329042 0, -86.27645641503131912 48.71667554430282365 0, -86.27634426512177868 48.71662395323048855 0, -86.27622038145729277 48.71658250527222833 0, -86.27609065729126314 48.7165483703430624 0, -86.27597646747638294 48.71650681659777149 0, -86.27584696683453558 48.71647806609675513 0, -86.27572677019473701 48.71643003940032202 0, -86.27561411787395684 48.71640709091047228 0, -86.27560318663194039 48.71640478034286303 0) | R442 | AN | D | Temp | WF7 | D018 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR1 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D018 | AN | 0 | Pic River RD - ML - WF7 - BR1 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.27267408014012062 48.7155440712508252 0, -86.27253879575008 48.71552169117094166 0, -86.27238942996439164 48.71549893413077115 0, -86.27225431403381606 48.71548430766823401 0, -86.27200788558896249 48.71543912943583621 0, -86.27186723758916287 48.71541465455668174 0, -86.27172088926739946 48.71540836788998519 0, -86.27158426435437377 48.71542060532327412 0, -86.27144344934501419 48.71541863455716026 0, -86.27130581778439478 48.71542140223715478 0, -86.2711688575322313 48.71539717833020688 0, -86.2710297172235272 48.71537396063144598 0, -86.27085101619034901 48.71531302431717592 0, -86.27072221386717388 48.71528067309771615 0, -86.27057871585428472 48.71527831365010286 0, -86.27044373928211485 48.71528439959745782 0, -86.27030267110039574 48.71527467744258644 0, -86.27017325405554971 48.71523259956756391 0, -86.27003243874861482 48.71521772208544832 0, -86.2699178574003156 48.71516713668707865 0, -86.26982289137464477 48.71510213499458786 0, -86.26968433865289398 48.71506969742962667 0, -86.26954695795700445 48.71505012533714307 0, -86.26940496863335284 48.7150347871368794 0, -86.26927312122346336 48.71500310319064653 0, -86.26914144139534812 48.71497506539959232 0, -86.26901219316061997 48.71493684393961132 0, -86.26891697446754392 48.71487222042999576 0, -86.26886893734337036 48.71482140218139278 0) | R443 | AN | D | Temp | WF7 | D020 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D020 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.25479 | 0.045214
LineStringZ (-86.26580955085846369 48.71387054018550344 0, -86.26567803789085076 48.71384631655782016 0, -86.26562309177764121 48.71383102372857365 0, -86.26555230989336565 48.7138113225674303 0, -86.26538103954023029 48.71377166503818046 0, -86.26528447948737721 48.71375042743397188 0, -86.26518291947039074 48.71372331215486184 0, -86.26503564916409061 48.71371874376634992 0, -86.26489718051709588 48.71371870243814328 0, -86.26475083167807156 48.7137226418369309 0, -86.26460901005350479 48.71372264173869837 0, -86.264493842194085 48.71366757158607186 0, -86.26438965611677645 48.71360923475540972 0, -86.26429468861783789 48.71354427524470054 0, -86.26416887633195074 48.71350781372721883 0, -86.26404256042877705 48.71346544287448666 0, -86.26390954001459477 48.71344432026672422 0, -86.26377551262876864 48.71342085116886267 0, -86.26365020322631949 48.71337680493317635 0, -86.26352833040783707 48.71333007538135007 0, -86.26341416887522939 48.71327521568767338 0, -86.26331945329656037 48.71319927536121952 0, -86.26319439526987765 48.71315036780791274 0, -86.2630602017399184 48.71311675633769056 0, -86.26295215838271702 48.71305418512066865 0, -86.26281159441987256 48.71304722782209495 0, -86.26267496943633262 48.71305045492650265 0, -86.26254479823217025 48.71301466543474845 0, -86.26245603346035296 48.71294521992713555 0, -86.2623620728856082 48.7128789617121214 0, -86.26225872289042229 48.71281383439051638 0, -86.26223534455853326 48.71280401741707067 0) | R445 | AN | D | Temp | WF7 | D021 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D021 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.22819649703204448 48.69996962831277187 0, -86.22821812619390869 48.70002041007641225 0, -86.22827562566014592 48.7001033488083408 0, -86.22838685269704229 48.70015619705212373 0, -86.2284946445019358 48.70022245529738569 0, -86.22861232641399454 48.70027182543741873 0, -86.22874249820904424 48.70029986273532785 0, -86.22885137893698015 48.7003547639443255 0, -86.22897367032746274 48.7003963801617914 0, -86.2290802040989206 48.70045530473608153 0, -86.22921808672934674 48.70047693022728197 0, -86.22931414343833012 48.7005426440846847 0, -86.22943593294137088 48.70058727827210276 0, -86.22956316965709789 48.70061954840741691 0, -86.22968269653945583 48.70066686426001468 0, -86.22979920479561144 48.70071455743934763 0, -86.22993121971842356 48.70074733140992862 0, -86.23006625193158925 48.70078073263595542 0, -86.23020547521083756 48.70081639726013378 0, -86.23029172579821022 48.70089036714954034 0, -86.23039683462113203 48.70095583020391672 0, -86.23050051918177417 48.70101827532244698 0, -86.23062457044211726 48.70106018491248534 0, -86.23074988025425114 48.70109773602102621 0, -86.23085926424295167 48.70115393682931426 0, -86.23098205874279643 48.70119907267218196 0, -86.23109697565075749 48.70125619540988282 0, -86.23122144647675213 48.70129454286369963 0, -86.2313537960675518 48.70132379542206991 0, -86.2314747474978418 48.70137069158968046 0, -86.2315400343636469 48.70139883714031726 0) | R450 | AN | D | Temp | WF7 | D029 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D029 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.2823 | 0.017698
LineStringZ (-86.27790778865008292 48.70712829289010415 0, -86.27785166633971414 48.70736995335457209 0, -86.27783339285350905 48.70746320284771258 0, -86.27781051046495975 48.70756345035359658 0, -86.27780523074555674 48.70765845907205716 0, -86.27777882769770201 48.70775870609074332 0, -86.2777384271607275 48.70785027941209933 0, -86.27771336501746191 48.70794742484372364 0, -86.27769961790306752 48.70804197294197024 0, -86.27768000456141806 48.70814427404068425 0, -86.27764061003976792 48.70823760698235816 0, -86.27758478665984399 48.70832431737645862 0, -86.27752007818213542 48.7084189489274948 0, -86.27744992174645233 48.70850159486798248 0, -86.27733450289780137 48.70855645379223375 0, -86.27720290654670521 48.70859396366223848 0, -86.27707541821483517 48.70864102789757055 0, -86.27695178508059826 48.70868473902500284 0, -86.27683728768627702 48.70874039489611107 0, -86.27672052740594211 48.70879420662740955 0, -86.27657594078338832 48.70883729012147256 0, -86.27644987638140606 48.70887236801675613 0, -86.27631115554808616 48.70889235887266722 0, -86.2761855109568927 48.70893946519055362 0, -86.27607696495297773 48.708996797695022 0, -86.27600127692363685 48.70908665170587426 0, -86.27589382007376173 48.70914335485229429 0, -86.2758721508762676 48.70918383455222056 0) | R594 | AU2 | D | Temp | WF7 | D018 | 0.3 | 7.5 | 15 | Pic River RD - ML - WF7 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D018 | AU2 | Required | Pic River RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.23165477454001859 48.69521212085040673 0, -86.23147047245879548 48.6953470373134607 0, -86.23138849703892106 48.69542871839063025 0, -86.23132512993363719 48.69551027437279345 0, -86.23123234151398719 48.69558022141895748 0, -86.23116503528638077 48.69566064629286473 0, -86.23104458717057241 48.69571973820497135 0, -86.23094928524123759 48.69578549400918632 0, -86.230850630268435 48.69585099884505297 0, -86.23073378637141673 48.69589940541991524 0, -86.23060571069150626 48.69593754237508421 0, -86.23046673877394142 48.69599047442262219 0, -86.23032307339036606 48.69599495830827607 0, -86.23020723514785857 48.6960470514123287 0, -86.23006239508046633 48.69606599480970743 0, -86.22991805977282809 48.69609273300618213 0, -86.22977657269353813 48.69611875867305884 0, -86.22965176673558574 48.69615547163863312 0, -86.22951287764831818 48.69619432224068589 0, -86.22937834840547566 48.69622868844601271 0, -86.22925446379676373 48.69627026239218992 0, -86.22911691663966849 48.69626292781756405 0, -86.22899009886700128 48.69629561699957065 0, -86.22887057273447908 48.69634452641360411 0, -86.22874341941991361 48.69639586489522998 0, -86.22863302995479273 48.6964543289155074 0, -86.22850637904909377 48.69654078805659481 0, -86.22843219930267367 48.6966186976427764 0, -86.22839376119739541 48.69663440306089086 0) | R667 | AU2 | D | Temp | WF7 | D030 | 0.3 | 7.5 | 15 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corporation |  | WF7 | D030 | AU2 | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.16607 | 0.13393
LineStringZ (-86.31315944040791521 48.72158675056882515 0, -86.31333160502491353 48.72163691631716631 0, -86.31343973220825205 48.72165280010911204 0, -86.3135341118508137 48.7216909797868567 0, -86.31365179355751138 48.7217032588747756 0, -86.31376101074708629 48.72169030904143483 0, -86.3138675438311509 48.72167056992952183 0, -86.31396871366487744 48.72163628801740032 0, -86.31407700846068565 48.721623262222856 0, -86.31418236869109251 48.72159496500959364 0, -86.31428580179910171 48.72156579620052241 0, -86.3143935922822152 48.72154354156862155 0, -86.31449518093860718 48.72151571371598067 0, -86.31458386216895917 48.72147179316963417 0, -86.31468452805147251 48.72144421605064935 0, -86.31479801914029792 48.72142585968691009 0, -86.31489944113381796 48.72139945727411003 0, -86.3150011135082309 48.72136261894214471 0, -86.31511980104743031 48.72135205772064381 0, -86.31521784098949013 48.72133158766871475 0, -86.31532364812311187 48.72131454803501072 0, -86.31542705304639185 48.72131802141786494 0, -86.31553705256573039 48.72131425510790592 0, -86.31564431262491155 48.72131979242023192 0, -86.31575355687876083 48.72131827944815541 0, -86.31586922713646004 48.72132024824841068 0, -86.3159810416584321 48.72132280488058598 0, -86.31610358507822411 48.72132024780889026 0, -86.31622294345787338 48.72133168858663055 0, -86.31632782853793628 48.72133129260974016 0, -86.31644355471051711 48.72133164725808996 0, -86.31655260331402246 48.72132741463467909 0, -86.31667129112540238 48.7213285458954104 0, -86.31678251907446509 48.72133747293356265 0, -86.31689198645858596 48.72134367979014513 0, -86.31700598135013536 48.72133915040209473 0, -86.31708284010086629 48.72133926591324382 0) | R691 | AN | D | Temp | WF7 | D010 | 0.3 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D010 | AN | Required | Three Finger Lake RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.31315944040791521 48.72158675056882515 0, -86.31301954645422825 48.72161491382330922 0, -86.31288191578427416 48.72163142601323926 0, -86.31273095795977213 48.72162078107267291 0, -86.31259919472338993 48.72165590134788715 0, -86.31248628934690714 48.72171558099939404 0, -86.31234340654258119 48.72172795716964089 0, -86.31222854687140966 48.72170606772296964 0, -86.31208907133533614 48.72167626933258333 0, -86.31195370358517494 48.72165363823582851 0, -86.31182898045287288 48.72161696731092917 0, -86.31169126642397771 48.72161763808160373 0, -86.31155841209017865 48.7216229671364971 0, -86.31143209733662047 48.72164106645310255 0, -86.31130628520500636 48.72167890976007243 0, -86.31117862882850034 48.72171608338714321 0, -86.31103663861722453 48.7217491921737178 0, -86.31090043264644862 48.72174106199890531 0, -86.31075509121006917 48.72172387907910007 0, -86.31061516840898662 48.72173591996364195 0, -86.31048837830580567 48.72174856374254404 0, -86.31035410039407907 48.7217497824506296 0, -86.31021244589206276 48.72173582443837603 0, -86.31008923213896367 48.72169345261569617 0, -86.30997917761028759 48.72163892831767384 0, -86.30988655842659796 48.72157304636306208 0, -86.30978589077922436 48.72151240315095322 0, -86.30964624856999023 48.72141475462388627 0, -86.30950912115589801 48.7213797602093095 0, -86.30939940662027254 48.7213833227586548 0) | R338 | AN | D | Temp | WF7 | D011 | 0.3 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D011 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.22888 | 0.071119
LineStringZ (-86.30815612271365467 48.72144091800956289 0, -86.30811596452726064 48.72144090627632806 0, -86.30798445184798595 48.72141425169540696 0, -86.3078632211753245 48.72139352241181598 0, -86.30772911050803486 48.72136874831883091 0, -86.30759008372221786 48.72136991098265213 0, -86.30742688720812339 48.72135855401301541 0, -86.3072926931121458 48.72133977843520825 0, -86.30715690672474238 48.72132804969788822 0, -86.30701307313250936 48.72132024869537759 0, -86.30688242664393783 48.72133748662963626 0, -86.30675390427472848 48.72133470729165339 0, -86.30661015497956612 48.72134313083061841 0, -86.3064720203681901 48.72136919882797201 0, -86.30633346779086423 48.72137700557908602 0, -86.30619776450571123 48.7213704139067616 0, -86.30606952233024742 48.7213382693945718 0, -86.3059297112680639 48.72133240204529869 0, -86.30578319541838539 48.72131253841850196 0, -86.30564682218529526 48.72130416082472948 0, -86.30551003018970846 48.72131731460494564 0, -86.30537147634167638 48.72133202562841348 0, -86.30522923579925987 48.72135813485447642 0, -86.30509755644276026 48.72138160426002429 0, -86.30496704956466658 48.72141756273143187 0, -86.30485012211487117 48.72146697394479986 0, -86.30475800528806474 48.72153482569875393 0, -86.30462355865776658 48.72160334762425293 0, -86.30449481248940913 48.72163352267291714 0, -86.30438073579726677 48.72168595082961673 0, -86.3042876473453191 48.72171139843549525 0) | R339 | AN | D | Temp | WF7 | D012 | 0.3 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D012 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.1855 | 0.1145
LineStringZ (-86.28856305712440644 48.72050256230708953 0, -86.28863423543818101 48.72055271897403372 0, -86.28873708096661233 48.72061906173079393 0, -86.28883406018424296 48.7206864522223313 0, -86.28896062732161454 48.72075618969669364 0, -86.2890978383476579 48.72077148686242509 0, -86.28923437991775813 48.72075826465564319 0, -86.28934745152120911 48.72072873865838716 0, -86.28949405202259015 48.72072010504421513 0, -86.28964296957215652 48.7207373251544098 0, -86.28976948123457191 48.7207371208713198 0, -86.28990912338203145 48.72076855314693944 0, -86.29004264706483696 48.72080425940487203 0, -86.2901825416953443 48.72081477866785804 0, -86.29031355098979361 48.72084319393950835 0, -86.29045897680808253 48.72085216181428535 0, -86.29059738890971687 48.72086679527608766 0, -86.29074949387766935 48.72088887530360779 0, -86.29088796165547137 48.72089540233339733 0, -86.2910184961701674 48.72093403709807546 0, -86.29114503600158059 48.72096079202046326 0, -86.291272105520477 48.72101120901984217 0, -86.29139070971358194 48.72105575870984495 0, -86.2915252386990943 48.72107558223850532 0, -86.29166597100712011 48.72108287433388796 0, -86.29180083547107927 48.72111241993567177 0, -86.29193469501275615 48.72114276255933163 0, -86.29204349256472995 48.72120139414700901 0, -86.292147595679765 48.72127251492428712 0, -86.29224314867551016 48.72133789302646534 0, -86.29224392796082554 48.72133816859717825 0) | R341 | AN | D | Temp | WF7 | D015 | 0.3 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D015 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.28472625367899695 48.71930209390036737 0, -86.28496379923974757 48.71937208566977517 0, -86.28508156507962212 48.71942313189642704 0, -86.28516597050915493 48.71949617982632219 0, -86.28522282886784467 48.71954749124195416 0, -86.2852733430250538 48.71960200188828338 0, -86.2853894314896479 48.71966527125264435 0, -86.28546512094449383 48.71971771410299112 0, -86.28558087413279054 48.71978011666356423 0, -86.28571599040375872 48.71982739067647827 0, -86.28585035354690547 48.71984692114327942 0, -86.2859798539470404 48.71988178943638559 0, -86.28611622682019799 48.71990919827741351 0, -86.28623790417427131 48.71994014406865858 0, -86.28635569811441997 48.71996959031029206 0, -86.28645784517452455 48.72002744202439573 0, -86.28655677950403913 48.72008002180377417 0, -86.28669253874200251 48.72011002244867939 0, -86.28681055632463881 48.72011533024910079 0, -86.2869344689440112 48.72014296956012913 0, -86.28707017195758056 48.72015860166646917 0, -86.28720269034992896 48.72018927975726399 0, -86.28731333092258637 48.72024309090554084 0, -86.28743428183661024 48.72029862190028382 0, -86.28756380967396922 48.72032236844117392 0, -86.28768791860598242 48.72034945758931457 0, -86.28781414973951769 48.7203922642920233 0, -86.28794842843875301 48.7204153398646298 0, -86.28806359579770913 48.72045272431362406 0, -86.2881853846859741 48.72046110459933743 0, -86.28827949062453229 48.72045193680775554 0) | R342 | AN | D | Temp | WF7 | D016 | 0.3 | 10 | 20 | Three Finger Lake RD - ML - WF7 | Three Finger Lake RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D016 | AN | 0 | Three Finger Lake RD - ML - WF7 | 0.3 | 0.3 | All-season | 0.3 | 0
LineStringZ (-86.26147853572520319 48.71265696559857616 0, -86.26136504528876969 48.7126059207385893 0, -86.2612376391481348 48.71256711308431875 0, -86.26109841671008382 48.71258534255839123 0, -86.26096179084220239 48.71261237507332709 0, -86.26081887909495549 48.71262519903967103 0, -86.26068284147234522 48.7125957372864633 0, -86.26059030560605834 48.71252847199275493 0, -86.26058913127698702 48.71243736119693324 0, -86.26052224406193147 48.71235735544751577 0, -86.26042819953713092 48.71229159978931733 0, -86.26028478492035845 48.71226125716471245 0, -86.26015310495121469 48.71223016026801389 0, -86.26001161835689857 48.71221473722845019 0, -86.25987046703276917 48.71221297774519599 0, -86.25974088327784273 48.71218032940910092 0, -86.25961314183051343 48.71214516844163001 0, -86.25947559566958489 48.71211553813063944 0, -86.25933075670586447 48.71210367767914562 0, -86.25919563914844446 48.71207346080208822 0, -86.25905851173556016 48.71205820585846169 0, -86.25893244753879685 48.71201793070455466 0, -86.25880998802401223 48.71197325518648569 0, -86.25869524038284908 48.71191868839306238 0, -86.25857210954411869 48.71187920988465692 0, -86.25843506593128041 48.71185201142647259 0, -86.2583275255056634 48.7117963967184906 0, -86.2582919860567614 48.71170796772283751 0, -86.25829852411867193 48.71161543116217985 0, -86.2582927488951583 48.71152382200396858 0) | R343 | AN | D | Temp | WF7 | D022 | 0.3 | 10 | 20 | Pic River RD - ML - WF7 - BR2 | Pic River RD - ML - WF7 |  | Nawiinginokiima Forest Management Corp. |  | WF7 | D022 | AN | 0 | Pic River RD - ML - WF7 - BR2 | 0.3 | 0.3 | All-season | 0.15709 | 0.14291
Figure 1: All-season access is shown in Red

## All Season Access - Credits
The following table shows the credit associated with the winter road built. As Valard constructed 42 km of all-season roads under WF6/7, these roads don’t require the 3rd season of winter construction.
Credit Items | Qty* | UoM | Contracted Unit Rate | Amount
Winter Credit - WF6 | 32.4717 | km | -15444 | -501493.6023
Winter Credit - WF7 | 9.726 | km | -12040 | -117100.578
Total Credits |  |  |  | -618594.1804
*see "All-season Road Built" tab

## All Season Access - LEM Backup
Company | ID | ROWSegment | TicketID | TimeTicket | CostCode | Category | NightShift | Activity | Rate | ActivityUnits | UnitofMeasure | StandByRate | StandByUnit | OvertimeRate | OvertimeUnit | SubTotal | GST | Total | TicketDate | Paid | InvoiceNumber | InvoiceDate | Invoice ID | Error | ExtraWork | AddedBy | Task | AssociatedTask | Contract_Number | PO_Number | WorkOrder | Notes | ChangeManagementID | Status | DESCRIPTION OF CHANGE | CHANGE ORDER NUMBER | Description | WF | Specific IDs | LocationsWorked | CM_Boolean | SubmittedToValard | ChangeManagementType | ApprovedBy | ApprovedDate | ThirdPartyTicket | ThirdPartyNote | Crossing # | Road Type | Crossing Type | ApproverFullName | Workfront | ID-1 | ID-2 | Item - 1 | Item - 2 | Net
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Subsistence Per Day61350 | Northern Mat & Bridge995421658Subsistence Per Day61350ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator8931.6 | Northern Mat & Bridge995421658Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81058.64 | Northern Mat & Bridge995421658Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81058.64 | Northern Mat & Bridge995421658Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81185.68 | Northern Mat & Bridge995421658Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81058.64 | Northern Mat & Bridge995421658Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Supervisor81456.92 | Northern Mat & Bridge995421658Supervisor81456.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 20 | HR |  | 0 |  |  | 3750 | 487.5 | 4237.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Flatbed Truck203750 | Northern Mat & Bridge995421658Flatbed Truck203750ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 11 | HR |  | 0 |  |  | 2190.54 | 284.7702 | 2475.3102 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Float Truck112190.54 | Northern Mat & Bridge995421658Float Truck112190.54ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 19 | HR |  | 0 |  |  | 3278.64 | 426.2232 | 3704.8632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Track Carrier193278.64 | Northern Mat & Bridge995421658Track Carrier193278.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 8 | HR |  | 0 |  |  | 790.64 | 102.7832 | 893.4232 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Loader8790.64 | Northern Mat & Bridge995421658Loader8790.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | HR |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Loader10988.3 | Northern Mat & Bridge995421658Loader10988.3ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 9 | HR |  | 0 |  |  | 1150.29 | 149.5377 | 1299.8277 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Excavator91150.29 | Northern Mat & Bridge995421658Excavator91150.29ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Crew Truck2450 | Northern Mat & Bridge995421658Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Subsistence Per Day61350 | Northern Mat & Bridge994921657Subsistence Per Day61350ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator81185.68 | Northern Mat & Bridge994921657Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator8677.52 | Northern Mat & Bridge994921657Operator8677.52ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator8677.52 | Northern Mat & Bridge994921657Operator8677.52ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator81185.68 | Northern Mat & Bridge994921657Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator8931.6 | Northern Mat & Bridge994921657Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Supervisor81456.92 | Northern Mat & Bridge994921657Supervisor81456.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 8.5 | HR |  | 0 |  |  | 1593.75 | 207.1875 | 1800.9375 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Flatbed Truck8.51593.75 | Northern Mat & Bridge994921657Flatbed Truck8.51593.75ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 13 | HR |  | 0 |  |  | 2588.82 | 336.5466 | 2925.3666 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Float Truck132588.82 | Northern Mat & Bridge994921657Float Truck132588.82ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 8 | HR |  | 0 |  |  | 790.64 | 102.7832 | 893.4232 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Loader8790.64 | Northern Mat & Bridge994921657Loader8790.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 2 | HR |  | 0 |  |  | 197.66 | 25.6958 | 223.3558 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Loader2197.66 | Northern Mat & Bridge994921657Loader2197.66ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 1 | HR |  | 0 |  |  | 127.81 | 16.6153 | 144.4253 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Excavator1127.81 | Northern Mat & Bridge994921657Excavator1127.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Crew Truck2450 | Northern Mat & Bridge994921657Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Subsistence Per Day61350 | Northern Mat & Bridge988921655Subsistence Per Day61350ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 3 | 1198.92 | 155.8596 | 1354.7796 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Supervisor81198.92 | Northern Mat & Bridge988921655Supervisor81198.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 9 | HR |  | 0 |  |  | 1553.04 | 201.8952 | 1754.9352 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Track Carrier91553.04 | Northern Mat & Bridge988921655Track Carrier91553.04ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 9 | HR |  | 0 |  |  | 1553.04 | 201.8952 | 1754.9352 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Track Carrier91553.04 | Northern Mat & Bridge988921655Track Carrier91553.04ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | HR |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Loader4395.32 | Northern Mat & Bridge988921655Loader4395.32ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 9 | HR |  | 0 |  |  | 889.47 | 115.6311 | 1005.1011 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Loader9889.47 | Northern Mat & Bridge988921655Loader9889.47ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 9 | HR |  | 0 |  |  | 1150.29 | 149.5377 | 1299.8277 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Excavator91150.29 | Northern Mat & Bridge988921655Excavator91150.29ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Crew Truck3675 | Northern Mat & Bridge988921655Crew Truck3675ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 7 | DAY |  |  |  | 0 | 1575 | 204.75 | 1779.75 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Subsistence Per Day71575 | Northern Mat & Bridge988821654Subsistence Per Day71575ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 214 | km |  |  |  | 0 | 175.48 | 22.8124 | 198.2924 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Travel per KM214175.48 | Northern Mat & Bridge988821654Travel per KM214175.48ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 4 | 677.68 | 88.0984 | 765.7784 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays0677.68 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays0677.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays | [5 empty] | 169.42 | 2.5 | 423.55 | 55.0615 | 478.6115 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays423.55 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays423.55ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Supervisor - Sunday/Stat Holidays |  | 0 |  |  |  | 156.9 | 11 | 1725.9 | 224.367 | 1950.267 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Supervisor - Sunday/Stat Holidays01725.9 | Northern Mat & Bridge988821654Supervisor - Sunday/Stat Holidays01725.9ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 8 | HR |  | 0 |  |  | 1380.48 | 179.4624 | 1559.9424 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Track Carrier81380.48 | Northern Mat & Bridge988821654Track Carrier81380.48ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 7 | HR |  | 0 |  |  | 1207.92 | 157.0296 | 1364.9496 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Track Carrier71207.92 | Northern Mat & Bridge988821654Track Carrier71207.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 2 | HR |  | 0 |  |  | 197.66 | 25.6958 | 223.3558 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Loader2197.66 | Northern Mat & Bridge988821654Loader2197.66ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 9 | HR |  | 0 |  |  | 889.47 | 115.6311 | 1005.1011 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Loader9889.47 | Northern Mat & Bridge988821654Loader9889.47ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Excavator7894.67 | Northern Mat & Bridge988821654Excavator7894.67ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Crew Truck3675 | Northern Mat & Bridge988821654Crew Truck3675ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 8 | DAY |  |  |  | 0 | 1800 | 234 | 2034 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Subsistence Per Day81800 | Northern Mat & Bridge983821653Subsistence Per Day81800ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 1472 | km |  |  |  | 0 | 1207.04 | 156.9152 | 1363.9552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Travel per KM14721207.04 | Northern Mat & Bridge983821653Travel per KM14721207.04ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 2 | HR |  |  | 127.04 | 6 | 931.62 | 121.1106 | 1052.7306 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator2931.62 | Northern Mat & Bridge983821653Operator2931.62ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 11 | 1397.44 | 181.6672 | 1579.1072 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01397.44 | Northern Mat & Bridge983821653Operator01397.44ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 10 | 1270.4 | 165.152 | 1435.552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01270.4 | Northern Mat & Bridge983821653Operator01270.4ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 5.5 | 698.72 | 90.8336 | 789.5536 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator0698.72 | Northern Mat & Bridge983821653Operator0698.72ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 10 | 1270.4 | 165.152 | 1435.552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01270.4 | Northern Mat & Bridge983821653Operator01270.4ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 10 | 1270.4 | 165.152 | 1435.552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01270.4 | Northern Mat & Bridge983821653Operator01270.4ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 0 | HR |  |  | 129 | 12 | 1548 | 201.24 | 1749.24 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Supervisor01548 | Northern Mat & Bridge983821653Supervisor01548ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 3 | HR |  | 0 |  |  | 597.42 | 77.6646 | 675.0846 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Float Truck3597.42 | Northern Mat & Bridge983821653Float Truck3597.42ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 32 | HR |  | 0 |  |  | 6372.48 | 828.4224 | 7200.9024 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Float Truck326372.48 | Northern Mat & Bridge983821653Float Truck326372.48ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 2 | HR |  | 0 |  |  | 345.12 | 44.8656 | 389.9856 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Track Carrier2345.12 | Northern Mat & Bridge983821653Track Carrier2345.12ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 7 | HR |  | 0 |  |  | 1207.92 | 157.0296 | 1364.9496 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Track Carrier71207.92 | Northern Mat & Bridge983821653Track Carrier71207.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | HR |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Loader4395.32 | Northern Mat & Bridge983821653Loader4395.32ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | HR |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Loader10988.3 | Northern Mat & Bridge983821653Loader10988.3ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 7 | HR |  | 0 |  |  | 691.81 | 89.9353 | 781.7453 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Loader7691.81 | Northern Mat & Bridge983821653Loader7691.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Excavator7894.67 | Northern Mat & Bridge983821653Excavator7894.67ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Crew Truck3675 | Northern Mat & Bridge983821653Crew Truck3675ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | DAY |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Subsistence Per Day51125 | Northern Mat & Bridge983621651Subsistence Per Day51125ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 3 | HR |  |  | 127.04 | 0 | 254.07 | 33.0291 | 287.0991 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator3254.07 | Northern Mat & Bridge983621651Operator3254.07ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator8677.52 | Northern Mat & Bridge983621651Operator8677.52ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator81185.68 | Northern Mat & Bridge983621651Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator81185.68 | Northern Mat & Bridge983621651Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator81185.68 | Northern Mat & Bridge983621651Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Supervisor81456.92 | Northern Mat & Bridge983621651Supervisor81456.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 3 | HR |  | 0 |  |  | 597.42 | 77.6646 | 675.0846 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Float Truck3597.42 | Northern Mat & Bridge983621651Float Truck3597.42ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | HR |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Track Carrier101725.6 | Northern Mat & Bridge983621651Track Carrier101725.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 3 | HR |  | 0 |  |  | 296.49 | 38.5437 | 335.0337 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Loader3296.49 | Northern Mat & Bridge983621651Loader3296.49ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 7 | HR |  | 0 |  |  | 691.81 | 89.9353 | 781.7453 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Loader7691.81 | Northern Mat & Bridge983621651Loader7691.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | HR |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Loader10988.3 | Northern Mat & Bridge983621651Loader10988.3ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 10 | HR |  | 0 |  |  | 1278.1 | 166.153 | 1444.253 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Excavator101278.1 | Northern Mat & Bridge983621651Excavator101278.1ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Crew Truck2450 | Northern Mat & Bridge983621651Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | DAY |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Subsistence Per Day51125 | Northern Mat & Bridge983521650Subsistence Per Day51125ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 475 | km |  |  |  | 0 | 389.5 | 50.635 | 440.135 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Travel per KM475389.5 | Northern Mat & Bridge983521650Travel per KM475389.5ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator81249.2 | Northern Mat & Bridge983521650Operator81249.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 1 | 804.56 | 104.5928 | 909.1528 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator8804.56 | Northern Mat & Bridge983521650Operator8804.56ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator81058.64 | Northern Mat & Bridge983521650Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator81058.64 | Northern Mat & Bridge983521650Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5.5 | 1521.42 | 197.7846 | 1719.2046 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Supervisor81521.42 | Northern Mat & Bridge983521650Supervisor81521.42ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 28.7235 | HR |  | 0 |  |  | 5719.9978 | 743.5997 | 6463.5975 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Float Truck28.72355719.9978 | Northern Mat & Bridge983521650Float Truck28.72355719.9978ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 28.7235 | HR |  | 0 |  |  | 5719.9978 | 743.5997 | 6463.5975 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Float Truck28.72355719.9978 | Northern Mat & Bridge983521650Float Truck28.72355719.9978ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | HR |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Loader111087.13 | Northern Mat & Bridge983521650Loader111087.13ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 7 | HR |  | 0 |  |  | 691.81 | 89.9353 | 781.7453 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Loader7691.81 | Northern Mat & Bridge983521650Loader7691.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Excavator7894.67 | Northern Mat & Bridge983521650Excavator7894.67ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Crew Truck2450 | Northern Mat & Bridge983521650Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 7 | DAY |  |  |  | 0 | 1575 | 204.75 | 1779.75 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Subsistence Per Day71575 | Northern Mat & Bridge983421649Subsistence Per Day71575ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 2518 | km |  |  |  | 0 | 2064.76 | 268.4188 | 2333.1788 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Travel per KM25182064.76 | Northern Mat & Bridge983421649Travel per KM25182064.76ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 8 | HR |  |  |  | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Operator - Travel8677.52 | Northern Mat & Bridge983421649Operator - Travel8677.52ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 16 | HR |  |  |  | 0 | 1355.04 | 176.1552 | 1531.1952 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Operator - Travel161355.04 | Northern Mat & Bridge983421649Operator - Travel161355.04ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 10.5 | HR |  |  | 129 | 0 | 1065.645 | 138.5339 | 1204.1788 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Supervisor10.51065.645 | Northern Mat & Bridge983421649Supervisor10.51065.645ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | HR |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Loader4395.32 | Northern Mat & Bridge983421649Loader4395.32ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Crew Truck3675 | Northern Mat & Bridge983421649Crew Truck3675ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 2 | DAY |  |  |  | 0 | 450 | 58.5 | 508.5 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Subsistence Per Day2450 | Northern Mat & Bridge995721661Subsistence Per Day2450ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 504 | km |  |  |  | 0 | 413.28 | 53.7264 | 467.0064 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Travel per KM504413.28 | Northern Mat & Bridge995721661Travel per KM504413.28ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 6 | HR |  |  | 129 | 0 | 608.94 | 79.1622 | 688.1022 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Supervisor6608.94 | Northern Mat & Bridge995721661Supervisor6608.94ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 28.7235 | HR |  | 0 |  |  | 5720 | 743.6 | 6463.6 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Float Truck28.7235115720 | Northern Mat & Bridge995721661Float Truck28.7235115720ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 1 | DAY |  | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Crew Truck1225 | Northern Mat & Bridge995721661Crew Truck1225ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Subsistence Per Day61350 | Northern Mat & Bridge995621660Subsistence Per Day61350ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 4464 | km |  |  |  | 0 | 3660.48 | 475.8624 | 4136.3424 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Travel per KM44643660.48 | Northern Mat & Bridge995621660Travel per KM44643660.48ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 11.5 | HR |  |  |  | 0 | 973.935 | 126.6115 | 1100.5465 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Operator - Travel11.5973.935 | Northern Mat & Bridge995621660Operator - Travel11.5973.935ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 12 | HR |  |  | 129 | 0 | 1217.88 | 158.3244 | 1376.2044 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Supervisor121217.88 | Northern Mat & Bridge995621660Supervisor121217.88ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 24.8569 | HR |  | 0 |  |  | 4949.9991 | 643.4999 | 5593.499 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Float Truck24.856884949.9991 | Northern Mat & Bridge995621660Float Truck24.856884949.9991ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 24.8569 | HR |  | 0 |  |  | 4949.9991 | 643.4999 | 5593.499 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Float Truck24.856884949.9991 | Northern Mat & Bridge995621660Float Truck24.856884949.9991ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Crew Truck2450 | Northern Mat & Bridge995621660Crew Truck2450ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Subsistence Per Day61350 | Northern Mat & Bridge995521659Subsistence Per Day61350ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8677.52 | Northern Mat & Bridge995521659Operator8677.52ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8677.52 | Northern Mat & Bridge995521659Operator8677.52ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8677.52 | Northern Mat & Bridge995521659Operator8677.52ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8931.6 | Northern Mat & Bridge995521659Operator8931.6ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8931.6 | Northern Mat & Bridge995521659Operator8931.6ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 3 | 1198.92 | 155.8596 | 1354.7796 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Supervisor81198.92 | Northern Mat & Bridge995521659Supervisor81198.92ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 10 | HR |  | 0 |  |  | 1875 | 243.75 | 2118.75 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Flatbed Truck101875 | Northern Mat & Bridge995521659Flatbed Truck101875ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 21 | HR |  | 0 |  |  | 4181.94 | 543.6522 | 4725.5922 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Float Truck214181.94 | Northern Mat & Bridge995521659Float Truck214181.94ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 13 | HR |  | 0 |  |  | 2243.28 | 291.6264 | 2534.9064 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Track Carrier132243.28 | Northern Mat & Bridge995521659Track Carrier132243.28ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 13 | HR |  | 0 |  |  | 1284.79 | 167.0227 | 1451.8127 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Loader131284.79 | Northern Mat & Bridge995521659Loader131284.79ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Excavator7894.67 | Northern Mat & Bridge995521659Excavator7894.67ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Crew Truck2450 | Northern Mat & Bridge995521659Crew Truck2450ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975620210828-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 132 | HR |  |  | 75 | 0 | 9900 | 1287 | 11187 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Operator - Principle - After Jan 101329900 | Corbiere and Sons Contracting975620210828-3Operator - Principle - After Jan 101329900INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3L.O.A.142940 | Corbiere and Sons Contracting975620210828-3L.O.A.142940INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Foreman121140 | Corbiere and Sons Contracting975620210828-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 107966.35INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975620210828-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 106881.76INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975520210827-3-R1Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting975520210827-3-R1Driver - AZ - After Jan 1012840INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975520210827-3-R1Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | L.O.A. | 210 | 17 | DAY |  |  |  | 0 | 3570 | 464.1 | 4034.1 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1L.O.A.173570 | Corbiere and Sons Contracting975520210827-3-R1L.O.A.173570INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting975520210827-3-R1Tractor Trailer - 60 Ton- After Jan 10121468.68INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Marooka- After Jan 105723 | Corbiere and Sons Contracting975520210827-3-R1Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975420210826-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975420210826-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3L.O.A.153150 | Corbiere and Sons Contracting975420210826-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Foreman121140 | Corbiere and Sons Contracting975420210826-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975420210826-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8.5 | HR | 47.54 | 0 |  |  | 538.73 | 70.0349 | 608.7649 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 108.51249.16INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975320210825-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting975320210825-3Driver - AZ - After Jan 1011.5805INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975320210825-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3L.O.A.163360 | Corbiere and Sons Contracting975320210825-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Foreman121140 | Corbiere and Sons Contracting975320210825-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11.5 | Dynamic | 91.79 | 0 |  |  | 1407.485 | 182.9731 | 1590.458 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Tractor Trailer - 60 Ton- After Jan 1011.51407.485 | Corbiere and Sons Contracting975320210825-3Tractor Trailer - 60 Ton- After Jan 1011.51407.485INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975320210825-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1081107.6INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting975220210824-4Operator - Principle - After Jan 1011825INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4L.O.A.1210 | Corbiere and Sons Contracting975220210824-4L.O.A.1210INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975220210824-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975220210824-4Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975120210824-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1011825INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3L.O.A.163360 | Corbiere and Sons Contracting975120210824-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Foreman121140 | Corbiere and Sons Contracting975120210824-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975120210824-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 107443.66INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 102293.92INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 105692.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 107969.15INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting975120210824-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting974020210823-4Operator - Principle - After Jan 1011825INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4L.O.A.1210 | Corbiere and Sons Contracting974020210823-4L.O.A.1210INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting974020210823-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting974020210823-4Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting973320210823-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting973320210823-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3L.O.A.153150 | Corbiere and Sons Contracting973320210823-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Foreman121140 | Corbiere and Sons Contracting973320210823-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Marooka- After Jan 105723 | Corbiere and Sons Contracting973320210823-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 105692.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting973320210823-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting973220210822-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 121 | HR |  |  | 75 | 0 | 9075 | 1179.75 | 10254.75 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Operator - Principle - After Jan 101219075 | Corbiere and Sons Contracting973220210822-3Operator - Principle - After Jan 101219075INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3L.O.A.132730 | Corbiere and Sons Contracting973220210822-3L.O.A.132730INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Foreman121140 | Corbiere and Sons Contracting973220210822-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Marooka- After Jan 105723 | Corbiere and Sons Contracting973220210822-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting973220210822-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting973220210822-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972720210821-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 121 | HR |  |  | 0 | 0 | 9075 | 1179.75 | 10254.75 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Operator - Principle - After Jan 101219075 | Corbiere and Sons Contracting972720210821-3Operator - Principle - After Jan 101219075INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  | 0 | 0 | 2730 | 354.9 | 3084.9 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3L.O.A.132730 | Corbiere and Sons Contracting972720210821-3L.O.A.132730INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Foreman121140 | Corbiere and Sons Contracting972720210821-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972720210821-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972720210821-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972620210820-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 139 | HR |  |  | 0 | 0 | 10425 | 1355.25 | 11780.25 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Operator - Principle - After Jan 1013910425 | Corbiere and Sons Contracting972620210820-3Operator - Principle - After Jan 1013910425INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3L.O.A.153150 | Corbiere and Sons Contracting972620210820-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Foreman121140 | Corbiere and Sons Contracting972620210820-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 10162208.8INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972620210820-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 108507.04INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972620210820-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972520210819-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 149 | HR |  |  | 0 | 0 | 11175 | 1452.75 | 12627.75 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Operator - Principle - After Jan 1014911175 | Corbiere and Sons Contracting972520210819-3Operator - Principle - After Jan 1014911175INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3L.O.A.163360 | Corbiere and Sons Contracting972520210819-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Foreman121140 | Corbiere and Sons Contracting972520210819-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 105690.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 0 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972520210819-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 0 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972520210819-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 16 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Labourer - General - After Jan 1016960 | Corbiere and Sons Contracting972420210818-3Labourer - General - After Jan 1016960INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting972420210818-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3L.O.A.163360 | Corbiere and Sons Contracting972420210818-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Foreman121140 | Corbiere and Sons Contracting972420210818-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 0 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972420210818-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 0 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972420210818-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972320210817-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting972320210817-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3L.O.A.153150 | Corbiere and Sons Contracting972320210817-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Foreman121140 | Corbiere and Sons Contracting972320210817-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 0 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972320210817-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972320210817-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972220210816-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting972220210816-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3L.O.A.163360 | Corbiere and Sons Contracting972220210816-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Foreman242280 | Corbiere and Sons Contracting972220210816-3Foreman242280INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972220210816-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972220210816-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting983020210909-5Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5L.O.A.1210 | Corbiere and Sons Contracting983020210909-5L.O.A.1210INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting983020210909-5Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting983020210909-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting983020210909-5Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting981220210908-5Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting981220210908-5Driver - AZ - After Jan 10191330INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting981220210908-5Operator - Principle - After Jan 105375INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5L.O.A.3630 | Corbiere and Sons Contracting981220210908-5L.O.A.3630INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 108979.12INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 10111346.29INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting981220210908-5Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting982120210907-5Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting982120210907-5Driver - AZ - After Jan 1010700INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting982120210907-5Operator - Principle - After Jan 1011825INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5L.O.A.4840 | Corbiere and Sons Contracting982120210907-5L.O.A.4840INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Foreman121140 | Corbiere and Sons Contracting982120210907-5Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting982120210907-5Tractor Trailer - 60 Ton- After Jan 10101223.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting982120210907-5Light Truck - Pick up- After Jan 102487.5INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting982120210907-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting982120210907-5Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting981920210906-4Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting981920210906-4Driver - AZ - After Jan 1010700INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 0 | 0 | 1875 | 243.75 | 2118.75 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10251875INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 0 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10332475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  | 0 | 0 | 2310 | 300.3 | 2610.3 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4L.O.A.112310 | Corbiere and Sons Contracting981920210906-4L.O.A.112310INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Foreman121140 | Corbiere and Sons Contracting981920210906-4Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting981920210906-4Tractor Trailer - 60 Ton- After Jan 10101223.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Marooka- After Jan 105723 | Corbiere and Sons Contracting981920210906-4Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 0 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting981920210906-4Light Truck - Pick up- After Jan 103731.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting981920210906-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting981920210906-4Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting981820210905-4Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10251875INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10332475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4L.O.A.102100 | Corbiere and Sons Contracting981820210905-4L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Foreman121140 | Corbiere and Sons Contracting981820210905-4Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Marooka- After Jan 105723 | Corbiere and Sons Contracting981820210905-4Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting981820210905-4Light Truck - Pick up- After Jan 103731.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting981820210905-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting981820210905-4Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting979420210904-3Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10251875INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10332475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3L.O.A.102100 | Corbiere and Sons Contracting979420210904-3L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Foreman121140 | Corbiere and Sons Contracting979420210904-3Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 20 | Dynamic | 103.54 | 0 |  |  | 2761 | 358.93 | 3119.93 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 10202761 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 10202761INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Marooka- After Jan 105723 | Corbiere and Sons Contracting979420210904-3Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting979420210904-3Light Truck - Pick up- After Jan 1061462.5INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979420210904-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979420210904-3Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting979320210903-5Labourer - General - After Jan 1010600INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 80 | HR |  |  | 75 | 0 | 6000 | 780 | 6780 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Operator - Principle - After Jan 10806000 | Corbiere and Sons Contracting979320210903-5Operator - Principle - After Jan 10806000INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5L.O.A.102100 | Corbiere and Sons Contracting979320210903-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Foreman111045 | Corbiere and Sons Contracting979320210903-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 10162208.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979320210903-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979320210903-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting979320210903-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting979320210903-5Excavator - 30 ton- After Jan 1081107.6INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 99 | HR |  |  | 75 | 0 | 7425 | 965.25 | 8390.25 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Operator - Principle - After Jan 10997425 | Corbiere and Sons Contracting979220210902-5Operator - Principle - After Jan 10997425INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5L.O.A.102100 | Corbiere and Sons Contracting979220210902-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Foreman111045 | Corbiere and Sons Contracting979220210902-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979220210902-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979220210902-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 106380.28INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 103440.88INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 106830.7INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 99 | HR |  |  | 75 | 0 | 7425 | 965.25 | 8390.25 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Operator - Principle - After Jan 10997425 | Corbiere and Sons Contracting979120210901-5Operator - Principle - After Jan 10997425INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5L.O.A.102100 | Corbiere and Sons Contracting979120210901-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Foreman111045 | Corbiere and Sons Contracting979120210901-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979120210901-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979120210901-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979120210901-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979120210901-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 110 | HR |  |  | 75 | 0 | 8250 | 1072.5 | 9322.5 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Operator - Principle - After Jan 101108250 | Corbiere and Sons Contracting979020210831-5Operator - Principle - After Jan 101108250INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5L.O.A.112310 | Corbiere and Sons Contracting979020210831-5L.O.A.112310INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Foreman111045 | Corbiere and Sons Contracting979020210831-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979020210831-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979020210831-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting978920210830-6Operator - Principle - After Jan 1011825INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6L.O.A.1210 | Corbiere and Sons Contracting978920210830-6L.O.A.1210INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting978920210830-6Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting978920210830-6Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10201500INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10554125INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5L.O.A.102100 | Corbiere and Sons Contracting978820210830-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Foreman121140 | Corbiere and Sons Contracting978820210830-5Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Marooka- After Jan 105723 | Corbiere and Sons Contracting978820210830-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 1051218.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9774 | 20210829-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | RT hauling from KM17 on Henson Road | 6 | F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977420210829-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting977420210829-5Operator - Principle - After Jan 1011825INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9774 | 20210829-5 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | RT hauling from KM17 on Henson Road | 6 | F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977420210829-5L.O.A.1210 | Corbiere and Sons Contracting977420210829-5L.O.A.1210INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9774 | 20210829-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | RT hauling from KM17 on Henson Road | 6 | F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977420210829-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting977420210829-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Labourer - General - After Jan 105300 | Corbiere and Sons Contracting977320210829-4Labourer - General - After Jan 105300INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting977320210829-4Driver - AZ - After Jan 1012840INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting977320210829-4Operator - Principle - After Jan 10554125INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4L.O.A.142940 | Corbiere and Sons Contracting977320210829-4L.O.A.142940INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Foreman5475 | Corbiere and Sons Contracting977320210829-4Foreman5475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Marooka- After Jan 105723 | Corbiere and Sons Contracting977320210829-4Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 1061462.5INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting985720210916-7Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting985720210916-7Driver - AZ - After Jan 103210INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting985720210916-7Operator - Principle - After Jan 10443300INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7L.O.A.71470 | Corbiere and Sons Contracting985720210916-7L.O.A.71470INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Foreman121140 | Corbiere and Sons Contracting985720210916-7Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting985720210916-7Tractor Trailer - 60 Ton- After Jan 103367.17INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting985720210916-7Rock Truck - 30 Ton- After Jan 10101380.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting985720210916-7Light Truck - Pick up- After Jan 103731.25INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10 | HR | 47.54 | 0 |  |  | 633.8 | 82.394 | 716.194 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator Hammer - 30 - 50 ton- After Jan 1010633.8 | Corbiere and Sons Contracting985720210916-7Excavator Hammer - 30 - 50 ton- After Jan 1010633.8INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10101469.6INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10111616.56INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting985720210916-7Excavator - 30 ton- After Jan 107969.15INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting985520210916-5Operator - Principle - After Jan 10483600INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5L.O.A.4840 | Corbiere and Sons Contracting985520210916-5L.O.A.4840INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting985520210916-5Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting985520210916-5Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting985520210916-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting985520210916-5Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting986420210916-14Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting986420210916-14Operator - Principle - After Jan 10604500INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14L.O.A.81680 | Corbiere and Sons Contracting986420210916-14L.O.A.81680INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Foreman121140 | Corbiere and Sons Contracting986420210916-14Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting986420210916-14Light Truck - Pick up- After Jan 104975INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting986420210916-14Excavator - 36 ton- After Jan 10111616.56INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting986420210916-14Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting986420210916-14Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting986320210916-13Operator - Principle - After Jan 10362700INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13L.O.A.3630 | Corbiere and Sons Contracting986320210916-13L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986320210916-13Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting986320210916-13Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting986320210916-13Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting986320210916-13Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting986220210916-12Operator - Principle - After Jan 10241800INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12L.O.A.2420 | Corbiere and Sons Contracting986220210916-12L.O.A.2420INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986220210916-12Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting986220210916-12Light Truck - Pick up- After Jan 101243.75INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986220210916-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting986220210916-12Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting986120210916-11Operator - Principle - After Jan 10241800INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11L.O.A.3630 | Corbiere and Sons Contracting986120210916-11L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Foreman121140 | Corbiere and Sons Contracting986120210916-11Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting986120210916-11Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986120210916-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting986120210916-11Excavator - 36 ton- After Jan 10223233.12INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting986020210916-10Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting986020210916-10Operator - Principle - After Jan 10241800INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10L.O.A.3630 | Corbiere and Sons Contracting986020210916-10L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting986020210916-10Rock Truck - 30 Ton- After Jan 10223037.1INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting986020210916-10Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986020210916-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting986020210916-10Excavator - 36 ton- After Jan 10111616.56INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting985020210915-9Labourer - General - After Jan 10221320INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting985020210915-9Operator - Principle - After Jan 10443300INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9L.O.A.71470 | Corbiere and Sons Contracting985020210915-9L.O.A.71470INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Foreman121140 | Corbiere and Sons Contracting985020210915-9Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 1081104.4INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 106828.3INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting985020210915-9Light Truck - Pick up- After Jan 104975INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting985020210915-9Excavator - 36 ton- After Jan 10101469.6INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting985020210915-9Excavator - 30 ton- After Jan 10101384.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting984920210915-8Operator - Principle - After Jan 10332475INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8L.O.A.3630 | Corbiere and Sons Contracting984920210915-8L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting984920210915-8Rock Truck - 30 Ton- After Jan 10101380.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984920210915-8Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting984920210915-8Excavator - 30 ton- After Jan 10101384.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting984920210915-8Dozer D6 or equal- After Jan 10101314.8INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7L.O.A.2420 | Corbiere and Sons Contracting984820210915-7L.O.A.2420INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting984820210915-7Rock Truck - 30 Ton- After Jan 106828.3INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting984820210915-7Light Truck - Pick up- After Jan 101243.75INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting984820210915-7Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting984820210915-7Excavator - 30 ton- After Jan 106830.7INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6L.O.A.51050 | Corbiere and Sons Contracting984720210915-6L.O.A.51050INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Foreman121140 | Corbiere and Sons Contracting984720210915-6Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting984720210915-6Rock Truck - 30 Ton- After Jan 106828.3INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984720210915-6Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting984720210915-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting984720210915-6Excavator - 36 ton- After Jan 1010.51543.08INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 105300 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 105300INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 105375INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4L.O.A.71470 | Corbiere and Sons Contracting984520210915-4L.O.A.71470INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Foreman4380 | Corbiere and Sons Contracting984520210915-4Foreman4380INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting984520210915-4Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting984520210915-4Light Truck - Pick up- After Jan 103731.25INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984520210915-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting984520210915-4Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting984520210915-4Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9859 | 20210916-9 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivering rig mats to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985920210916-9Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting985920210916-9Driver - AZ - After Jan 108560INV #148 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9859 | 20210916-9 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivering rig mats to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985920210916-9L.O.A.1210 | Corbiere and Sons Contracting985920210916-9L.O.A.1210INV #148 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9859 | 20210916-9 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivering rig mats to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985920210916-9Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting985920210916-9Tractor Trailer - 60 Ton- After Jan 108979.12INV #148 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 42.5 | HR |  |  | 70 | 0 | 2975 | 386.75 | 3361.75 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 1042.52975 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 1042.52975INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 10694830 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 10694830INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4L.O.A.112310 | Corbiere and Sons Contracting985420210916-4L.O.A.112310INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Construction Coordinator7560 | Corbiere and Sons Contracting985420210916-4Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting985420210916-4Light Truck - Pick up- After Jan 101243.75INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 42.5 | Dynamic | 41.4 | 0 |  |  | 2346 | 304.98 | 2650.98 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 1042.52346 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 1042.52346INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69 | Dynamic | 41.4 | 0 |  |  | 3808.8 | 495.144 | 4303.944 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 10693808.8 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 10693808.8INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56 | HR |  |  | 70 | 0 | 3920 | 509.6 | 4429.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 10563920 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 10563920INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 68.5 | HR |  |  | 70 | 0 | 4795 | 623.35 | 5418.35 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 1068.54795 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 1068.54795INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984420210915-3Operator - Principle - After Jan 1012900INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3L.O.A.122520 | Corbiere and Sons Contracting984420210915-3L.O.A.122520INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Foreman4380 | Corbiere and Sons Contracting984420210915-3Foreman4380INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Construction Coordinator7560 | Corbiere and Sons Contracting984420210915-3Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984420210915-3Light Truck - Pick up- After Jan 102487.5INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56 | Dynamic | 41.4 | 0 |  |  | 3091.2 | 401.856 | 3493.056 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 10563091.2 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 10563091.2INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69.5 | Dynamic | 41.4 | 0 |  |  | 3836.4 | 498.732 | 4335.132 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 1069.53836.4 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 1069.53836.4INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984420210915-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting984420210915-3Excavator - 36 ton- After Jan 10111616.56INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69.5 | HR |  |  | 70 | 0 | 4865 | 632.45 | 5497.45 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Driver - AZ - After Jan 1069.54865 | Corbiere and Sons Contracting984120210914-4Driver - AZ - After Jan 1069.54865INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984120210914-4Operator - Principle - After Jan 1012900INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4L.O.A.71470 | Corbiere and Sons Contracting984120210914-4L.O.A.71470INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Construction Coordinator7560 | Corbiere and Sons Contracting984120210914-4Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984120210914-4Light Truck - Pick up- After Jan 102487.5INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69.5 | Dynamic | 41.4 | 0 |  |  | 3836.4 | 498.732 | 4335.132 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Dump - Triaxle- After Jan 1069.53836.4 | Corbiere and Sons Contracting984120210914-4Dump - Triaxle- After Jan 1069.53836.4INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984120210914-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting984120210914-4Excavator - 36 ton- After Jan 10111616.56INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 141 | HR |  |  | 70 | 0 | 9870 | 1283.1 | 11153.1 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Driver - AZ - After Jan 101419870 | Corbiere and Sons Contracting984020210913-5Driver - AZ - After Jan 101419870INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984020210913-5Operator - Principle - After Jan 1012900INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5L.O.A.142940 | Corbiere and Sons Contracting984020210913-5L.O.A.142940INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Construction Coordinator7560 | Corbiere and Sons Contracting984020210913-5Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984020210913-5Light Truck - Pick up- After Jan 102487.5INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 141 | Dynamic | 41.4 | 0 |  |  | 7783.2 | 1011.816 | 8795.016 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Dump - Triaxle- After Jan 101417783.2 | Corbiere and Sons Contracting984020210913-5Dump - Triaxle- After Jan 101417783.2INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984020210913-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting984020210913-5Excavator - 36 ton- After Jan 10111616.56INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting1007420210927-8Labourer - General - After Jan 108480INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1007420210927-8Operator - Principle - After Jan 10322400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8L.O.A.4840 | Corbiere and Sons Contracting1007420210927-8L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1007420210927-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1007420210927-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1007420210927-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1007320210927-7Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 10221540INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 103210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 76 | HR |  |  | 75 | 0 | 5700 | 741 | 6441 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Operator - Principle - After Jan 10765700 | Corbiere and Sons Contracting1007320210927-7Operator - Principle - After Jan 10765700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7L.O.A.91890 | Corbiere and Sons Contracting1007320210927-7L.O.A.91890INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Foreman121140 | Corbiere and Sons Contracting1007320210927-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 25 | Dynamic | 91.79 | 0 |  |  | 3059.75 | 397.7675 | 3457.5175 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Tractor Trailer - 60 Ton- After Jan 10253059.75 | Corbiere and Sons Contracting1007320210927-7Tractor Trailer - 60 Ton- After Jan 10253059.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 103.54 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting1007320210927-7Rock Truck - 30 Ton- After Jan 10364969.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1007320210927-7Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1007320210927-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1007320210927-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1007320210927-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1007320210927-7Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1007220210927-6Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6L.O.A.3630 | Corbiere and Sons Contracting1007220210927-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1007220210927-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1007220210927-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1007220210927-6Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1007220210927-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1007220210927-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 56 | HR |  |  | 75 | 0 | 4200 | 546 | 4746 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Operator - Principle - After Jan 10564200 | Corbiere and Sons Contracting1008320210927-17Operator - Principle - After Jan 10564200INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Foreman121140 | Corbiere and Sons Contracting1008320210927-17Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1008320210927-17Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1008320210927-17Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1008320210927-17Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1008220210927-16Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16L.O.A.3630 | Corbiere and Sons Contracting1008220210927-16L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1008220210927-16Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1008220210927-16Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008220210927-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008220210927-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1008220210927-16Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting1008120210927-15Operator - Principle - After Jan 10151125INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15L.O.A.1210 | Corbiere and Sons Contracting1008120210927-15L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1008120210927-15Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1008120210927-15Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 101146.96INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting1008020210927-14Driver - AZ - After Jan 1010700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting1008020210927-14Operator - Principle - After Jan 10201500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14L.O.A.2420 | Corbiere and Sons Contracting1008020210927-14L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting1008020210927-14Tractor Trailer - 60 Ton- After Jan 10101223.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 2.5 | Dynamic | 103.54 | 0 |  |  | 345.125 | 44.8663 | 389.9912 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Rock Truck - 30 Ton- After Jan 102.5345.125 | Corbiere and Sons Contracting1008020210927-14Rock Truck - 30 Ton- After Jan 102.5345.125INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008020210927-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008020210927-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2.5 | Dynamic | 98.61 | 0 |  |  | 328.7 | 42.731 | 371.431 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Dozer D6 or equal- After Jan 102.5328.7 | Corbiere and Sons Contracting1008020210927-14Dozer D6 or equal- After Jan 102.5328.7INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1007820210927-12Operator - Principle - After Jan 10322400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12L.O.A.51050 | Corbiere and Sons Contracting1007820210927-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Foreman121140 | Corbiere and Sons Contracting1007820210927-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting1007820210927-12Rock Truck - 30 Ton- After Jan 10162208.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1007820210927-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1007820210927-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1007820210927-12Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1007820210927-12Dozer D6 or equal- After Jan 1081051.84INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Labourer - General - After Jan 108480 | Corbiere and Sons Contracting1007620210927-10Labourer - General - After Jan 108480INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 56 | HR |  |  | 75 | 0 | 4200 | 546 | 4746 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Operator - Principle - After Jan 10564200 | Corbiere and Sons Contracting1007620210927-10Operator - Principle - After Jan 10564200INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10L.O.A.71470 | Corbiere and Sons Contracting1007620210927-10L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Foreman121140 | Corbiere and Sons Contracting1007620210927-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1007620210927-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1007620210927-10Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1007620210927-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1007620210927-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1007620210927-10Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1007620210927-10Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1007620210927-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1005720210926-9Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9L.O.A.61260 | Corbiere and Sons Contracting1005720210926-9L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Foreman121140 | Corbiere and Sons Contracting1005720210926-9Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1005720210926-9Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1005720210926-9Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1005720210926-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1005720210926-9Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1005720210926-9Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005720210926-9Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005720210926-9Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1005620210926-8Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1005620210926-8Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8L.O.A.51050 | Corbiere and Sons Contracting1005620210926-8L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1005620210926-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1005620210926-8Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005620210926-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1005620210926-8Dozer D6 or equal- After Jan 1091183.32INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1005520210926-7Operator - Principle - After Jan 10725400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7L.O.A.71470 | Corbiere and Sons Contracting1005520210926-7L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Foreman121140 | Corbiere and Sons Contracting1005520210926-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 33 | Dynamic | 103.54 | 0 |  |  | 4555.65 | 592.2345 | 5147.8845 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Rock Truck - 30 Ton- After Jan 10334555.65 | Corbiere and Sons Contracting1005520210926-7Rock Truck - 30 Ton- After Jan 10334555.65INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1005520210926-7Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1005520210926-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1005520210926-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005520210926-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005520210926-7Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1005420210926-6Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6L.O.A.3630 | Corbiere and Sons Contracting1005420210926-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1005420210926-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005420210926-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1005420210926-6Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005420210926-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005420210926-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting1006020210926-12Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1006020210926-12Driver - AZ - After Jan 1012840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1006020210926-12Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12L.O.A.61260 | Corbiere and Sons Contracting1006020210926-12L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1006020210926-12Tractor Trailer - 60 Ton- After Jan 10121468.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1006020210926-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1006020210926-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1006020210926-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1006020210926-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1006020210926-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1005920210926-11Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11L.O.A.1210 | Corbiere and Sons Contracting1005920210926-11L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1005920210926-11Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1005920210926-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1005820210926-10Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10L.O.A.51050 | Corbiere and Sons Contracting1005820210926-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Foreman121140 | Corbiere and Sons Contracting1005820210926-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1005820210926-10Rock Truck - 30 Ton- After Jan 10182484.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1005820210926-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1005820210926-10Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1005820210926-10Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005820210926-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1002420210924-8Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8L.O.A.3630 | Corbiere and Sons Contracting1002420210924-8L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1002420210924-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1002420210924-8Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1002420210924-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1002420210924-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1002320210924-7Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7L.O.A.61260 | Corbiere and Sons Contracting1002320210924-7L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Foreman121140 | Corbiere and Sons Contracting1002320210924-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 25 | Dynamic | 103.54 | 0 |  |  | 3451.25 | 448.6625 | 3899.9125 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Rock Truck - 30 Ton- After Jan 10253451.25 | Corbiere and Sons Contracting1002320210924-7Rock Truck - 30 Ton- After Jan 10253451.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1002320210924-7Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1002320210924-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1002320210924-7Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1002320210924-7Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1002320210924-7Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1002220210924-6Labourer - General - After Jan 1011660INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1002220210924-6Driver - AZ - After Jan 105350INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1002220210924-6Operator - Principle - After Jan 10392925INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6L.O.A.61260 | Corbiere and Sons Contracting1002220210924-6L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1002220210924-6Tractor Trailer - 60 Ton- After Jan 105611.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1002220210924-6Rock Truck - 30 Ton- After Jan 104552.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting1002220210924-6Light Truck w/ Tandum Trailer- After Jan 101337.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1002220210924-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1002220210924-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1002220210924-6Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1002220210924-6Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1002220210924-6Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1013910INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46.5 | HR |  |  | 70 | 0 | 3255 | 423.15 | 3678.15 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1046.53255 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1046.53255INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5L.O.A.4840 | Corbiere and Sons Contracting1002120210924-5L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 1013717.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 10462539.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10020 | 20210924-4 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23.5 | HR |  |  | 70 | 0 | 1645 | 213.85 | 1858.85 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda hauling over to Pic River West | 6 | D018-D024 | Pic River | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002020210924-4Driver - AZ - After Jan 1023.51645 | Corbiere and Sons Contracting1002020210924-4Driver - AZ - After Jan 1023.51645INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10020 | 20210924-4 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda hauling over to Pic River West | 6 | D018-D024 | Pic River | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002020210924-4L.O.A.2420 | Corbiere and Sons Contracting1002020210924-4L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10020 | 20210924-4 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23.5 | Dynamic | 41.4 | 0 |  |  | 1297.2 | 168.636 | 1465.836 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda hauling over to Pic River West | 6 | D018-D024 | Pic River | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002020210924-4Dump - Triaxle- After Jan 1023.51297.2 | Corbiere and Sons Contracting1002020210924-4Dump - Triaxle- After Jan 1023.51297.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 71 | HR |  |  | 70 | 0 | 4970 | 646.1 | 5616.1 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Driver - AZ - After Jan 10714970 | Corbiere and Sons Contracting1001920210924-3Driver - AZ - After Jan 10714970INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3L.O.A.71470 | Corbiere and Sons Contracting1001920210924-3L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Construction Coordinator7560 | Corbiere and Sons Contracting1001920210924-3Construction Coordinator7560INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1001920210924-3Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 71 | Dynamic | 41.4 | 0 |  |  | 3919.2 | 509.496 | 4428.696 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Dump - Triaxle- After Jan 10713919.2 | Corbiere and Sons Contracting1001920210924-3Dump - Triaxle- After Jan 10713919.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10032 | 20210924-16 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  | 0 | 0 | 105 | 13.65 | 118.65 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1003220210924-16L.O.A.0.5105 | Corbiere and Sons Contracting1003220210924-16L.O.A.0.5105INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10032 | 20210924-16 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 0 | 0 | 595 | 77.35 | 672.35 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1003220210924-16Safety Advisor7595 | Corbiere and Sons Contracting1003220210924-16Safety Advisor7595INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10032 | 20210924-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1003220210924-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1003220210924-16Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 0 | 0 | 4500 | 585 | 5085 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1003120210924-15Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Foreman121140 | Corbiere and Sons Contracting1003120210924-15Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 0 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1003120210924-15Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 0 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1003120210924-15Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 0 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 0 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 0 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 0 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1003120210924-15Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1003020210924-14Driver - AZ - After Jan 106420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1003020210924-14Operator - Principle - After Jan 1010750INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14L.O.A.1210 | Corbiere and Sons Contracting1003020210924-14L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1003020210924-14Tractor Trailer - 60 Ton- After Jan 106734.34INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1003020210924-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1003020210924-14Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1002920210924-13Operator - Principle - After Jan 10322400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13L.O.A.3630 | Corbiere and Sons Contracting1002920210924-13L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1002920210924-13Rock Truck - 30 Ton- After Jan 1081104.4INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1002920210924-13Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1002920210924-13Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1002920210924-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 50 | HR |  |  | 75 | 0 | 3750 | 487.5 | 4237.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Operator - Principle - After Jan 10503750 | Corbiere and Sons Contracting1002820210924-12Operator - Principle - After Jan 10503750INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12L.O.A.51050 | Corbiere and Sons Contracting1002820210924-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Foreman121140 | Corbiere and Sons Contracting1002820210924-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1002820210924-12Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1002820210924-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12.5 | HR | 9.16 | 0 |  |  | 152.625 | 19.8413 | 172.4662 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Excavator Thumb - 30 - 50 ton- After Jan 1012.5152.625 | Corbiere and Sons Contracting1002820210924-12Excavator Thumb - 30 - 50 ton- After Jan 1012.5152.625INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12.5 | Dynamic | 110.22 | 0 |  |  | 1837 | 238.81 | 2075.81 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Excavator - 36 ton- After Jan 1012.51837 | Corbiere and Sons Contracting1002820210924-12Excavator - 36 ton- After Jan 1012.51837INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1002820210924-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1002720210924-11Operator - Principle - After Jan 1010750INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11L.O.A.1210 | Corbiere and Sons Contracting1002720210924-11L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1002720210924-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1002720210924-11Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1002620210924-10Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10L.O.A.51050 | Corbiere and Sons Contracting1002620210924-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Foreman121140 | Corbiere and Sons Contracting1002620210924-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1002620210924-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1002620210924-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1002620210924-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1002620210924-10Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1002620210924-10Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1001020210923-9Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9L.O.A.4840 | Corbiere and Sons Contracting1001020210923-9L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1001020210923-9Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001020210923-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 22 | Dynamic | 103.84 | 0 |  |  | 3045.9 | 395.967 | 3441.867 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Excavator - 30 ton- After Jan 10223045.9 | Corbiere and Sons Contracting1001020210923-9Excavator - 30 ton- After Jan 10223045.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1001020210923-9Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1000920210923-8Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8L.O.A.61260 | Corbiere and Sons Contracting1000920210923-8L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Foreman121140 | Corbiere and Sons Contracting1000920210923-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1000920210923-8Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1000920210923-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000920210923-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1000920210923-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1000920210923-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1000820210923-7-R1Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1000820210923-7-R1Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1L.O.A.51050 | Corbiere and Sons Contracting1000820210923-7-R1L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1000820210923-7-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1000820210923-7-R1Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000820210923-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1000820210923-7-R1Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10018 | 20210923-15 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1001820210923-15L.O.A.0.5105 | Corbiere and Sons Contracting1001820210923-15L.O.A.0.5105INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10018 | 20210923-15 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1001820210923-15Safety Advisor7595 | Corbiere and Sons Contracting1001820210923-15Safety Advisor7595INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10018 | 20210923-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1001820210923-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1001820210923-15Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1001720210923-14Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Foreman121140 | Corbiere and Sons Contracting1001720210923-14Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1001720210923-14Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1001720210923-14Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1001720210923-14Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting1001620210923-13Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1001620210923-13Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13L.O.A.61260 | Corbiere and Sons Contracting1001620210923-13L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1001620210923-13Rock Truck - 30 Ton- After Jan 10101380.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1001620210923-13Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001620210923-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1001620210923-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1001520210923-12Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12L.O.A.4840 | Corbiere and Sons Contracting1001520210923-12L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Foreman121140 | Corbiere and Sons Contracting1001520210923-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1001520210923-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1001520210923-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001520210923-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001520210923-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1001520210923-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1001420210923-11Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11L.O.A.2420 | Corbiere and Sons Contracting1001420210923-11L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1001420210923-11Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001420210923-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001420210923-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1001120210923-10Driver - AZ - After Jan 1012840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1001120210923-10Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10L.O.A.71470 | Corbiere and Sons Contracting1001120210923-10L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Foreman121140 | Corbiere and Sons Contracting1001120210923-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1001120210923-10Tractor Trailer - 60 Ton- After Jan 10121468.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1001120210923-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1001120210923-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1001120210923-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1001120210923-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1001120210923-10Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting1001120210923-10Dozer D6 or equal- After Jan 107.5986.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 1011770INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 106420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting999720210922-9-R1Operator - Principle - After Jan 10141050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1L.O.A.3630 | Corbiere and Sons Contracting999720210922-9-R1L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 17 | Dynamic | 91.79 | 0 |  |  | 2080.63 | 270.4819 | 2351.1119 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Tractor Trailer - 60 Ton- After Jan 10172080.63 | Corbiere and Sons Contracting999720210922-9-R1Tractor Trailer - 60 Ton- After Jan 10172080.63INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 2 | Dynamic | 103.54 | 0 |  |  | 276.1 | 35.893 | 311.993 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Rock Truck - 30 Ton- After Jan 102276.1 | Corbiere and Sons Contracting999720210922-9-R1Rock Truck - 30 Ton- After Jan 102276.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting999720210922-9-R1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting999720210922-9-R1Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting999620210922-8Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting999620210922-8Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8L.O.A.61260 | Corbiere and Sons Contracting999620210922-8L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Foreman121140 | Corbiere and Sons Contracting999620210922-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting999620210922-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting999620210922-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting999620210922-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting999620210922-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting999620210922-8Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999620210922-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting999520210922-7Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7L.O.A.4840 | Corbiere and Sons Contracting999520210922-7L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting999520210922-7Rock Truck - 30 Ton- After Jan 106828.3INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting999520210922-7Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999520210922-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting999520210922-7Dozer D6 or equal- After Jan 105657.4INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting999420210922-6Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6L.O.A.61260 | Corbiere and Sons Contracting999420210922-6L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Foreman121140 | Corbiere and Sons Contracting999420210922-6Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting999420210922-6Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting999420210922-6Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999420210922-6Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999420210922-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999420210922-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5L.O.A.61260 | Corbiere and Sons Contracting999320210922-5L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting999320210922-5Rock Truck - 30 Ton- After Jan 10192622.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting999320210922-5Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 106881.76INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999320210922-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999320210922-5Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10002 | 20210922-14 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed time for billable ATV | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000220210922-14ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1000220210922-14ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1000020210922-12-R1Operator - Principle - After Jan 10554125INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Foreman121140 | Corbiere and Sons Contracting1000020210922-12-R1Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1000020210922-12-R1Rock Truck - 30 Ton- After Jan 10182484.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1000020210922-12-R1Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting999920210922-11Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting999920210922-11Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11L.O.A.61260 | Corbiere and Sons Contracting999920210922-11L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting999920210922-11Rock Truck - 30 Ton- After Jan 10101380.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting999920210922-11Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999920210922-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999920210922-11Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting999820210922-10Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10L.O.A.4840 | Corbiere and Sons Contracting999820210922-10L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Foreman121140 | Corbiere and Sons Contracting999820210922-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting999820210922-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting999820210922-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999820210922-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999820210922-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999820210922-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9L.O.A.61260 | Corbiere and Sons Contracting997620210921-9L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Foreman121140 | Corbiere and Sons Contracting997620210921-9Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting997620210921-9Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting997620210921-9Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997620210921-9Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting997620210921-9Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting997620210921-9Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 108600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8L.O.A.51050 | Corbiere and Sons Contracting997520210921-8L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting997520210921-8Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting997520210921-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997520210921-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting997520210921-8Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting997520210921-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 40 | HR |  |  | 75 | 0 | 3000 | 390 | 3390 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Operator - Principle - After Jan 10403000 | Corbiere and Sons Contracting998220210921-15Operator - Principle - After Jan 10403000INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Foreman9855 | Corbiere and Sons Contracting998220210921-15Foreman9855INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting998220210921-15Rock Truck - 30 Ton- After Jan 107966.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting998220210921-15Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting998220210921-15Excavator - 30 ton- After Jan 1081107.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting998220210921-15Dozer D6 or equal- After Jan 102262.96INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9981 | 20210921-14 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998120210921-14ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting998120210921-14ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting998020210921-13-R1Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1L.O.A.3630 | Corbiere and Sons Contracting998020210921-13-R1L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting998020210921-13-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting998020210921-13-R1Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting998020210921-13-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting998020210921-13-R1Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting997920210921-12Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12L.O.A.51050 | Corbiere and Sons Contracting997920210921-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Foreman121140 | Corbiere and Sons Contracting997920210921-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997920210921-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting997920210921-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting997920210921-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting997820210921-11Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting997820210921-11Driver - AZ - After Jan 1012840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting997820210921-11Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11L.O.A.71470 | Corbiere and Sons Contracting997820210921-11L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Foreman121140 | Corbiere and Sons Contracting997820210921-11Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting997820210921-11Tractor Trailer - 60 Ton- After Jan 10121468.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997820210921-11Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting997820210921-11Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting997820210921-11ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting997820210921-11Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting997820210921-11Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1011.5862.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10L.O.A.4840 | Corbiere and Sons Contracting997720210921-10L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997720210921-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting997720210921-10Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997720210921-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7092 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 1010.51453.725INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting997720210921-10Dozer D6 or equal- After Jan 102262.96INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9939 | 20210920-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC605.01 | 6 | C186-C195 | Del lake | 0 | 2021-09-23 |  | 37 | 2021-09-25 |  |  | 605.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting993920210920-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting993920210920-8Operator - Principle - After Jan 104300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9939 | 20210920-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC605.01 | 6 | C186-C195 | Del lake | 0 | 2021-09-23 |  | 37 | 2021-09-25 |  |  | 605.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting993920210920-8Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting993920210920-8Excavator - 36 ton- After Jan 104587.84INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting993820210920-7Operator - Principle - After Jan 10443300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7L.O.A.51050 | Corbiere and Sons Contracting993820210920-7L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Foreman121140 | Corbiere and Sons Contracting993820210920-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting993820210920-7Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting993820210920-7Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting993820210920-7Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting993820210920-7Excavator - 30 ton- After Jan 106830.7INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting993820210920-7Dozer D6 or equal- After Jan 104525.92INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting993720210920-6Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6L.O.A.3630 | Corbiere and Sons Contracting993720210920-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting993720210920-6Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting993720210920-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993720210920-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9967 | 20210920-19 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996720210920-19ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996720210920-19ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9966 | 20210920-18 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage from Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996620210920-18ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996620210920-18ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting994820210920-17Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Foreman121140 | Corbiere and Sons Contracting994820210920-17Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting994820210920-17Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting994820210920-17Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994820210920-17Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting994820210920-17Dozer D6 or equal- After Jan 104525.92INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting994720210920-16Driver - AZ - After Jan 105350INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting994720210920-16Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16L.O.A.61260 | Corbiere and Sons Contracting994720210920-16L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Foreman121140 | Corbiere and Sons Contracting994720210920-16Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting994720210920-16Tractor Trailer - 60 Ton- After Jan 105611.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting994720210920-16Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting994720210920-16Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8.5 | HR | 9.16 | 0 |  |  | 103.785 | 13.4921 | 117.277 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting994720210920-16Excavator - 36 ton- After Jan 108.51249.16INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994720210920-16Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting994720210920-16Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting994520210920-14-R1Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1L.O.A.4840 | Corbiere and Sons Contracting994520210920-14-R1L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994520210920-14-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting994320210920-12Operator - Principle - After Jan 10302250INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12L.O.A.2420 | Corbiere and Sons Contracting994320210920-12L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting994320210920-12Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 105.5808.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting994320210920-12Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 42 | HR |  |  | 75 | 0 | 3150 | 409.5 | 3559.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Operator - Principle - After Jan 10423150 | Corbiere and Sons Contracting994120210920-10Operator - Principle - After Jan 10423150INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10L.O.A.51050 | Corbiere and Sons Contracting994120210920-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Foreman121140 | Corbiere and Sons Contracting994120210920-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting994120210920-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting994120210920-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 105.5808.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting994120210920-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting992820210919-9Driver - AZ - After Jan 104280INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting992820210919-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9L.O.A.1210 | Corbiere and Sons Contracting992820210919-9L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting992820210919-9Tractor Trailer - 60 Ton- After Jan 104489.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting992820210919-9Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting992820210919-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992820210919-9Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting992620210919-7Operator - Principle - After Jan 10443300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7L.O.A.51050 | Corbiere and Sons Contracting992620210919-7L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Foreman121140 | Corbiere and Sons Contracting992620210919-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting992620210919-7Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting992620210919-7Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting992620210919-7Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting992520210919-6Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting992520210919-6Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6L.O.A.81680 | Corbiere and Sons Contracting992520210919-6L.O.A.81680INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Foreman121140 | Corbiere and Sons Contracting992520210919-6Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting992520210919-6Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting992520210919-6Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting992520210919-6Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting992520210919-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting992520210919-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting992420210919-5Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5L.O.A.3630 | Corbiere and Sons Contracting992420210919-5L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting992420210919-5Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting992420210919-5Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting992420210919-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9965 | 20210919-16 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for ATV usage on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996520210919-16ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996520210919-16ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9964 | 20210919-15 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Del | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996420210919-15ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996420210919-15ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10161200INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 1011825INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Foreman8760 | Corbiere and Sons Contracting993220210919-13Foreman8760INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting993220210919-13Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting993220210919-13Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993220210919-13Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting993220210919-13Dozer D6 or equal- After Jan 1091183.32INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting993120210919-12Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12L.O.A.51050 | Corbiere and Sons Contracting993120210919-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting993120210919-12Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting993120210919-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting993120210919-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993120210919-12Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting993120210919-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting993020210919-11Driver - AZ - After Jan 107490INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting993020210919-11Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11L.O.A.71470 | Corbiere and Sons Contracting993020210919-11L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Foreman121140 | Corbiere and Sons Contracting993020210919-11Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting993020210919-11Tractor Trailer - 60 Ton- After Jan 107856.73INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10101380.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting993020210919-11Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting993020210919-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting993020210919-11Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting990920210918-8Labourer - General - After Jan 108480INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 46 | HR |  |  | 75 | 0 | 3450 | 448.5 | 3898.5 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Operator - Principle - After Jan 10463450 | Corbiere and Sons Contracting990920210918-8Operator - Principle - After Jan 10463450INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8L.O.A.51050 | Corbiere and Sons Contracting990920210918-8L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Foreman121140 | Corbiere and Sons Contracting990920210918-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting990920210918-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting990920210918-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting990920210918-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 105.5808.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting990920210918-8Excavator - 30 ton- After Jan 103415.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting990920210918-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 10191425INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6L.O.A.3630 | Corbiere and Sons Contracting990720210918-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting990720210918-6Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting990720210918-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting990720210918-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9962 | 20210918-22 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Hare Lake Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996220210918-22ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996220210918-22ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9961 | 20210918-21 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996120210918-21ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996120210918-21ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting991920210918-18Operator - Principle - After Jan 10523900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Foreman9855 | Corbiere and Sons Contracting991920210918-18Foreman9855INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting991920210918-18Rock Truck - 30 Ton- After Jan 1081104.4INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting991920210918-18Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting991920210918-18Excavator - 30 ton- After Jan 1081107.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting991920210918-18Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting991820210918-17Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting991820210918-17Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17L.O.A.71470 | Corbiere and Sons Contracting991820210918-17L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Foreman121140 | Corbiere and Sons Contracting991820210918-17Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting991820210918-17Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991820210918-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting991820210918-17Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting991820210918-17Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting991520210918-14Operator - Principle - After Jan 10282100INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14L.O.A.3630 | Corbiere and Sons Contracting991520210918-14L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991520210918-14Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting991520210918-14Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991520210918-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 103415.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting991420210918-13Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13L.O.A.3630 | Corbiere and Sons Contracting991420210918-13L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991420210918-13Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting991420210918-13Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991420210918-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting991420210918-13Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting991420210918-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting991320210918-12Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12L.O.A.1210 | Corbiere and Sons Contracting991320210918-12L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting991320210918-12Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991320210918-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991320210918-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting991120210918-10Operator - Principle - After Jan 10443300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10L.O.A.51050 | Corbiere and Sons Contracting991120210918-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Foreman121140 | Corbiere and Sons Contracting991120210918-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991120210918-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting991120210918-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting991120210918-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting987520210917-8Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 108600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8L.O.A.81680 | Corbiere and Sons Contracting987520210917-8L.O.A.81680INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Foreman121140 | Corbiere and Sons Contracting987520210917-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting987520210917-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting987520210917-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting987520210917-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting987520210917-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting987520210917-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 108600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5L.O.A.3630 | Corbiere and Sons Contracting987220210917-5L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting987220210917-5Rock Truck - 30 Ton- After Jan 105690.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting987220210917-5Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting987220210917-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9960 | 20210917-21 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for ATV used on site | 6 | C186-C195 | Del lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996020210917-21ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996020210917-21ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 10332475INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 102150INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Foreman5475 | Corbiere and Sons Contracting989720210917-16Foreman5475INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting989720210917-16Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting989720210917-16Excavator - 30 ton- After Jan 103415.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting988120210917-14Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting988120210917-14Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14L.O.A.81680 | Corbiere and Sons Contracting988120210917-14L.O.A.81680INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Foreman121140 | Corbiere and Sons Contracting988120210917-14Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting988120210917-14Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting988120210917-14Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 22 | HR | 9.16 | 0 |  |  | 268.62 | 34.9206 | 303.5406 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Excavator Thumb - 30 - 50 ton- After Jan 1022268.62 | Corbiere and Sons Contracting988120210917-14Excavator Thumb - 30 - 50 ton- After Jan 1022268.62INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting988120210917-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting988120210917-14Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting988120210917-14Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting988020210917-13Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13L.O.A.3630 | Corbiere and Sons Contracting988020210917-13L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting988020210917-13Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting988020210917-13Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting988020210917-13Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting988020210917-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting987920210917-12Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12L.O.A.2420 | Corbiere and Sons Contracting987920210917-12L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting987920210917-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting987920210917-12Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting987920210917-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting987920210917-12Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting987720210917-10Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting987720210917-10Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10L.O.A.4840 | Corbiere and Sons Contracting987720210917-10L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Foreman121140 | Corbiere and Sons Contracting987720210917-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting987720210917-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting987720210917-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting987720210917-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting987720210917-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting987720210917-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9959 | 20210916-20 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for ATV used in field | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting995920210916-20ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting995920210916-20ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 105375INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Foreman7665 | Corbiere and Sons Contracting989420210916-16Foreman7665INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting989420210916-16Rock Truck - 30 Ton- After Jan 105690.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting989420210916-16Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting989420210916-16Excavator - 30 ton- After Jan 101138.45INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting989420210916-16Dozer D6 or equal- After Jan 107920.36INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 35 | HR |  |  | 75 | 0 | 2625 | 341.25 | 2966.25 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Operator - Principle - After Jan 10352625 | Corbiere and Sons Contracting989020210915-11Operator - Principle - After Jan 10352625INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Foreman6570 | Corbiere and Sons Contracting989020210915-11Foreman6570INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting989020210915-11Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting989020210915-11Excavator - 30 ton- After Jan 102276.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting989020210915-11Dozer D6 or equal- After Jan 106788.88INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9940 | 20210920-9 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 4x20' rig mats to Del Lake East | 6 | C191-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994020210920-9Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting994020210920-9Driver - AZ - After Jan 106420INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9940 | 20210920-9 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 4x20' rig mats to Del Lake East | 6 | C191-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994020210920-9L.O.A.1210 | Corbiere and Sons Contracting994020210920-9L.O.A.1210INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9940 | 20210920-9 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 4x20' rig mats to Del Lake East | 6 | C191-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994020210920-9Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting994020210920-9Tractor Trailer - 60 Ton- After Jan 106734.34INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9917 | 20210918-16 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float delivered rig mats to Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991720210918-16Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting991720210918-16Driver - AZ - After Jan 104280INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9917 | 20210918-16 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float delivered rig mats to Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991720210918-16Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting991720210918-16Tractor Trailer - 60 Ton- After Jan 104489.56INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9912 | 20210918-11 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float dropped off 2 loads of mats and Op unloaded with Ex | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991220210918-11Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting991220210918-11Driver - AZ - After Jan 107490INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9912 | 20210918-11 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float dropped off 2 loads of mats and Op unloaded with Ex | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991220210918-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting991220210918-11Operator - Principle - After Jan 104300INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9912 | 20210918-11 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float dropped off 2 loads of mats and Op unloaded with Ex | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991220210918-11L.O.A.1210 | Corbiere and Sons Contracting991220210918-11L.O.A.1210INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9873 | 20210917-6 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing Rig Mats on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987320210917-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting987320210917-6Operator - Principle - After Jan 104300INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9873 | 20210917-6 | 53530601 | Rig/Access Mats | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing Rig Mats on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987320210917-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting987320210917-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9873 | 20210917-6 | 53530601 | Rig/Access Mats | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing Rig Mats on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987320210917-6Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting987320210917-6Excavator - 30 ton- After Jan 104553.8INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10064 | 20210916-22 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Move 4x20' rig mats and 2 swamps mats from Marathon Laydown to Dead Horse Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-10-05 |  | 36 | 2021-10-07 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006420210916-22Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1006420210916-22Driver - AZ - After Jan 103210INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10064 | 20210916-22 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Move 4x20' rig mats and 2 swamps mats from Marathon Laydown to Dead Horse Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-10-05 |  | 36 | 2021-10-07 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006420210916-22Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1006420210916-22Tractor Trailer - 60 Ton- After Jan 103367.17INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56 | HR |  |  | 70 | 0 | 3920 | 509.6 | 4429.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 10563920 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 10563920INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5L.O.A.4840 | Corbiere and Sons Contracting1007120210927-5L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56 | Dynamic | 41.4 | 0 |  |  | 3091.2 | 401.856 | 3493.056 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 10563091.2 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 10563091.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10070 | 20210927-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007020210927-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1007020210927-4Driver - AZ - After Jan 1034.52415INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10070 | 20210927-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007020210927-4L.O.A.3630 | Corbiere and Sons Contracting1007020210927-4L.O.A.3630INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10070 | 20210927-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007020210927-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1007020210927-4Dump - Triaxle- After Jan 1034.51904.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1006920210927-3Labourer - General - After Jan 1012720INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 92 | HR |  |  | 70 | 0 | 6440 | 837.2 | 7277.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 10926440 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 10926440INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3L.O.A.91890 | Corbiere and Sons Contracting1006920210927-3L.O.A.91890INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1006920210927-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 92 | Dynamic | 41.4 | 0 |  |  | 5078.4 | 660.192 | 5738.592 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 10925078.4 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 10925078.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10033 | 20210924-18 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel hauling ticket for Hurd Bros hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003320210924-18Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1003320210924-18Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10033 | 20210924-18 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel hauling ticket for Hurd Bros hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003320210924-18Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1003320210924-18Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10065 | 20210924-17-R1 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 50 | HR |  |  | 70 | 0 | 3500 | 455 | 3955 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Additional gravel hauling tickets for Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006520210924-17-R1Driver - AZ - After Jan 10503500 | Corbiere and Sons Contracting1006520210924-17-R1Driver - AZ - After Jan 10503500INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10065 | 20210924-17-R1 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Additional gravel hauling tickets for Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006520210924-17-R1L.O.A.4840 | Corbiere and Sons Contracting1006520210924-17-R1L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10065 | 20210924-17-R1 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 50 | Dynamic | 41.4 | 0 |  |  | 2760 | 358.8 | 3118.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Additional gravel hauling tickets for Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006520210924-17-R1Dump - Triaxle- After Jan 10502760 | Corbiere and Sons Contracting1006520210924-17-R1Dump - Triaxle- After Jan 10502760INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 27.5 | HR |  |  | 70 | 0 | 1925 | 250.25 | 2175.25 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1027.51925 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1027.51925INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6L.O.A.3630 | Corbiere and Sons Contracting1000720210923-6L.O.A.3630INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 24 | Dynamic | 41.4 | 0 |  |  | 1324.8 | 172.224 | 1497.024 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 10241324.8 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 10241324.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 27.5 | Dynamic | 41.4 | 0 |  |  | 1518 | 197.34 | 1715.34 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 1027.51518 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 1027.51518INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 1011.5805INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5L.O.A.51050 | Corbiere and Sons Contracting1000620210923-5L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 11.5 | Dynamic | 41.4 | 0 |  |  | 634.8 | 82.524 | 717.324 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 1011.5634.8 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 1011.5634.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 60.5 | HR |  |  | 70 | 0 | 4235 | 550.55 | 4785.55 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Driver - AZ - After Jan 1060.54235 | Corbiere and Sons Contracting1000420210923-3Driver - AZ - After Jan 1060.54235INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3L.O.A.61260 | Corbiere and Sons Contracting1000420210923-3L.O.A.61260INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Construction Coordinator7560 | Corbiere and Sons Contracting1000420210923-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1000420210923-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 60.5 | Dynamic | 41.4 | 0 |  |  | 3339.6 | 434.148 | 3773.748 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Dump - Triaxle- After Jan 1060.53339.6 | Corbiere and Sons Contracting1000420210923-3Dump - Triaxle- After Jan 1060.53339.6INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 48 | HR |  |  | 70 | 0 | 3360 | 436.8 | 3796.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 10483360 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 10483360INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1013910INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4L.O.A.4840 | Corbiere and Sons Contracting999220210922-4L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 48 | Dynamic | 41.4 | 0 |  |  | 2649.6 | 344.448 | 2994.048 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 10482649.6 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 10482649.6INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1013717.6INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 139 | HR |  |  | 70 | 0 | 9730 | 1264.9 | 10994.9 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Driver - AZ - After Jan 101399730 | Corbiere and Sons Contracting999120210922-3Driver - AZ - After Jan 101399730INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3L.O.A.132730 | Corbiere and Sons Contracting999120210922-3L.O.A.132730INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Construction Coordinator7560 | Corbiere and Sons Contracting999120210922-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting999120210922-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 139 | Dynamic | 41.4 | 0 |  |  | 7672.8 | 997.464 | 8670.264 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Dump - Triaxle- After Jan 101397672.8 | Corbiere and Sons Contracting999120210922-3Dump - Triaxle- After Jan 101397672.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9972 | 20210921-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997220210921-5Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting997220210921-5Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9972 | 20210921-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997220210921-5L.O.A.4840 | Corbiere and Sons Contracting997220210921-5L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9972 | 20210921-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997220210921-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting997220210921-5Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4L.O.A.4840 | Corbiere and Sons Contracting997120210921-4L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 24 | Dynamic | 41.4 | 0 |  |  | 1324.8 | 172.224 | 1497.024 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10241324.8 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10241324.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Driver - AZ - After Jan 10694830 | Corbiere and Sons Contracting997020210921-3Driver - AZ - After Jan 10694830INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3L.O.A.71470 | Corbiere and Sons Contracting997020210921-3L.O.A.71470INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Construction Coordinator7560 | Corbiere and Sons Contracting997020210921-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting997020210921-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69 | Dynamic | 41.4 | 0 |  |  | 3808.8 | 495.144 | 4303.944 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Dump - Triaxle- After Jan 10693808.8 | Corbiere and Sons Contracting997020210921-3Dump - Triaxle- After Jan 10693808.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9936 | 20210920-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 57.5 | HR |  |  | 70 | 0 | 4025 | 523.25 | 4548.25 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993620210920-5Driver - AZ - After Jan 1057.54025 | Corbiere and Sons Contracting993620210920-5Driver - AZ - After Jan 1057.54025INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9936 | 20210920-5 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993620210920-5L.O.A.51050 | Corbiere and Sons Contracting993620210920-5L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9936 | 20210920-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 57.5 | Dynamic | 41.4 | 0 |  |  | 3174 | 412.62 | 3586.62 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993620210920-5Dump - Triaxle- After Jan 1057.53174 | Corbiere and Sons Contracting993620210920-5Dump - Triaxle- After Jan 1057.53174INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting993420210920-3Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3L.O.A.51050 | Corbiere and Sons Contracting993420210920-3L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Construction Coordinator7560 | Corbiere and Sons Contracting993420210920-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting993420210920-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting993420210920-3Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9923 | 20210919-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 49.5 | HR |  |  | 70 | 0 | 3465 | 450.45 | 3915.45 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5Padda Tri-axles hauling from Cress pit to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992320210919-4Driver - AZ - After Jan 1049.53465 | Corbiere and Sons Contracting992320210919-4Driver - AZ - After Jan 1049.53465INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9923 | 20210919-4 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5Padda Tri-axles hauling from Cress pit to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992320210919-4L.O.A.51050 | Corbiere and Sons Contracting992320210919-4L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9923 | 20210919-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 49.5 | Dynamic | 41.4 | 0 |  |  | 2732.4 | 355.212 | 3087.612 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5Padda Tri-axles hauling from Cress pit to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992320210919-4Dump - Triaxle- After Jan 1049.52732.4 | Corbiere and Sons Contracting992320210919-4Dump - Triaxle- After Jan 1049.52732.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 85 | HR |  |  | 70 | 0 | 5950 | 773.5 | 6723.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | hare lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Driver - AZ - After Jan 10855950 | Corbiere and Sons Contracting992220210919-3Driver - AZ - After Jan 10855950INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | hare lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3L.O.A.91890 | Corbiere and Sons Contracting992220210919-3L.O.A.91890INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | hare lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Construction Coordinator7560 | Corbiere and Sons Contracting992220210919-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | hare lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting992220210919-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 85 | Dynamic | 41.4 | 0 |  |  | 4692 | 609.96 | 5301.96 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | hare lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Dump - Triaxle- After Jan 10854692 | Corbiere and Sons Contracting992220210919-3Dump - Triaxle- After Jan 10854692INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9906 | 20210918-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Tri-axles hauling from Cress pit to Neys Road | 6 | C219-C236 | Neys Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990620210918-5Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting990620210918-5Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9906 | 20210918-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Tri-axles hauling from Cress pit to Neys Road | 6 | C219-C236 | Neys Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990620210918-5L.O.A.4840 | Corbiere and Sons Contracting990620210918-5L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9906 | 20210918-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Tri-axles hauling from Cress pit to Neys Road | 6 | C219-C236 | Neys Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990620210918-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting990620210918-5Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9905 | 20210918-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990520210918-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting990520210918-4Driver - AZ - After Jan 1034.52415INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9905 | 20210918-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990520210918-4L.O.A.3630 | Corbiere and Sons Contracting990520210918-4L.O.A.3630INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9905 | 20210918-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990520210918-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting990520210918-4Dump - Triaxle- After Jan 1034.51904.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 57.5 | HR |  |  | 70 | 0 | 4025 | 523.25 | 4548.25 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Driver - AZ - After Jan 1057.54025 | Corbiere and Sons Contracting990420210918-3Driver - AZ - After Jan 1057.54025INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3L.O.A.61260 | Corbiere and Sons Contracting990420210918-3L.O.A.61260INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Construction Coordinator7560 | Corbiere and Sons Contracting990420210918-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting990420210918-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 57.5 | Dynamic | 41.4 | 0 |  |  | 3174 | 412.62 | 3586.62 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Dump - Triaxle- After Jan 1057.53174 | Corbiere and Sons Contracting990420210918-3Dump - Triaxle- After Jan 1057.53174INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012.5875 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012.5875INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12.5 | Dynamic | 41.4 | 0 |  |  | 690 | 89.7 | 779.7 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012.5690 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012.5690INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 52 | HR |  |  | 70 | 0 | 3640 | 473.2 | 4113.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 10523640 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 10523640INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4L.O.A.4840 | Corbiere and Sons Contracting987120210917-4L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 52 | Dynamic | 41.4 | 0 |  |  | 2870.4 | 373.152 | 3243.552 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 10522870.4 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 10522870.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 157.5 | HR |  |  | 70 | 0 | 11025 | 1433.25 | 12458.25 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Driver - AZ - After Jan 10157.511025 | Corbiere and Sons Contracting987020210917-3Driver - AZ - After Jan 10157.511025INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3L.O.A.153150 | Corbiere and Sons Contracting987020210917-3L.O.A.153150INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Construction Coordinator7560 | Corbiere and Sons Contracting987020210917-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting987020210917-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 157.5 | Dynamic | 41.4 | 0 |  |  | 8694 | 1130.22 | 9824.22 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Dump - Triaxle- After Jan 10157.58694 | Corbiere and Sons Contracting987020210917-3Dump - Triaxle- After Jan 10157.58694INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9901 | 20210917-20 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East access | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990120210917-20Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting990120210917-20Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9901 | 20210917-20 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East access | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990120210917-20Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting990120210917-20Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting989820210917-17Operator - Principle - After Jan 1010750INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting989820210917-17Rock Truck - 30 Ton- After Jan 105690.25INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting989820210917-17Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting989820210917-17Excavator - 30 ton- After Jan 105692.25INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting989820210917-17Dozer D6 or equal- After Jan 105657.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting989520210916-17Operator - Principle - After Jan 10161200INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Foreman2190 | Corbiere and Sons Contracting989520210916-17Foreman2190INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting989520210916-17Rock Truck - 30 Ton- After Jan 105690.25INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting989520210916-17Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting989520210916-17Excavator - 30 ton- After Jan 10101384.5INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting989520210916-17Dozer D6 or equal- After Jan 102262.96INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 1 | HR |  |  | 60 | 0 | 60 | 7.8 | 67.8 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Labourer - General - After Jan 10160 | Corbiere and Sons Contracting989120210915-12Labourer - General - After Jan 10160INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting989120210915-12Operator - Principle - After Jan 108600INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Foreman2190 | Corbiere and Sons Contracting989120210915-12Foreman2190INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting989120210915-12Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting989120210915-12Excavator - 30 ton- After Jan 107969.15INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting989120210915-12Dozer D6 or equal- After Jan 103394.44INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1018620211004-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 91 | HR |  |  | 75 | 0 | 6825 | 887.25 | 7712.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Operator - Principle - After Jan 10916825 | Corbiere and Sons Contracting1018620211004-9Operator - Principle - After Jan 10916825INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9L.O.A.91890 | Corbiere and Sons Contracting1018620211004-9L.O.A.91890INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Foreman131235 | Corbiere and Sons Contracting1018620211004-9Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1018620211004-9Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1018620211004-9Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1018620211004-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1018620211004-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 9.16 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting1018620211004-9Excavator Thumb - 30 - 50 ton- After Jan 1036439.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting1018620211004-9Excavator - 36 ton- After Jan 10487054.08INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1018620211004-9Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 65 | HR |  |  | 75 | 0 | 4875 | 633.75 | 5508.75 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Operator - Principle - After Jan 10654875 | Corbiere and Sons Contracting1018420211004-7Operator - Principle - After Jan 10654875INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7L.O.A.51050 | Corbiere and Sons Contracting1018420211004-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 103.54 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting1018420211004-7Rock Truck - 30 Ton- After Jan 10364969.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1018420211004-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1018420211004-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1018420211004-7Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1018420211004-7Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 21 | HR |  |  | 60 | 0 | 1260 | 163.8 | 1423.8 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Labourer - General - After Jan 10211260 | Corbiere and Sons Contracting1018320211004-6Labourer - General - After Jan 10211260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 70 | HR |  |  | 75 | 0 | 5250 | 682.5 | 5932.5 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Operator - Principle - After Jan 10705250 | Corbiere and Sons Contracting1018320211004-6Operator - Principle - After Jan 10705250INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6L.O.A.81680 | Corbiere and Sons Contracting1018320211004-6L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Foreman131235 | Corbiere and Sons Contracting1018320211004-6Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1018320211004-6Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1018320211004-6Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1018320211004-6ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1018320211004-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 17 | HR | 9.16 | 0 |  |  | 207.57 | 26.9841 | 234.5541 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator Thumb - 30 - 50 ton- After Jan 1017207.57 | Corbiere and Sons Contracting1018320211004-6Excavator Thumb - 30 - 50 ton- After Jan 1017207.57INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1018320211004-6Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1018320211004-6Excavator - 30 ton- After Jan 105692.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1018320211004-6Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1019120211004-14Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1019120211004-14Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1019120211004-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1019120211004-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting1019020211004-13Operator - Principle - After Jan 10201500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Foreman6570 | Corbiere and Sons Contracting1019020211004-13Foreman6570INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 1 | Dynamic | 103.54 | 0 |  |  | 138.05 | 17.9465 | 155.9965 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Rock Truck - 30 Ton- After Jan 101138.05 | Corbiere and Sons Contracting1019020211004-13Rock Truck - 30 Ton- After Jan 101138.05INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1019020211004-13Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 101146.96INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9918 | 860.4667 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting1019020211004-13Excavator - 30 ton- After Jan 105.5761.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1019020211004-13Dozer D6 or equal- After Jan 107920.36INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1018820211004-11Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting1018820211004-11Operator - Principle - After Jan 10523900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11L.O.A.61260 | Corbiere and Sons Contracting1018820211004-11L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Foreman131235 | Corbiere and Sons Contracting1018820211004-11Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1018820211004-11Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1018820211004-11Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1018820211004-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1018820211004-11Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 35 | HR |  |  | 75 | 0 | 2625 | 341.25 | 2966.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Operator - Principle - After Jan 10352625 | Corbiere and Sons Contracting1018720211004-10Operator - Principle - After Jan 10352625INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10L.O.A.3630 | Corbiere and Sons Contracting1018720211004-10L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1018720211004-10Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1018720211004-10Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1018720211004-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1018720211004-10Excavator - 36 ton- After Jan 1081175.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1018720211004-10Dozer D6 or equal- After Jan 1081051.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1017320211003-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 104 | HR |  |  | 75 | 0 | 7800 | 1014 | 8814 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Operator - Principle - After Jan 101047800 | Corbiere and Sons Contracting1017320211003-9Operator - Principle - After Jan 101047800INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9L.O.A.102100 | Corbiere and Sons Contracting1017320211003-9L.O.A.102100INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Foreman131235 | Corbiere and Sons Contracting1017320211003-9Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017320211003-9Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1017320211003-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1017320211003-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017320211003-9Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017320211003-9Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1017220211003-8Operator - Principle - After Jan 1013975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8L.O.A.1210 | Corbiere and Sons Contracting1017220211003-8L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1017220211003-8Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017220211003-8Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 59 | HR |  |  | 75 | 0 | 4425 | 575.25 | 5000.25 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Operator - Principle - After Jan 10594425 | Corbiere and Sons Contracting1017120211003-7Operator - Principle - After Jan 10594425INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7L.O.A.51050 | Corbiere and Sons Contracting1017120211003-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting1017120211003-7Rock Truck - 30 Ton- After Jan 10192622.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1017120211003-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017120211003-7Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017120211003-7Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017120211003-7Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1017020211003-6Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1017020211003-6Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6L.O.A.81680 | Corbiere and Sons Contracting1017020211003-6L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Foreman131235 | Corbiere and Sons Contracting1017020211003-6Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1017020211003-6Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017020211003-6Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1017020211003-6ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1017020211003-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017020211003-6Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017020211003-6Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10179 | 20211003-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017920211003-15Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1017920211003-15Operator - Principle - After Jan 104300INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10179 | 20211003-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017920211003-15Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1017920211003-15Rock Truck - 30 Ton- After Jan 104552.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1017820211003-14Operator - Principle - After Jan 107525INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Foreman195 | Corbiere and Sons Contracting1017820211003-14Foreman195INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1017820211003-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1017820211003-14Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 53 | HR |  |  | 75 | 0 | 3975 | 516.75 | 4491.75 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Operator - Principle - After Jan 10533975 | Corbiere and Sons Contracting1017720211003-13Operator - Principle - After Jan 10533975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Foreman10950 | Corbiere and Sons Contracting1017720211003-13Foreman10950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1017720211003-13Rock Truck - 30 Ton- After Jan 10182484.9INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017720211003-13Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1017720211003-13Excavator - 30 ton- After Jan 107969.15INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1017720211003-13Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1017520211003-11Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting1017520211003-11Operator - Principle - After Jan 10523900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11L.O.A.61260 | Corbiere and Sons Contracting1017520211003-11L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Foreman131235 | Corbiere and Sons Contracting1017520211003-11Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017520211003-11Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017520211003-11Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017520211003-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017520211003-11Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1017420211003-10Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10L.O.A.3630 | Corbiere and Sons Contracting1017420211003-10L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017420211003-10Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1017420211003-10Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017420211003-10Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017420211003-10Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017420211003-10Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1015920211002-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting1015920211002-9Driver - AZ - After Jan 107490INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 96 | HR |  |  | 75 | 0 | 7200 | 936 | 8136 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Operator - Principle - After Jan 10967200 | Corbiere and Sons Contracting1015920211002-9Operator - Principle - After Jan 10967200INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9L.O.A.91890 | Corbiere and Sons Contracting1015920211002-9L.O.A.91890INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Foreman131235 | Corbiere and Sons Contracting1015920211002-9Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 |  |  |  | 856.73 | 111.3749 | 968.1049 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting1015920211002-9Tractor Trailer - 60 Ton- After Jan 107856.73INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 106828.3INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1015920211002-9Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1015920211002-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1015920211002-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 24 | HR | 9.16 | 0 |  |  | 293.04 | 38.0952 | 331.1352 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 1024293.04 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 1024293.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1015920211002-9Excavator - 30 ton- After Jan 106830.7INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Labourer - General - After Jan 104240 | Corbiere and Sons Contracting1015820211002-8Labourer - General - After Jan 104240INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 1013975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 104300INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8L.O.A.3630 | Corbiere and Sons Contracting1015820211002-8L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1015820211002-8Rock Truck - 30 Ton- After Jan 104552.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1015820211002-8Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1015820211002-8Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 104553.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 59 | HR |  |  | 75 | 0 | 4425 | 575.25 | 5000.25 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Operator - Principle - After Jan 10594425 | Corbiere and Sons Contracting1015720211002-7Operator - Principle - After Jan 10594425INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7L.O.A.51050 | Corbiere and Sons Contracting1015720211002-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting1015720211002-7Rock Truck - 30 Ton- After Jan 10192622.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1015720211002-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1015720211002-7Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1015720211002-7Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1015720211002-7Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 0 | 0 | 780 | 101.4 | 881.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1015620211002-6Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 0 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1015620211002-6Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  | 0 | 0 | 1680 | 218.4 | 1898.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6L.O.A.81680 | Corbiere and Sons Contracting1015620211002-6L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 0 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Foreman131235 | Corbiere and Sons Contracting1015620211002-6Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1015620211002-6Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1015620211002-6Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1015620211002-6ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1015620211002-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 0 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 0 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1015620211002-6Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 0 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1015620211002-6Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 43 | HR |  |  | 75 | 0 | 3225 | 419.25 | 3644.25 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Operator - Principle - After Jan 10433225 | Corbiere and Sons Contracting1016320211002-13Operator - Principle - After Jan 10433225INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Foreman10950 | Corbiere and Sons Contracting1016320211002-13Foreman10950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 14 | Dynamic | 103.54 | 0 |  |  | 1932.7 | 251.251 | 2183.951 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Rock Truck - 30 Ton- After Jan 10141932.7 | Corbiere and Sons Contracting1016320211002-13Rock Truck - 30 Ton- After Jan 10141932.7INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1016320211002-13Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1016320211002-13Excavator - 30 ton- After Jan 104553.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1016320211002-13Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1016220211002-12Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1016220211002-12Driver - AZ - After Jan 106420INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1016220211002-12Operator - Principle - After Jan 10554125INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12L.O.A.61260 | Corbiere and Sons Contracting1016220211002-12L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Foreman131235 | Corbiere and Sons Contracting1016220211002-12Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1016220211002-12Tractor Trailer - 60 Ton- After Jan 106734.34INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 104552.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 10101380.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1016220211002-12Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1016220211002-12Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1016220211002-12Dozer D6 or equal- After Jan 1081051.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1013920211001-9Operator - Principle - After Jan 10554125INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9L.O.A.51050 | Corbiere and Sons Contracting1013920211001-9L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 20 | Dynamic | 103.54 | 0 |  |  | 2761 | 358.93 | 3119.93 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Rock Truck - 30 Ton- After Jan 10202761 | Corbiere and Sons Contracting1013920211001-9Rock Truck - 30 Ton- After Jan 10202761INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1013920211001-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1013920211001-9Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1013920211001-9Excavator - 30 ton- After Jan 10101384.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1013920211001-9Dozer D6 or equal- After Jan 10101314.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1013820211001-8Driver - AZ - After Jan 104280INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1013820211001-8Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8L.O.A.61260 | Corbiere and Sons Contracting1013820211001-8L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Foreman121140 | Corbiere and Sons Contracting1013820211001-8Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1013820211001-8Tractor Trailer - 60 Ton- After Jan 104489.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting1013820211001-8Rock Truck - 30 Ton- After Jan 10212899.05INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1013820211001-8Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1013820211001-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1013820211001-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1013820211001-8Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1013820211001-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1013820211001-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10151 | 20211001-21 | 53510602 | Access | 0 | 3rd Party Charges | 1 | 20607 | Unit |  |  |  |  | 20607 | 2678.91 | 23285.91 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing from Sept 22nd to Oct 1st | 6 | C130-C277 | WF6 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | NO NUMBER AVAILABLE | Flagging by Best Towing |  |  |  |  | 06 | Corbiere and Sons Contracting1015120211001-213rd Party Charges2060720607 | Corbiere and Sons Contracting1015120211001-213rd Party Charges2060720607INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 65 | HR |  |  | 75 | 0 | 4875 | 633.75 | 5508.75 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Operator - Principle - After Jan 10654875 | Corbiere and Sons Contracting1014620211001-16Operator - Principle - After Jan 10654875INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Foreman9855 | Corbiere and Sons Contracting1014620211001-16Foreman9855INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting1014620211001-16Rock Truck - 30 Ton- After Jan 10212899.05INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1014620211001-16Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1014620211001-16Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1014620211001-16Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting1014520211001-15Labourer - General - After Jan 1010600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting1014520211001-15Operator - Principle - After Jan 10261950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15L.O.A.3630 | Corbiere and Sons Contracting1014520211001-15L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1014520211001-15Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1014520211001-15Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1014520211001-15Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014520211001-15Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 38 | HR |  |  | 75 | 0 | 2850 | 370.5 | 3220.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Operator - Principle - After Jan 10382850 | Corbiere and Sons Contracting1014420211001-14Operator - Principle - After Jan 10382850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14L.O.A.4840 | Corbiere and Sons Contracting1014420211001-14L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Foreman131235 | Corbiere and Sons Contracting1014420211001-14Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9.5 | Dynamic | 103.54 | 0 |  |  | 1311.475 | 170.4917 | 1481.9667 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Rock Truck - 30 Ton- After Jan 109.51311.475 | Corbiere and Sons Contracting1014420211001-14Rock Truck - 30 Ton- After Jan 109.51311.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1014420211001-14Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1014420211001-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1014420211001-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting1014420211001-14Dozer D6 or equal- After Jan 109.51249.06INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1014320211001-13Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13L.O.A.3630 | Corbiere and Sons Contracting1014320211001-13L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1014320211001-13Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1014320211001-13Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014320211001-13Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1014320211001-13Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1014120211001-11Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1014120211001-11Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11L.O.A.81680 | Corbiere and Sons Contracting1014120211001-11L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Foreman131235 | Corbiere and Sons Contracting1014120211001-11Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1014120211001-11Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1014120211001-11Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1014120211001-11ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1014120211001-11Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 1091322.64INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1014120211001-11Dozer D6 or equal- After Jan 1091183.32INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1012520210930-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1012520210930-9Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9L.O.A.4840 | Corbiere and Sons Contracting1012520210930-9L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1012520210930-9Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1012520210930-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1012520210930-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting1012520210930-9Excavator - 30 ton- After Jan 10243322.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1012420210930-8Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1012420210930-8Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8L.O.A.61260 | Corbiere and Sons Contracting1012420210930-8L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1012420210930-8Rock Truck - 30 Ton- After Jan 10182484.9INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1012420210930-8Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012420210930-8Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1012420210930-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012420210930-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1012320210930-7-R1Operator - Principle - After Jan 10483600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1L.O.A.51050 | Corbiere and Sons Contracting1012320210930-7-R1L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Foreman121140 | Corbiere and Sons Contracting1012320210930-7-R1Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1012320210930-7-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1012320210930-7-R1Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1012320210930-7-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012320210930-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012320210930-7-R1Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 67 | HR |  |  | 75 | 0 | 5025 | 653.25 | 5678.25 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Operator - Principle - After Jan 10675025 | Corbiere and Sons Contracting1013020210930-14Operator - Principle - After Jan 10675025INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Foreman10950 | Corbiere and Sons Contracting1013020210930-14Foreman10950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1013020210930-14Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1013020210930-14Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1013020210930-14Excavator - 30 ton- After Jan 107969.15INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1012920210930-13Driver - AZ - After Jan 1012840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting1012920210930-13Operator - Principle - After Jan 10261950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13L.O.A.3630 | Corbiere and Sons Contracting1012920210930-13L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1012920210930-13Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1012920210930-13Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1012920210930-13Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1012920210930-13Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1012920210930-13Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1012820210930-12Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12L.O.A.4840 | Corbiere and Sons Contracting1012820210930-12L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Foreman131235 | Corbiere and Sons Contracting1012820210930-12Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1012820210930-12Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1012820210930-12Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012820210930-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012820210930-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012820210930-12Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1012720210930-11Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11L.O.A.3630 | Corbiere and Sons Contracting1012720210930-11L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1012720210930-11Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1012720210930-11Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012720210930-11Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012720210930-11Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1012620210930-10Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1012620210930-10Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10L.O.A.81680 | Corbiere and Sons Contracting1012620210930-10L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Foreman131235 | Corbiere and Sons Contracting1012620210930-10Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1012620210930-10Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1012620210930-10Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1012620210930-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1012620210930-10Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 24 | HR | 9.16 | 0 |  |  | 293.04 | 38.0952 | 331.1352 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Excavator Thumb - 30 - 50 ton- After Jan 1024293.04 | Corbiere and Sons Contracting1012620210930-10Excavator Thumb - 30 - 50 ton- After Jan 1024293.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting1012620210930-10Excavator - 36 ton- After Jan 10487054.08INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1012620210930-10Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1010920210929-9Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1010920210929-9Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9L.O.A.4840 | Corbiere and Sons Contracting1010920210929-9L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1010920210929-9Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1010920210929-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010920210929-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1010820210929-8-R1Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1010820210929-8-R1Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1L.O.A.81680 | Corbiere and Sons Contracting1010820210929-8-R1L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Foreman121140 | Corbiere and Sons Contracting1010820210929-8-R1Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 29 | Dynamic | 103.54 | 0 |  |  | 4003.45 | 520.4485 | 4523.8985 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Rock Truck - 30 Ton- After Jan 10294003.45 | Corbiere and Sons Contracting1010820210929-8-R1Rock Truck - 30 Ton- After Jan 10294003.45INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1010820210929-8-R1Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1010820210929-8-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1010820210929-8-R1Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1010620210929-7Driver - AZ - After Jan 10221540INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1010620210929-7Operator - Principle - After Jan 10483600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7L.O.A.51050 | Corbiere and Sons Contracting1010620210929-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1010620210929-7Tractor Trailer - 60 Ton- After Jan 10222692.58INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1010620210929-7Rock Truck - 30 Ton- After Jan 10101380.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1010620210929-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010620210929-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010620210929-7Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010620210929-7Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1010620210929-7Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10117 | 20210929-17 | 53510602 | Access | 0 | Driver - Other - After Jan 10 | 60 | 16 | HR |  |  | 60 | 0 | 960 | 124.8 | 1084.8 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and demobilization of pickups | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011720210929-17Driver - Other - After Jan 1016960 | Corbiere and Sons Contracting1011720210929-17Driver - Other - After Jan 1016960INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10117 | 20210929-17 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and demobilization of pickups | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011720210929-17L.O.A.2420 | Corbiere and Sons Contracting1011720210929-17L.O.A.2420INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10117 | 20210929-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and demobilization of pickups | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011720210929-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1011720210929-17Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1011520210929-15Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Foreman121140 | Corbiere and Sons Contracting1011520210929-15Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1011520210929-15Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1011520210929-15Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1011520210929-15Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1011420210929-14Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14L.O.A.1210 | Corbiere and Sons Contracting1011420210929-14L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1011420210929-14Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011420210929-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011420210929-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 31.5 | HR |  |  | 75 | 0 | 2362.5 | 307.125 | 2669.625 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Operator - Principle - After Jan 1031.52362.5 | Corbiere and Sons Contracting1011320210929-13Operator - Principle - After Jan 1031.52362.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13L.O.A.4840 | Corbiere and Sons Contracting1011320210929-13L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Foreman121140 | Corbiere and Sons Contracting1011320210929-13Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9.5 | Dynamic | 103.54 | 0 |  |  | 1311.475 | 170.4917 | 1481.9667 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Rock Truck - 30 Ton- After Jan 109.51311.475 | Corbiere and Sons Contracting1011320210929-13Rock Truck - 30 Ton- After Jan 109.51311.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1011320210929-13Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0794 | 131.0743 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting1011320210929-13Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting1011320210929-13Excavator - 36 ton- After Jan 109.51396.12INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting1011320210929-13Dozer D6 or equal- After Jan 109.51249.06INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1011220210929-12Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12L.O.A.3630 | Corbiere and Sons Contracting1011220210929-12L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1011220210929-12Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1011220210929-12Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011220210929-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1011220210929-12Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1011020210929-10Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1011020210929-10Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10L.O.A.71470 | Corbiere and Sons Contracting1011020210929-10L.O.A.71470INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Foreman121140 | Corbiere and Sons Contracting1011020210929-10Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1011020210929-10Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1011020210929-10Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1011020210929-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1011020210929-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1011020210929-10Excavator - 36 ton- After Jan 10223233.12INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1011020210929-10Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1011020210929-10Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1009420210928-9Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1009420210928-9Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9L.O.A.4840 | Corbiere and Sons Contracting1009420210928-9L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009420210928-9Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1009420210928-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009420210928-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1009320210928-8Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1009320210928-8Driver - AZ - After Jan 1012840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1009320210928-8Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8L.O.A.91890 | Corbiere and Sons Contracting1009320210928-8L.O.A.91890INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Foreman121140 | Corbiere and Sons Contracting1009320210928-8Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1009320210928-8Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 33 | Dynamic | 103.54 | 0 |  |  | 4555.65 | 592.2345 | 5147.8845 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Rock Truck - 30 Ton- After Jan 10334555.65 | Corbiere and Sons Contracting1009320210928-8Rock Truck - 30 Ton- After Jan 10334555.65INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1009320210928-8Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1009320210928-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009320210928-8Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009320210928-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009320210928-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1009220210928-7Operator - Principle - After Jan 10483600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7L.O.A.4840 | Corbiere and Sons Contracting1009220210928-7L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1009220210928-7Rock Truck - 30 Ton- After Jan 10101380.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1009220210928-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009220210928-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009220210928-7Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009220210928-7Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009220210928-7Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1010020210928-15Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Foreman121140 | Corbiere and Sons Contracting1010020210928-15Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1010020210928-15Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1010020210928-15Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010020210928-15Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1009820210928-13Operator - Principle - After Jan 108600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13L.O.A.1210 | Corbiere and Sons Contracting1009820210928-13L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1009820210928-13Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6824 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting1009820210928-13Excavator Thumb - 30 - 50 ton- After Jan 106.579.365INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting1009820210928-13Excavator - 36 ton- After Jan 106.5955.24INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1009720210928-12Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12L.O.A.3630 | Corbiere and Sons Contracting1009720210928-12L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009720210928-12Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1009720210928-12Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009720210928-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009720210928-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009720210928-12Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1009620210928-11Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11L.O.A.3630 | Corbiere and Sons Contracting1009620210928-11L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009620210928-11Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1009620210928-11Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009620210928-11Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009620210928-11Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1009520210928-10Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1009520210928-10Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10L.O.A.71470 | Corbiere and Sons Contracting1009520210928-10L.O.A.71470INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Foreman121140 | Corbiere and Sons Contracting1009520210928-10Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009520210928-10Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1009520210928-10Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1009520210928-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1009520210928-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1009520210928-10Excavator - 36 ton- After Jan 10223233.12INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009520210928-10Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009520210928-10Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10062 | 20210926-14 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-08 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006220210926-14L.O.A.0.5105 | Corbiere and Sons Contracting1006220210926-14L.O.A.0.5105INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10062 | 20210926-14 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-08 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006220210926-14Safety Advisor7595 | Corbiere and Sons Contracting1006220210926-14Safety Advisor7595INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10062 | 20210926-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-08 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006220210926-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1006220210926-14Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1006120210926-13Operator - Principle - After Jan 10554125INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Foreman121140 | Corbiere and Sons Contracting1006120210926-13Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1006120210926-13Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1006120210926-13Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 106881.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1006120210926-13Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1006120210926-13Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1004120210925-8Labourer - General - After Jan 106360INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 42 | HR |  |  | 75 | 0 | 3150 | 409.5 | 3559.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Operator - Principle - After Jan 10423150 | Corbiere and Sons Contracting1004120210925-8Operator - Principle - After Jan 10423150INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8L.O.A.51050 | Corbiere and Sons Contracting1004120210925-8L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1004120210925-8Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1004120210925-8Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1004120210925-8Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9918 | 860.4667 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 105.5761.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004120210925-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1004020210925-7Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7L.O.A.71470 | Corbiere and Sons Contracting1004020210925-7L.O.A.71470INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Foreman121140 | Corbiere and Sons Contracting1004020210925-7Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 33 | Dynamic | 103.54 | 0 |  |  | 4555.65 | 592.2345 | 5147.8845 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Rock Truck - 30 Ton- After Jan 10334555.65 | Corbiere and Sons Contracting1004020210925-7Rock Truck - 30 Ton- After Jan 10334555.65INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1004020210925-7Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1004020210925-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004020210925-7Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004020210925-7Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004020210925-7Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1003920210925-6Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6L.O.A.3630 | Corbiere and Sons Contracting1003920210925-6L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1003920210925-6Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003920210925-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1003920210925-6Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1003920210925-6Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1003920210925-6Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10049 | 20210925-16 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1004920210925-16L.O.A.0.5105 | Corbiere and Sons Contracting1004920210925-16L.O.A.0.5105INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10049 | 20210925-16 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1004920210925-16Safety Advisor7595 | Corbiere and Sons Contracting1004920210925-16Safety Advisor7595INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10049 | 20210925-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1004920210925-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1004920210925-16Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 40 | HR |  |  | 75 | 0 | 3000 | 390 | 3390 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Operator - Principle - After Jan 10403000 | Corbiere and Sons Contracting1004820210925-15Operator - Principle - After Jan 10403000INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Foreman4380 | Corbiere and Sons Contracting1004820210925-15Foreman4380INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1004820210925-15Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1004820210925-15Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 1091322.64INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004820210925-15Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004820210925-15Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting1004720210925-14Labourer - General - After Jan 10241440INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1004720210925-14Driver - AZ - After Jan 1012840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 41 | HR |  |  | 75 | 0 | 3075 | 399.75 | 3474.75 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Operator - Principle - After Jan 10413075 | Corbiere and Sons Contracting1004720210925-14Operator - Principle - After Jan 10413075INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14L.O.A.81680 | Corbiere and Sons Contracting1004720210925-14L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Foreman121140 | Corbiere and Sons Contracting1004720210925-14Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1004720210925-14Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9.5 | Dynamic | 103.54 | 0 |  |  | 1311.475 | 170.4917 | 1481.9667 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Rock Truck - 30 Ton- After Jan 109.51311.475 | Corbiere and Sons Contracting1004720210925-14Rock Truck - 30 Ton- After Jan 109.51311.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1004720210925-14Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1004720210925-14Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1004720210925-14Excavator - 36 ton- After Jan 1091322.64INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004720210925-14Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1004620210925-13Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13L.O.A.1210 | Corbiere and Sons Contracting1004620210925-13L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1004620210925-13Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004620210925-13Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 42 | HR |  |  | 75 | 0 | 3150 | 409.5 | 3559.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Operator - Principle - After Jan 10423150 | Corbiere and Sons Contracting1004520210925-12Operator - Principle - After Jan 10423150INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12L.O.A.51050 | Corbiere and Sons Contracting1004520210925-12L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Foreman121140 | Corbiere and Sons Contracting1004520210925-12Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 | 0 |  |  | 2070.75 | 269.1975 | 2339.9475 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting1004520210925-12Rock Truck - 30 Ton- After Jan 10152070.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1004520210925-12Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1004520210925-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1004520210925-12Excavator - 36 ton- After Jan 1081175.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1004520210925-12Dozer D6 or equal- After Jan 107920.36INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1004420210925-11Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11L.O.A.1210 | Corbiere and Sons Contracting1004420210925-11L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004420210925-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004420210925-11Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 58 | HR |  |  | 75 | 0 | 4350 | 565.5 | 4915.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Operator - Principle - After Jan 10584350 | Corbiere and Sons Contracting1004320210925-10-R1Operator - Principle - After Jan 10584350INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1L.O.A.61260 | Corbiere and Sons Contracting1004320210925-10-R1L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Foreman121140 | Corbiere and Sons Contracting1004320210925-10-R1Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1004320210925-10-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1004320210925-10-R1Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1004320210925-10-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1004320210925-10-R1Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1004320210925-10-R1Dozer D6 or equal- After Jan 1081051.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10147 | 20211001-17 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float brought mats over to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014720211001-17Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1014720211001-17Driver - AZ - After Jan 103210INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10147 | 20211001-17 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float brought mats over to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014720211001-17Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1014720211001-17Tractor Trailer - 60 Ton- After Jan 103367.17INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1014220211001-12Driver - AZ - After Jan 103210INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1014220211001-12Operator - Principle - After Jan 106450INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12L.O.A.1210 | Corbiere and Sons Contracting1014220211001-12L.O.A.1210INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1014220211001-12Tractor Trailer - 60 Ton- After Jan 103367.17INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1014220211001-12Excavator - 36 ton- After Jan 103440.88INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1014220211001-12Dozer D6 or equal- After Jan 103394.44INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1011120210929-11Driver - AZ - After Jan 1012840INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1011120210929-11Operator - Principle - After Jan 105375INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11L.O.A.2420 | Corbiere and Sons Contracting1011120210929-11L.O.A.2420INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1011120210929-11Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting1011120210929-11Excavator - 36 ton- After Jan 102293.92INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10185 | 20211004-8 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018520211004-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1018520211004-8Operator - Principle - After Jan 107525INV #150 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10185 | 20211004-8 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018520211004-8L.O.A.1210 | Corbiere and Sons Contracting1018520211004-8L.O.A.1210INV #150 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10185 | 20211004-8 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018520211004-8Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1018520211004-8Excavator - 30 ton- After Jan 106830.7INV #150 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 1012.5875 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 1012.5875INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 10443080 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 10443080INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5L.O.A.4840 | Corbiere and Sons Contracting1018220211004-5L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12.5 | Dynamic | 41.4 | 0 |  |  | 690 | 89.7 | 779.7 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 1012.5690 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 1012.5690INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 44 | Dynamic | 41.4 | 0 |  |  | 2428.8 | 315.744 | 2744.544 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 10442428.8 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 10442428.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10181 | 20211004-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 77.5 | HR |  |  | 70 | 0 | 5425 | 705.25 | 6130.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 7 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018120211004-4Driver - AZ - After Jan 1077.55425 | Corbiere and Sons Contracting1018120211004-4Driver - AZ - After Jan 1077.55425INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10181 | 20211004-4 | 53510604 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 7 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018120211004-4L.O.A.71470 | Corbiere and Sons Contracting1018120211004-4L.O.A.71470INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10181 | 20211004-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 77.5 | Dynamic | 41.4 | 0 |  |  | 4278 | 556.14 | 4834.14 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 7 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018120211004-4Dump - Triaxle- After Jan 1077.54278 | Corbiere and Sons Contracting1018120211004-4Dump - Triaxle- After Jan 1077.54278INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10192 | 20211004-15 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019220211004-15Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1019220211004-15Operator - Principle - After Jan 1012900INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10192 | 20211004-15 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019220211004-15Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1019220211004-15Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10169 | 20211003-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 92 | HR |  |  | 70 | 0 | 6440 | 837.2 | 7277.2 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 Padda Trucks hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016920211003-5Driver - AZ - After Jan 10926440 | Corbiere and Sons Contracting1016920211003-5Driver - AZ - After Jan 10926440INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10169 | 20211003-5 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 Padda Trucks hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016920211003-5L.O.A.81680 | Corbiere and Sons Contracting1016920211003-5L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10169 | 20211003-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 92 | Dynamic | 41.4 | 0 |  |  | 5078.4 | 660.192 | 5738.592 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 Padda Trucks hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016920211003-5Dump - Triaxle- After Jan 10925078.4 | Corbiere and Sons Contracting1016920211003-5Dump - Triaxle- After Jan 10925078.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10168 | 20211003-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016820211003-4Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1016820211003-4Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10168 | 20211003-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016820211003-4L.O.A.4840 | Corbiere and Sons Contracting1016820211003-4L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10168 | 20211003-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016820211003-4Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1016820211003-4Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1016720211003-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 41.5 | HR |  |  | 70 | 0 | 2905 | 377.65 | 3282.65 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Driver - AZ - After Jan 1041.52905 | Corbiere and Sons Contracting1016720211003-3Driver - AZ - After Jan 1041.52905INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3L.O.A.51050 | Corbiere and Sons Contracting1016720211003-3L.O.A.51050INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1016720211003-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 41.5 | Dynamic | 41.4 | 0 |  |  | 2290.8 | 297.804 | 2588.604 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Dump - Triaxle- After Jan 1041.52290.8 | Corbiere and Sons Contracting1016720211003-3Dump - Triaxle- After Jan 1041.52290.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012.5875 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012.5875INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5L.O.A.3630 | Corbiere and Sons Contracting1015420211002-5L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12.5 | Dynamic | 41.4 | 0 |  |  | 690 | 89.7 | 779.7 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012.5690 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012.5690INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10153 | 20211002-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015320211002-4Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1015320211002-4Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10153 | 20211002-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015320211002-4L.O.A.4840 | Corbiere and Sons Contracting1015320211002-4L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10153 | 20211002-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015320211002-4Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1015320211002-4Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1015220211002-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 151.5 | HR |  |  | 70 | 0 | 10605 | 1378.65 | 11983.65 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Driver - AZ - After Jan 10151.510605 | Corbiere and Sons Contracting1015220211002-3Driver - AZ - After Jan 10151.510605INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3L.O.A.142940 | Corbiere and Sons Contracting1015220211002-3L.O.A.142940INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1015220211002-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 151.5 | Dynamic | 41.4 | 0 |  |  | 8362.8 | 1087.164 | 9449.964 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Dump - Triaxle- After Jan 10151.58362.8 | Corbiere and Sons Contracting1015220211002-3Dump - Triaxle- After Jan 10151.58362.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10137 | 20211001-7 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 24.5 | HR |  |  | 70 | 0 | 1715 | 222.95 | 1937.95 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Taranis Truck and 1 Valentino truck hauling to Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013720211001-7Driver - AZ - After Jan 1024.51715 | Corbiere and Sons Contracting1013720211001-7Driver - AZ - After Jan 1024.51715INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10137 | 20211001-7 | 53510604 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Taranis Truck and 1 Valentino truck hauling to Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013720211001-7L.O.A.1210 | Corbiere and Sons Contracting1013720211001-7L.O.A.1210INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10137 | 20211001-7 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 24.5 | Dynamic | 41.4 | 0 |  |  | 1352.4 | 175.812 | 1528.212 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Taranis Truck and 1 Valentino truck hauling to Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013720211001-7Dump - Triaxle- After Jan 1024.51352.4 | Corbiere and Sons Contracting1013720211001-7Dump - Triaxle- After Jan 1024.51352.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 10332310 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 10332310INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6L.O.A.3630 | Corbiere and Sons Contracting1013620211001-6L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 33 | Dynamic | 41.4 | 0 |  |  | 1821.6 | 236.808 | 2058.408 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 10331821.6 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 10331821.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10135 | 20211001-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013520211001-5Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting1013520211001-5Driver - AZ - After Jan 10231610INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10135 | 20211001-5 | 53510604 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013520211001-5L.O.A.2420 | Corbiere and Sons Contracting1013520211001-5L.O.A.2420INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10135 | 20211001-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23 | Dynamic | 41.4 | 0 |  |  | 1269.6 | 165.048 | 1434.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013520211001-5Dump - Triaxle- After Jan 10231269.6 | Corbiere and Sons Contracting1013520211001-5Dump - Triaxle- After Jan 10231269.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10134 | 20211001-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013420211001-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1013420211001-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10134 | 20211001-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013420211001-4L.O.A.3630 | Corbiere and Sons Contracting1013420211001-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10134 | 20211001-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013420211001-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1013420211001-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1013320211001-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 80.5 | HR |  |  | 70 | 0 | 5635 | 732.55 | 6367.55 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Driver - AZ - After Jan 1080.55635 | Corbiere and Sons Contracting1013320211001-3Driver - AZ - After Jan 1080.55635INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3L.O.A.81680 | Corbiere and Sons Contracting1013320211001-3L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1013320211001-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 80.5 | Dynamic | 41.4 | 0 |  |  | 4443.6 | 577.668 | 5021.268 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Dump - Triaxle- After Jan 1080.54443.6 | Corbiere and Sons Contracting1013320211001-3Dump - Triaxle- After Jan 1080.54443.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 43 | HR |  |  | 70 | 0 | 3010 | 391.3 | 3401.3 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10433010 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10433010INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10231610INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6L.O.A.61260 | Corbiere and Sons Contracting1012220210930-6L.O.A.61260INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 43 | Dynamic | 41.4 | 0 |  |  | 2373.6 | 308.568 | 2682.168 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10432373.6 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10432373.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23 | Dynamic | 41.4 | 0 |  |  | 1269.6 | 165.048 | 1434.648 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10231269.6 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10231269.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10121 | 20210930-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino truck hauling to Mink Creek from Cress Pit | 6 | C244-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012120210930-5Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting1012120210930-5Driver - AZ - After Jan 1013910INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10121 | 20210930-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino truck hauling to Mink Creek from Cress Pit | 6 | C244-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012120210930-5Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting1012120210930-5Dump - Triaxle- After Jan 1013717.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10119 | 20210930-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011920210930-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1011920210930-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10119 | 20210930-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011920210930-4L.O.A.3630 | Corbiere and Sons Contracting1011920210930-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10119 | 20210930-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011920210930-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1011920210930-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1011820210930-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 80.5 | HR |  |  | 70 | 0 | 5635 | 732.55 | 6367.55 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Driver - AZ - After Jan 1080.55635 | Corbiere and Sons Contracting1011820210930-3Driver - AZ - After Jan 1080.55635INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3L.O.A.81680 | Corbiere and Sons Contracting1011820210930-3L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1011820210930-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 80.5 | Dynamic | 41.4 | 0 |  |  | 4443.6 | 577.668 | 5021.268 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Dump - Triaxle- After Jan 1080.54443.6 | Corbiere and Sons Contracting1011820210930-3Dump - Triaxle- After Jan 1080.54443.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10105 | 20210929-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010520210929-6Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1010520210929-6Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10105 | 20210929-6 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010520210929-6L.O.A.4840 | Corbiere and Sons Contracting1010520210929-6L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10105 | 20210929-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010520210929-6Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1010520210929-6Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5L.O.A.3630 | Corbiere and Sons Contracting1010420210929-5L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10103 | 20210929-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010320210929-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1010320210929-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10103 | 20210929-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010320210929-4L.O.A.3630 | Corbiere and Sons Contracting1010320210929-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10103 | 20210929-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010320210929-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1010320210929-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1010220210929-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 81 | HR |  |  | 70 | 0 | 5670 | 737.1 | 6407.1 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 10815670 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 10815670INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3L.O.A.81680 | Corbiere and Sons Contracting1010220210929-3L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1010220210929-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 81 | Dynamic | 41.4 | 0 |  |  | 4471.2 | 581.256 | 5052.456 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 10814471.2 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 10814471.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10091 | 20210928-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009120210928-6Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1009120210928-6Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10091 | 20210928-6 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009120210928-6L.O.A.4840 | Corbiere and Sons Contracting1009120210928-6L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10091 | 20210928-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009120210928-6Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1009120210928-6Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 45.5 | HR |  |  | 70 | 0 | 3185 | 414.05 | 3599.05 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1045.53185 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1045.53185INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5L.O.A.4840 | Corbiere and Sons Contracting1009020210928-5L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 45.5 | Dynamic | 41.4 | 0 |  |  | 2511.6 | 326.508 | 2838.108 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1045.52511.6 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1045.52511.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10088 | 20210928-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008820210928-4Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting1008820210928-4Driver - AZ - After Jan 10231610INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10088 | 20210928-4 | 53510604 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008820210928-4L.O.A.2420 | Corbiere and Sons Contracting1008820210928-4L.O.A.2420INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10088 | 20210928-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23 | Dynamic | 41.4 |  |  |  | 1269.6 | 165.048 | 1434.648 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008820210928-4Dump - Triaxle- After Jan 10231269.6 | Corbiere and Sons Contracting1008820210928-4Dump - Triaxle- After Jan 10231269.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1008720210928-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56.5 | HR |  |  | 70 | 0 | 3955 | 514.15 | 4469.15 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1056.53955 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1056.53955INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3L.O.A.61260 | Corbiere and Sons Contracting1008720210928-3L.O.A.61260INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1008720210928-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56.5 | Dynamic | 41.4 | 0 |  |  | 3118.8 | 405.444 | 3524.244 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1056.53118.8 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1056.53118.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10053 | 20210926-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 6 Padda trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005320210926-5Driver - AZ - After Jan 10694830 | Corbiere and Sons Contracting1005320210926-5Driver - AZ - After Jan 10694830INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10053 | 20210926-5 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 6 Padda trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005320210926-5L.O.A.61260 | Corbiere and Sons Contracting1005320210926-5L.O.A.61260INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10053 | 20210926-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69 | Dynamic | 41.4 | 0 |  |  | 3808.8 | 495.144 | 4303.944 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 6 Padda trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005320210926-5Dump - Triaxle- After Jan 10693808.8 | Corbiere and Sons Contracting1005320210926-5Dump - Triaxle- After Jan 10693808.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10052 | 20210926-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005220210926-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1005220210926-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10052 | 20210926-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005220210926-4L.O.A.3630 | Corbiere and Sons Contracting1005220210926-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10052 | 20210926-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005220210926-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1005220210926-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 103.5 | HR |  |  | 70 | 0 | 7245 | 941.85 | 8186.85 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Driver - AZ - After Jan 10103.57245 | Corbiere and Sons Contracting1005120210926-3Driver - AZ - After Jan 10103.57245INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3L.O.A.102100 | Corbiere and Sons Contracting1005120210926-3L.O.A.102100INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Construction Coordinator7560 | Corbiere and Sons Contracting1005120210926-3Construction Coordinator7560INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1005120210926-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 103.5 | Dynamic | 41.4 | 0 |  |  | 5713.2 | 742.716 | 6455.916 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Dump - Triaxle- After Jan 10103.55713.2 | Corbiere and Sons Contracting1005120210926-3Dump - Triaxle- After Jan 10103.55713.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 1013910INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 104280INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 1013717.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 4 | Dynamic | 41.4 | 0 |  |  | 220.8 | 28.704 | 249.504 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 104220.8 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 104220.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10037 | 20210925-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 57.5 | HR |  |  | 70 | 0 | 4025 | 523.25 | 4548.25 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003720210925-4Driver - AZ - After Jan 1057.54025 | Corbiere and Sons Contracting1003720210925-4Driver - AZ - After Jan 1057.54025INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10037 | 20210925-4 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003720210925-4L.O.A.51050 | Corbiere and Sons Contracting1003720210925-4L.O.A.51050INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10037 | 20210925-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 57.5 | Dynamic | 41.4 | 0 |  |  | 3174 | 412.62 | 3586.62 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003720210925-4Dump - Triaxle- After Jan 1057.53174 | Corbiere and Sons Contracting1003720210925-4Dump - Triaxle- After Jan 1057.53174INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 150.5 | HR |  |  | 70 | 0 | 10535 | 1369.55 | 11904.55 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Driver - AZ - After Jan 10150.510535 | Corbiere and Sons Contracting1003520210925-3Driver - AZ - After Jan 10150.510535INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3L.O.A.142940 | Corbiere and Sons Contracting1003520210925-3L.O.A.142940INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Construction Coordinator7560 | Corbiere and Sons Contracting1003520210925-3Construction Coordinator7560INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1003520210925-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 150.5 | Dynamic | 41.4 | 0 |  |  | 8307.6 | 1079.988 | 9387.588 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Dump - Triaxle- After Jan 10150.58307.6 | Corbiere and Sons Contracting1003520210925-3Dump - Triaxle- After Jan 10150.58307.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10215 | 20211007-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Utilization of DZ to pull out pickup | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021520211007-6Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1021520211007-6Dozer D6 or equal- After Jan 102262.96INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1019920211005-9Driver - AZ - After Jan 1012840INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1019920211005-9Operator - Principle - After Jan 10322400INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9L.O.A.4840 | Corbiere and Sons Contracting1019920211005-9L.O.A.4840INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1019920211005-9Tractor Trailer - 60 Ton- After Jan 10121468.68INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1019920211005-9Rock Truck - 30 Ton- After Jan 10101380.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1019920211005-9Light Truck - Pick up- After Jan 101243.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1019920211005-9Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 10101469.6INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 1071028.72INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1019820211005-8Labourer - General - After Jan 1013780INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1019820211005-8Operator - Principle - After Jan 10483600INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8L.O.A.61260 | Corbiere and Sons Contracting1019820211005-8L.O.A.61260INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Foreman131235 | Corbiere and Sons Contracting1019820211005-8Foreman131235INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1019820211005-8Rock Truck - 30 Ton- After Jan 10121656.6INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1019820211005-8Light Truck - Pick up- After Jan 1051218.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1019820211005-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 1081175.68INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 10121763.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1019820211005-8Dozer D6 or equal- After Jan 10121577.76INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1019720211005-7Labourer - General - After Jan 1013780INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1019720211005-7Operator - Principle - After Jan 10785850INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7L.O.A.81680 | Corbiere and Sons Contracting1019720211005-7L.O.A.81680INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Foreman131235 | Corbiere and Sons Contracting1019720211005-7Foreman131235INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1019720211005-7Rock Truck - 30 Ton- After Jan 10243313.2INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1019720211005-7Light Truck - Pick up- After Jan 1051218.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1019720211005-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1019720211005-7Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 9.16 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting1019720211005-7Excavator Thumb - 30 - 50 ton- After Jan 1036439.56INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10243527.04INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10121763.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1019720211005-7Excavator - 30 ton- After Jan 10121661.4INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1019520211005-5Labourer - General - After Jan 1012720INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 70 | HR |  |  | 75 | 0 | 5250 | 682.5 | 5932.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Operator - Principle - After Jan 10705250 | Corbiere and Sons Contracting1019520211005-5Operator - Principle - After Jan 10705250INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5L.O.A.71470 | Corbiere and Sons Contracting1019520211005-5L.O.A.71470INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Foreman131235 | Corbiere and Sons Contracting1019520211005-5Foreman131235INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 39 | Dynamic | 103.54 | 0 |  |  | 5383.95 | 699.9135 | 6083.8635 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Rock Truck - 30 Ton- After Jan 10395383.95 | Corbiere and Sons Contracting1019520211005-5Rock Truck - 30 Ton- After Jan 10395383.95INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1019520211005-5Light Truck - Pick up- After Jan 104975INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1019520211005-5ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 13 | HR | 9.16 | 0 |  |  | 158.73 | 20.6349 | 179.3649 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Excavator Thumb - 30 - 50 ton- After Jan 1013158.73 | Corbiere and Sons Contracting1019520211005-5Excavator Thumb - 30 - 50 ton- After Jan 1013158.73INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 13 | Dynamic | 103.84 | 0 |  |  | 1799.85 | 233.9805 | 2033.8305 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Excavator - 30 ton- After Jan 10131799.85 | Corbiere and Sons Contracting1019520211005-5Excavator - 30 ton- After Jan 10131799.85INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 13 | Dynamic | 98.61 | 0 |  |  | 1709.24 | 222.2012 | 1931.4412 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Dozer D6 or equal- After Jan 10131709.24 | Corbiere and Sons Contracting1019520211005-5Dozer D6 or equal- After Jan 10131709.24INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1019420211005-4Labourer - General - After Jan 1013780INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 65 | HR |  |  | 75 | 0 | 4875 | 633.75 | 5508.75 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Operator - Principle - After Jan 10654875 | Corbiere and Sons Contracting1019420211005-4Operator - Principle - After Jan 10654875INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4L.O.A.61260 | Corbiere and Sons Contracting1019420211005-4L.O.A.61260INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1019420211005-4Rock Truck - 30 Ton- After Jan 10243313.2INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1019420211005-4Light Truck - Pick up- After Jan 103731.25INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1019420211005-4Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1019420211005-4Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1019420211005-4Excavator - 36 ton- After Jan 10121763.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1019420211005-4Excavator - 30 ton- After Jan 10121661.4INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1019420211005-4Dozer D6 or equal- After Jan 10121577.76INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 54 | HR |  |  | 75 | 0 | 4050 | 526.5 | 4576.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Operator - Principle - After Jan 10544050 | Corbiere and Sons Contracting1020120211005-11Operator - Principle - After Jan 10544050INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Foreman10950 | Corbiere and Sons Contracting1020120211005-11Foreman10950INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1020120211005-11Rock Truck - 30 Ton- After Jan 10101380.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1020120211005-11Light Truck - Pick up- After Jan 1051218.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 28 | HR | 9.16 | 0 |  |  | 341.88 | 44.4444 | 386.3244 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Excavator Thumb - 30 - 50 ton- After Jan 1028341.88 | Corbiere and Sons Contracting1020120211005-11Excavator Thumb - 30 - 50 ton- After Jan 1028341.88INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 17 | Dynamic | 110.22 | 0 |  |  | 2498.32 | 324.7816 | 2823.1016 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Excavator - 36 ton- After Jan 10172498.32 | Corbiere and Sons Contracting1020120211005-11Excavator - 36 ton- After Jan 10172498.32INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1020120211005-11Excavator - 30 ton- After Jan 10111522.95INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1020120211005-11Dozer D6 or equal- After Jan 10111446.28INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10222 | 20211008-4 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating swamp mats over to 3 Fingers Lake Road | 6 | D009-D017 | Three Finger | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022220211008-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1022220211008-4Driver - AZ - After Jan 105350INV #151 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10222 | 20211008-4 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating swamp mats over to 3 Fingers Lake Road | 6 | D009-D017 | Three Finger | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022220211008-4L.O.A.1210 | Corbiere and Sons Contracting1022220211008-4L.O.A.1210INV #151 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10222 | 20211008-4 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating swamp mats over to 3 Fingers Lake Road | 6 | D009-D017 | Three Finger | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022220211008-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1022220211008-4Tractor Trailer - 60 Ton- After Jan 105611.95INV #151 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1025920211015-3Operator - Principle - After Jan 109675INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Foreman4380 | Corbiere and Sons Contracting1025920211015-3Foreman4380INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 3 | Dynamic | 103.54 | 0 |  |  | 414.15 | 53.8395 | 467.9895 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Rock Truck - 30 Ton- After Jan 103414.15 | Corbiere and Sons Contracting1025920211015-3Rock Truck - 30 Ton- After Jan 103414.15INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1025920211015-3Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1025920211015-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1025920211015-3Excavator - 36 ton- After Jan 103440.88INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1025920211015-3Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1025620211014-5Operator - Principle - After Jan 10241800INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5L.O.A.3630 | Corbiere and Sons Contracting1025620211014-5L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Foreman6570 | Corbiere and Sons Contracting1025620211014-5Foreman6570INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025620211014-5Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025620211014-5Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1025620211014-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1025620211014-5Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1025620211014-5Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1025420211014-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3L.O.A.4840 | Corbiere and Sons Contracting1025420211014-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Foreman121140 | Corbiere and Sons Contracting1025420211014-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025420211014-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025420211014-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1025420211014-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1025420211014-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1025420211014-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1025420211014-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1025220211013-5Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5L.O.A.4840 | Corbiere and Sons Contracting1025220211013-5L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Foreman6570 | Corbiere and Sons Contracting1025220211013-5Foreman6570INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025220211013-5Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025220211013-5Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting1025220211013-5Excavator Thumb - 30 - 50 ton- After Jan 1020244.2INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 20 | Dynamic | 110.22 | 0 |  |  | 2939.2 | 382.096 | 3321.296 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Excavator - 36 ton- After Jan 10202939.2 | Corbiere and Sons Contracting1025220211013-5Excavator - 36 ton- After Jan 10202939.2INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1025020211013-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3L.O.A.4840 | Corbiere and Sons Contracting1025020211013-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Foreman121140 | Corbiere and Sons Contracting1025020211013-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025020211013-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025020211013-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1025020211013-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting1025020211013-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1025020211013-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1025020211013-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting1025020211013-3Excavator - 30 ton- After Jan 1091246.05INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1025020211013-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1024820211012-5Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5L.O.A.4840 | Corbiere and Sons Contracting1024820211012-5L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Foreman121140 | Corbiere and Sons Contracting1024820211012-5Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024820211012-5Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1024820211012-5Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 22 | HR | 9.16 | 0 |  |  | 268.62 | 34.9206 | 303.5406 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Excavator Thumb - 30 - 50 ton- After Jan 1022268.62 | Corbiere and Sons Contracting1024820211012-5Excavator Thumb - 30 - 50 ton- After Jan 1022268.62INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 33 | Dynamic | 110.22 | 0 |  |  | 4849.68 | 630.4584 | 5480.1384 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Excavator - 36 ton- After Jan 10334849.68 | Corbiere and Sons Contracting1024820211012-5Excavator - 36 ton- After Jan 10334849.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1024620211012-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3L.O.A.4840 | Corbiere and Sons Contracting1024620211012-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Foreman121140 | Corbiere and Sons Contracting1024620211012-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1024620211012-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024620211012-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1024620211012-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting1024620211012-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1024620211012-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1024620211012-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1024620211012-3Excavator - 30 ton- After Jan 105692.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1024620211012-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting1024520211011-6Operator - Principle - After Jan 10272025INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6L.O.A.4840 | Corbiere and Sons Contracting1024520211011-6L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Foreman9855 | Corbiere and Sons Contracting1024520211011-6Foreman9855INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1024520211011-6Rock Truck - 30 Ton- After Jan 1081104.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024520211011-6Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting1024520211011-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 16 | HR | 9.16 | 0 |  |  | 195.36 | 25.3968 | 220.7568 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Excavator Thumb - 30 - 50 ton- After Jan 1016195.36 | Corbiere and Sons Contracting1024520211011-6Excavator Thumb - 30 - 50 ton- After Jan 1016195.36INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1024520211011-6Excavator - 36 ton- After Jan 10243527.04INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1024220211011-4Operator - Principle - After Jan 10322400INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4L.O.A.4840 | Corbiere and Sons Contracting1024220211011-4L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Foreman121140 | Corbiere and Sons Contracting1024220211011-4Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1024220211011-4Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024220211011-4Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1024220211011-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 1071028.72INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1024220211011-4Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1024120211011-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3L.O.A.4840 | Corbiere and Sons Contracting1024120211011-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Foreman121140 | Corbiere and Sons Contracting1024120211011-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1024120211011-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024120211011-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1024120211011-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting1024120211011-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1024120211011-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1024120211011-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1024120211011-3Excavator - 30 ton- After Jan 105692.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1024120211011-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting1024020211010-5Operator - Principle - After Jan 10272025INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5L.O.A.3630 | Corbiere and Sons Contracting1024020211010-5L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1024020211010-5Rock Truck - 30 Ton- After Jan 1081104.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1024020211010-5Light Truck - Pick up- After Jan 102487.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 16 | HR | 9.16 | 0 |  |  | 195.36 | 25.3968 | 220.7568 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Excavator Thumb - 30 - 50 ton- After Jan 1016195.36 | Corbiere and Sons Contracting1024020211010-5Excavator Thumb - 30 - 50 ton- After Jan 1016195.36INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1024020211010-5Excavator - 36 ton- After Jan 1081175.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting1024020211010-5Excavator - 30 ton- After Jan 1081107.6INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10238 | 20211010-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023820211010-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1023820211010-3Operator - Principle - After Jan 105375INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10238 | 20211010-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023820211010-3Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting1023820211010-3Excavator - 36 ton- After Jan 102293.92INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10238 | 20211010-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023820211010-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1023820211010-3Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1023620211009-8Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8L.O.A.1210 | Corbiere and Sons Contracting1023620211009-8L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1023620211009-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1023620211009-8Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1023520211009-7Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Foreman4380 | Corbiere and Sons Contracting1023520211009-7Foreman4380INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5.5 | Dynamic | 103.54 | 0 |  |  | 759.275 | 98.7057 | 857.9807 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Rock Truck - 30 Ton- After Jan 105.5759.275 | Corbiere and Sons Contracting1023520211009-7Rock Truck - 30 Ton- After Jan 105.5759.275INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1023520211009-7Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1023520211009-7Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1023520211009-7Dozer D6 or equal- After Jan 104525.92INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1023220211009-4Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4L.O.A.2420 | Corbiere and Sons Contracting1023220211009-4L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting1023220211009-4Rock Truck - 30 Ton- After Jan 105690.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1023220211009-4Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1023220211009-4Excavator - 36 ton- After Jan 105734.8INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10231 | 20211009-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Mink Creek - Building a diversion at shoefly for C246 | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023120211009-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1023120211009-3Operator - Principle - After Jan 109675INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10231 | 20211009-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Mink Creek - Building a diversion at shoefly for C246 | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023120211009-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1023120211009-3Excavator - 36 ton- After Jan 105734.8INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10231 | 20211009-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Mink Creek - Building a diversion at shoefly for C246 | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023120211009-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1023120211009-3Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting1022520211008-7Operator - Principle - After Jan 1014.51087.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7L.O.A.2420 | Corbiere and Sons Contracting1022520211008-7L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting1022520211008-7Rock Truck - 30 Ton- After Jan 105690.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting1022520211008-7Excavator - 30 ton- After Jan 107.51038.375INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1022320211008-5Operator - Principle - After Jan 10241800INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5L.O.A.1210 | Corbiere and Sons Contracting1022320211008-5L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting1022320211008-5Rock Truck - 30 Ton- After Jan 106828.3INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 14 | HR | 9.16 | 0 |  |  | 170.94 | 22.2222 | 193.1622 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Excavator Thumb - 30 - 50 ton- After Jan 1014170.94 | Corbiere and Sons Contracting1022320211008-5Excavator Thumb - 30 - 50 ton- After Jan 1014170.94INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1022320211008-5Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting1022320211008-5Excavator - 30 ton- After Jan 103415.35INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1022320211008-5Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1022920211008-11Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11L.O.A.3630 | Corbiere and Sons Contracting1022920211008-11L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1022920211008-11Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1022920211008-11Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1022920211008-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 108600INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 105375INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1022820211008-10Excavator - 36 ton- After Jan 105734.8INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1022820211008-10Dozer D6 or equal- After Jan 107920.36INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1021820211007-9Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9L.O.A.2420 | Corbiere and Sons Contracting1021820211007-9L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5.5 | Dynamic | 103.54 | 0 |  |  | 759.275 | 98.7057 | 857.9807 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9Rock Truck - 30 Ton- After Jan 105.5759.275 | Corbiere and Sons Contracting1021820211007-9Rock Truck - 30 Ton- After Jan 105.5759.275INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9918 | 860.4667 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting1021820211007-9Excavator - 30 ton- After Jan 105.5761.475INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1021720211007-8Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8L.O.A.3630 | Corbiere and Sons Contracting1021720211007-8L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1021720211007-8Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1021720211007-8Light Truck - Pick up- After Jan 102487.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1021720211007-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1021620211007-7Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7L.O.A.1210 | Corbiere and Sons Contracting1021620211007-7L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1021620211007-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1021620211007-7Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1021920211007-10Labourer - General - After Jan 106360INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1021920211007-10Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10L.O.A.4840 | Corbiere and Sons Contracting1021920211007-10L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Foreman6570 | Corbiere and Sons Contracting1021920211007-10Foreman6570INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1021920211007-10Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Labourer - General - After Jan 109540 | Corbiere and Sons Contracting1021020211006-9Labourer - General - After Jan 109540INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29 | HR |  |  | 75 | 0 | 2175 | 282.75 | 2457.75 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Operator - Principle - After Jan 10292175 | Corbiere and Sons Contracting1021020211006-9Operator - Principle - After Jan 10292175INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9L.O.A.51050 | Corbiere and Sons Contracting1021020211006-9L.O.A.51050INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Foreman8760 | Corbiere and Sons Contracting1021020211006-9Foreman8760INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting1021020211006-9Rock Truck - 30 Ton- After Jan 1091242.45INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1021020211006-9Light Truck - Pick up- After Jan 104975INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1021020211006-9Excavator - 36 ton- After Jan 1091322.64INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1021020211006-9Dozer D6 or equal- After Jan 1081051.84INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 19 | HR |  |  | 60 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Labourer - General - After Jan 10191140 | Corbiere and Sons Contracting1020620211006-5Labourer - General - After Jan 10191140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 71 | HR |  |  | 75 | 0 | 5325 | 692.25 | 6017.25 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Operator - Principle - After Jan 10715325 | Corbiere and Sons Contracting1020620211006-5Operator - Principle - After Jan 10715325INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5L.O.A.91890 | Corbiere and Sons Contracting1020620211006-5L.O.A.91890INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Foreman8760 | Corbiere and Sons Contracting1020620211006-5Foreman8760INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 | 0 |  |  | 2070.75 | 269.1975 | 2339.9475 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting1020620211006-5Rock Truck - 30 Ton- After Jan 10152070.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1020620211006-5Light Truck - Pick up- After Jan 1051218.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1020620211006-5ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1020620211006-5Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 1071028.72INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1020620211006-5Excavator - 30 ton- After Jan 10121661.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting1020520211006-4Operator - Principle - After Jan 10141050INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4L.O.A.2420 | Corbiere and Sons Contracting1020520211006-4L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Foreman5475 | Corbiere and Sons Contracting1020520211006-4Foreman5475INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1020520211006-4Tractor Trailer - 60 Ton- After Jan 105611.95INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting1020520211006-4Rock Truck - 30 Ton- After Jan 106828.3INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1020520211006-4Excavator - 30 ton- After Jan 106830.7INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1020420211006-3Operator - Principle - After Jan 1010750INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3L.O.A.1210 | Corbiere and Sons Contracting1020420211006-3L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1020420211006-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1020420211006-3Excavator - 36 ton- After Jan 1091322.64INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting1021120211006-10Operator - Principle - After Jan 10302250INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10L.O.A.3630 | Corbiere and Sons Contracting1021120211006-10L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1021120211006-10Rock Truck - 30 Ton- After Jan 1081104.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1021120211006-10Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1021120211006-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 10101469.6INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 1081175.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10196 | 20211005-6 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019620211005-6Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1019620211005-6Operator - Principle - After Jan 107525INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10196 | 20211005-6 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019620211005-6L.O.A.1210 | Corbiere and Sons Contracting1019620211005-6L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10196 | 20211005-6 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019620211005-6Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1019620211005-6Excavator - 30 ton- After Jan 106830.7INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1019320211005-3-R1Labourer - General - After Jan 1012720INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1011.5805INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 93.5 | HR |  |  | 70 | 0 | 6545 | 850.85 | 7395.85 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1093.56545 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1093.56545INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1L.O.A.102100 | Corbiere and Sons Contracting1019320211005-3-R1L.O.A.102100INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1019320211005-3-R1Light Truck - Pick up- After Jan 101243.75INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 11.5 | Dynamic | 41.4 | 0 |  |  | 634.8 | 82.524 | 717.324 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1011.5634.8 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1011.5634.8INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 93.5 | Dynamic | 41.4 | 0 |  |  | 5161.2 | 670.956 | 5832.156 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1093.55161.2 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1093.55161.2INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10202 | 20211005-12 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020220211005-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1020220211005-12Operator - Principle - After Jan 1012900INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10202 | 20211005-12 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020220211005-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1020220211005-12Rock Truck - 30 Ton- After Jan 10111518.55INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10562 | 20211122-3 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 9.5 | HR |  |  | 70 | 0 | 665 | 86.45 | 751.45 | 2021-11-22 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 15 swamp mats to Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056220211122-3Driver - AZ - After Jan 109.5665 | Corbiere and Sons Contracting1056220211122-3Driver - AZ - After Jan 109.5665INV #155 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10562 | 20211122-3 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-22 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 15 swamp mats to Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056220211122-3L.O.A.1210 | Corbiere and Sons Contracting1056220211122-3L.O.A.1210INV #155 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10562 | 20211122-3 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9.5 | Dynamic | 91.79 | 0 |  |  | 1162.705 | 151.1516 | 1313.8566 | 2021-11-22 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 15 swamp mats to Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056220211122-3Tractor Trailer - 60 Ton- After Jan 109.51162.705 | Corbiere and Sons Contracting1056220211122-3Tractor Trailer - 60 Ton- After Jan 109.51162.705INV #155 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1033520211026-3Operator - Principle - After Jan 109675INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3L.O.A.1210 | Corbiere and Sons Contracting1033520211026-3L.O.A.1210INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1033520211026-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Dump - Tandum- After Jan 10 | 51.78 | 5 | Dynamic | 38.84 | 0 |  |  | 258.9 | 33.657 | 292.557 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Dump - Tandum- After Jan 105258.9 | Corbiere and Sons Contracting1033520211026-3Dump - Tandum- After Jan 105258.9INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1033520211026-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1033520211026-3Excavator - 36 ton- After Jan 1081175.68INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1033020211024-3Operator - Principle - After Jan 1011825INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3L.O.A.1210 | Corbiere and Sons Contracting1033020211024-3L.O.A.1210INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1033020211024-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1033020211024-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1033020211024-3Excavator - 36 ton- After Jan 10101469.6INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1032820211023-3Operator - Principle - After Jan 1011825INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3L.O.A.1210 | Corbiere and Sons Contracting1032820211023-3L.O.A.1210INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1032820211023-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting1032820211023-3Excavator Hammer - 30 - 50 ton- After Jan 106380.28INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1032820211023-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1032820211023-3Excavator - 36 ton- After Jan 10101469.6INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1029820211020-3Operator - Principle - After Jan 105.5412.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Foreman | 95 | 5.5 | HR |  |  | 95 | 0 | 522.5 | 67.925 | 590.425 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Foreman5.5522.5 | Corbiere and Sons Contracting1029820211020-3Foreman5.5522.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1029820211020-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting1029820211020-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1029820211020-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1029820211020-3Excavator - 36 ton- After Jan 105734.8INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1029820211020-3Excavator - 30 ton- After Jan 105692.25INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1029420211019-3Operator - Principle - After Jan 1012900INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3L.O.A.2420 | Corbiere and Sons Contracting1029420211019-3L.O.A.2420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting1029420211019-3Rock Truck - 30 Ton- After Jan 105690.25INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1029420211019-3Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1029420211019-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1029420211019-3Excavator - 36 ton- After Jan 103440.88INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1029420211019-3Dozer D6 or equal- After Jan 103394.44INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1029220211018-3Operator - Principle - After Jan 10241800INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3L.O.A.2420 | Corbiere and Sons Contracting1029220211018-3L.O.A.2420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Foreman4380 | Corbiere and Sons Contracting1029220211018-3Foreman4380INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1029220211018-3Rock Truck - 30 Ton- After Jan 10111518.55INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1029220211018-3Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1029220211018-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting1029220211018-3Excavator - 36 ton- After Jan 106881.76INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1029220211018-3Dozer D6 or equal- After Jan 105657.4INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34 | HR |  |  | 75 | 0 | 2550 | 331.5 | 2881.5 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Operator - Principle - After Jan 10342550 | Corbiere and Sons Contracting1028920211017-3Operator - Principle - After Jan 10342550INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3L.O.A.3630 | Corbiere and Sons Contracting1028920211017-3L.O.A.3630INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Foreman4380 | Corbiere and Sons Contracting1028920211017-3Foreman4380INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1028920211017-3Rock Truck - 30 Ton- After Jan 10111518.55INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1028920211017-3Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1028920211017-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1028920211017-3Excavator - 36 ton- After Jan 1091322.64INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1028920211017-3Dozer D6 or equal- After Jan 10111446.28INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1028720211016-4Driver - AZ - After Jan 106420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1028720211016-4Operator - Principle - After Jan 10241800INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4L.O.A.2420 | Corbiere and Sons Contracting1028720211016-4L.O.A.2420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Foreman4380 | Corbiere and Sons Contracting1028720211016-4Foreman4380INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1028720211016-4Rock Truck - 30 Ton- After Jan 10111518.55INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1028720211016-4Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1028720211016-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1028720211016-4Excavator - 36 ton- After Jan 10111616.56INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1028720211016-4Dozer D6 or equal- After Jan 106788.88INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1056420211123-3Operator - Principle - After Jan 1011825INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3L.O.A.1210 | Corbiere and Sons Contracting1056420211123-3L.O.A.1210INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1056420211123-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1056420211123-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1056420211123-3Excavator - 36 ton- After Jan 10101469.6INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11033 | 20220111-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked 350 Ex out of Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103320220111-9Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1103320220111-9Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11033 | 20220111-9 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked 350 Ex out of Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103320220111-9Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1103320220111-9Excavator - 36 ton- After Jan 101146.96INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1103220220111-8Driver - AZ - After Jan 105.5385INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1103220220111-8Operator - Principle - After Jan 108600INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8L.O.A.1210 | Corbiere and Sons Contracting1103220220111-8L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6538 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1103220220111-8Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1103220220111-8Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting1103220220111-8Dozer D6 or equal- After Jan 105.5723.14INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1102320220110-9Driver - AZ - After Jan 105350INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1102320220110-9Operator - Principle - After Jan 109675INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9L.O.A.1210 | Corbiere and Sons Contracting1102320220110-9L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1102320220110-9Tractor Trailer - 60 Ton- After Jan 105611.95INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1102320220110-9Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1102320220110-9Dozer D6 or equal- After Jan 105657.4INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11026 | 20220110-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102620220110-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1102620220110-12Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11026 | 20220110-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102620220110-12Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102620220110-12Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11025 | 20220110-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102520220110-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1102520220110-11Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11025 | 20220110-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102520220110-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102520220110-11Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11024 | 20220110-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102420220110-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1102420220110-10Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11024 | 20220110-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102420220110-10L.O.A.1210 | Corbiere and Sons Contracting1102420220110-10L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11024 | 20220110-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102420220110-10Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102420220110-10Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11012 | 20220109-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101220220109-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101220220109-9Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11012 | 20220109-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101220220109-9Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1101220220109-9Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11011 | 20220109-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101120220109-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101120220109-8Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11011 | 20220109-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101120220109-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1101120220109-8Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11016 | 20220109-13 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbing 336 Ex from Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101620220109-13Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1101620220109-13Driver - AZ - After Jan 10221540INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11016 | 20220109-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbing 336 Ex from Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101620220109-13L.O.A.1210 | Corbiere and Sons Contracting1101620220109-13L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11016 | 20220109-13 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbing 336 Ex from Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101620220109-13Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1101620220109-13Tractor Trailer - 60 Ton- After Jan 10222692.58INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11014 | 20220109-11 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 0 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C236 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101420220109-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1101420220109-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101320220109-10Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10L.O.A.1210 | Corbiere and Sons Contracting1101320220109-10L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1101320220109-10Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1101320220109-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting1101320220109-10Excavator - 30 ton- After Jan 103415.35INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1100520220108-7Operator - Principle - After Jan 105375INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7L.O.A.1210 | Corbiere and Sons Contracting1100520220108-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100520220108-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1100520220108-7Excavator - 30 ton- After Jan 105692.25INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099920220107-7Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7L.O.A.1210 | Corbiere and Sons Contracting1099920220107-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099920220107-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1099920220107-7Dozer D6 or equal- After Jan 10101314.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1099420220106-7Driver - AZ - After Jan 108560INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099420220106-7Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7L.O.A.2420 | Corbiere and Sons Contracting1099420220106-7L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1099420220106-7Tractor Trailer - 60 Ton- After Jan 108979.12INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099420220106-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1099420220106-7Dozer D6 or equal- After Jan 105657.4INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10989 | 20220105-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098920220105-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1098920220105-8Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10989 | 20220105-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098920220105-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1098920220105-8Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10988 | 20220105-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities for C129 | 6 | C129 | Lake B | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098820220105-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1098820220105-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10988 | 20220105-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities for C129 | 6 | C129 | Lake B | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098820220105-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1098820220105-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10980 | 20220103-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098020220103-8Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1098020220103-8Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10980 | 20220103-8 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098020220103-8Pickup w/ plow3150 | Corbiere and Sons Contracting1098020220103-8Pickup w/ plow3150INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7L.O.A.1210 | Corbiere and Sons Contracting1097920220103-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097920220103-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1097920220103-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1097920220103-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 1 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1097920220103-7Excavator - 36 ton- After Jan 1091322.64INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10969 | 20220102-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096920220102-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1096920220102-9Operator - Principle - After Jan 106450INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10969 | 20220102-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096920220102-9L.O.A.1210 | Corbiere and Sons Contracting1096920220102-9L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10969 | 20220102-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096920220102-9Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1096920220102-9Pickup w/ plow and sander6480INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1096820220102-8Operator - Principle - After Jan 105375INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8L.O.A.1210 | Corbiere and Sons Contracting1096820220102-8L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1096820220102-8Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1096820220102-8Excavator - 36 ton- After Jan 101146.96INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1096720220102-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1096720220102-7Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 1 | Dynamic | 163.13 | 0 |  |  | 217.5 | 28.275 | 245.775 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Dozer D8 or equal- After Jan 101217.5 | Corbiere and Sons Contracting1096720220102-7Dozer D8 or equal- After Jan 101217.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10974 | 20220102-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097420220102-14Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1097420220102-14Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10974 | 20220102-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097420220102-14Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1097420220102-14Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10973 | 20220102-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097320220102-13Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1097320220102-13Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10973 | 20220102-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097320220102-13Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097320220102-13Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10972 | 20220102-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onNeys | 6 | C219-C235 | Neys | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097220220102-12Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1097220220102-12Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10972 | 20220102-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onNeys | 6 | C219-C235 | Neys | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097220220102-12Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097220220102-12Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10971 | 20220102-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097120220102-11Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1097120220102-11Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10971 | 20220102-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097120220102-11L.O.A.1210 | Corbiere and Sons Contracting1097120220102-11L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10971 | 20220102-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097120220102-11Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097120220102-11Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10970 | 20220102-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del West | 6 | C186-C190 | Del Lake West | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097020220102-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1097020220102-10Operator - Principle - After Jan 106450INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10970 | 20220102-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del West | 6 | C186-C190 | Del Lake West | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097020220102-10Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1097020220102-10Pickup w/ plow and sander6480INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1095920220101-9Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095920220101-9Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9L.O.A.1210 | Corbiere and Sons Contracting1095920220101-9L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10958 | 20220101-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095820220101-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095820220101-8Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10958 | 20220101-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095820220101-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095820220101-8Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10957 | 20220101-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095720220101-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095720220101-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10957 | 20220101-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095720220101-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095720220101-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5L.O.A.2420 | Corbiere and Sons Contracting1095520220101-5L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095520220101-5Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1095520220101-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1095520220101-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10962 | 20220101-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Jackfish | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096220220101-12Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1096220220101-12Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10962 | 20220101-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Jackfish | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096220220101-12Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1096220220101-12Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10961 | 20220101-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096120220101-11Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1096120220101-11Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10961 | 20220101-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096120220101-11Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1096120220101-11Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10960 | 20220101-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096020220101-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1096020220101-10Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10960 | 20220101-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096020220101-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1096020220101-10Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10950 | 20211231-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 0 | 0 | 75 | 9.75 | 84.75 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C214 | 6 | C214 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095020211231-9Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1095020211231-9Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10950 | 20211231-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 1 |  | 0 | 0 |  |  | 80 | 10.4 | 90.4 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C214 | 6 | C214 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095020211231-9Pickup w/ plow and sander180 | Corbiere and Sons Contracting1095020211231-9Pickup w/ plow and sander180INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10949 | 20211231-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094920211231-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1094920211231-8Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10949 | 20211231-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094920211231-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1094920211231-8Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10948 | 20211231-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Mink Creek | 6 | C237-C247 | Mink Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094820211231-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1094820211231-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10948 | 20211231-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Mink Creek | 6 | C237-C247 | Mink Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094820211231-7L.O.A.1210 | Corbiere and Sons Contracting1094820211231-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10948 | 20211231-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Mink Creek | 6 | C237-C247 | Mink Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094820211231-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1094820211231-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1094720211231-6Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6L.O.A.1210 | Corbiere and Sons Contracting1094720211231-6L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1094720211231-6Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1094720211231-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10952 | 20211231-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Hare Lake Road | 6 | C257-C267 | Hare Lake Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095220211231-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1095220211231-11Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10952 | 20211231-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Hare Lake Road | 6 | C257-C267 | Hare Lake Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095220211231-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1095220211231-11Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10951 | 20211231-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 0 | 0 | 75 | 9.75 | 84.75 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C217 | 6 | C217 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095120211231-10Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1095120211231-10Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10951 | 20211231-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 1 |  | 0 | 0 |  |  | 80 | 10.4 | 90.4 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C217 | 6 | C217 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095120211231-10Pickup w/ plow and sander180 | Corbiere and Sons Contracting1095120211231-10Pickup w/ plow and sander180INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10943 | 20211230-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 0 | 0 | 150 | 19.5 | 169.5 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094320211230-8Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1094320211230-8Operator - Principle - After Jan 102150INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10943 | 20211230-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094320211230-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1094320211230-8Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10942 | 20211230-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 0 | 0 | 150 | 19.5 | 169.5 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094220211230-7Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1094220211230-7Operator - Principle - After Jan 102150INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10942 | 20211230-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094220211230-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1094220211230-7Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10941 | 20211230-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094120211230-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1094120211230-6Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10941 | 20211230-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094120211230-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1094120211230-6Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 106450INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093620211229-6Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 3 | Dynamic | 163.13 | 0 |  |  | 652.5 | 84.825 | 737.325 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Dozer D8 or equal- After Jan 103652.5 | Corbiere and Sons Contracting1093620211229-6Dozer D8 or equal- After Jan 103652.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10932 | 20211228-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093220211228-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1093220211228-6Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10932 | 20211228-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093220211228-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093220211228-6Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10931 | 20211228-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093120211228-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1093120211228-5Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10931 | 20211228-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093120211228-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093120211228-5Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1092720211219-6Labourer - General - After Jan 1011660INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6L.O.A.2420 | Corbiere and Sons Contracting1092720211219-6L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6Foreman6570 | Corbiere and Sons Contracting1092720211219-6Foreman6570INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092720211219-6Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1092620211219-5Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5L.O.A.1210 | Corbiere and Sons Contracting1092620211219-5L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092620211219-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1092620211219-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1092620211219-5Excavator - 36 ton- After Jan 10101469.6INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1092320211218-7Labourer - General - After Jan 106360INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1092320211218-7Driver - AZ - After Jan 10221540INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7L.O.A.2420 | Corbiere and Sons Contracting1092320211218-7L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1092320211218-7Tractor Trailer - 60 Ton- After Jan 10222692.58INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092320211218-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10922 | 20211218-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092220211218-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1092220211218-6Operator - Principle - After Jan 105.5412.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10922 | 20211218-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092220211218-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1092220211218-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10922 | 20211218-6 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092220211218-6Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1092220211218-6Excavator - 36 ton- After Jan 105734.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1092120211218-5Operator - Principle - After Jan 105.5412.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5L.O.A.1210 | Corbiere and Sons Contracting1092120211218-5L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092120211218-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 0 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1092120211218-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 0 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1092120211218-5Excavator - 36 ton- After Jan 105734.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1091720211217-5Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5L.O.A.1210 | Corbiere and Sons Contracting1091720211217-5L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091720211217-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1091720211217-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1091720211217-5Excavator - 36 ton- After Jan 1081175.68INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10911 | 20211216-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-16 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091120211216-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1091120211216-6Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10911 | 20211216-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-16 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091120211216-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1091120211216-6Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10904 | 20211215-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-15 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090420211215-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1090420211215-6Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10904 | 20211215-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-15 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090420211215-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1090420211215-6Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10886 | 20211212-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088620211212-14Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1088620211212-14Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10886 | 20211212-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088620211212-14Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1088620211212-14Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10885 | 20211212-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088520211212-13Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1088520211212-13Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10885 | 20211212-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088520211212-13Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1088520211212-13Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10884 | 20211212-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C186 - C195 | Del Lake West | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088420211212-12Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1088420211212-12Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10884 | 20211212-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C186 - C195 | Del Lake West | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088420211212-12Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1088420211212-12Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10883 | 20211212-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088320211212-11Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1088320211212-11Operator - Intermdiate - After Jan 104280INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10883 | 20211212-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088320211212-11L.O.A.1210 | Corbiere and Sons Contracting1088320211212-11L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10883 | 20211212-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088320211212-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1088320211212-11Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10772 | 20211211-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 34.125 | 296.625 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing snow towards WC603 | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077220211211-9Operator - Principle - After Jan 103.5262.5 | Corbiere and Sons Contracting1077220211211-9Operator - Principle - After Jan 103.5262.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10772 | 20211211-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing snow towards WC603 | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077220211211-9Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting1077220211211-9Dozer D6 or equal- After Jan 103.5460.18INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10778 | 20211211-15 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077820211211-15Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1077820211211-15Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10778 | 20211211-15 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077820211211-15Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1077820211211-15Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10777 | 20211211-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C190 | Del Lake West | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077720211211-14Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1077720211211-14Operator - Intermdiate - After Jan 104280INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10777 | 20211211-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C190 | Del Lake West | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077720211211-14Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1077720211211-14Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10776 | 20211211-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077620211211-13Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1077620211211-13Operator - Intermdiate - After Jan 104280INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10776 | 20211211-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077620211211-13L.O.A.1210 | Corbiere and Sons Contracting1077620211211-13L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10776 | 20211211-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077620211211-13Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1077620211211-13Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10644 | 20211201-6-R1 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1914 | Unit |  |  |  |  | 1914 | 248.82 | 2162.82 | 2021-12-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Mike disputed and had hours reduced |  | Approved |  |  | Float went to North Shore pit to get mats, turned around after it was cancelled and went back to Dorion to mobilize fuel Buggy | 6 | C130-C277 | WF6 | 0 | 2021-12-08 |  | 36 | 2022-01-06 | 347 |  |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1064420211201-6-R13rd Party Charges19141914 | Corbiere and Sons Contracting1064420211201-6-R13rd Party Charges19141914INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1152720220213-8Operator - Intermdiate - After Jan 1011770INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1152720220213-8Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8L.O.A.1210 | Corbiere and Sons Contracting1152720220213-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1152720220213-8Pickup w/ plow and sander11880INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1152720220213-8Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1152420220213-5Operator - Principle - After Jan 107525INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5L.O.A.1210 | Corbiere and Sons Contracting1152420220213-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152420220213-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1152420220213-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1152320220213-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4L.O.A.1210 | Corbiere and Sons Contracting1152320220213-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152320220213-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1152320220213-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1152220220213-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3L.O.A.1210 | Corbiere and Sons Contracting1152220220213-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152220220213-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1152220220213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11519 | 20220212-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151920220212-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1151920220212-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11519 | 20220212-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151920220212-6L.O.A.1210 | Corbiere and Sons Contracting1151920220212-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11519 | 20220212-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151920220212-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1151920220212-6Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151820220212-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5L.O.A.1210 | Corbiere and Sons Contracting1151820220212-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151820220212-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1151820220212-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1151720220212-4Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4L.O.A.1210 | Corbiere and Sons Contracting1151720220212-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151720220212-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1151720220212-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151620220212-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3L.O.A.1210 | Corbiere and Sons Contracting1151620220212-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151620220212-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151620220212-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11513 | 20220211-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151320220211-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1151320220211-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11513 | 20220211-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151320220211-6L.O.A.1210 | Corbiere and Sons Contracting1151320220211-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11513 | 20220211-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151320220211-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1151320220211-6Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151220220211-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5L.O.A.1210 | Corbiere and Sons Contracting1151220220211-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151220220211-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151220220211-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151120220211-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4L.O.A.1210 | Corbiere and Sons Contracting1151120220211-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151120220211-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151120220211-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151020220211-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3L.O.A.1210 | Corbiere and Sons Contracting1151020220211-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151020220211-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151020220211-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11507 | 20220210-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150720220210-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1150720220210-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11507 | 20220210-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150720220210-6L.O.A.1210 | Corbiere and Sons Contracting1150720220210-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11507 | 20220210-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150720220210-6Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1150720220210-6Pickup w/ plow and sander10800INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150520220210-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5L.O.A.1210 | Corbiere and Sons Contracting1150520220210-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150520220210-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1150520220210-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150420220210-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4L.O.A.1210 | Corbiere and Sons Contracting1150420220210-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150420220210-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1150420220210-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150320220210-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3L.O.A.1210 | Corbiere and Sons Contracting1150320220210-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150320220210-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1150320220210-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 0 | 0 | 37.5 | 4.875 | 42.375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 100.537.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7L.O.A.1210 | Corbiere and Sons Contracting1150020220209-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1150020220209-7Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 75 | 0 | 37.5 | 4.875 | 42.375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 100.537.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 1010750INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6L.O.A.1210 | Corbiere and Sons Contracting1149920220209-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Light Truck - 1 to 3 Ton- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Light Truck - 1 to 3 Ton- After Jan 101243.75 | Corbiere and Sons Contracting1149920220209-6Light Truck - 1 to 3 Ton- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting1149920220209-6Dozer D6 or equal- After Jan 107.5986.1INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149820220209-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5L.O.A.1210 | Corbiere and Sons Contracting1149820220209-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149820220209-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149820220209-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1149720220209-4Driver - AZ - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149720220209-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4L.O.A.2420 | Corbiere and Sons Contracting1149720220209-4L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1149720220209-4Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149720220209-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149720220209-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149620220209-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3L.O.A.1210 | Corbiere and Sons Contracting1149620220209-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149620220209-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149620220209-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1149420220208-7Driver - AZ - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149420220208-7Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7L.O.A.1210 | Corbiere and Sons Contracting1149420220208-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1149420220208-7Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149420220208-7Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1149420220208-7Dozer D6 or equal- After Jan 1091183.32INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1149320220208-6Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6L.O.A.1210 | Corbiere and Sons Contracting1149320220208-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149320220208-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1149320220208-6Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5L.O.A.2420 | Corbiere and Sons Contracting1149220220208-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1149220220208-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149220220208-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149220220208-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3.5 | HR |  |  | 70 | 0 | 245 | 31.85 | 276.85 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Driver - AZ - After Jan 103.5245 | Corbiere and Sons Contracting1149120220208-4Driver - AZ - After Jan 103.5245INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1149120220208-4Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4L.O.A.1210 | Corbiere and Sons Contracting1149120220208-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3.5 | Dynamic | 91.79 | 0 |  |  | 428.365 | 55.6875 | 484.0524 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Tractor Trailer - 60 Ton- After Jan 103.5428.365 | Corbiere and Sons Contracting1149120220208-4Tractor Trailer - 60 Ton- After Jan 103.5428.365INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1149120220208-4Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1149020220208-3Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3L.O.A.1210 | Corbiere and Sons Contracting1149020220208-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149020220208-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1149020220208-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5L.O.A.3630 | Corbiere and Sons Contracting1148820220207-5L.O.A.3630INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1148820220207-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1148820220207-5Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1148820220207-5Dozer D6 or equal- After Jan 1091183.32INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148720220207-4Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4L.O.A.1210 | Corbiere and Sons Contracting1148720220207-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148720220207-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1148720220207-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148620220207-3Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3L.O.A.1210 | Corbiere and Sons Contracting1148620220207-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148620220207-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1148620220207-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1148420220206-7Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 108600INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7L.O.A.1210 | Corbiere and Sons Contracting1148420220206-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1148420220206-7Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148420220206-7Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1148420220206-7Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1148420220206-7Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11482 | 20220206-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148220220206-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148220220206-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11482 | 20220206-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148220220206-5L.O.A.1210 | Corbiere and Sons Contracting1148220220206-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11482 | 20220206-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148220220206-5Pickup w/ plow and sander8640 | Corbiere and Sons Contracting1148220220206-5Pickup w/ plow and sander8640INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148120220206-4Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4L.O.A.1210 | Corbiere and Sons Contracting1148120220206-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148120220206-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1148120220206-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1148020220206-3Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting1148020220206-3Operator - Principle - After Jan 10141050INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3L.O.A.2420 | Corbiere and Sons Contracting1148020220206-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1148020220206-3Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148020220206-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1148020220206-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11477 | 20220205-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147720220205-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1147720220205-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11477 | 20220205-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147720220205-5L.O.A.1210 | Corbiere and Sons Contracting1147720220205-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11477 | 20220205-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147720220205-5Pickup w/ plow and sander8640 | Corbiere and Sons Contracting1147720220205-5Pickup w/ plow and sander8640INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1147620220205-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4L.O.A.1210 | Corbiere and Sons Contracting1147620220205-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147620220205-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1147620220205-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 0 | 0 | 350 | 45.5 | 395.5 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1147520220205-3Driver - AZ - After Jan 105350INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1147520220205-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3L.O.A.2420 | Corbiere and Sons Contracting1147520220205-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 0 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1147520220205-3Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147520220205-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1147520220205-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1147220220204-6Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6L.O.A.1210 | Corbiere and Sons Contracting1147220220204-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147220220204-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1147220220204-6Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11471 | 20220204-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147120220204-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1147120220204-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11471 | 20220204-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147120220204-5L.O.A.1210 | Corbiere and Sons Contracting1147120220204-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11471 | 20220204-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147120220204-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1147120220204-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1147020220204-4Operator - Principle - After Jan 1010750INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4L.O.A.1210 | Corbiere and Sons Contracting1147020220204-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147020220204-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1147020220204-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1146920220204-3Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146920220204-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3L.O.A.2420 | Corbiere and Sons Contracting1146920220204-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1146920220204-3Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146920220204-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1146920220204-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146720220203-6Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6L.O.A.1210 | Corbiere and Sons Contracting1146720220203-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146720220203-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1146720220203-6Dozer D6 or equal- After Jan 1091183.32INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11466 | 20220203-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146620220203-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1146620220203-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11466 | 20220203-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146620220203-5L.O.A.1210 | Corbiere and Sons Contracting1146620220203-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11466 | 20220203-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146620220203-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1146620220203-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146520220203-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4L.O.A.1210 | Corbiere and Sons Contracting1146520220203-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146520220203-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1146520220203-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1146420220203-3Driver - AZ - After Jan 106420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1146420220203-3Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3L.O.A.2420 | Corbiere and Sons Contracting1146420220203-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 0 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1146420220203-3Tractor Trailer - 60 Ton- After Jan 106734.34INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146420220203-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting1146420220203-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1146120220202-9Driver - AZ - After Jan 108560INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1146120220202-9Operator - Principle - After Jan 108600INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9L.O.A.1210 | Corbiere and Sons Contracting1146120220202-9L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1146120220202-9Tractor Trailer - 60 Ton- After Jan 108979.12INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1146120220202-9Dozer D6 or equal- After Jan 106788.88INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1146020220202-8Operator - Principle - After Jan 103225INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8L.O.A.1210 | Corbiere and Sons Contracting1146020220202-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146020220202-8Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1146020220202-8Dozer D6 or equal- After Jan 103394.44INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11459 | 20220202-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145920220202-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1145920220202-7Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11459 | 20220202-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145920220202-7L.O.A.1210 | Corbiere and Sons Contracting1145920220202-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11459 | 20220202-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145920220202-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1145920220202-7Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1145820220202-6Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6L.O.A.1210 | Corbiere and Sons Contracting1145820220202-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1145820220202-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1145820220202-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1145620220202-4Operator - Principle - After Jan 103225INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4L.O.A.1210 | Corbiere and Sons Contracting1145620220202-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1145620220202-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 0 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1145620220202-4Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1145520220202-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3L.O.A.1210 | Corbiere and Sons Contracting1145520220202-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1145520220202-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1145520220202-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11452 | 20220201-9 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 53.35 | Unit |  |  |  |  | 53.35 | 6.9355 | 60.2855 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sand provided by Valentino | 6 | C129-D005 | WF6 | 0 | 2022-02-13 |  | 36 | 2022-02-16 | 418 | Winter road sand |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1145220220201-93rd Party Charges53.3553.35 | Corbiere and Sons Contracting1145220220201-93rd Party Charges53.3553.35INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11451 | 20220201-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float moved Dozer from Jackpine to Culvert Creek | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145120220201-8Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1145120220201-8Driver - AZ - After Jan 105350INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11451 | 20220201-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float moved Dozer from Jackpine to Culvert Creek | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145120220201-8Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1145120220201-8Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11448 | 20220201-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144820220201-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1144820220201-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11448 | 20220201-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144820220201-6L.O.A.1210 | Corbiere and Sons Contracting1144820220201-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11448 | 20220201-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144820220201-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1144820220201-6Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144720220201-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5L.O.A.1210 | Corbiere and Sons Contracting1144720220201-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144720220201-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144720220201-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144620220201-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4L.O.A.1210 | Corbiere and Sons Contracting1144620220201-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144620220201-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144620220201-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144520220201-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3L.O.A.1210 | Corbiere and Sons Contracting1144520220201-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144520220201-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144520220201-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5L.O.A.2420 | Corbiere and Sons Contracting1144320220131-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1144320220131-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144320220131-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144320220131-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144220220131-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4L.O.A.1210 | Corbiere and Sons Contracting1144220220131-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144220220131-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144220220131-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11439 | 20220130-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143920220130-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1143920220130-6Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11439 | 20220130-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143920220130-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143920220130-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11439 | 20220130-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143920220130-6Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1143920220130-6Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5L.O.A.2420 | Corbiere and Sons Contracting1143820220130-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1143820220130-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143820220130-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1143820220130-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 0 | 0 | 675 | 87.75 | 762.75 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1143720220130-4Operator - Principle - After Jan 109675INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4L.O.A.1210 | Corbiere and Sons Contracting1143720220130-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143720220130-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1143720220130-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1143620220130-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3L.O.A.1210 | Corbiere and Sons Contracting1143620220130-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143620220130-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1143620220130-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11434 | 20220129-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143420220129-8Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1143420220129-8Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11434 | 20220129-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143420220129-8L.O.A.1210 | Corbiere and Sons Contracting1143420220129-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11434 | 20220129-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143420220129-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1143420220129-8Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1143320220129-7Driver - AZ - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1143320220129-7Operator - Principle - After Jan 105.5412.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6538 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1143320220129-7Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 0 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting1143320220129-7Dozer D6 or equal- After Jan 104.5591.66INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1141620220129-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5L.O.A.1210 | Corbiere and Sons Contracting1141620220129-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141620220129-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1141620220129-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1141520220129-4Driver - AZ - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1141520220129-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4L.O.A.2420 | Corbiere and Sons Contracting1141520220129-4L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6538 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1141520220129-4Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141520220129-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1141520220129-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1141420220129-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3L.O.A.1210 | Corbiere and Sons Contracting1141420220129-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141420220129-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1141420220129-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11296 | 20220128-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129620220128-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1129620220128-7Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11296 | 20220128-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129620220128-7L.O.A.1210 | Corbiere and Sons Contracting1129620220128-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11296 | 20220128-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129620220128-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1129620220128-7Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1129420220128-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5L.O.A.1210 | Corbiere and Sons Contracting1129420220128-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1129420220128-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1129420220128-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1129220220128-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3L.O.A.1210 | Corbiere and Sons Contracting1129220220128-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1129220220128-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1129220220128-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11290 | 20220127-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129020220127-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1129020220127-9Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11290 | 20220127-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129020220127-9Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1129020220127-9Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11289 | 20220127-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128920220127-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1128920220127-8Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11289 | 20220127-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128920220127-8L.O.A.1210 | Corbiere and Sons Contracting1128920220127-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11289 | 20220127-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128920220127-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1128920220127-8Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1128720220127-6Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6L.O.A.1210 | Corbiere and Sons Contracting1128720220127-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128720220127-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1128720220127-6Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1128620220127-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5L.O.A.1210 | Corbiere and Sons Contracting1128620220127-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128620220127-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1128620220127-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1128420220127-3-R1Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1L.O.A.1210 | Corbiere and Sons Contracting1128420220127-3-R1L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128420220127-3-R1Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1128420220127-3-R1Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11291 | 20220127-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129120220127-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1129120220127-10Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11291 | 20220127-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129120220127-10Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1129120220127-10Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting1128320220126-7Driver - AZ - After Jan 1010700INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1128320220126-7Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7L.O.A.1210 | Corbiere and Sons Contracting1128320220126-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting1128320220126-7Tractor Trailer - 60 Ton- After Jan 10101223.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1128320220126-7Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11282 | 20220126-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128220220126-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1128220220126-6Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11282 | 20220126-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128220220126-6Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1128220220126-6Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1128120220126-5Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5L.O.A.1210 | Corbiere and Sons Contracting1128120220126-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128120220126-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1128120220126-5Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3L.O.A.2420 | Corbiere and Sons Contracting1127920220126-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1127920220126-3Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127920220126-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127920220126-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1127720220125-5Operator - Intermdiate - After Jan 106420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127720220125-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5L.O.A.2420 | Corbiere and Sons Contracting1127720220125-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1127720220125-5Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127720220125-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127720220125-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127520220125-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3L.O.A.1210 | Corbiere and Sons Contracting1127520220125-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127520220125-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1127520220125-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11274 | 20220124-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 4972.8 | Unit |  |  |  |  | 4972.8 | 646.464 | 5619.264 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Charges for Sand used | 6 | C129-D005 |  | 0 | 2022-01-30 |  | 37 | 2022-01-31 | 18520 | Sand |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1127420220124-83rd Party Charges4972.84972.8 | Corbiere and Sons Contracting1127420220124-83rd Party Charges4972.84972.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11274 | 20220124-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 3824.9 | Unit |  |  |  |  | 3824.9 | 497.237 | 4322.137 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Charges for Sand used | 6 | C129-D005 |  | 0 | 2022-01-30 |  | 37 | 2022-01-31 | 414-413 | sand |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1127420220124-83rd Party Charges3824.93824.9 | Corbiere and Sons Contracting1127420220124-83rd Party Charges3824.93824.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1127220220124-6Operator - Principle - After Jan 105.5412.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6L.O.A.1210 | Corbiere and Sons Contracting1127220220124-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127220220124-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting1127220220124-6Dozer D6 or equal- After Jan 103.5460.18INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1127120220124-5Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127120220124-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5L.O.A.1210 | Corbiere and Sons Contracting1127120220124-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1127120220124-5Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127120220124-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127120220124-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11268 | 20220123-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126820220123-8Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1126820220123-8Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11268 | 20220123-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126820220123-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1126820220123-8Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11267 | 20220123-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126720220123-7Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126720220123-7Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11267 | 20220123-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126720220123-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126720220123-7Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11266 | 20220123-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C185-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126620220123-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126620220123-6Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11266 | 20220123-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C185-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126620220123-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126620220123-6Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126520220123-5Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5L.O.A.3630 | Corbiere and Sons Contracting1126520220123-5L.O.A.3630INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126520220123-5Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1126520220123-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1126520220123-5Dozer D6 or equal- After Jan 10101314.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11260 | 20220122-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126020220122-9Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1126020220122-9Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11260 | 20220122-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126020220122-9Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1126020220122-9Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11259 | 20220122-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125920220122-8Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1125920220122-8Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11259 | 20220122-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125920220122-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1125920220122-8Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11258 | 20220122-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125820220122-7Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1125820220122-7Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11258 | 20220122-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125820220122-7L.O.A.1210 | Corbiere and Sons Contracting1125820220122-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11258 | 20220122-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125820220122-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1125820220122-7Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1125720220122-6Operator - Principle - After Jan 107525INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6L.O.A.1210 | Corbiere and Sons Contracting1125720220122-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125720220122-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1125720220122-6Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1125620220122-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5L.O.A.1210 | Corbiere and Sons Contracting1125620220122-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125620220122-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1125620220122-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11261 | 20220122-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126120220122-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126120220122-10Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11261 | 20220122-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126120220122-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126120220122-10Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11252 | 20220121-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125220220121-6Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1125220220121-6Operator - Intermdiate - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11252 | 20220121-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125220220121-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1125220220121-6Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1125120220121-5Operator - Intermdiate - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1125120220121-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5L.O.A.1210 | Corbiere and Sons Contracting1125120220121-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1125120220121-5Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125120220121-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1125120220121-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1124820220120-8Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124820220120-8Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8L.O.A.2420 | Corbiere and Sons Contracting1124820220120-8L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1124820220120-8Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124820220120-8Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1124820220120-8Dozer D6 or equal- After Jan 1081051.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11247 | 20220120-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2021-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124720220120-7Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1124720220120-7Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11247 | 20220120-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2021-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124720220120-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1124720220120-7Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1124520220120-5Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124520220120-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5L.O.A.1210 | Corbiere and Sons Contracting1124520220120-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1124520220120-5Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124520220120-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1124520220120-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11241 | 20220119-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124120220119-9Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1124120220119-9Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11241 | 20220119-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124120220119-9Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1124120220119-9Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11240 | 20220119-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124020220119-8Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1124020220119-8Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11240 | 20220119-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124020220119-8Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1124020220119-8Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11239 | 20220119-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123920220119-7Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1123920220119-7Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11239 | 20220119-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123920220119-7Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1123920220119-7Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11238 | 20220119-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123820220119-6Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1123820220119-6Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11238 | 20220119-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123820220119-6L.O.A.1210 | Corbiere and Sons Contracting1123820220119-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11238 | 20220119-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123820220119-6Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1123820220119-6Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11242 | 20220119-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124220220119-10Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1124220220119-10Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11242 | 20220119-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124220220119-10Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1124220220119-10Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11230 | 20220117-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1123020220117-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1123020220117-9Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11230 | 20220117-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1123020220117-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1123020220117-9Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11229 | 20220117-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122920220117-8Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1122920220117-8Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11229 | 20220117-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122920220117-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1122920220117-8Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11228 | 20220117-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122820220117-7Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1122820220117-7Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11228 | 20220117-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122820220117-7L.O.A.1210 | Corbiere and Sons Contracting1122820220117-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11228 | 20220117-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122820220117-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1122820220117-7Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11227 | 20220117-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122720220117-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1122720220117-6Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11227 | 20220117-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122720220117-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1122720220117-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11227 | 20220117-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122720220117-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1122720220117-6Dozer D6 or equal- After Jan 10101314.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11231 | 20220117-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123120220117-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1123120220117-10Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11231 | 20220117-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123120220117-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1123120220117-10Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11221 | 20220116-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122120220116-8Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1122120220116-8Operator - Intermdiate - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11221 | 20220116-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122120220116-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1122120220116-8Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11219 | 20220116-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1121920220116-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1121920220116-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11219 | 20220116-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1121920220116-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1121920220116-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11219 | 20220116-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1121920220116-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1121920220116-6Dozer D6 or equal- After Jan 10111446.28INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11223 | 20220116-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-D005 | WF6 | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122320220116-10Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1122320220116-10Driver - AZ - After Jan 1011770INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11223 | 20220116-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-D005 | WF6 | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122320220116-10L.O.A.1210 | Corbiere and Sons Contracting1122320220116-10L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11223 | 20220116-10 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-D005 | WF6 | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122320220116-10Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1122320220116-10Tractor Trailer - 60 Ton- After Jan 10111346.29INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11172 | 20220115-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117220220115-8Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1117220220115-8Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11172 | 20220115-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117220220115-8L.O.A.1210 | Corbiere and Sons Contracting1117220220115-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11172 | 20220115-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117220220115-8Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1117220220115-8Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11170 | 20220115-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117020220115-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1117020220115-6Operator - Principle - After Jan 103225INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11170 | 20220115-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117020220115-6Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1117020220115-6Dozer D6 or equal- After Jan 103394.44INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11169 | 20220115-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116920220115-5Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1116920220115-5Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11169 | 20220115-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116920220115-5Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1116920220115-5Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1116620220114-8Driver - AZ - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1116620220114-8Operator - Principle - After Jan 107525INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1116620220114-8Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1116620220114-8Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11165 | 20220114-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116520220114-7Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1116520220114-7Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11165 | 20220114-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116520220114-7Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1116520220114-7Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1115920220113-7Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1115920220113-7Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7L.O.A.2420 | Corbiere and Sons Contracting1115920220113-7L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1115920220113-7Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1115920220113-7Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1115920220113-7Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1108420220112-9Driver - AZ - After Jan 105350INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1108420220112-9Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1108420220112-9Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1108420220112-9Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1108320220112-8Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8L.O.A.1210 | Corbiere and Sons Contracting1108320220112-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1108320220112-8Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting1108320220112-8Dozer D6 or equal- After Jan 104.5591.66INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11130 | 20220112-11-R1 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1113020220112-11-R1Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1113020220112-11-R1Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11130 | 20220112-11-R1 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1113020220112-11-R1Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1113020220112-11-R1Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11085 | 20220112-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108520220112-10Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1108520220112-10Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11085 | 20220112-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108520220112-10L.O.A.1210 | Corbiere and Sons Contracting1108520220112-10L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11085 | 20220112-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108520220112-10Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1108520220112-10Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11432 | 20220106-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1763.2 | Unit |  |  |  |  | 1763.2 | 229.216 | 1992.416 | 2022-01-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-31 |  | 37 | 2022-02-04 | no number provided | Flagging done by Best Towing - Lake A |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1143220220106-83rd Party Charges1763.21763.2 | Corbiere and Sons Contracting1143220220106-83rd Party Charges1763.21763.2INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11430 | 20220102-17 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143020220102-17Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1143020220102-17Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11430 | 20220102-17 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143020220102-17Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1143020220102-17Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11429 | 20220102-16 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1142920220102-16Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1142920220102-16Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11429 | 20220102-16 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1142920220102-16Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1142920220102-16Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11428 | 20220102-15 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 2204 | Unit |  |  |  |  | 2204 | 286.52 | 2490.52 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | no number provided | Flagging done by Best Towing - Little Red Sucker Creek |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142820220102-153rd Party Charges22042204 | Corbiere and Sons Contracting1142820220102-153rd Party Charges22042204INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11427 | 20211216-10 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1102 | Unit |  |  |  |  | 1102 | 143.26 | 1245.26 | 2021-12-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Jackfish Lake | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Jackfish Lake |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142720211216-103rd Party Charges11021102 | Corbiere and Sons Contracting1142720211216-103rd Party Charges11021102INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11426 | 20211213-11 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1454.64 | Unit |  |  |  |  | 1454.64 | 189.1032 | 1643.7432 | 2021-12-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Jackfish Lake | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Jackfish Lake |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142620211213-113rd Party Charges1454.641454.64 | Corbiere and Sons Contracting1142620211213-113rd Party Charges1454.641454.64INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11425 | 20211129-13 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1895.44 | Unit |  |  |  |  | 1895.44 | 246.4072 | 2141.8472 | 2021-11-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Lake A |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142520211129-133rd Party Charges1895.441895.44 | Corbiere and Sons Contracting1142520211129-133rd Party Charges1895.441895.44INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11424 | 20211128-12 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1763.2 | Unit |  |  |  |  | 1763.2 | 229.216 | 1992.416 | 2021-11-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Dead Horse Creek and Lake A | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Dead Horse Creek |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142420211128-123rd Party Charges1763.21763.2 | Corbiere and Sons Contracting1142420211128-123rd Party Charges1763.21763.2INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11866 | 20211012-8 | 53510612 | Access | 0 | 3rd Party Charges | 1 | 2865.2 | Unit |  |  |  |  | 2865.2 | 372.476 | 3237.676 | 2021-10-12 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing, Dead Horse Creek, Ripple Lake Road, Mink Creek Road | 6 | C129-D005 | WF6 | 0 |  |  | 36 | 2022-02-23 | Not available | Best Towing price before mark up 2470.00 |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1186620211012-83rd Party Charges2865.22865.2 | Corbiere and Sons Contracting1186620211012-83rd Party Charges2865.22865.2INV #165 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 11566 | 20220219-7 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Shouldl be WF7 winter maint CC |  | Approved |  |  | WAM Activities Pic River - WWF7 | 6 | D018-D024 | Pic River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156620220219-7Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1156620220219-7Operator - Principle - After Jan 104300INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11566 | 20220219-7 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Shouldl be WF7 winter maint CC |  | Approved |  |  | WAM Activities Pic River - WWF7 | 6 | D018-D024 | Pic River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156620220219-7Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1156620220219-7Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11565 | 20220219-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM ActivitiesThreee Fingers - WWF7 | 6 | D006-D017 | Three Fingers - WF7 | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156520220219-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1156520220219-6Operator - Principle - After Jan 105375INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11565 | 20220219-6 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM ActivitiesThreee Fingers - WWF7 | 6 | D006-D017 | Three Fingers - WF7 | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156520220219-6Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1156520220219-6Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1162420220301-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5L.O.A.1210 | Corbiere and Sons Contracting1162420220301-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1162420220301-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1162420220301-5Dozer D6 or equal- After Jan 10101314.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1162320220301-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4L.O.A.1210 | Corbiere and Sons Contracting1162320220301-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1162320220301-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1162320220301-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1162220220301-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3L.O.A.1210 | Corbiere and Sons Contracting1162220220301-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1162220220301-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1162220220301-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11620 | 20220228-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 0 | 0 | 490 | 63.7 | 553.7 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162020220228-6Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting1162020220228-6Operator - Intermdiate - After Jan 107490INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11620 | 20220228-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162020220228-6L.O.A.1210 | Corbiere and Sons Contracting1162020220228-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11620 | 20220228-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162020220228-6Pickup w/ plow and sander7560 | Corbiere and Sons Contracting1162020220228-6Pickup w/ plow and sander7560INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11619 | 20220228-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161920220228-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1161920220228-5Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11619 | 20220228-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161920220228-5Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1161920220228-5Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1161820220228-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4L.O.A.1210 | Corbiere and Sons Contracting1161820220228-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161820220228-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1161820220228-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8.5 | HR |  |  | 0 | 0 | 595 | 77.35 | 672.35 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Driver - AZ - After Jan 108.5595 | Corbiere and Sons Contracting1161720220228-3Driver - AZ - After Jan 108.5595INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3L.O.A.4840 | Corbiere and Sons Contracting1161720220228-3L.O.A.4840INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1161720220228-3Pickup w/ plow and sander5400INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8.5 | Dynamic | 0 | 0 |  |  | 1040.315 | 135.2409 | 1175.5559 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Tractor Trailer - 60 Ton- After Jan 108.51040.315 | Corbiere and Sons Contracting1161720220228-3Tractor Trailer - 60 Ton- After Jan 108.51040.315INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 0 | 0 |  |  | 825.37 | 107.2981 | 932.6681 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting1161720220228-3Grader - Cat 12 to 14 or equal- After Jan 106.5825.37INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1161720220228-3Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1161520220227-7Operator - Principle - After Jan 108600INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7L.O.A.1210 | Corbiere and Sons Contracting1161520220227-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161520220227-7Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1161520220227-7Dozer D6 or equal- After Jan 105657.4INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11614 | 20220227-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161420220227-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1161420220227-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11614 | 20220227-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161420220227-6L.O.A.1210 | Corbiere and Sons Contracting1161420220227-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11614 | 20220227-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161420220227-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1161420220227-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11613 | 20220227-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161320220227-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1161320220227-5Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11613 | 20220227-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161320220227-5L.O.A.1210 | Corbiere and Sons Contracting1161320220227-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11613 | 20220227-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161320220227-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1161320220227-5Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11612 | 20220227-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161220220227-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1161220220227-4Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11612 | 20220227-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161220220227-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1161220220227-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1161120220227-3Driver - AZ - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  | 0 | 0 | 630 | 81.9 | 711.9 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3L.O.A.3630 | Corbiere and Sons Contracting1161120220227-3L.O.A.3630INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1161120220227-3Tractor Trailer - 60 Ton- After Jan 10111346.29INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1161120220227-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 0 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1161120220227-3Dozer D6 or equal- After Jan 103394.44INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11609 | 20220226-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160920220226-5L.O.A.1210 | Corbiere and Sons Contracting1160920220226-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11609 | 20220226-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160920220226-5Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1160920220226-5Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11608 | 20220226-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160820220226-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1160820220226-4Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11608 | 20220226-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160820220226-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1160820220226-4Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1160720220226-3Driver - AZ - After Jan 106420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 1013975INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 109675INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3L.O.A.3630 | Corbiere and Sons Contracting1160720220226-3L.O.A.3630INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 9 |  | 0 | 0 |  |  | 720 | 93.6 | 813.6 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Pickup w/ plow and sander9720 | Corbiere and Sons Contracting1160720220226-3Pickup w/ plow and sander9720INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1160720220226-3Tractor Trailer - 60 Ton- After Jan 106734.34INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1160720220226-3Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1160720220226-3Dozer D6 or equal- After Jan 10121577.76INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11605 | 20220225-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160520220225-6L.O.A.1210 | Corbiere and Sons Contracting1160520220225-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11605 | 20220225-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160520220225-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1160520220225-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1160420220225-5Operator - Principle - After Jan 1010750INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5L.O.A.1210 | Corbiere and Sons Contracting1160420220225-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160420220225-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1160420220225-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1160320220225-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4L.O.A.1210 | Corbiere and Sons Contracting1160320220225-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160320220225-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1160320220225-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3L.O.A.2420 | Corbiere and Sons Contracting1160220220225-3L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1160220220225-3Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160220220225-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1160220220225-3Dozer D6 or equal- After Jan 10101314.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1160020220224-7Driver - AZ - After Jan 1012840INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7L.O.A.2420 | Corbiere and Sons Contracting1160020220224-7L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1160020220224-7Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 0 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1160020220224-7Tractor Trailer - 60 Ton- After Jan 10121468.68INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1160020220224-7Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11599 | 20220224-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159920220224-6L.O.A.1210 | Corbiere and Sons Contracting1159920220224-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11599 | 20220224-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159920220224-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1159920220224-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1159820220224-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5L.O.A.1210 | Corbiere and Sons Contracting1159820220224-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159820220224-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1159820220224-5Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1159820220224-5Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1159720220224-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4L.O.A.1210 | Corbiere and Sons Contracting1159720220224-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159720220224-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1159720220224-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1159620220224-3Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3L.O.A.1210 | Corbiere and Sons Contracting1159620220224-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159620220224-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1159620220224-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11593 | 20220223-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159320220223-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1159320220223-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11593 | 20220223-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159320220223-7L.O.A.1210 | Corbiere and Sons Contracting1159320220223-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11593 | 20220223-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159320220223-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1159320220223-7Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11592 | 20220223-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159220220223-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1159220220223-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11592 | 20220223-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159220220223-6L.O.A.1210 | Corbiere and Sons Contracting1159220220223-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11592 | 20220223-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159220220223-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1159220220223-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13.5 | HR |  |  | 0 | 0 | 1012.5 | 131.625 | 1144.125 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5Operator - Principle - After Jan 1013.51012.5 | Corbiere and Sons Contracting1159120220223-5Operator - Principle - After Jan 1013.51012.5INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5L.O.A.1210 | Corbiere and Sons Contracting1159120220223-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159120220223-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12.5 | Dynamic | 0 | 0 |  |  | 1587.25 | 206.3425 | 1793.5925 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5Grader - Cat 12 to 14 or equal- After Jan 1012.51587.25 | Corbiere and Sons Contracting1159120220223-5Grader - Cat 12 to 14 or equal- After Jan 1012.51587.25INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1159020220223-4Operator - Principle - After Jan 103225INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4L.O.A.1210 | Corbiere and Sons Contracting1159020220223-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159020220223-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1159020220223-4Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158920220223-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3L.O.A.1210 | Corbiere and Sons Contracting1158920220223-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158920220223-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1158920220223-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11587 | 20220222-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158720220222-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1158720220222-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11587 | 20220222-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158720220222-6L.O.A.1210 | Corbiere and Sons Contracting1158720220222-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11587 | 20220222-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158720220222-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1158720220222-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5L.O.A.3630 | Corbiere and Sons Contracting1158620220222-5L.O.A.3630INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1158620220222-5Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1158620220222-5Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1158620220222-5Dozer D6 or equal- After Jan 10101314.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158520220222-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4L.O.A.1210 | Corbiere and Sons Contracting1158520220222-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158520220222-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1158520220222-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158420220222-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3L.O.A.1210 | Corbiere and Sons Contracting1158420220222-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158420220222-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1158420220222-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11582 | 20220221-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158220220221-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1158220220221-8Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11582 | 20220221-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158220220221-8L.O.A.1210 | Corbiere and Sons Contracting1158220220221-8L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11582 | 20220221-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158220220221-8Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1158220220221-8Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11581 | 20220221-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158120220221-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1158120220221-7Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11581 | 20220221-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158120220221-7L.O.A.1210 | Corbiere and Sons Contracting1158120220221-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11581 | 20220221-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158120220221-7Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1158120220221-7Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157920220221-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5L.O.A.1210 | Corbiere and Sons Contracting1157920220221-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157920220221-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1157920220221-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157820220221-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4L.O.A.1210 | Corbiere and Sons Contracting1157820220221-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157820220221-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157820220221-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157720220221-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3L.O.A.1210 | Corbiere and Sons Contracting1157720220221-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157720220221-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157720220221-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11574 | 20220220-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157420220220-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1157420220220-7Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11574 | 20220220-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157420220220-7L.O.A.1210 | Corbiere and Sons Contracting1157420220220-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11574 | 20220220-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157420220220-7Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1157420220220-7Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1157220220220-5Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5L.O.A.1210 | Corbiere and Sons Contracting1157220220220-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157220220220-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1157220220220-5Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157120220220-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4L.O.A.1210 | Corbiere and Sons Contracting1157120220220-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157120220220-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157120220220-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157020220220-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3L.O.A.1210 | Corbiere and Sons Contracting1157020220220-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157020220220-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157020220220-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11567 | 20220219-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156720220219-8Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1156720220219-8Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11567 | 20220219-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156720220219-8L.O.A.1210 | Corbiere and Sons Contracting1156720220219-8L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11567 | 20220219-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156720220219-8Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1156720220219-8Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1156420220219-5Operator - Principle - After Jan 103225INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5L.O.A.1210 | Corbiere and Sons Contracting1156420220219-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1156420220219-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1156420220219-5Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1156320220219-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4L.O.A.1210 | Corbiere and Sons Contracting1156320220219-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1156320220219-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1156320220219-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1156220220219-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3L.O.A.1210 | Corbiere and Sons Contracting1156220220219-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1156220220219-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1156220220219-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11560 | 20220218-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156020220218-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1156020220218-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11560 | 20220218-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156020220218-7L.O.A.1210 | Corbiere and Sons Contracting1156020220218-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11560 | 20220218-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156020220218-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1156020220218-7Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155820220218-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5L.O.A.1210 | Corbiere and Sons Contracting1155820220218-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155820220218-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1155820220218-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155720220218-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4L.O.A.1210 | Corbiere and Sons Contracting1155720220218-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155720220218-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155720220218-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155620220218-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3L.O.A.1210 | Corbiere and Sons Contracting1155620220218-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155620220218-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155620220218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 109675INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7L.O.A.2420 | Corbiere and Sons Contracting1155420220217-7L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1155420220217-7Pickup w/ plow and sander10800INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11553 | 20220217-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155320220217-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1155320220217-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11553 | 20220217-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155320220217-6L.O.A.1210 | Corbiere and Sons Contracting1155320220217-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11553 | 20220217-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155320220217-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1155320220217-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155220220217-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5L.O.A.1210 | Corbiere and Sons Contracting1155220220217-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155220220217-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155220220217-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155020220217-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3L.O.A.1210 | Corbiere and Sons Contracting1155020220217-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155020220217-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155020220217-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11548 | 20220216-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154820220216-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154820220216-8Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11548 | 20220216-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154820220216-8L.O.A.1210 | Corbiere and Sons Contracting1154820220216-8L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11548 | 20220216-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154820220216-8Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1154820220216-8Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11547 | 20220216-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154720220216-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154720220216-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11547 | 20220216-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154720220216-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154720220216-7Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11547 | 20220216-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 0 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154720220216-7Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1154720220216-7Dozer D6 or equal- After Jan 1081051.84INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11546 | 20220216-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154620220216-6Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting1154620220216-6Operator - Intermdiate - After Jan 1012840INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11546 | 20220216-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154620220216-6L.O.A.1210 | Corbiere and Sons Contracting1154620220216-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11546 | 20220216-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154620220216-6Pickup w/ plow and sander7560 | Corbiere and Sons Contracting1154620220216-6Pickup w/ plow and sander7560INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154520220216-5Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5L.O.A.1210 | Corbiere and Sons Contracting1154520220216-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154520220216-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1154520220216-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154420220216-4Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4L.O.A.1210 | Corbiere and Sons Contracting1154420220216-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154420220216-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 0 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting1154420220216-4Grader - Cat 12 to 14 or equal- After Jan 108.51079.33INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154320220216-3Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3L.O.A.1210 | Corbiere and Sons Contracting1154320220216-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154320220216-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1154320220216-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1154120220215-8Driver - AZ - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1154120220215-8Operator - Principle - After Jan 107525INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1154120220215-8Tractor Trailer - 60 Ton- After Jan 10111346.29INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1154120220215-8Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11540 | 20220215-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 10 | HR |  |  | 0 | 0 | 700 | 91 | 791 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154020220215-7Operator - Intermdiate - After Jan 1010700 | Corbiere and Sons Contracting1154020220215-7Operator - Intermdiate - After Jan 1010700INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11540 | 20220215-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154020220215-7L.O.A.1210 | Corbiere and Sons Contracting1154020220215-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11540 | 20220215-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154020220215-7Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1154020220215-7Pickup w/ plow and sander10800INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1010750INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5L.O.A.2420 | Corbiere and Sons Contracting1153820220215-5L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1153820220215-5Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153820220215-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1153820220215-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1153720220215-3Operator - Principle - After Jan 1010750INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3L.O.A.1210 | Corbiere and Sons Contracting1153720220215-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153720220215-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1153720220215-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11535 | 20220214-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153520220214-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1153520220214-9Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11535 | 20220214-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153520220214-9L.O.A.1210 | Corbiere and Sons Contracting1153520220214-9L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11535 | 20220214-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153520220214-9Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1153520220214-9Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11534 | 20220214-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activitites Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153420220214-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1153420220214-8Operator - Principle - After Jan 107525INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11534 | 20220214-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activitites Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153420220214-8Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1153420220214-8Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11533 | 20220214-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152-C157 | Jackfish Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153320220214-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1153320220214-7Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11533 | 20220214-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152-C157 | Jackfish Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153320220214-7L.O.A.1210 | Corbiere and Sons Contracting1153320220214-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11533 | 20220214-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152-C157 | Jackfish Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153320220214-7Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1153320220214-7Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1153120220214-5Driver - AZ - After Jan 104280INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1153120220214-5Operator - Principle - After Jan 104300INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5L.O.A.1210 | Corbiere and Sons Contracting1153120220214-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1153120220214-5Tractor Trailer - 60 Ton- After Jan 104489.56INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153120220214-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 0 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1153120220214-5Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1153020220214-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4L.O.A.1210 | Corbiere and Sons Contracting1153020220214-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153020220214-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1153020220214-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1152920220214-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3L.O.A.1210 | Corbiere and Sons Contracting1152920220214-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152920220214-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1152920220214-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10638 | 20211130-9 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-11-30 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 7 Rig Mats to Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063820211130-9Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1063820211130-9Driver - AZ - After Jan 105350INV# 157 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10638 | 20211130-9 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-30 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 7 Rig Mats to Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063820211130-9L.O.A.1210 | Corbiere and Sons Contracting1063820211130-9L.O.A.1210INV# 157 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10638 | 20211130-9 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-11-30 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 7 Rig Mats to Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063820211130-9Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1063820211130-9Tractor Trailer - 60 Ton- After Jan 105611.95INV# 157 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1060720211012-7Driver - AZ - After Jan 108560INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1060720211012-7Operator - Principle - After Jan 108600INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1060720211012-7Tractor Trailer - 60 Ton- After Jan 108979.12INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1060720211012-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1060720211012-7Grader - Cat 12 to 14 or equal- After Jan 103380.94INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10744 | 20211208-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074420211208-14Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1074420211208-14Operator - Intermdiate - After Jan 105.5385INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10744 | 20211208-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074420211208-14Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1074420211208-14Pickup w/ plow and sander5.5440INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10743 | 20211208-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074320211208-13Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1074320211208-13Operator - Intermdiate - After Jan 105.5385INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10743 | 20211208-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074320211208-13L.O.A.1210 | Corbiere and Sons Contracting1074320211208-13L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10743 | 20211208-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074320211208-13Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1074320211208-13Pickup w/ plow and sander5.5440INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10741 | 20211208-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron did WAM on Prairie River Road for 9 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074120211208-11Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1074120211208-11Operator - Principle - After Jan 109675INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10741 | 20211208-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron did WAM on Prairie River Road for 9 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074120211208-11L.O.A.1210 | Corbiere and Sons Contracting1074120211208-11L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10741 | 20211208-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron did WAM on Prairie River Road for 9 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074120211208-11Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1074120211208-11Dozer D6 or equal- After Jan 1081051.84INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072420211207-7Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7L.O.A.1210 | Corbiere and Sons Contracting1072420211207-7L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1072420211207-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1072420211207-7Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10732 | 20211207-15 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073220211207-15Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1073220211207-15Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10732 | 20211207-15 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073220211207-15Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1073220211207-15Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10731 | 20211207-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073120211207-14Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1073120211207-14Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10731 | 20211207-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073120211207-14Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1073120211207-14Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10729 | 20211207-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072920211207-12Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1072920211207-12Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10729 | 20211207-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072920211207-12L.O.A.1210 | Corbiere and Sons Contracting1072920211207-12L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10729 | 20211207-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072920211207-12Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1072920211207-12Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10727 | 20211207-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and DZ did Winter Access Maitnenance for 3 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072720211207-10Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1072720211207-10Operator - Principle - After Jan 103225INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10727 | 20211207-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and DZ did Winter Access Maitnenance for 3 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072720211207-10Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1072720211207-10Dozer D6 or equal- After Jan 103394.44INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1070220211206-8Driver - AZ - After Jan 1011770INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1070220211206-8Operator - Principle - After Jan 1010750INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8L.O.A.2420 | Corbiere and Sons Contracting1070220211206-8L.O.A.2420INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1070220211206-8Tractor Trailer - 60 Ton- After Jan 10111346.29INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1070220211206-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1070220211206-8Excavator - 36 ton- After Jan 1081175.68INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10677 | 20211204-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-04 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing of Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067720211204-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1067720211204-8Driver - AZ - After Jan 104280INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10677 | 20211204-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-04 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing of Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067720211204-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1067720211204-8Pickup w/ plow and sander4320INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10666 | 20211203-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066620211203-9Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1066620211203-9Operator - Intermdiate - After Jan 102140INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10666 | 20211203-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066620211203-9Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1066620211203-9Pickup w/ plow and sander2160INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10667 | 20211203-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C130-C151 | Lake A | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066720211203-10Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1066720211203-10Operator - Intermdiate - After Jan 102140INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10667 | 20211203-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C130-C151 | Lake A | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066720211203-10Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1066720211203-10Pickup w/ plow and sander2160INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10653 | 20211202-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1726.02 | Unit |  |  |  |  | 1726.02 | 224.3826 | 1950.4026 | 2021-12-02 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Relocation of office trailer by Secure Store back to Marathon Laydown for work over the next few months | 6 | C130-C277 | WF6 | 0 | 2021-12-09 |  | 37 | 2021-12-12 | 2112044 | $1487.95 marked up to $1726.02 |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1065320211202-83rd Party Charges1726.021726.02 | Corbiere and Sons Contracting1065320211202-83rd Party Charges1726.021726.02INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10652 | 20211202-7 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1531.2 | Unit |  |  |  |  | 1531.2 | 199.056 | 1730.256 | 2021-12-02 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of Fuel Buggy for use in Prairie And Lake A - 2 hours deducted for delay caused by Corbiere | 6 | C130-C277 | WF6 | 0 | 2021-12-09 |  | 37 | 2021-12-12 | 381 | $1320 marked up to $1531.20 |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1065220211202-73rd Party Charges1531.21531.2 | Corbiere and Sons Contracting1065220211202-73rd Party Charges1531.21531.2INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10621 | 20211128-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Ripple Creek Road to the tracks | 6 | C198-C202 | Ripple Creek Road | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062120211128-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1062120211128-5Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10621 | 20211128-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Ripple Creek Road to the tracks | 6 | C198-C202 | Ripple Creek Road | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062120211128-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1062120211128-5Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10620 | 20211128-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062020211128-4Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1062020211128-4Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10620 | 20211128-4 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062020211128-4Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1062020211128-4Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1061820211128-3Driver - AZ - After Jan 10221540INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1061820211128-3Operator - Principle - After Jan 106450INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3L.O.A.2420 | Corbiere and Sons Contracting1061820211128-3L.O.A.2420INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1061820211128-3Tractor Trailer - 60 Ton- After Jan 10222692.58INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1061820211128-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting1061820211128-3Excavator - 36 ton- After Jan 104587.84INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10615 | 20211127-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 2nd grader from Sudbury | 6 | C129-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061520211127-4Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1061520211127-4Driver - AZ - After Jan 10221540INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10615 | 20211127-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 2nd grader from Sudbury | 6 | C129-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061520211127-4L.O.A.1210 | Corbiere and Sons Contracting1061520211127-4L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10615 | 20211127-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 2nd grader from Sudbury | 6 | C129-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061520211127-4Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1061520211127-4Tractor Trailer - 60 Ton- After Jan 10222692.58INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1061420211127-3Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3L.O.A.1210 | Corbiere and Sons Contracting1061420211127-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061420211127-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1061420211127-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1061420211127-3Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1061120211126-4Driver - AZ - After Jan 108560INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1061120211126-4Operator - Principle - After Jan 104300INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4L.O.A.2420 | Corbiere and Sons Contracting1061120211126-4L.O.A.2420INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1061120211126-4Tractor Trailer - 60 Ton- After Jan 108979.12INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061120211126-4Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1061120211126-4Dozer D6 or equal- After Jan 102262.96INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1061020211126-3Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3L.O.A.1210 | Corbiere and Sons Contracting1061020211126-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061020211126-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1061020211126-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1061020211126-3Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1057220211125-3Labourer - General - After Jan 105300INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1057220211125-3Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3L.O.A.1210 | Corbiere and Sons Contracting1057220211125-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1057220211125-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1057220211125-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1057220211125-3Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10570 | 20211124-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057020211124-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1057020211124-4Operator - Principle - After Jan 105375INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10570 | 20211124-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057020211124-4Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1057020211124-4Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10570 | 20211124-4 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057020211124-4Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1057020211124-4Excavator - 36 ton- After Jan 103440.88INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1056920211124-3Labourer - General - After Jan 105300INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1056920211124-3Operator - Principle - After Jan 106450INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3L.O.A.1210 | Corbiere and Sons Contracting1056920211124-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1056920211124-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1056920211124-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1056920211124-3Excavator - 36 ton- After Jan 105734.8INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970820210815-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 20 | HR |  |  | 70 | 0 | 1400 | 182 | 1582 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Driver - AZ - After Jan 10201400 | Corbiere and Sons Contracting970820210815-3Driver - AZ - After Jan 10201400Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 165 | HR |  |  | 0 | 0 | 12375 | 1608.75 | 13983.75 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Operator - Principle - After Jan 1016512375 | Corbiere and Sons Contracting970820210815-3Operator - Principle - After Jan 1016512375Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | L.O.A. | 210 | 18 | DAY |  |  | 0 | 0 | 3780 | 491.4 | 4271.4 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3L.O.A.183780 | Corbiere and Sons Contracting970820210815-3L.O.A.183780Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Foreman121140 | Corbiere and Sons Contracting970820210815-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 20 | Dynamic | 91.79 | 0 |  |  | 2447.8 | 318.214 | 2766.014 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Tractor Trailer - 60 Ton- After Jan 10202447.8 | Corbiere and Sons Contracting970820210815-3Tractor Trailer - 60 Ton- After Jan 10202447.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970820210815-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970820210815-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970820210815-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 27 | HR | 0 | 0 |  |  | 1711.26 | 222.4638 | 1933.7238 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator Hammer - 30 - 50 ton- After Jan 10271711.26 | Corbiere and Sons Contracting970820210815-3Excavator Hammer - 30 - 50 ton- After Jan 10271711.26Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting970820210815-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 27 | Dynamic | 0 | 0 |  |  | 3967.92 | 515.8296 | 4483.7496 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator - 36 ton- After Jan 10273967.92 | Corbiere and Sons Contracting970820210815-3Excavator - 36 ton- After Jan 10273967.92Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970820210815-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting970820210815-3Dozer D6 or equal- After Jan 1091183.32Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970720210814-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 154 | HR |  |  | 0 | 0 | 11550 | 1501.5 | 13051.5 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Operator - Principle - After Jan 1015411550 | Corbiere and Sons Contracting970720210814-3Operator - Principle - After Jan 1015411550Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3L.O.A.163360 | Corbiere and Sons Contracting970720210814-3L.O.A.163360Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Foreman121140 | Corbiere and Sons Contracting970720210814-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970720210814-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970720210814-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970720210814-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 18 | HR | 0 | 0 |  |  | 1140.84 | 148.3092 | 1289.1492 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator Hammer - 30 - 50 ton- After Jan 10181140.84 | Corbiere and Sons Contracting970720210814-3Excavator Hammer - 30 - 50 ton- After Jan 10181140.84Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting970720210814-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970720210814-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970720210814-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting970720210814-3Dozer D6 or equal- After Jan 1091183.32Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting970620210813-3Labourer - General - After Jan 1010600Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 140 | HR |  |  | 0 | 0 | 10500 | 1365 | 11865 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Operator - Principle - After Jan 1014010500 | Corbiere and Sons Contracting970620210813-3Operator - Principle - After Jan 1014010500Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3L.O.A.163360 | Corbiere and Sons Contracting970620210813-3L.O.A.163360Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 0 | 0 | 1045 | 135.85 | 1180.85 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Foreman111045 | Corbiere and Sons Contracting970620210813-3Foreman111045Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 48 | Dynamic | 0 | 0 |  |  | 6626.4 | 861.432 | 7487.832 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Rock Truck - 30 Ton- After Jan 10486626.4 | Corbiere and Sons Contracting970620210813-3Rock Truck - 30 Ton- After Jan 10486626.4Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970620210813-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970620210813-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 16 | HR | 0 | 0 |  |  | 1014.08 | 131.8304 | 1145.9104 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator Hammer - 30 - 50 ton- After Jan 10161014.08 | Corbiere and Sons Contracting970620210813-3Excavator Hammer - 30 - 50 ton- After Jan 10161014.08Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 32 | HR | 0 | 0 |  |  | 390.72 | 50.7936 | 441.5136 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator Thumb - 30 - 50 ton- After Jan 1032390.72 | Corbiere and Sons Contracting970620210813-3Excavator Thumb - 30 - 50 ton- After Jan 1032390.72Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 16 | Dynamic | 0 | 0 |  |  | 2351.36 | 305.6768 | 2657.0368 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator - 36 ton- After Jan 10162351.36 | Corbiere and Sons Contracting970620210813-3Excavator - 36 ton- After Jan 10162351.36Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 40 | Dynamic | 0 | 0 |  |  | 5538 | 719.94 | 6257.94 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator - 30 ton- After Jan 10405538 | Corbiere and Sons Contracting970620210813-3Excavator - 30 ton- After Jan 10405538Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting970620210813-3Dozer D6 or equal- After Jan 1081051.84Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970520210812-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting970520210812-3Driver - AZ - After Jan 1012840Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 153 | HR |  |  | 0 | 0 | 11475 | 1491.75 | 12966.75 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Operator - Principle - After Jan 1015311475 | Corbiere and Sons Contracting970520210812-3Operator - Principle - After Jan 1015311475Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | L.O.A. | 210 | 17 | DAY |  |  | 0 | 0 | 3570 | 464.1 | 4034.1 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3L.O.A.173570 | Corbiere and Sons Contracting970520210812-3L.O.A.173570Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Foreman121140 | Corbiere and Sons Contracting970520210812-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting970520210812-3Tractor Trailer - 60 Ton- After Jan 10121468.68Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970520210812-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970520210812-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970520210812-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting970520210812-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 45 | HR | 0 | 0 |  |  | 549.45 | 71.4285 | 620.8785 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45 | Corbiere and Sons Contracting970520210812-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970520210812-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970520210812-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970420210811-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting970420210811-3Operator - Principle - After Jan 1014310725Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3L.O.A.153150 | Corbiere and Sons Contracting970420210811-3L.O.A.153150Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Foreman121140 | Corbiere and Sons Contracting970420210811-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970420210811-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970420210811-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 9 | DAY | 0 | 0 |  |  | 2193.75 | 285.1875 | 2478.9375 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Light Truck - Pick up- After Jan 1092193.75 | Corbiere and Sons Contracting970420210811-3Light Truck - Pick up- After Jan 1092193.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting970420210811-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 45 | HR | 0 | 0 |  |  | 549.45 | 71.4285 | 620.8785 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45 | Corbiere and Sons Contracting970420210811-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970420210811-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970420210811-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970320210810-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 24 | HR |  |  | 70 | 0 | 1680 | 218.4 | 1898.4 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Driver - AZ - After Jan 10241680 | Corbiere and Sons Contracting970320210810-3Driver - AZ - After Jan 10241680Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting970320210810-3Operator - Principle - After Jan 1014310725Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3L.O.A.163360 | Corbiere and Sons Contracting970320210810-3L.O.A.163360Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Foreman121140 | Corbiere and Sons Contracting970320210810-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 24 | Dynamic | 91.79 | 0 |  |  | 2937.36 | 381.8568 | 3319.2168 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Tractor Trailer - 60 Ton- After Jan 10242937.36 | Corbiere and Sons Contracting970320210810-3Tractor Trailer - 60 Ton- After Jan 10242937.36Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 45 | Dynamic | 0 | 0 |  |  | 6212.25 | 807.5925 | 7019.8425 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Rock Truck - 30 Ton- After Jan 10456212.25 | Corbiere and Sons Contracting970320210810-3Rock Truck - 30 Ton- After Jan 10456212.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970320210810-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 9 | DAY | 0 | 0 |  |  | 2193.75 | 285.1875 | 2478.9375 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Light Truck - Pick up- After Jan 1092193.75 | Corbiere and Sons Contracting970320210810-3Light Truck - Pick up- After Jan 1092193.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting970320210810-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 45 | HR | 0 | 0 |  |  | 549.45 | 71.4285 | 620.8785 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45 | Corbiere and Sons Contracting970320210810-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970320210810-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970320210810-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting968920210809-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 110 | HR |  |  | 0 | 0 | 8250 | 1072.5 | 9322.5 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Operator - Principle - After Jan 101108250 | Corbiere and Sons Contracting968920210809-3Operator - Principle - After Jan 101108250Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  | 0 | 0 | 2520 | 327.6 | 2847.6 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3L.O.A.122520 | Corbiere and Sons Contracting968920210809-3L.O.A.122520Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Foreman121140 | Corbiere and Sons Contracting968920210809-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting968920210809-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968920210809-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968920210809-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting968920210809-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting968920210809-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting968920210809-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 36 | Dynamic | 0 | 0 |  |  | 4984.2 | 647.946 | 5632.146 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator - 30 ton- After Jan 10364984.2 | Corbiere and Sons Contracting968920210809-3Excavator - 30 ton- After Jan 10364984.2Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting968820210808-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 110 | HR |  |  | 0 | 0 | 8250 | 1072.5 | 9322.5 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Operator - Principle - After Jan 101108250 | Corbiere and Sons Contracting968820210808-3Operator - Principle - After Jan 101108250Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  | 0 | 0 | 2520 | 327.6 | 2847.6 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3L.O.A.122520 | Corbiere and Sons Contracting968820210808-3L.O.A.122520Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Foreman121140 | Corbiere and Sons Contracting968820210808-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting968820210808-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968820210808-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968820210808-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting968820210808-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting968820210808-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting968820210808-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 36 | Dynamic | 0 | 0 |  |  | 4984.2 | 647.946 | 5632.146 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator - 30 ton- After Jan 10364984.2 | Corbiere and Sons Contracting968820210808-3Excavator - 30 ton- After Jan 10364984.2Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting968720210807-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 121 | HR |  |  | 0 | 0 | 9075 | 1179.75 | 10254.75 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Operator - Principle - After Jan 101219075 | Corbiere and Sons Contracting968720210807-3Operator - Principle - After Jan 101219075Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  | 0 | 0 | 2730 | 354.9 | 3084.9 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3L.O.A.132730 | Corbiere and Sons Contracting968720210807-3L.O.A.132730Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Foreman121140 | Corbiere and Sons Contracting968720210807-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting968720210807-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968720210807-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968720210807-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting968720210807-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 34 | HR | 0 | 0 |  |  | 415.14 | 53.9682 | 469.1082 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator Thumb - 30 - 50 ton- After Jan 1034415.14 | Corbiere and Sons Contracting968720210807-3Excavator Thumb - 30 - 50 ton- After Jan 1034415.14Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting968720210807-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 34 | Dynamic | 0 | 0 |  |  | 4707.3 | 611.949 | 5319.249 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator - 30 ton- After Jan 10344707.3 | Corbiere and Sons Contracting968720210807-3Excavator - 30 ton- After Jan 10344707.3Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting968020210806-3Labourer - General - After Jan 105300Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 0 | 0 | 4500 | 585 | 5085 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting968020210806-3Operator - Principle - After Jan 10604500Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  | 0 | 0 | 2940 | 382.2 | 3322.2 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3L.O.A.142940 | Corbiere and Sons Contracting968020210806-3L.O.A.142940Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 0 | 0 | 475 | 61.75 | 536.75 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Foreman5475 | Corbiere and Sons Contracting968020210806-3Foreman5475Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 30 | Dynamic | 0 | 0 |  |  | 4141.5 | 538.395 | 4679.895 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Rock Truck - 30 Ton- After Jan 10304141.5 | Corbiere and Sons Contracting968020210806-3Rock Truck - 30 Ton- After Jan 10304141.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968020210806-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968020210806-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting968020210806-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 0 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting968020210806-3Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting968020210806-3Excavator - 36 ton- After Jan 10101469.6Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 20 | Dynamic | 0 | 0 |  |  | 2769 | 359.97 | 3128.97 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator - 30 ton- After Jan 10202769 | Corbiere and Sons Contracting968020210806-3Excavator - 30 ton- After Jan 10202769Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting967920210805-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting967920210805-3Driver - AZ - After Jan 1011770Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 104 | HR |  |  | 0 | 0 | 7800 | 1014 | 8814 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Operator - Principle - After Jan 101047800 | Corbiere and Sons Contracting967920210805-3Operator - Principle - After Jan 101047800Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  | 0 | 0 | 2730 | 354.9 | 3084.9 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3L.O.A.132730 | Corbiere and Sons Contracting967920210805-3L.O.A.132730Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Foreman121140 | Corbiere and Sons Contracting967920210805-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting967920210805-3Tractor Trailer - 60 Ton- After Jan 10111346.29Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting967920210805-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Marooka- After Jan 105723 | Corbiere and Sons Contracting967920210805-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting967920210805-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 33 | HR | 0 | 0 |  |  | 402.93 | 52.3809 | 455.3109 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Excavator Thumb - 30 - 50 ton- After Jan 1033402.93 | Corbiere and Sons Contracting967920210805-3Excavator Thumb - 30 - 50 ton- After Jan 1033402.93Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting967920210805-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 0 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting967920210805-3Excavator - 30 ton- After Jan 10243322.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting967820210804-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Driver - AZ - After Jan 10443080 | Corbiere and Sons Contracting967820210804-3Driver - AZ - After Jan 10443080Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 0 | 0 | 5775 | 750.75 | 6525.75 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting967820210804-3Operator - Principle - After Jan 10775775Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  | 0 | 0 | 2100 | 273 | 2373 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3L.O.A.102100 | Corbiere and Sons Contracting967820210804-3L.O.A.102100Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Foreman121140 | Corbiere and Sons Contracting967820210804-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 44 | Dynamic | 91.79 | 0 |  |  | 5385.16 | 700.0708 | 6085.2308 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Tractor Trailer - 60 Ton- After Jan 10445385.16 | Corbiere and Sons Contracting967820210804-3Tractor Trailer - 60 Ton- After Jan 10445385.16Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting967820210804-3Rock Truck - 30 Ton- After Jan 1091242.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Marooka- After Jan 105723 | Corbiere and Sons Contracting967820210804-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 0 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting967820210804-3Light Truck - Pick up- After Jan 1051218.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting967820210804-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting967820210804-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 27 | Dynamic | 0 | 0 |  |  | 3738.15 | 485.9595 | 4224.1095 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Excavator - 30 ton- After Jan 10273738.15 | Corbiere and Sons Contracting967820210804-3Excavator - 30 ton- After Jan 10273738.15Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting967120210803-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 75 | 0 | 5775 | 750.75 | 6525.75 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting967120210803-3Operator - Principle - After Jan 10775775Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3L.O.A.91890 | Corbiere and Sons Contracting967120210803-3L.O.A.91890Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Foreman121140 | Corbiere and Sons Contracting967120210803-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting967120210803-3Rock Truck - 30 Ton- After Jan 1091242.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Marooka- After Jan 105723 | Corbiere and Sons Contracting967120210803-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting967120210803-3Light Truck - Pick up- After Jan 1051218.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 9.16 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting967120210803-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting967120210803-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 27 | Dynamic | 103.84 | 0 |  |  | 3738.15 | 485.9595 | 4224.1095 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Excavator - 30 ton- After Jan 10273738.15 | Corbiere and Sons Contracting967120210803-3Excavator - 30 ton- After Jan 10273738.15Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9638 | 20210727-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-07-27 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake 2 from KM34-KM37 and KM44-KM45 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963820210727-3Marooka- After Jan 105723 | Corbiere and Sons Contracting963820210727-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9636 | 20210726-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-07-26 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake 2 from KM43-KM40 and from F066-F073 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963620210726-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting963620210726-3Light Truck - Pick up- After Jan 103731.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9636 | 20210726-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-07-26 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake 2 from KM43-KM40 and from F066-F073 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963620210726-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting963620210726-3Excavator - 36 ton- After Jan 1091322.64Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9634 | 20210725-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-07-25 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake Road from KM29-KM34, KM45-KM43 and KM27-KM30 - Darwin spent part of day on Henson at KM17.5 - Time split | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963420210725-3Marooka- After Jan 105723 | Corbiere and Sons Contracting963420210725-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Supervisor3252OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Pickup 1/2 Ton23575OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1CAT 25 ton Articulated Truck101780OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-130 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-130 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-25 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210825-1 | Excavator spreading existing material on road sections @ km 41/42 - MC-13132 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-33rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-33rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-08-24 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210824-1 | Slope and clean up excavations @ F108/level ruts and shape road F107 to F108 - MC-13131 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2065.452065.45OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-08-24 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210824-2 | Continue leveling ruts and replacing access mats fromKm 45 to Km 44 for gravel - SSF-14346 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2452.732452.73OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-23 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 2021-08-31 | MC-20210823-1 | Check for capping material & pile up stockpile @ F-108. |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-23 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 2021-08-31 | SSF-20210823-2 | Continue leveling ruts and shaping road from 46 Km to 44 Km for gravel haul. SSF-14343 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-22 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 50 | 2021-09-01 | MC-20210822-1 | Continue road maintenance and shaping road from F110 to F111 - MC-13128 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-22 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 50 | 2021-09-01 | SSF-20210822-1 | Continue leveling ruts and shaping road from 46.5 Km to 45 Km for gravel haul and spreading gravel where required. - SSF-14341 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2581.822581.82OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-21 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 50 | 2021-08-27 | MC-20210821-1 | Continue road maintenance and shaping road from F110 to F111 - MC-13128 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-21 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 50 | 2021-08-27 | SSF-20210821-2 | Continue leveling ruts and shaping road from 46.5 Km to 45 Km for gravel haul - SSF-14340 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2581.822581.82OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-20 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 50 | 2021-08-27 | MC-20210820-1 | Continue road maintenace shaping road to ROW and from F109 to F110 - MC-13127 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2194.55 | Each |  |  |  |  | 2194.55 | 285.2915 | 2479.8415 | 2021-08-20 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 50 | 2021-08-27 | SSF-20210820-2 | Continue Leveling ruts and shaping road from Km 47 to km 45 For gravel haul - SSF-14337 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2194.552194.55 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2194.552194.55OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-19 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 50 | 2021-08-27 | MC-20210819-1 | Excavator Tracking from Km 49 to Km 44 and start road maintenace shaping ahead of gravel crew - MC-13126 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-43rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-43rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2425.41 | Each |  |  |  |  | 2425.41 | 315.3033 | 2740.7133 | 2021-08-12 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210812-1 | grading road - SSF-14324 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-13rd Party Services2425.412425.41 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-13rd Party Services2425.412425.41OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2425.41 | Each |  |  |  |  | 2425.41 | 315.3033 | 2740.7133 | 2021-08-11 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210811-1 | Grading road - SSF-14324 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-13rd Party Services2425.412425.41 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-13rd Party Services2425.412425.41OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-08-10 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210810-1 | Grading road - SSF-14323 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-13rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-13rd Party Services25292529OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7210 | KL-20210809-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-08-09 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float grader from Hensen road to Paint Lake Road #2, start grading Paint Lake Road 2 from Km 0 to Km 2 - SSF-14322 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210809-2 | Grading road - SSF-14321 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7210KL-20210809-33rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD7210KL-20210809-33rd Party Services1160.911160.91OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | Labourer | 65 | 3 | HR |  |  | 65 | 0 | 195 | 25.35 | 220.35 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Labourer3195 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Labourer3195OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Supervisor0.542OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Supervisor0.542OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Supervisor3252OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Supervisor3252OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Supervisor184OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.090909 | DAY |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.090909 | DAY |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.68182 | DAY |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1L.O.A.0.6818182166.3636OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-330 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-330 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7.5 | HR | 147 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-130 Ton Excavator c/w Hydraulic Thumb7.51462.5 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-130 Ton Excavator c/w Hydraulic Thumb7.51462.5OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Pickup Truck - Truck Only3.587.5 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Pickup Truck - Truck Only3.587.5OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Pickup Truck - Truck Only8200OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Pickup Truck - Truck Only13325OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Pickup Truck - Truck Only13325OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Pickup Truck - Truck Only21525 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Pickup Truck - Truck Only21525OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7389 | KL-20210925-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4792.37 | Each |  |  |  |  | 4792.37 | 623.0081 | 5415.3781 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 finishing placing trees @Km 21 hill and working out to 16.5/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-29 |  | 50 | 2021-10-01 | SFF-20210925-1 | Excavator placing trees @ km 40.5 and shaping road/ grader starting sections of Paint Lake Road 2 to Km 5 - SFF-14381 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7389KL-20210925-13rd Party Services4792.374792.37 | KABI LAKE FOREST PRODUCTS LTD7389KL-20210925-13rd Party Services4792.374792.37OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6450.96 | Each |  |  |  |  | 6450.96 | 838.6248 | 7289.5848 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | MC-20210922-1 | Excavator 1 placing corduroy in low areas @ km 43 Hill and building road around a broken down drill/Excavator tracking from km 46 and loading trees/rock truck hauling trees from F104 to Km 43 hill - MC- 13159-1 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services6450.966450.96 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services6450.966450.96OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | SSF-20210922-1 | Excavator loading Chapman Rock Truck and Morin rock truck with trees for corduroy and Carrying trees from F104.5 to F104 for loading - SSF-14379 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services2702.732702.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 968.73 | Each |  |  |  |  | 968.73 | 125.9349 | 1094.6649 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | MC-20210921-1 | Excavator 1 placing corduroy in low areas @ km 43 Hill/Excavator 2 working on ditching for drainage/rock truck driving in from Hwy and hauling trees from F104 to Km 43 hill - MC- 13158 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services968.73968.73 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services968.73968.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1937.45 | Each |  |  |  |  | 1937.45 | 251.8685 | 2189.3185 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | MC-20210920-1 | Road maintenance - MC-13157 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services1937.451937.45 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services1937.451937.45OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | MC-20210919-1 | Excavator 1 placing corduroy in low areas @ km 41 and 42/Excavator 2 working on road maintenance @ km 44/46 - MC- 13156 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2179.642179.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2421.82 | Each |  |  |  |  | 2421.82 | 314.8366 | 2736.6566 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | MC-20210918-1 | Excavator leveling ruts, working on drainage and shaping road, fixing access mats and cleaning up broken mats from km 44 to 46 - MC- 13155 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2421.822421.82 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2421.822421.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | SSF-20210918-1 | Excavator working on drainage and shaping road from km 39 to 42.5 - SSF-14375 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2573.642573.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | MC-20210908-1 | Excavator Continuing road repairs with access mats and working on drainage @ km 44 to 42 Km - MC-13145 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | SSF-20210908-1 | Excavator Continuing Shaping road and fixing access mats from 36 to 38 km - SSF-14364 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | MC-20210908-1 | Excavator Continuing road repairs with access mats and working on drainage @ km 40.5 to 43.5 Km - MC-13144 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | SSF-20210907-1 | Excavator Continuing Shaping road and fixing access mats from 36 to 33 km - SSF-14363 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7316 | KL-20210906-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1161.82 | Each |  |  |  |  | 1161.82 | 151.0366 | 1312.8566 | 2021-09-06 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continuing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13143. Shaping road and fixing access mats from 38 to 36 km - SSF-14362 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | MC-20210906-1 | Excavator Continuing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13143 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1161.821161.82 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1161.821161.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7316 | KL-20210906-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1807.27 | Each |  |  |  |  | 1807.27 | 234.9451 | 2042.2151 | 2021-09-06 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continuing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13143. Shaping road and fixing access mats from 38 to 36 km - SSF-14362 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210906-1 | Excavator Continuing Shaping road and fixing access mats from 38 to 36 km - SSF-14362 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1807.271807.27 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1807.271807.27OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7315 | KL-20210905-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-05 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13142. Shaping road and fixing access mats from 43 to 48 km - SSF-14361 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | MC-20210905-1 | Excavator doing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13142 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7315 | KL-20210905-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-05 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13142. Shaping road and fixing access mats from 43 to 48 km - SSF-14361 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210905-1 | Excavator Continuing Shaping road and fixing access mats from 43 to 48 km - SSF-14361 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7313 | KL-20210904-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-04 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40.5 to 43 Km - MC-13141. Shaping road and fixing access mats from 45 to 47 km - SSF-14360 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | MC-20210904-1 | Excavator doing road repairs with access mats and working on drainage @ km 40.5 to 43 Km - MC-13141 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7313 | KL-20210904-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-04 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40.5 to 43 Km - MC-13141. Shaping road and fixing access mats from 45 to 47 km - SSF-14360 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210904-1 | Excavator Continuing Shaping road and fixing access mats from 45 to 47 km - SSF-14360 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-03 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210903-1 | Excavator Continuing Shaping road and fixing access mats from 43 to 45 km - SSF-14359 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-02 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 37 | 2021-09-18 | SSF-20210902-1 | Excavator Shaping road and fixing access mats from 43 to 45 km - SSF-14358 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-01 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 37 | 2021-09-18 | MC-20210901-1 | Excavator continuing leveling ruts, working on drainage and shaping road sections @ km 40/42 for gravel haul - MC-13138 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-01 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 37 | 2021-09-18 | SSF-20210901-1 | Excavator Shaping road and spreading Gravel, @ km 44/43 - SSF-14357 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-31 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-03 |  | 37 | 2021-09-06 | MC-20210831-1 | Excavator leveling ruts, working on drainage & shaping road sections @ 40/42km. MC-13137 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-31 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-03 |  | 37 | 2021-09-06 | SSF-20210831-1 | Excavator spreading gravel, placing corduroy & shaping road from 44km to 43km |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | SSF-20210830-1 | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 774.55 | Each |  |  |  |  | 774.55 | 100.6915 | 875.2415 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | MC-20210829-1 | Excavator leveling ruts, working on drainage and shaping road sections @ 40/42 - MC-13136 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-23rd Party Services774.55774.55 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-23rd Party Services774.55774.55OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-08-28 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210828-1 | Excavator leveling ruts and shaping road sections @ km 41/43- Pulls pick ups as required - MC-13135 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2452.732452.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-28 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210828-2 | Track to km 46 and spread gravel in soft sections to km 45 - SSF-14354 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210827-1 | Excavator continuing spreading existing material and lay corduroy on road sections @ km 41/42 - MC-13134 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2452.732452.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210827-2 | Excavator doing road repairs and replacing access mats @ 44/46 km - SSF- 14352 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210826-1 | Excavator continuing spreading existing material and lay corduroy on road sections @ km 41/42 - MC-13133 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210826-2 | Excavator cleaning up gravel haul excavations @ 42/43 km and shaping road @ 43 to 45 km - SSF- 14350 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2194.55 | Each |  |  |  |  | 2194.55 | 285.2915 | 2479.8415 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | MC-20210917-1 | Excavator leveling ruts, working on drainage and shaping road from km 43 to 40.5 - MC- 13154 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2194.552194.55 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2194.552194.55OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | SSF-20210917-1 | Excavator working on drainage and shaping road from km 38 to 40.5 - SSF-14374 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2702.732702.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4752.45 | Each |  |  |  |  | 4752.45 | 617.8185 | 5370.2685 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | MC-20210916-1 | Excavator spreading gravel @ km 42 and doing road work / leveling ruts after hours for pickup access/ Excavator 2 leveling ruts and shaping access mats from km 46 to 44 - MC- 13153 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-13rd Party Services4752.454752.45 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-13rd Party Services4752.454752.45OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4519.27 | Each |  |  |  |  | 4519.27 | 587.5051 | 5106.7751 | 2021-09-15 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  |  | 2021-09-25 | MC-20210915-1 | Excavator 1 working from km 43 to km 44 doing road repairs and replacing access mats/ Excavator 2 leveling ruts and shaping road from km 49 to 46 - MC- 13152 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services4519.274519.27 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services4519.274519.27OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2186.36 | Each |  |  |  |  | 2186.36 | 284.2268 | 2470.5868 | 2021-09-15 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  |  | 2021-09-25 | SSF-20210915-1 | Excavator working on road maintenance from Km 40.5 to 43 - SSF-14371 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services2186.362186.36 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services2186.362186.36OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | MC-20210914-1 | Excavator Continuing road repairs and spreading gravel @ km 40.5 to 43.5 Km/ doing road repairs after hours for pickup access - MC-13151 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services28152815OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2603.64 | Each |  |  |  |  | 2603.64 | 338.4732 | 2942.1132 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | SSF-20210914-1 | Excavator loading Existing material and cleaning up excavation @ km 38 /working on road maintenance from Km 38 to 40.5 - SSF-14370 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services2603.642603.64 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services2603.642603.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | MC-20210913-1 | Excavator Continuing road repairs and spreading gravel @ km 43 to 40.5 Km/ doing road repairs after hours for pickup access - MC-13150 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-23rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-23rd Party Services28152815OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | MC-20210912-1 | Excavator Continuing road repairs and spreading Gravel @ km 40.5 to 42.5 Km - MC-13149 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | SSF-20210912-1 | Excavator Continue loading Gravel @ km 38 /leveling ruts for pick up access from Km 38 to Km 40 - SSF-14368 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | MC-20210911-1 | Excavator Continuing road repairs for pick up access due to rain @ km 43 to 40 Km - MC-13148 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | SSF-20210911-1 | Excavator Continue loading Gravel @ km 38 /leveling ruts for pick up access from Km 38 to Km 40 - SSF-14367 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | MC-20210910-1 | Excavator Continuing road repairs and spreading gravel @ km 43 to 40 Km - MC-13147 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | SSF-20210910-1 | Excavator Continue loading Gravel @ km 38 /leveling ruts for pick up access- SSF-14366 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2452.732452.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Operator4320 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Operator4320OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Supervisor7588OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Supervisor7588OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Supervisor7588OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-15 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Supervisor5420OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Supervisor5420OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.9090909221.8182OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.63636 | DAY |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.6363636155.2727OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | L.O.A. | 244 | 1.5909 | DAY |  | 0 |  |  | 388.1818 | 50.4636 | 438.6454 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2L.O.A.1.5909091388.1818 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2L.O.A.1.5909091388.1818OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.54545 | DAY |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.5454545133.0909OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | DAY |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.7727273188.5455OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 38 | HR | 19 | 0 |  |  | 950 | 123.5 | 1073.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Pickup 1/2 Ton38950 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Pickup 1/2 Ton38950OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 26 | HR | 19 | 0 |  |  | 650 | 84.5 | 734.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Pickup 1/2 Ton26650 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Pickup 1/2 Ton26650OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 32 | HR | 19 | 0 |  |  | 800 | 104 | 904 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Pickup 1/2 Ton32800 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Pickup 1/2 Ton32800OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Pickup 1/2 Ton17425OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 14.5 | HR | 19 | 0 |  |  | 362.5 | 47.125 | 409.625 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Pickup 1/2 Ton14.5362.5 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Pickup 1/2 Ton14.5362.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 21.5 | HR | 19 | 0 |  |  | 537.5 | 69.875 | 607.375 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Pickup 1/2 Ton21.5537.5 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Pickup 1/2 Ton21.5537.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton8200OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton9.5237.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 13.5 | HR | 19 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Pickup 1/2 Ton13.5337.5 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Pickup 1/2 Ton13.5337.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Pickup 1/2 Ton13325OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Pickup 1/2 Ton22550OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Pickup 1/2 Ton19475OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Pickup 1/2 Ton22550OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1CAT 25 ton Articulated Truck101780OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 7 | HR | 134 | 0 |  |  | 1246 | 161.98 | 1407.98 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1CAT 25 ton Articulated Truck71246 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1CAT 25 ton Articulated Truck71246OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 6.5 | HR | 134 | 0 |  |  | 1157 | 150.41 | 1307.41 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2CAT 25 ton Articulated Truck6.51157 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2CAT 25 ton Articulated Truck6.51157OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8.5 | HR | 134 | 0 |  |  | 1513 | 196.69 | 1709.69 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3CAT 25 ton Articulated Truck8.51513 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3CAT 25 ton Articulated Truck8.51513OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 12 | HR | 147 | 0 |  |  | 2340 | 304.2 | 2644.2 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-230 Ton Excavator c/w Hydraulic Thumb122340 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-230 Ton Excavator c/w Hydraulic Thumb122340OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 6 | HR | 147 | 0 |  |  | 1170 | 152.1 | 1322.1 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb61170 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb61170OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only21525 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only21525OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only9225OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only9225OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Supervisor184OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | L.O.A. | 244 | 0.45455 | DAY |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.4545455110.9091OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.8181818199.6364OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  |  |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Pickup 1/2 Ton13325OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Pickup 1/2 Ton13325OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Pickup 1/2 Ton13325OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Pickup 1/2 Ton21525OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Pickup 1/2 Ton23575OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4CAT 25 ton Articulated Truck5890OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5CAT 25 ton Articulated Truck91602OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-430 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-430 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5ATV - side by side - Daily1250OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5ATV - side by side - Daily1250OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3ATV - side by side - Daily1250OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Supervisor0.542OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Supervisor3252OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Supervisor4336OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Supervisor3252OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2L.O.A.0.8636364210.7273OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.72727 | DAY |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.7272727177.4545OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.72727 | DAY |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.7272727177.4545OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | Pickup 1/2 Ton | 25 | 0.5 | HR | 19 | 0 |  |  | 12.5 | 1.625 | 14.125 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Pickup 1/2 Ton0.512.5 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Pickup 1/2 Ton0.512.5OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | Pickup 1/2 Ton | 25 | 33 | HR | 19 | 0 |  |  | 825 | 107.25 | 932.25 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Pickup 1/2 Ton33825 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Pickup 1/2 Ton33825OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | Pickup 1/2 Ton | 25 | 30.5 | HR | 19 | 0 |  |  | 762.5 | 99.125 | 861.625 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Pickup 1/2 Ton30.5762.5 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Pickup 1/2 Ton30.5762.5OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | Pickup 1/2 Ton | 25 | 34 | HR | 19 | 0 |  |  | 850 | 110.5 | 960.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Pickup 1/2 Ton34850 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Pickup 1/2 Ton34850OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 7.5 | HR | 142 | 0 |  |  | 1417.5 | 184.275 | 1601.775 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 30 ton Articulated Truck7.51417.5 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 30 ton Articulated Truck7.51417.5OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 30 ton Articulated Truck101890OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 30 ton Articulated Truck101890OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 9.5 | HR | 92 | 0 |  |  | 1159 | 150.67 | 1309.67 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Tri-Axle Gravel Dump Truck9.51159 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Tri-Axle Gravel Dump Truck9.51159OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3ATV - side by side - Daily1250OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3ATV - side by side - Daily1250OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5431.28 | Each |  |  |  |  | 5431.28 | 706.0664 | 6137.3464 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210928-1 | Excavator 1 shaping, ditching & capping corduroy @42.5km. Excavator 2 loading trees & existing materials to 38km. Rock truck hauling from 38km to 42.5km. |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5431.285431.28 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5431.285431.28OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5153.64 | Each |  |  |  |  | 5153.64 | 669.9732 | 5823.6132 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210928-1 | Excavator starting road repairs @36km, loading trees and existing material @38km. Grader finishing grading of Paint Lake Road 2 to 13km. SSF-14384 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5153.645153.64 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5153.645153.64OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210927-1 | Excavator 1 shaping, ditching & capping corduroy @43km. Excavator 2 loading existing materials at 38km. Rock truck hauling from 38km to 42.5km. MC-13164 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services6304.926304.92OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4766.37 | Each |  |  |  |  | 4766.37 | 619.6281 | 5385.9981 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210927-1 | Excavator shaping road from 41 to 36km. Grader continuing grading sections of Paint Lake Road from 5 to 10km. SSF-14383 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services4766.374766.37 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services4766.374766.37OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6087.73 | Each |  |  |  |  | 6087.73 | 791.4049 | 6879.1349 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210926-1 | Excavator 1 shaping, ditching & spreading gravel @ 42 to 43km. Excavator 2 loading trees at 38km. Rock truck hauling trees from 38km to 40.5km. MC-13163 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services6087.736087.73 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services6087.736087.73OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4869.96 | Each |  |  |  |  | 4869.96 | 633.0948 | 5503.0548 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210926-1 | Excavator finishing placing trees @ 40.5km & shaping road. Grader continue grading sections of Paint Lake Road from 5km to 8km, and spread gravel @ 7 & 5 km. SSF-14382 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services4869.964869.96 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services4869.964869.96OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4575.46 | Each |  |  |  |  | 4575.46 | 594.8098 | 5170.2698 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | MC-20210930-1 | Excavator tracking from 400km to 38km for loading trees & existing material. Rock truck hauling trees & existing material from 38km to 35/34km. MC-13168 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services4575.464575.46 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services4575.464575.46OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.74 | Each |  |  |  |  | 2702.74 | 351.3562 | 3054.0962 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | SFF-20210930-1 | Tracking from 38km to 35km, placing trees in low/soft areas & shaping road. SSF-14386 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services2702.742702.74 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services2702.742702.74OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5267 | Each |  |  |  |  | 5267 | 684.71 | 5951.71 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210929-1 | Excavator shaping, ditching, placing trees & capping with existing material @ 42 km. Rock truck hauling trees/existing material from 38km to 42km. MC-13167 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services52675267 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services52675267OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2948.42 | Each |  |  |  |  | 2948.42 | 383.2946 | 3331.7146 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210929-1 | Loading trees & existing material on rock trucks @ 38 km. SSF-14385 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services2948.422948.42 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services2948.422948.42OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Supervisor8672OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Supervisor7588OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Supervisor8672OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | Supervisor | 84 | 8.5 | HR |  |  | 84 | 0 | 714 | 92.82 | 806.82 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Supervisor8.5714 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Supervisor8.5714OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Supervisor8672OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.54545 | DAY |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.5454545133.0909OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | L.O.A. | 244 | 1.7727 | DAY |  | 0 |  |  | 432.5455 | 56.2309 | 488.7764 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.1.7727273432.5455 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.1.7727273432.5455OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 32 | HR | 19 | 0 |  |  | 800 | 104 | 904 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Pickup 1/2 Ton32800 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Pickup 1/2 Ton32800OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 34.5 | HR | 19 | 0 |  |  | 862.5 | 112.125 | 974.625 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Pickup 1/2 Ton34.5862.5 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Pickup 1/2 Ton34.5862.5OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Pickup 1/2 Ton17.5437.5 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Pickup 1/2 Ton17.5437.5OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 36 | HR | 19 | 0 |  |  | 900 | 117 | 1017 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Pickup 1/2 Ton36900 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Pickup 1/2 Ton36900OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 25 ton Articulated Truck91602OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 11 | HR | 134 | 0 |  |  | 1958 | 254.54 | 2212.54 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 25 ton Articulated Truck111958 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 25 ton Articulated Truck111958OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 25 ton Articulated Truck101780OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 25 ton Articulated Truck91602OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 6 | HR | 142 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 30 ton Articulated Truck61134 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 30 ton Articulated Truck61134OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 8.5 | HR | 142 | 0 |  |  | 1606.5 | 208.845 | 1815.345 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 30 ton Articulated Truck8.51606.5 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 30 ton Articulated Truck8.51606.5OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 30 ton Articulated Truck101890OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 36 | HR | 19 | 0 |  |  | 900 | 117 | 1017 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Pickup Truck - Truck Only36900 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Pickup Truck - Truck Only36900OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Supervisor3252OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Supervisor3252OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7466 | KL-20211017-2 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.18182 | DAY |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-10-17 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat back to Valard Marathon Yard | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2L.O.A.0.181818244.3636OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7450 | KL-20211013-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.18182 | DAY |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-10-13 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat from Pic River West for dragging of Access Mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3L.O.A.0.181818244.3636OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7455 | KL-20211014-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.31818 | DAY |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Pic River West for hauling of access mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3L.O.A.0.318181877.6364OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.5 | DAY |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.5122OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Pickup 1/2 Ton23575OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | Pickup 1/2 Ton | 25 | 18.5 | HR | 19 | 0 |  |  | 462.5 | 60.125 | 522.625 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Pickup 1/2 Ton18.5462.5 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Pickup 1/2 Ton18.5462.5OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3CAT D6 - LPG101790OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 15.5 | HR | 147 | 0 |  |  | 3022.5 | 392.925 | 3415.425 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-230 Ton Excavator c/w Hydraulic Thumb15.53022.5 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-230 Ton Excavator c/w Hydraulic Thumb15.53022.5OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7466 | KL-20211017-2 | 53530701 | Rig/Access Mats | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2021-10-17 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat back to Valard Marathon Yard | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2Float Truck - 60 ton2376OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7450 | KL-20211013-3 | 53530701 | Rig/Access Mats | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2021-10-13 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat from Pic River West for dragging of Access Mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3Float Truck - 60 ton2376OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7455 | KL-20211014-3 | 53530701 | Rig/Access Mats | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Pic River West for hauling of access mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3Float Truck - 60 ton3.5658OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Labourer2130 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Labourer2130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Labourer | 65 | 6 | HR |  |  | 65 | 0 | 390 | 50.7 | 440.7 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Labourer6390 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Labourer6390OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Supervisor3252OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Supervisor4336OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Supervisor3252OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Supervisor3252OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | Supervisor | 84 | 3.5 | HR |  |  | 84 | 0 | 294 | 38.22 | 332.22 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Supervisor3.5294 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Supervisor3.5294OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.77273 | DAY |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3L.O.A.0.7727273188.5455OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.59091 | DAY |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.59091 | DAY |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  |  |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Pickup 1/2 Ton10.5262.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 19.5 | HR | 19 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Pickup 1/2 Ton19.5487.5 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Pickup 1/2 Ton19.5487.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 23.5 | HR | 19 | 0 |  |  | 587.5 | 76.375 | 663.875 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Pickup 1/2 Ton23.5587.5 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Pickup 1/2 Ton23.5587.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Pickup 1/2 Ton12300OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 25 | HR | 19 | 0 |  |  | 625 | 81.25 | 706.25 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Pickup 1/2 Ton25625 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Pickup 1/2 Ton25625OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Pickup 1/2 Ton22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Pickup 1/2 Ton22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 27 | HR | 19 | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Pickup 1/2 Ton27675 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Pickup 1/2 Ton27675OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Pickup 1/2 Ton23575OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Pickup 1/2 Ton22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 6.5 | HR | 134 | 0 |  |  | 1157 | 150.41 | 1307.41 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3CAT 25 ton Articulated Truck6.51157 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3CAT 25 ton Articulated Truck6.51157OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10.5 | HR | 134 | 0 |  |  | 1869 | 242.97 | 2111.97 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5CAT 25 ton Articulated Truck10.51869 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5CAT 25 ton Articulated Truck10.51869OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 17 | HR | 147 | 0 |  |  | 3315 | 430.95 | 3745.95 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-330 Ton Excavator c/w Hydraulic Thumb173315 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-330 Ton Excavator c/w Hydraulic Thumb173315OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-330 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-330 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 21 | HR | 147 | 0 |  |  | 4095 | 532.35 | 4627.35 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-530 Ton Excavator c/w Hydraulic Thumb214095 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-530 Ton Excavator c/w Hydraulic Thumb214095OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-230 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-230 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-230 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-230 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-230 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-230 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Pickup Truck - Truck Only22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Tandum Trailer - without pickup - Daily | 75 | 1 | Daily |  | 0 |  |  | 75 | 9.75 | 84.75 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Tandum Trailer - without pickup - Daily175 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Tandum Trailer - without pickup - Daily175OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2ATV - side by side - Daily1250OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2ATV - side by side - Daily1250OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2ATV - side by side - Daily1250OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Supervisor184OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Supervisor184OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Supervisor2168OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.77273 | DAY |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3L.O.A.0.7727273188.5455OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | DAY |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.4545455110.9091OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Pickup 1/2 Ton21525OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton250OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton8.5212.5OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Pickup 1/2 Ton11275OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2CAT 25 ton Articulated Truck5890OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2CAT D6 - LPG101790OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-230 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-230 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-230 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-230 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1176520220309-5Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5L.O.A.1210 | Corbiere and Sons Contracting1176520220309-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1176520220309-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1176520220309-5Dozer D6 or equal- After Jan 10101314.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 0 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1176320220309-3Light Truck - Pick up- After Jan 102487.5 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1176320220309-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1176120220308-6Driver - AZ - After Jan 105350 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1176120220308-6Operator - Principle - After Jan 105375 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1176120220308-6Tractor Trailer - 60 Ton- After Jan 105611.95 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 0 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1176120220308-6Dozer D6 or equal- After Jan 102262.96 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1175820220308-3Driver - AZ - After Jan 106420 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1175820220308-3Pickup w/ plow and sander6480 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175820220308-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1175820220308-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175520220307-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4L.O.A.1210 | Corbiere and Sons Contracting1175520220307-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175520220307-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1175520220307-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175420220307-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1175420220307-3Grader - Cat 12 to 14 or equal- After Jan 107888.86 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1175220220306-5Driver - AZ - After Jan 104280 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2.5 | HR |  |  | 75 | 0 | 187.5 | 24.375 | 211.875 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Operator - Principle - After Jan 102.5187.5 | Corbiere and Sons Contracting1175220220306-5Operator - Principle - After Jan 102.5187.5 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5L.O.A.1210 | Corbiere and Sons Contracting1175220220306-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1175220220306-5Tractor Trailer - 60 Ton- After Jan 104489.56 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2.5 | Dynamic | 98.61 | 0 |  |  | 328.7 | 42.731 | 371.431 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Dozer D6 or equal- After Jan 102.5328.7 | Corbiere and Sons Contracting1175220220306-5Dozer D6 or equal- After Jan 102.5328.7 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174920220306-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4L.O.A.1210 | Corbiere and Sons Contracting1174920220306-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174920220306-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1174920220306-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1174820220306-3Pickup w/ plow and sander12960 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174820220306-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1174820220306-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1174420220305-5Operator - Principle - After Jan 108600 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5L.O.A.1210 | Corbiere and Sons Contracting1174420220305-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174420220305-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 0 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1174420220305-5Dozer D6 or equal- After Jan 107920.36 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174220220305-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4L.O.A.1210 | Corbiere and Sons Contracting1174220220305-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174220220305-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1174220220305-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1174320220305-3Driver - AZ - After Jan 103210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174320220305-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3L.O.A.1210 | Corbiere and Sons Contracting1174320220305-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1174320220305-3Tractor Trailer - 60 Ton- After Jan 103367.17 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174320220305-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1174320220305-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1173520220304-5Operator - Principle - After Jan 107525 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5L.O.A.1210 | Corbiere and Sons Contracting1173520220304-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173520220304-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 0 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1173520220304-5Dozer D6 or equal- After Jan 106788.88 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1173420220304-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4L.O.A.1210 | Corbiere and Sons Contracting1173420220304-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173420220304-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1173420220304-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1174120220304-3Driver - AZ - After Jan 103210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174120220304-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1174120220304-3Tractor Trailer - 60 Ton- After Jan 103367.17 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174120220304-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1174120220304-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1173020220303-5Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5L.O.A.1210 | Corbiere and Sons Contracting1173020220303-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173020220303-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting1173020220303-5Dozer D6 or equal- After Jan 106.5854.62 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172920220303-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4L.O.A.1210 | Corbiere and Sons Contracting1172920220303-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172920220303-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1172920220303-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1172820220303-3Driver - AZ - After Jan 1011770 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172820220303-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1172820220303-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172820220303-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1172820220303-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172420220302-6Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6L.O.A.1210 | Corbiere and Sons Contracting1172420220302-6L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172420220302-6Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting1172420220302-6Dozer D6 or equal- After Jan 106.5854.62 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1172320220302-4Operator - Principle - After Jan 108600 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4L.O.A.1210 | Corbiere and Sons Contracting1172320220302-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172320220302-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1172320220302-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1172220220302-3Driver - AZ - After Jan 1011770 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172220220302-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1172220220302-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172220220302-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1172220220302-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance

## All Season Access - Bx Rental
Bridge Rental Planned vs. Actual Comparison
Bridges required within the 42km of all-season access built
Work Fronts | Type | Size (ft) | CID | WID | Rental Start Date | Invoice Ending Date | Total Cost Paid ($) | Estimated Removal Date | Forecasted Rental Months | Total Forecasted Rental Amount | Rate | ID
6 | ASLP | 20 | WC224 | 600 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7083
6 | ASLP | 30 | WC252 | 605 | 2021-08-01 | 2022-02-28 | 9048.06 | 2022-10-15 | 7.6333 | 9866.694 | 1292.58 | 806
6 | ASLP | 20 | WC229 | 609 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7065
6 | ASLP | 40 | WC193 | 8110.01 | 2021-08-01 | 2022-02-28 | 12034.96 | 2022-10-15 | 7.6333 | 13123.8373 | 1719.28 | 832
6 | ASLP | 30 | WC195 | 8130.01 | 2021-08-01 | 2022-02-28 | 9048.06 | 2022-10-15 | 7.6333 | 9866.694 | 1292.58 | 863
6 | ASLP | 20 | WC196 | 8140 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7115
6 | ASLP | 50 | WC197 | 8150.01 | 2021-08-01 | 2022-02-28 | 14703.08 | 2022-10-15 | 7.6333 | 16033.3587 | 2100.44 | 873
6 | ASLP | 20 | WC198 | 8160 | 2021-08-01 | 2022-01-28 | 5406 | 2022-10-15 | 8.6667 | 7808.6667 | 901 | 7112
6 | ASLP | 20 | WC218 | 8240 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7098
6 | ASLP | 20 | WC219 | 8350.03 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7071
6 | ASLP | 20 | WC207 | 8351 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7078
6 | ASLP | 20 | WC209 | 8370 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7067
6 | ASLP | 20 | WC211 | 8400.01 | 2021-08-01 | 2022-02-28 | 6660.36 | 2022-10-15 | 7.6333 | 7262.964 | 951.48 | 7077
6 | ASLP | 40 | WC212 | 8440.01 | 2021-08-01 | 2022-02-28 | 12034.96 | 2022-10-15 | 7.6333 | 13123.8373 | 1719.28 | 831
7 | ASLP | 60 | WC254 | 8530 | 2021-08-01 | 2022-01-30 | 15349.44 | 2022-10-15 | 8.6 | 22000.864 | 2558.24 | 736
7 | ASLP | 20 | WC277 | 8560.01 | 2021-08-01 | 2022-01-30 | 5708.88 | 2022-10-15 | 8.6 | 8182.728 | 951.48 | 843
7 | ASLP | 20 | WC278 | 8570 | 2021-08-01 | 2022-01-30 | 5708.88 | 2022-10-15 | 8.6 | 8182.728 | 951.48 | 7061
7 | ASLP | 30.0197 | WC255 | 8550.01 | 2021-08-01 | 2022-01-30 | 7755.48 | 2022-10-15 | 8.6 | 11116.188 | 1292.58 | 837
7 | ASLP | 30.0197 | WC279 | 8571 | 2021-08-01 | 2022-01-30 | 7755.48 | 2022-10-15 | 8.6 | 11116.188 | 1292.58 | 864
[6 empty] | Acutal (Invoices provided on Summary Tab) | 157836.16 |  | Forecast Rental Amount | 188525.496

## All Season Access - Seedlings
Raw data extracted from approved clearing plan and limited to CZ within WF6/WF7
All Season Access Seedling Requirements | [10 empty] | POLY_ID | Structure | RIPARIAN | AREA_HA | Segment | SUBC_CLEAR | FDMS_CAT | RD_TYPE | WF | MAP | STRUCTURES | ROW | ROAD | LAYDOWN | RET_REV | COMMENTS
| Seedlings | [8 empty] | 448376.2 | WF5_6455 | C106 | NO | 0.21566 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
|  | Item |  |  |  | Rate** | UoM | Qty (m2) | Amount |  | WF5_2306 | C106 | NO | 0.12525 |  | Harvest Processing | Non-Mulch | AN | 5 | 54 | C106-C108 | 0 | 1 | 0 | 0
|  | Seedlings (93ha off-row temp. road cleared areas)* |  |  |  | 0.53031 | $/m2 | 845499.6033 | 448376.2 |  | WF5_7828 | C106 | NO | 1.241 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0 | Clearing type change based on field request
|  | *across full off-row clearing under Caribou zone | [8 empty] | WF5_6456 | C107 | NO | 0.79355 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
|  | ** An estimated all-inclusive cost required to complete seeding scope, including purchase, direct seeding, mob/demob, LOA and Travel | [8 empty] | WF5_6892 | C107 | NO | 0.61212 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
[11 empty] | WF5_6893 | C107 | NO | 0.1468 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
| Seeding Direct Work | [9 empty] | WF5_6894 | C107 | NO | 0.057519 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
| Description | Qty | Hrs per day | # of days | Rate | Amount |  |  |  |  | WF5_2313 | C107 | NO | 0.087571 |  | Retention | Retention |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 8
| Labour | 2 | 11 | 21 | 65 | 30030 |  |  |  |  | WF5_7769 | C107 | NO | 0.37839 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
| Truck | 1 |  | 21 | 247 | 5187 |  |  |  |  | WF5_8056 | C107 | NO | 0.26492 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0 | Clearing type change based on field request
| LOA | 2 |  | 21 | 210 | 8820 |  |  |  |  | WF5_8072 | C107 | NO | 0.066851 |  | Hand Fall / Lop and Scatter | Handfall | AN | 5 | 54 | C106-C108 | 0 | 1 | 0 | 0 | Clearing type change based on field request
| Travel | 1 |  |  | 988 | 988 |  |  |  |  | WF5_2316 | C108 | YES | 0.04455 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Grand Total |  |  |  |  | 45025 |  |  |  |  | WF5_6559 | C108 | YES | 0.079494 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
[11 empty] | WF5_6888 | C108 | NO | 0.053026 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Rural Ontario Roadside Native Seed Mixture 8145 | [9 empty] | WF5_6889 | C108 | NO | 0.088744 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| https://www.oscseeds.com/product/rural-ontario-roadside-native-mixture-8145/ | [9 empty] | WF5_6890 | C108 | NO | 0.010405 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Cost per kg | 190.8 | [8 empty] | WF5_6891 | C108 | NO | 0.11708 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Total Area (ha) | 84.55 | [8 empty] | WF5_6892 | C108 | NO | 0.056425 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Coverage (kg/ha) | 25 | [8 empty] | WF5_2310 | C108 | NO | 0.71615 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
| Seed Bags required (1kg) | 2114 | [8 empty] | WF5_2314 | C108 | NO | 0.25116 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
| Cost to pruchase Seed Mixture | 403351.2 | [8 empty] | WF5_2315 | C108 | NO | 0.044328 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
[11 empty] | WF5_2318 | C108 | NO | 0.40813 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
[11 empty] | WF5_7643 | C108 | NO | 0.35151 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
[11 empty] | WF5_7770 | C108 | NO | 0.71766 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
[11 empty] | WF5_8056 | C108 | NO | 0.050269 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_8072 | C108 | NO | 0.035085 |  | Hand Fall / Lop and Scatter | Handfall | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0 | Clearing type change based on field request
| Table showing OffROW clearing scope within WF6/WF7 (constructed from clearing plan) | [9 empty] | WF5_2317 | C109 | NO | 0.22937 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Sum of AREA_HA | Column Labels | [8 empty] | WF5_6457 | C109 | NO | 0.18077 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Row Labels | AN | ANWIN | AU2 | Grand Total | [5 empty] | WF5_6897 | C109 | NO | 0.062948 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Hand Fall / Lop and Scatter | 0.51731 |  |  | 0.51731 | [5 empty] | WF5_6898 | C109 | NO | 0.088698 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
| Harvest Disposal | 0.9683 | 0.31736 | 0.16079 | 1.4465 | [5 empty] | WF5_6899 | C109 | NO | 0.99311 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0 | Clearing type change based on field request
| Harvest Processing | 1.3495 | 0.10319 | 0.28566 | 1.7383 | [5 empty] | WF5_2310 | C109 | NO | 0.4434 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
| Non-Merch Disposal | 3.2643 | 71.2705 | 6.3131 | 80.8479 | [5 empty] | WF5_2310 | C109 | NO | 0.3028 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
| Grand Total | 6.0994 | 71.691 | 6.7596 | 84.55 | [5 empty] | WF5_2310 | C109 | NO | 0.14488 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
[5 empty] | 56.3666 | [5 empty] | WF5_2310 | C109 | NO | 0.083399 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
[11 empty] | WF5_2310 | C109 | NO | 0.013255 |  | Non-Merch Disposal | Mulch | AN | 5 | 56 | C110-C112 | 0 | 1 | 0 | 0
[11 empty] | WF5_2319 | C109 | NO | 0.039634 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
[11 empty] | WF5_2320 | C109 | NO | 0.085978 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
[11 empty] | WF5_2310 | C109 | NO | 0.048209 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
[11 empty] | WF5_2310 | C109 | NO | 0.048209 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
[11 empty] | WF5_2323 | C110 | YES | 0.18006 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2328 | C110 | YES | 0.11798 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6458 | C110 | NO | 0.097886 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6896 | C110 | NO | 0.58002 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_6901 | C110 | NO | 0.20274 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2310 | C110 | NO | 0.38567 |  | Non-Merch Disposal | Mulch | AN | 5 | 56 | C110-C112 | 0 | 1 | 0 | 0
[11 empty] | WF5_2324 | C110 | NO | 0.083685 |  | Non Productive | Non-Treed |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2321 | C110 | NO | 0.23394 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
[11 empty] | WF5_2322 | C110 | YES | 0.051331 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
[11 empty] | WF5_2325 | C110 | NO | 0.27117 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
[11 empty] | WF5_2330 | C110 | NO | 0.43828 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
[11 empty] | WF5_2332 | C110 | NO | 0.58527 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
[11 empty] | WF5_7644 | C110 | NO | 0.083277 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_7645 | C110 | NO | 0.39898 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_7771 | C110 | NO | 0.13665 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2327 | C111 | NO | 0.2174 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2331 | C111 | NO | 0.5123 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2329 | C111 | YES | 0.11212 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2335 | C111 | YES | 0.075132 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6560 | C111 | YES | 0.15822 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6561 | C111 | YES | 0.10529 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6563 | C111 | YES | 0.1175 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6900 | C111 | NO | 0.078741 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_6901 | C111 | NO | 0.014033 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_6911 | C111 | NO | 0.11136 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2326 | C111 | YES | 0.27776 |  | Harvest Processing | Non-Mulch | AN | 5 | 56 | C110-C112 | 1 | 1 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2337 | C111 | NO | 0.15266 |  | Non Productive | Non-Treed |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
[11 empty] | WF5_2332 | C111 | NO | 0.81049 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
[11 empty] | WF5_2340 | C112 | YES | 0.10193 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6562 | C112 | YES | 0.01277 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6564 | C112 | YES | 0.06398 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6912 | C112 | NO | 0.099146 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_2337 | C112 | NO | 0.14499 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_2343 | C112 | NO | 0.018775 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_2336 | C112 | NO | 0.49146 |  | Retention | Retention |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 8
[11 empty] | WF5_7647 | C112 | NO | 1.0683 |  | Harvest Processing | Non-Mulch |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_7713 | C112 | YES | 0.052136 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_7802 | C112 | YES | 0.071379 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6908 | C113 | NO | 0.13377 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6909 | C113 | NO | 0.07249 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6910 | C113 | NO | 0.031688 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_2342 | C113 | NO | 0.062295 |  | Harvest Processing | Non-Mulch | AN | 5 | 57 | C112-C114 | 0 | 1 | 0 | 0
[11 empty] | WF5_2344 | C113 | NO | 0.045165 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_2347 | C113 | NO | 0.01272 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_2345 | C113 | NO | 0.3228 |  | Retention | Retention |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 8
[11 empty] | WF5_7648 | C113 | NO | 0.95851 |  | Harvest Processing | Non-Mulch |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_7803 | C113 | YES | 0.024706 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
[11 empty] | WF5_6905 | C114 | NO | 0.073905 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_6906 | C114 | NO | 0.24823 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_6907 | C114 | NO | 0.016182 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_2346 | C114 | NO | 0.15058 |  | Retention | Retention |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 8
[11 empty] | WF5_2348 | C114 | NO | 0.10177 |  | Retention | Retention |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 8
[11 empty] | WF5_7649 | C114 | NO | 1.1885 |  | Harvest Processing | Non-Mulch |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_7829 | C114 | NO | 0.14704 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_6903 | C115 | NO | 0.27611 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_2353 | C115 | NO | 0.18612 |  | Non-Merch Disposal | Mulch | AN | 5 | 58 | C114-C116 | 0 | 1 | 0 | 0
[11 empty] | WF5_2356 | C115 | NO | 0.27612 |  | Non-Merch Disposal | Mulch | AN | 5 | 58 | C114-C116 | 0 | 1 | 0 | 0
[11 empty] | WF5_2360 | C115 | NO | 0.0045028 |  | Non-Merch Disposal | Mulch | AN | 5 | 58 | C114-C116 | 0 | 1 | 0 | 0
[11 empty] | WF5_7650 | C115 | NO | 1.0285 |  | Harvest Processing | Non-Mulch |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
[11 empty] | WF5_7898 | C115 | NO | 0.24255 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2351 | C116 | YES | 0.017334 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_2355 | C116 | YES | 0.15918 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_6565 | C116 | YES | 0.063433 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_6566 | C116 | YES | 0.040969 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_6902 | C116 | NO | 0.013849 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_6904 | C116 | NO | 0.035847 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_2360 | C116 | NO | 0.08723 |  | Non-Merch Disposal | Mulch | AN | 5 | 59 | C116-C118 | 0 | 1 | 0 | 0
[11 empty] | WF5_2350 | C116 | NO | 1.4024 |  | Non Productive | Non-Treed |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_2349 | C116 | YES | 0.12049 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
[11 empty] | WF5_2352 | C116 | YES | 0.076175 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
[11 empty] | WF5_2354 | C116 | YES | 0.086232 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
[11 empty] | WF5_2359 | C116 | YES | 0.053088 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
[11 empty] | WF5_7646 | C116 | NO | 0.29761 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_7651 | C116 | NO | 0.38417 |  | Harvest Processing | Non-Mulch |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_2361 | C117 | NO | 0.067577 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
[11 empty] | WF5_7652 | C117 | NO | 1.8555 |  | Harvest Processing | Non-Mulch |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
[11 empty] | WF5_2363 | C118 | NO | 0.04153 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_2357 | C118 | NO | 1.7578 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_2364 | C118 | NO | 0.011584 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_6913 | C118 | NO | 0.096073 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_6916 | C118 | NO | 0.10383 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_2362 | C118 | NO | 0.14656 |  | Retention | Retention |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 8
[11 empty] | WF5_7653 | C118 | NO | 0.10851 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_6915 | C119 | NO | 0.70943 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_6917 | C119 | NO | 0.034731 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_2368 | C119 | NO | 0.25203 |  | Non-Merch Disposal | Mulch | AU1 | 5 | 60 | C118-C120 | 0 | 1 | 0 | 0
[11 empty] | WF5_2368 | C119 | NO | 0.21664 |  | Non-Merch Disposal | Mulch | AU1 | 5 | 60 | C118-C120 | 0 | 1 | 0 | 0
[11 empty] | WF5_2365 | C119 | NO | 0.071552 |  | Retention | Retention |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 8
[11 empty] | WF5_7657 | C119 | NO | 0.25611 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_7830 | C119 | NO | 0.026716 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
[11 empty] | WF5_7899 | C119 | NO | 0.37315 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_8070 | C119 | NO | 0.23812 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_6162 | C120 | NO | 0.1723 |  | Non-Merch Disposal | Mulch | AN | 5 | 61 | C120-C122 | 0 | 1 | 0 | 0
[11 empty] | WF5_2366 | C120 | NO | 0.089991 |  | Retention | Retention |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 8
[11 empty] | WF5_2367 | C120 | NO | 0.052064 |  | Retention | Retention |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 8
[11 empty] | WF5_7656 | C120 | NO | 2.0672 |  | Harvest Processing | Non-Mulch |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0
[11 empty] | WF5_8033 | C120 | NO | 0.094428 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_6914 | C121 | NO | 0.12495 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0
[11 empty] | WF5_2369 | C121 | NO | 0.094871 |  | Retention | Retention |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 8
[11 empty] | WF5_7654 | C121 | NO | 1.6673 |  | Harvest Processing | Non-Mulch |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0
[11 empty] | WF5_8034 | C121 | NO | 0.13635 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_8035 | C121 | NO | 0.062134 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2370 | C122 | NO | 0.036332 |  | Harvest Processing | Non-Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2374 | C122 | NO | 0.21902 |  | Non-Merch Disposal | Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2371 | C122 | NO | 0.38656 |  | Non Productive | Non-Treed |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_7655 | C122 | NO | 0.91956 |  | Harvest Processing | Non-Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2373 | C123 | NO | 0.36656 |  | Non-Merch Disposal | Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2374 | C123 | NO | 0.23909 |  | Non-Merch Disposal | Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2376 | C123 | NO | 1.0252 |  | Harvest Processing | Non-Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2371 | C123 | NO | 0.29334 |  | Non Productive | Non-Treed |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2375 | C123 | NO | 0.12168 |  | Non Productive | Non-Treed |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
[11 empty] | WF5_2372 | C123 | NO | 0.11559 |  | Retention | Retention |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 8
[11 empty] | WF5_2376 | C124 | NO | 0.13223 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
[11 empty] | WF5_2378 | C124 | NO | 1.7768 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
[11 empty] | WF5_2377 | C124 | NO | 0.1142 |  | Non Productive | Non-Treed |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
[11 empty] | WF5_2379 | C124 | NO | 0.099251 |  | Retention | Retention |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 8
[11 empty] | WF5_2380 | C125 | NO | 0.023676 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
[11 empty] | WF5_2378 | C125 | NO | 1.5941 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
[11 empty] | WF5_2384 | C125 | NO | 0.22397 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
[11 empty] | WF5_2381 | C125 | NO | 0.19704 |  | Retention | Retention |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 8
[11 empty] | WF5_2382 | C125 | NO | 0.11025 |  | Retention | Retention |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 8
[11 empty] | WF5_8057 | C125 | NO | 0.091528 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2384 | C126 | NO | 2.3231 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
[11 empty] | WF5_2385 | C126 | NO | 0.02913 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
[11 empty] | WF5_2386 | C126 | NO | 0.031655 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
[11 empty] | WF5_2384 | C127 | NO | 1.89 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
[11 empty] | WF5_2895 | C128 | NO | 0.29402 |  | Non-Merch Disposal | Mulch | AU1 | 5 | 65 | C128-C129 | 0 | 1 | 0 | 0
[11 empty] | WF5_2388 | C128 | NO | 0.56531 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_6918 | C128 | NO | 0.55306 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0
[11 empty] | WF5_7291 | C128 | NO | 0.23112 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2384 | C128 | NO | 0.095013 |  | Harvest Processing | Non-Mulch |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0
[11 empty] | WF5_2387 | C128 | NO | 0.30481 |  | Non Productive | Non-Treed |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0
[11 empty] | WF5_2389 | C128 | NO | 0.11115 |  | Retention | Retention |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 8
[11 empty] | WF6_2402 | C129 | YES | 0.028122 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_2403 | C129 | YES | 0.038143 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF5_2388 | C129 | NO | 0.078628 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2390 | C129 | NO | 0.042984 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0 | Clearing type change based on field request
[11 empty] | WF5_2397 | C129 | NO | 0.02056 |  | Harvest Processing | Non-Mulch |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF5_2404 | C129 | NO | 0.053949 |  | Harvest Processing | Non-Mulch |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_7043 | C129 | YES | 0.23764 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_7184 | C129 | NO | 0.097484 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_2400 | C129 | NO | 1.1467 |  | Harvest Processing | Non-Mulch |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_2391 | C129 | NO | 0.027951 |  | Non Productive | Non-Treed |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_2395 | C129 | NO | 0.09076 |  | Non Productive | Non-Treed |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_2394 | C129 | YES | 0.028843 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2396 | C129 | YES | 0.06116 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2405 | C129 | YES | 0.15933 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2408 | C129 | NO | 0.078111 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2409 | C129 | NO | 0.06475 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2413 | C129 | NO | 0.17114 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2400 | C130 | NO | 1.7871 |  | Harvest Processing | Non-Mulch |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
[11 empty] | WF6_2414 | C130 | NO | 0.055606 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
[11 empty] | WF6_2400 | C131 | NO | 1.6871 |  | Harvest Processing | Non-Mulch |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 0
[11 empty] | WF6_2416 | C131 | NO | 0.22394 |  | Harvest Processing | Non-Mulch |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 0
[11 empty] | WF6_2415 | C131 | NO | 0.066456 |  | Retention | Retention |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 8
[11 empty] | WF6_2416 | C132 | NO | 1.5186 |  | Harvest Processing | Non-Mulch |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 0
[11 empty] | WF6_2416 | C133 | NO | 1.9621 |  | Harvest Processing | Non-Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
[11 empty] | WF6_2422 | C133 | NO | 0.22394 |  | Harvest Processing | Non-Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
[11 empty] | WF6_2420 | C133 | NO | 0.017745 |  | Retention | Retention |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 8
[11 empty] | WF6_2421 | C133 | NO | 0.052322 |  | Retention | Retention |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 8
[11 empty] | WF6_2424 | C133 | NO | 0.084027 |  | Retention | Retention |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 8
[11 empty] | WF6_2423 | C134 | NO | 0.051534 |  | Non-Merch Disposal | Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
[11 empty] | WF6_2422 | C134 | NO | 2.077 |  | Harvest Processing | Non-Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
[11 empty] | WF6_2422 | C135 | NO | 1.6064 |  | Harvest Processing | Non-Mulch |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 0
[11 empty] | WF6_6333 | C136 | NO | 0.61679 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 8 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6113 | C136 | NO | 0.61312 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 8 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6404 | C136 | NO | 0.36074 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6404 | C136 | NO | 0.35024 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6404 | C136 | NO | 0.19713 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6404 | C136 | NO | 0.015937 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6100 | C136 | NO | 0.27461 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 4 | C135-C137 | 0 | 1 | 0 | 0
[11 empty] | WF6_6100 | C136 | NO | 0.65728 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 4 | C135-C137 | 0 | 1 | 0 | 0
[11 empty] | WF6_6100 | C136 | NO | 0.098753 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2288 | C136 | NO | 0.16013 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2288 | C136 | NO | 0.1806 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2288 | C136 | NO | 0.35396 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2288 | C136 | NO | 0.19274 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2288 | C136 | NO | 0.037811 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2422 | C136 | NO | 1.7855 |  | Harvest Processing | Non-Mulch |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 0
[11 empty] | WF6_2426 | C136 | NO | 0.52039 |  | Retention | Retention |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 8
[11 empty] | WF6_2427 | C136 | NO | 0.099778 |  | Retention | Retention |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 8
[11 empty] | WF6_7044 | C137 | YES | 0.0214 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_7185 | C137 | NO | 0.03056 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_7186 | C137 | NO | 0.25585 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_6404 | C137 | NO | 0.016617 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2428 | C137 | YES | 0.025255 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_6101 | C137 | NO | 0.19908 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6101 | C137 | NO | 0.058764 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6101 | C137 | NO | 0.86918 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2288 | C137 | NO | 0.011718 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2422 | C137 | NO | 0.30569 |  | Harvest Processing | Non-Mulch |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2431 | C137 | NO | 0.061102 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2437 | C137 | YES | 0.041782 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2438 | C137 | YES | 0.066729 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2430 | C137 | NO | 2.8077 |  | Non Productive | Non-Treed |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2429 | C137 | YES | 0.083748 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
[11 empty] | WF6_2432 | C137 | NO | 0.069034 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
[11 empty] | WF6_2433 | C137 | YES | 0.070748 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
[11 empty] | WF6_2434 | C137 | NO | 0.040107 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
[11 empty] | WF6_2439 | C137 | YES | 0.094722 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
[11 empty] | WF6_7188 | C138 | NO | 0.080796 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2436 | C138 | NO | 0.284 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_6101 | C138 | NO | 0.24158 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
[11 empty] | WF6_2435 | C138 | NO | 0.85062 |  | Harvest Processing | Non-Mulch |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_2440 | C138 | NO | 0.33827 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
[11 empty] | WF6_7772 | C138 | NO | 0.67921 |  | Harvest Processing | Non-Mulch |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_7876 | C138 | NO | 0.50235 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
[11 empty] | WF6_6335 | C139 | NO | 0.089704 |  | Harvest Disposal | Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_6459 | C139 | NO | 0.13768 |  | Harvest Processing | Non-Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_7079 | C139 | NO | 0.20339 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_7080 | C139 | NO | 0.58828 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_7081 | C139 | NO | 0.078884 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_7189 | C139 | NO | 0.075276 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_2441 | C139 | NO | 0.30942 |  | Harvest Disposal | Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_2444 | C139 | NO | 0.077326 |  | Harvest Disposal | Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_2445 | C139 | NO | 0.14643 |  | Harvest Processing | Non-Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_2443 | C139 | NO | 0.043126 |  | Non Productive | Non-Treed |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_2442 | C139 | NO | 0.17106 |  | Retention | Retention |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 8
[11 empty] | WF6_2446 | C139 | NO | 0.30339 |  | Retention | Retention |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 8
[11 empty] | WF6_7259 | C139 | NO | 0.039859 |  | Non Productive | Non-Treed |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_7190 | C140 | NO | 0.044526 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_2450 | C140 | NO | 0.037091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 9 | C139-C141 | 0 | 1 | 0 | 0
[11 empty] | WF6_2445 | C140 | NO | 2.0508 |  | Harvest Processing | Non-Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_7877 | C140 | NO | 0.18456 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
[11 empty] | WF6_6336 | C141 | NO | 0.19083 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7082 | C141 | NO | 0.077691 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7083 | C141 | NO | 0.36252 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2447 | C141 | NO | 0.084783 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2460 | C141 | NO | 0.19837 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 10 | C141-C143 | 0 | 1 | 0 | 0
[11 empty] | WF6_2460 | C141 | NO | 0.11191 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 10 | C141-C143 | 0 | 1 | 0 | 0
[11 empty] | WF6_2445 | C141 | NO | 0.88692 |  | Harvest Processing | Non-Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7500 | C141 | YES | 0.019469 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7730 | C141 | NO | 0.2308 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7851 | C141 | YES | 0.010114 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2452 | C142 | YES | 0.058356 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2455 | C142 | YES | 0.011223 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2457 | C142 | YES | 0.039444 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2459 | C142 | YES | 0.021274 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_6337 | C142 | NO | 0.083654 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7045 | C142 | YES | 0.17682 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7084 | C142 | NO | 0.013761 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_7191 | C142 | NO | 0.25236 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2460 | C142 | NO | 1.4734 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 10 | C141-C143 | 0 | 1 | 0 | 0
[11 empty] | WF6_2460 | C142 | NO | 0.086568 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2458 | C142 | NO | 0.18565 |  | Harvest Processing | Non-Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2453 | C142 | NO | 0.019596 |  | Non Productive | Non-Treed |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2454 | C142 | NO | 0.48723 |  | Non Productive | Non-Treed |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
[11 empty] | WF6_2449 | C142 | YES | 0.90975 |  | Retention | Retention |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 8
[11 empty] | WF6_2456 | C142 | NO | 0.16981 |  | Retention | Retention |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 8
[11 empty] | WF6_2451 | C143 | NO | 0.72605 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2460 | C143 | NO | 0.087117 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2460 | C143 | NO | 1.9525 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2570 | C143 | NO | 0.31408 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2458 | C143 | NO | 2.0832 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
[11 empty] | WF6_2462 | C143 | NO | 0.149 |  | Retention | Retention |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 8
[11 empty] | WF6_2467 | C143 | NO | 0.28823 |  | Retention | Retention |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 8
[11 empty] | WF6_7085 | C144 | NO | 0.83519 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
[11 empty] | WF6_7192 | C144 | NO | 0.019699 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
[11 empty] | WF6_7193 | C144 | NO | 0.067386 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
[11 empty] | WF6_2460 | C144 | NO | 0.070062 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2466 | C144 | NO | 0.020399 |  | Harvest Disposal | Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
[11 empty] | WF6_2458 | C144 | NO | 0.47431 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
[11 empty] | WF6_2468 | C144 | NO | 0.13149 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
[11 empty] | WF6_2470 | C144 | NO | 0.18096 |  | Retention | Retention |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 8
[11 empty] | WF6_2468 | C144 | NO | 0.03268 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
[11 empty] | WF6_2468 | C144 | NO | 0.031172 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
[11 empty] | WF6_6460 | C145 | NO | 0.28023 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_7194 | C145 | NO | 0.48016 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2461 | C145 | NO | 0.49097 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
[11 empty] | WF6_2489 | C145 | NO | 0.15458 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
[11 empty] | WF6_2489 | C145 | NO | 0.68502 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
[11 empty] | WF6_2570 | C145 | NO | 0.20297 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
[11 empty] | WF6_2570 | C145 | NO | 0.4134 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
[11 empty] | WF6_2468 | C145 | NO | 0.85388 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
[11 empty] | WF6_2472 | C145 | NO | 0.04773 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2471 | C145 | NO | 0.039246 |  | Non Productive | Non-Treed |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2469 | C145 | NO | 0.21394 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
[11 empty] | WF6_2473 | C145 | NO | 0.069853 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
[11 empty] | WF6_2477 | C145 | NO | 0.12136 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
[11 empty] | WF6_2481 | C145 | NO | 0.19199 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
[11 empty] | WF6_7195 | C146 | NO | 0.063593 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2461 | C146 | NO | 0.081137 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
[11 empty] | WF6_2495 | C146 | NO | 0.50919 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
[11 empty] | WF6_2479 | C146 | NO | 1.854 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2478 | C146 | NO | 0.041319 |  | Non Productive | Non-Treed |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2482 | C146 | NO | 0.1511 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
[11 empty] | WF6_2487 | C146 | NO | 0.11939 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
[11 empty] | WF6_7725 | C146 | YES | 0.014877 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_7773 | C146 | NO | 0.16897 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
[11 empty] | WF6_2483 | C148 | YES | 0.32931 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2488 | C148 | YES | 0.16339 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2493 | C148 | YES | 0.1423 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2497 | C148 | YES | 0.053696 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_7196 | C148 | NO | 0.011447 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_7198 | C148 | NO | 0.034789 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2507 | C148 | NO | 0.70054 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 13 | C148-C150 | 0 | 1 | 0 | 0
[11 empty] | WF6_2479 | C148 | NO | 0.071075 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2491 | C148 | NO | 0.31089 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2484 | C148 | NO | 0.1897 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2486 | C148 | NO | 0.63736 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2485 | C148 | YES | 0.15006 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
[11 empty] | WF6_2490 | C148 | NO | 0.1409 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
[11 empty] | WF6_2494 | C148 | YES | 0.15827 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
[11 empty] | WF6_2496 | C148 | YES | 0.012699 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
[11 empty] | WF6_7260 | C148 | NO | 0.049331 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_7261 | C148 | NO | 0.023063 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_6461 | C149 | NO | 1.2114 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_7197 | C149 | NO | 0.28443 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2492 | C149 | NO | 0.10401 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 13 | C148-C150 | 0 | 1 | 0 | 0
[11 empty] | WF6_2499 | C149 | NO | 0.68626 |  | Harvest Disposal | Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2499 | C149 | NO | 0.014928 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2507 | C149 | NO | 0.20846 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 13 | C148-C150 | 0 | 1 | 0 | 0
[11 empty] | WF6_2491 | C149 | NO | 0.37823 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2498 | C149 | NO | 0.10965 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
[11 empty] | WF6_2502 | C149 | NO | 0.11995 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
[11 empty] | WF6_2520 | C151 | YES | 0.09587 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2521 | C151 | NO | 0.043577 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2501 | C151 | NO | 0.099837 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2508 | C151 | NO | 0.33768 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2519 | C151 | NO | 0.20704 |  | Harvest Processing | Non-Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_7086 | C151 | NO | 0.57795 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_7087 | C151 | NO | 0.43899 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_7088 | C151 | NO | 0.14539 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2492 | C151 | NO | 0.62628 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 14 | C150-C152 | 0 | 1 | 0 | 0
[11 empty] | WF6_2499 | C151 | NO | 0.068394 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2505 | C151 | NO | 0.57178 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2511 | C151 | NO | 0.036366 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2513 | C151 | NO | 2.4667 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2518 | C151 | NO | 0.077743 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2500 | C151 | NO | 0.80604 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_2509 | C151 | NO | 0.18488 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_2510 | C151 | NO | 0.16738 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_2512 | C151 | NO | 0.48491 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_2517 | C151 | YES | 0.16707 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_2525 | C151 | YES | 0.26637 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_2515 | C151 | NO | 0.14909 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
[11 empty] | WF6_7262 | C151 | NO | 0.025711 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_7263 | C151 | NO | 0.054775 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_7857 | C151 | NO | 0.37041 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
[11 empty] | WF6_2464 | C152 | NO | 0.043125 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
[11 empty] | WF6_6338 | C152 | NO | 0.037734 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
[11 empty] | WF6_2480 | C152 | NO | 0.18666 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
[11 empty] | WF6_2480 | C152 | NO | 0.25269 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
[11 empty] | WF6_2522 | C152 | NO | 0.035624 |  | Non Productive | Non-Treed |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
[11 empty] | WF6_2524 | C152 | NO | 0.21008 |  | Retention | Retention |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 8
[11 empty] | WF6_7658 | C152 | NO | 1.5862 |  | Harvest Processing | Non-Mulch |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
[11 empty] | WF6_7660 | C152 | NO | 1.2336 |  | Harvest Processing | Non-Mulch |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
[11 empty] | WF6_2526 | C153 | NO | 0.10319 |  | Harvest Processing | Non-Mulch | ANWIN | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
[11 empty] | WF6_7659 | C153 | NO | 2.1478 |  | Harvest Processing | Non-Mulch |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
[11 empty] | WF6_2523 | C154 | NO | 0.42967 |  | Harvest Processing | Non-Mulch |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_7089 | C154 | NO | 0.65107 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_7091 | C154 | NO | 0.30376 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_2530 | C154 | NO | 0.10923 |  | Harvest Disposal | Mulch |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_2528 | C154 | NO | 0.076976 |  | Non Productive | Non-Treed |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_2527 | C154 | NO | 0.35162 |  | Retention | Retention |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 8
[11 empty] | WF6_2529 | C154 | NO | 0.16454 |  | Retention | Retention |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 8
[11 empty] | WF6_2531 | C154 | NO | 0.13976 |  | Retention | Retention |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 8
[11 empty] | WF6_7090 | C155 | NO | 0.82923 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_2516 | C155 | NO | 0.27488 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 16 | C154-C156 | 0 | 1 | 0 | 0
[11 empty] | WF6_2516 | C155 | NO | 0.27083 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 16 | C154-C156 | 0 | 1 | 0 | 0
[11 empty] | WF6_2516 | C155 | NO | 0.29812 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 16 | C154-C156 | 0 | 1 | 0 | 0
[11 empty] | WF6_2530 | C155 | NO | 0.59154 |  | Harvest Disposal | Mulch |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
[11 empty] | WF6_6406 | C156 | NO | 0.24621 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 19 | C156-C158 | 0 | 1 | 0 | 0
[11 empty] | WF6_6115 | C156 | NO | 0.24163 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 19 | C156-C158 | 0 | 1 | 0 | 0
[11 empty] | WF6_7092 | C156 | NO | 0.16452 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2530 | C156 | NO | 2.1884 |  | Harvest Disposal | Mulch |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2572 | C156 | NO | 0.15561 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 17 | C156-C158 | 0 | 1 | 0 | 0
[11 empty] | WF6_2572 | C156 | NO | 0.028348 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 17 | C156-C158 | 0 | 1 | 0 | 0
[11 empty] | WF6_2572 | C156 | NO | 0.899 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 18 | C156-C158 | 0 | 1 | 0 | 0
[11 empty] | WF6_2533 | C156 | NO | 0.096645 |  | Retention | Retention |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 8
[11 empty] | WF6_7046 | C157 | YES | 0.14579 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_7093 | C157 | NO | 1.0079 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2542 | C157 | YES | 0.061137 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2530 | C157 | NO | 0.31183 |  | Harvest Disposal | Mulch |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2535 | C157 | NO | 0.1388 |  | Non-Merch Disposal | Mulch |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2548 | C157 | YES | 0.088784 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2550 | C157 | NO | 0.014131 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
[11 empty] | WF6_2534 | C157 | NO | 0.28199 |  | Retention | Retention |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 8
[11 empty] | WF6_2555 | C157 | NO | 0.061689 |  | Retention | Retention |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 8
[11 empty] | WF6_7048 | C158 | YES | 0.10647 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_7094 | C158 | NO | 0.019833 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_6342 | C158 | NO | 0.042617 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
[11 empty] | WF6_6342 | C158 | NO | 0.010947 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
[11 empty] | WF6_2544 | C158 | YES | 0.058211 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_2535 | C158 | NO | 0.37447 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_2537 | C158 | NO | 1.4269 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_2574 | C158 | NO | 0.042909 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
[11 empty] | WF6_2574 | C158 | NO | 0.015608 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
[11 empty] | WF6_2536 | C158 | NO | 0.13955 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
[11 empty] | WF6_2556 | C158 | NO | 0.13517 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
[11 empty] | WF6_2552 | C159 | YES | 0.14867 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_7095 | C159 | NO | 0.34434 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_2537 | C159 | NO | 0.68017 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_2538 | C159 | NO | 0.086391 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
[11 empty] | WF6_2539 | C159 | NO | 0.19795 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
[11 empty] | WF6_2557 | C159 | NO | 0.29359 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
[11 empty] | WF6_7731 | C159 | NO | 0.62383 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
[11 empty] | WF6_6340 | C160 | NO | 1.7153 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
[11 empty] | WF6_2541 | C160 | NO | 0.43062 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
[11 empty] | WF6_2540 | C160 | NO | 0.11478 |  | Non Productive | Non-Treed |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
[11 empty] | WF6_2541 | C161 | NO | 2.2964 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
[11 empty] | WF6_7047 | C162 | YES | 0.4515 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_7096 | C162 | NO | 0.10892 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_7097 | C162 | NO | 0.055834 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_2543 | C162 | YES | 0.057548 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_2541 | C162 | NO | 0.018924 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
[11 empty] | WF6_2541 | C162 | NO | 0.94825 |  | Non-Merch Disposal | Mulch |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_2546 | C162 | NO | 0.48593 |  | Non-Merch Disposal | Mulch |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_2545 | C162 | YES | 0.10122 |  | Retention | Retention |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 8
[11 empty] | WF6_2558 | C162 | NO | 0.07434 |  | Retention | Retention |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 8
[11 empty] | WF6_2546 | C163 | NO | 2.2169 |  | Non-Merch Disposal | Mulch |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
[11 empty] | WF6_7098 | C164 | NO | 0.060644 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
[11 empty] | WF6_7099 | C164 | NO | 0.010821 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
[11 empty] | WF6_2546 | C164 | NO | 0.20999 |  | Non-Merch Disposal | Mulch |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
[11 empty] | WF6_2549 | C164 | NO | 1.9567 |  | Harvest Disposal | Mulch |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
[11 empty] | WF6_2547 | C164 | NO | 0.052652 |  | Retention | Retention |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 8
[11 empty] | WF6_2559 | C164 | NO | 0.046272 |  | Retention | Retention |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 8
[11 empty] | WF6_2549 | C165 | NO | 1.5329 |  | Harvest Disposal | Mulch |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
[11 empty] | WF6_2551 | C165 | NO | 0.13053 |  | Retention | Retention |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 8
[11 empty] | WF6_2549 | C166 | NO | 0.45926 |  | Harvest Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_2553 | C166 | NO | 1.3113 |  | Non-Merch Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_2554 | C166 | NO | 0.049653 |  | Non Productive | Non-Treed |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_2553 | C167 | NO | 0.70793 |  | Non-Merch Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_2561 | C167 | NO | 0.85254 |  | Non-Merch Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_2564 | C167 | NO | 0.58385 |  | Harvest Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_2560 | C167 | NO | 0.036613 |  | Non Productive | Non-Treed |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
[11 empty] | WF6_6341 | C168 | NO | 1.3505 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_7100 | C168 | NO | 0.49916 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_7101 | C168 | NO | 0.055486 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_2562 | C168 | NO | 0.17689 |  | Harvest Disposal | Mulch | ANWIN | 6 | 25 | C168-C170 | 0 | 1 | 0 | 0
[11 empty] | WF6_2564 | C168 | NO | 0.21239 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_2583 | C168 | NO | 0.19606 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
[11 empty] | WF6_2568 | C169 | NO | 0.045745 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_7102 | C169 | NO | 0.072506 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_2566 | C169 | NO | 0.13072 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_2567 | C169 | NO | 0.025441 |  | Non Productive | Non-Treed |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_2569 | C169 | NO | 0.44246 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
[11 empty] | WF6_2582 | C169 | NO | 0.40217 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
[11 empty] | WF6_7732 | C169 | NO | 0.70586 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
[11 empty] | WF6_2592 | C170 | YES | 0.06275 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_2578 | C170 | NO | 0.0135 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2594 | C170 | NO | 0.085007 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_3738 | C170 | NO | 0.014217 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2580 | C170 | YES | 0.13297 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2581 | C170 | YES | 0.11946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7103 | C170 | NO | 0.48748 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7104 | C170 | NO | 0.47462 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2566 | C170 | NO | 0.26845 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2579 | C170 | NO | 0.28467 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2576 | C170 | NO | 0.31347 |  | Non Productive | Non-Treed |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2565 | C170 | NO | 0.49975 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
[11 empty] | WF6_2573 | C170 | NO | 0.31289 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
[11 empty] | WF6_2582 | C170 | NO | 0.010744 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
[11 empty] | WF6_2582 | C170 | NO | 1.0109 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
[11 empty] | WF6_2589 | C170 | NO | 0.6653 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
[11 empty] | WF6_7264 | C170 | NO | 0.018536 |  | Non Productive | Non-Treed |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7532 | C170 | NO | 0.033908 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7533 | C170 | NO | 0.046237 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_7732 | C170 | NO | 0.092017 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2603 | C171 | YES | 0.044923 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_2590 | C171 | NO | 0.03518 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2584 | C171 | YES | 0.088083 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2585 | C171 | YES | 0.28755 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7049 | C171 | YES | 0.093333 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_7105 | C171 | NO | 1.2434 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7106 | C171 | NO | 0.12009 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_7108 | C171 | NO | 0.3064 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_2579 | C171 | NO | 0.64878 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2586 | C171 | NO | 0.32962 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2616 | C171 | NO | 0.36778 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 26 | C170-C172 | 0 | 1 | 0 | 0
[11 empty] | WF6_2589 | C171 | NO | 0.48927 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
[11 empty] | WF6_2593 | C171 | NO | 0.65044 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
[11 empty] | WF6_7501 | C171 | YES | 0.1032 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_7533 | C171 | NO | 0.22278 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_2591 | C171 | NO | 0.17331 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2604 | C172 | YES | 0.13403 |  | Retention | Retention |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
[11 empty] | WF6_2607 | C172 | NO | 0.014423 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2588 | C172 | YES | 0.17089 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2600 | C172 | NO | 0.026805 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_7107 | C172 | NO | 0.35845 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_7109 | C172 | NO | 0.05275 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2586 | C172 | NO | 0.018702 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
[11 empty] | WF6_2586 | C172 | NO | 0.23855 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2605 | C172 | NO | 0.56282 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2616 | C172 | NO | 0.012588 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 26 | C170-C172 | 0 | 1 | 0 | 0
[11 empty] | WF6_2616 | C172 | NO | 0.12933 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 27 | C172-C174 | 0 | 1 | 0 | 0
[11 empty] | WF6_2596 | C172 | NO | 1.1028 |  | Retention | Retention |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 8
[11 empty] | WF6_7858 | C172 | NO | 0.05621 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2606 | C173 | YES | 0.021305 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_7050 | C173 | YES | 0.33055 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_7110 | C173 | NO | 0.10912 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2605 | C173 | NO | 0.95339 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2609 | C173 | NO | 0.33105 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
[11 empty] | WF6_2609 | C174 | NO | 1.4573 |  | Harvest Disposal | Mulch |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_2614 | C175 | YES | 0.022294 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_7051 | C175 | YES | 0.18694 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_7053 | C175 | YES | 0.056678 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_7111 | C175 | NO | 0.44678 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_2609 | C175 | NO | 0.27904 |  | Harvest Disposal | Mulch |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_2610 | C175 | NO | 0.087473 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 28 | C174-C176 | 0 | 1 | 0 | 0
[11 empty] | WF6_2631 | C175 | NO | 0.10404 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 28 | C174-C176 | 0 | 1 | 0 | 0
[11 empty] | WF6_2619 | C175 | NO | 0.21817 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_7852 | C175 | YES | 0.15621 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
[11 empty] | WF6_7052 | C176 | YES | 0.96733 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_7112 | C176 | NO | 0.98284 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_7113 | C176 | NO | 0.032321 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2598 | C176 | NO | 0.12837 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
[11 empty] | WF6_2599 | C176 | NO | 0.01176 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
[11 empty] | WF6_2613 | C176 | NO | 0.11276 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
[11 empty] | WF6_2618 | C176 | NO | 0.55037 |  | Harvest Disposal | Mulch |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2619 | C176 | NO | 0.015359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2622 | C177 | YES | 0.028565 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2620 | C177 | YES | 0.34456 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2623 | C177 | NO | 0.10356 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_7054 | C177 | YES | 0.6263 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_7114 | C177 | NO | 0.033976 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2595 | C177 | NO | 0.32553 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
[11 empty] | WF6_2599 | C177 | NO | 0.041341 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
[11 empty] | WF6_2612 | C177 | NO | 0.31168 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
[11 empty] | WF6_2618 | C177 | NO | 0.28989 |  | Harvest Disposal | Mulch |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2625 | C177 | NO | 0.39961 |  | Harvest Disposal | Mulch |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2621 | C177 | YES | 0.18657 |  | Non Productive | Non-Treed |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_2628 | C177 | YES | 0.31603 |  | Retention | Retention |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 8
[11 empty] | WF6_2633 | C177 | NO | 0.060521 |  | Retention | Retention |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 8
[11 empty] | WF6_7265 | C177 | YES | 0.44009 |  | Non Productive | Non-Treed |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_7859 | C177 | NO | 0.60787 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
[11 empty] | WF6_7115 | C178 | NO | 0.070707 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_7116 | C178 | NO | 0.73634 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_2608 | C178 | NO | 0.24557 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 30 | C178-C180 | 0 | 1 | 0 | 0
[11 empty] | WF6_2612 | C178 | NO | 0.2554 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 30 | C178-C180 | 0 | 1 | 0 | 0
[11 empty] | WF6_2625 | C178 | NO | 2.1972 |  | Harvest Disposal | Mulch |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_2642 | C178 | YES | 0.092366 |  | Non Productive | Non-Treed |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_2633 | C178 | NO | 0.34854 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
[11 empty] | WF6_2637 | C178 | NO | 0.29497 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
[11 empty] | WF6_2638 | C178 | NO | 0.071407 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
[11 empty] | WF6_7734 | C178 | NO | 0.051937 |  | Harvest Disposal | Mulch |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_7117 | C179 | NO | 0.78942 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_2608 | C179 | NO | 0.80778 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 30 | C178-C180 | 0 | 1 | 0 | 0
[11 empty] | WF6_2642 | C179 | YES | 0.37651 |  | Non Productive | Non-Treed |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_2638 | C179 | NO | 1.1299 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
[11 empty] | WF6_7733 | C179 | NO | 1.1335 |  | Harvest Disposal | Mulch |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
[11 empty] | WF6_2646 | C180 | YES | 0.039988 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_6343 | C180 | NO | 1.2579 |  | Harvest Disposal | Mulch |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_7118 | C180 | NO | 0.088088 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_7119 | C180 | NO | 0.088226 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2608 | C180 | NO | 0.14185 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 31 | C180-C182 | 0 | 1 | 0 | 0
[11 empty] | WF6_2636 | C180 | NO | 0.69228 |  | Harvest Disposal | Mulch |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2653 | C180 | NO | 0.14472 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 31 | C180-C182 | 0 | 1 | 0 | 0
[11 empty] | WF6_2639 | C180 | YES | 0.05094 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2640 | C180 | YES | 0.05594 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2635 | C180 | NO | 0.031438 |  | Non Productive | Non-Treed |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2643 | C180 | YES | 0.029071 |  | Non Productive | Non-Treed |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2632 | C180 | NO | 0.24764 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_2634 | C180 | NO | 0.061944 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_2638 | C180 | NO | 0.012652 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
[11 empty] | WF6_2638 | C180 | NO | 0.24318 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_2641 | C180 | NO | 0.97877 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_2644 | C180 | NO | 0.47945 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_2647 | C180 | NO | 0.11948 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_7266 | C180 | NO | 0.01291 |  | Non Productive | Non-Treed |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_7120 | C181 | NO | 0.083887 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_7121 | C181 | NO | 0.08381 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2636 | C181 | NO | 2.4781 |  | Harvest Disposal | Mulch |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
[11 empty] | WF6_2653 | C181 | NO | 0.89529 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 31 | C180-C182 | 0 | 1 | 0 | 0
[11 empty] | WF6_2647 | C181 | NO | 0.64417 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_2648 | C181 | NO | 0.21394 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
[11 empty] | WF6_6344 | C182 | NO | 0.19753 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_2636 | C182 | NO | 0.72877 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_2653 | C182 | NO | 0.30234 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 32 | C182-C184 | 0 | 1 | 0 | 0
[11 empty] | WF6_7860 | C182 | NO | 1.4914 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_7055 | C183 | YES | 0.22546 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_7056 | C183 | YES | 0.18617 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_7122 | C183 | NO | 0.01952 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_2650 | C183 | YES | 0.25726 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_2649 | C183 | NO | 0.14047 |  | Harvest Disposal | Mulch | ANWIN | 6 | 32 | C182-C184 | 0 | 1 | 0 | 0
[11 empty] | WF6_2651 | C183 | NO | 0.081493 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_2654 | C183 | NO | 0.1066 |  | Retention | Retention |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 8
[11 empty] | WF6_2655 | C183 | YES | 0.10411 |  | Retention | Retention |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 8
[11 empty] | WF6_7735 | C183 | NO | 0.44734 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_7861 | C183 | NO | 0.17292 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_7862 | C183 | NO | 0.82017 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
[11 empty] | WF6_6345 | C184 | NO | 0.39795 |  | Harvest Disposal | Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_7123 | C184 | NO | 1.2583 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_7124 | C184 | NO | 0.0626 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_6346 | C184 | NO | 0.37299 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
[11 empty] | WF6_2659 | C184 | NO | 0.42279 |  | Harvest Disposal | Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2676 | C184 | NO | 0.3751 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
[11 empty] | WF6_2674 | C184 | NO | 0.15512 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
[11 empty] | WF6_2657 | C184 | NO | 0.026852 |  | Non Productive | Non-Treed |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2656 | C184 | NO | 0.022383 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_2658 | C184 | NO | 0.078919 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_6300 | C185 | NO | 0.016112 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_7057 | C185 | NO | 0.29407 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_7125 | C185 | NO | 0.014572 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_7199 | C185 | NO | 0.018519 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2663 | C185 | NO | 0.11079 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2659 | C185 | NO | 0.29544 |  | Harvest Disposal | Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2684 | C185 | NO | 0.13137 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
[11 empty] | WF6_2668 | C185 | NO | 0.23125 |  | Harvest Processing | Non-Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2670 | C185 | NO | 0.1751 |  | Harvest Processing | Non-Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2665 | C185 | YES | 0.12568 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2669 | C185 | YES | 0.07387 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2661 | C185 | NO | 0.14605 |  | Non Productive | Non-Treed |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2667 | C185 | NO | 0.042064 |  | Non Productive | Non-Treed |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
[11 empty] | WF6_2660 | C185 | NO | 0.13462 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_2662 | C185 | NO | 0.14863 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_2666 | C185 | NO | 0.02779 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_2671 | C185 | YES | 0.24796 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_2672 | C185 | NO | 0.095889 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_7276 | C185 | NO | 0.046412 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_7277 | C185 | NO | 0.045913 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
[11 empty] | WF6_2684 | C186 | NO | 0.10017 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
[11 empty] | WF6_2684 | C186 | NO | 0.82853 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
[11 empty] | WF6_2668 | C186 | NO | 1.6761 |  | Harvest Processing | Non-Mulch |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 0
[11 empty] | WF6_2677 | C186 | NO | 0.081844 |  | Non Productive | Non-Treed |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 0
[11 empty] | WF6_2699 | C187 | NO | 0.07672 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
[11 empty] | WF6_2668 | C187 | NO | 1.688 |  | Harvest Processing | Non-Mulch |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 0
[11 empty] | WF6_2673 | C187 | NO | 0.059106 |  | Retention | Retention |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 8
[11 empty] | WF6_2681 | C187 | NO | 0.096974 |  | Retention | Retention |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 8
[11 empty] | WF6_6347 | C188 | NO | 0.020325 |  | Harvest Disposal | Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_7126 | C188 | NO | 0.50044 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_7127 | C188 | NO | 0.13356 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_2664 | C188 | NO | 0.098355 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
[11 empty] | WF6_2678 | C188 | NO | 0.31202 |  | Harvest Disposal | Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_2699 | C188 | NO | 0.084412 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
[11 empty] | WF6_2699 | C188 | NO | 0.038507 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
[11 empty] | WF6_2699 | C188 | NO | 0.18621 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
[11 empty] | WF6_2699 | C188 | NO | 0.36961 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
[11 empty] | WF6_2668 | C188 | NO | 0.30402 |  | Harvest Processing | Non-Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_2675 | C188 | NO | 0.16436 |  | Retention | Retention |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 8
[11 empty] | WF6_2682 | C188 | NO | 0.082835 |  | Retention | Retention |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 8
[11 empty] | WF6_7128 | C189 | NO | 0.1736 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_7129 | C189 | NO | 0.10716 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_7130 | C189 | NO | 0.048283 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_2664 | C189 | NO | 0.73686 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
[11 empty] | WF6_2678 | C189 | NO | 1.2298 |  | Harvest Disposal | Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_2680 | C189 | NO | 0.073411 |  | Retention | Retention |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 8
[11 empty] | WF6_7863 | C189 | NO | 0.096278 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
[11 empty] | WF6_2690 | C190 | YES | 0.04131 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2696 | C190 | NO | 0.032499 |  | Harvest Disposal | Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2689 | C190 | NO | 0.066494 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2692 | C190 | YES | 0.15502 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7131 | C190 | NO | 0.034501 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7132 | C190 | NO | 0.14884 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7200 | C190 | NO | 0.029354 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2664 | C190 | NO | 0.28283 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
[11 empty] | WF6_2678 | C190 | NO | 0.35316 |  | Harvest Disposal | Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2686 | C190 | NO | 0.41222 |  | Harvest Disposal | Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2714 | C190 | NO | 0.24256 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
[11 empty] | WF6_2691 | C190 | NO | 0.065366 |  | Harvest Processing | Non-Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2685 | C190 | NO | 0.12099 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
[11 empty] | WF6_2687 | C190 | NO | 0.47626 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
[11 empty] | WF6_2694 | C190 | NO | 0.086853 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
[11 empty] | WF6_2697 | C190 | NO | 0.40992 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
[11 empty] | WF6_7278 | C190 | NO | 0.013491 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
[11 empty] | WF6_7279 | C190 | NO | 0.021345 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
[11 empty] | WF6_2693 | C191 | YES | 0.014537 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2695 | C191 | YES | 0.12738 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2703 | C191 | YES | 0.017661 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2700 | C191 | NO | 0.023563 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7058 | C191 | YES | 0.29392 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7059 | C191 | YES | 0.24925 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7201 | C191 | NO | 0.34763 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7203 | C191 | NO | 0.084732 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2722 | C191 | NO | 0.55491 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
[11 empty] | WF6_2714 | C191 | NO | 0.01668 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
[11 empty] | WF6_2691 | C191 | NO | 0.51061 |  | Harvest Processing | Non-Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2704 | C191 | NO | 0.04737 |  | Harvest Processing | Non-Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2701 | C191 | NO | 0.6625 |  | Non Productive | Non-Treed |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_7878 | C191 | NO | 0.054203 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
[11 empty] | WF6_2704 | C192 | NO | 1.4006 |  | Harvest Processing | Non-Mulch |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2705 | C192 | NO | 0.092919 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
[11 empty] | WF6_2706 | C192 | NO | 0.090367 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
[11 empty] | WF6_7879 | C192 | NO | 0.12542 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2709 | C193 | YES | 0.1969 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2712 | C193 | YES | 0.018417 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2713 | C193 | YES | 0.054629 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_7202 | C193 | NO | 0.11494 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_6199 | C193 | NO | 0.15593 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
[11 empty] | WF6_6199 | C193 | NO | 0.18736 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
[11 empty] | WF6_2729 | C193 | NO | 0.1763 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
[11 empty] | WF6_2729 | C193 | NO | 0.64013 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
[11 empty] | WF6_2729 | C193 | NO | 0.035472 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2704 | C193 | NO | 0.22352 |  | Harvest Processing | Non-Mulch |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2708 | C193 | NO | 0.46129 |  | Non Productive | Non-Treed |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2707 | C193 | NO | 0.098167 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
[11 empty] | WF6_2721 | C193 | NO | 0.057625 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
[11 empty] | WF6_7726 | C193 | NO | 0.18273 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
[11 empty] | WF6_2715 | C194 | YES | 0.13561 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2723 | C194 | YES | 0.10503 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2710 | C194 | NO | 0.52657 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_7133 | C194 | NO | 0.048956 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2720 | C194 | NO | 1.0301 |  | Harvest Disposal | Mulch |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2729 | C194 | NO | 0.73127 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2729 | C194 | NO | 0.23194 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2729 | C194 | NO | 0.62473 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2711 | C194 | NO | 0.15671 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
[11 empty] | WF6_2716 | C194 | YES | 0.056502 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
[11 empty] | WF6_2719 | C194 | NO | 0.029132 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
[11 empty] | WF6_2724 | C194 | NO | 0.2452 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
[11 empty] | WF6_2725 | C194 | NO | 0.05583 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
[11 empty] | WF6_2717 | C194 | YES | 0.019321 |  | Non Productive | Non-Treed |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2718 | C194 | NO | 0.031351 |  | Non Productive | Non-Treed |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_6348 | C195 | NO | 0.018646 |  | Harvest Disposal | Mulch |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_7136 | C195 | NO | 0.085488 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_6349 | C195 | NO | 0.0023091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2720 | C195 | NO | 1.8213 |  | Harvest Disposal | Mulch |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2745 | C195 | NO | 0.017506 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2734 | C195 | NO | 0.099529 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
[11 empty] | WF6_7864 | C195 | NO | 0.02946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_7865 | C195 | NO | 0.079798 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_7866 | C195 | NO | 0.024558 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
[11 empty] | WF6_2733 | C197 | NO | 0.10342 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_7134 | C197 | NO | 0.038987 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_7135 | C197 | NO | 0.04517 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_7137 | C197 | NO | 0.20761 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_7138 | C197 | NO | 0.17654 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_6349 | C197 | NO | 0.0080222 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2731 | C197 | NO | 0.50102 |  | Harvest Disposal | Mulch |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_2749 | C197 | NO | 0.23552 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
[11 empty] | WF6_2749 | C197 | NO | 0.24018 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
[11 empty] | WF6_2749 | C197 | NO | 0.25351 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
[11 empty] | WF6_2749 | C197 | NO | 0.33406 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
[11 empty] | WF6_2727 | C197 | NO | 0.21723 |  | Non Productive | Non-Treed |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_2730 | C197 | NO | 0.21385 |  | Non Productive | Non-Treed |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_2726 | C197 | NO | 0.087579 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
[11 empty] | WF6_2728 | C197 | NO | 0.11384 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
[11 empty] | WF6_2732 | C197 | NO | 0.24057 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
[11 empty] | WF6_2736 | C197 | NO | 0.07689 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
[11 empty] | WF6_2737 | C197 | NO | 0.16927 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
[11 empty] | WF6_7267 | C197 | NO | 0.020793 |  | Non Productive | Non-Treed |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_2749 | C197 | NO | 0.024582 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
[11 empty] | WF6_2749 | C197 | NO | 0.024582 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
[11 empty] | WF6_2731 | C198 | NO | 0.28991 |  | Harvest Disposal | Mulch |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_2735 | C198 | NO | 1.5391 |  | Harvest Processing | Non-Mulch |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
[11 empty] | WF6_2740 | C199 | NO | 0.023494 |  | Harvest Disposal | Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
[11 empty] | WF6_2743 | C199 | NO | 0.46199 |  | Harvest Disposal | Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
[11 empty] | WF6_2735 | C199 | NO | 1.1711 |  | Harvest Processing | Non-Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
[11 empty] | WF6_2744 | C199 | NO | 0.31124 |  | Harvest Processing | Non-Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
[11 empty] | WF6_2741 | C199 | NO | 0.28143 |  | Retention | Retention |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 8
[11 empty] | WF6_2744 | C200 | NO | 2.6769 |  | Harvest Processing | Non-Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
[11 empty] | WF6_2750 | C202 | YES | 0.019709 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2764 | C202 | YES | 0.091147 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_7060 | C202 | YES | 0.46813 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_7061 | C202 | NO | 0.25905 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_7139 | C202 | NO | 0.056934 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_7204 | C202 | NO | 0.13717 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2758 | C202 | NO | 0.088872 |  | Harvest Disposal | Mulch |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2744 | C202 | NO | 0.031918 |  | Harvest Processing | Non-Mulch |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2744 | C202 | NO | 2.2012 |  | Harvest Processing | Non-Mulch |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2751 | C202 | NO | 3.0673 |  | Non Productive | Non-Treed |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2747 | C202 | NO | 0.17842 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2748 | C202 | NO | 0.16061 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2753 | C202 | YES | 0.03653 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2754 | C202 | NO | 0.1544 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2756 | C202 | NO | 0.26486 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2757 | C202 | YES | 0.10962 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2760 | C202 | NO | 0.023881 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2761 | C202 | YES | 0.11621 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2762 | C202 | YES | 0.061263 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_2767 | C202 | YES | 0.076006 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
[11 empty] | WF6_7853 | C202 | YES | 0.044486 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_7880 | C202 | NO | 0.047143 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
[11 empty] | WF6_2766 | C203 | YES | 0.34025 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_7140 | C203 | NO | 0.063582 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_7141 | C203 | NO | 0.34827 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_7142 | C203 | NO | 0.068359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_7143 | C203 | NO | 0.020368 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_7145 | C203 | NO | 0.018548 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2758 | C203 | NO | 1.0673 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2768 | C203 | NO | 0.042352 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2772 | C203 | NO | 0.1472 |  | Retention | Retention |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 8
[11 empty] | WF6_7146 | C204 | NO | 0.25636 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2768 | C204 | NO | 0.54751 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2771 | C204 | NO | 0.73769 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2786 | C204 | NO | 0.50431 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 42 | C203-C205 | 0 | 1 | 0 | 0
[11 empty] | WF6_2770 | C204 | NO | 0.074474 |  | Non Productive | Non-Treed |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
[11 empty] | WF6_2769 | C204 | NO | 0.1016 |  | Retention | Retention |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 8
[11 empty] | WF6_2774 | C204 | NO | 0.13451 |  | Retention | Retention |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 8
[11 empty] | WF6_2776 | C205 | YES | 0.14993 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_2781 | C205 | YES | 0.14964 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_7147 | C205 | NO | 0.15154 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_7148 | C205 | NO | 0.17122 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_2777 | C205 | NO | 0.024738 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2771 | C205 | NO | 0.67291 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_2780 | C205 | NO | 0.32573 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_2792 | C205 | NO | 0.070251 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2775 | C205 | NO | 0.046732 |  | Non Productive | Non-Treed |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_2773 | C205 | NO | 0.24914 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
[11 empty] | WF6_2779 | C205 | NO | 0.069511 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
[11 empty] | WF6_2782 | C205 | NO | 0.11347 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
[11 empty] | WF6_2784 | C205 | NO | 0.0919 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
[11 empty] | WF6_6350 | C206 | NO | 0.07516 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_7149 | C206 | NO | 0.72938 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_7151 | C206 | NO | 0.052003 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_2777 | C206 | NO | 0.010482 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_6339 | C206 | NO | 0.38259 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_6407 | C206 | NO | 0.29706 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_6407 | C206 | NO | 0.038041 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2504 | C206 | NO | 0.38239 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2630 | C206 | NO | 0.37694 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2630 | C206 | NO | 0.0466 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2630 | C206 | NO | 0.10017 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2630 | C206 | NO | 0.68955 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2780 | C206 | NO | 0.35145 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
[11 empty] | WF6_6116 | C206 | NO | 0.30379 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_6116 | C206 | NO | 0.037246 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2630 | C206 | NO | 0.019503 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_2630 | C206 | NO | 0.019503 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
[11 empty] | WF6_7150 | C207 | NO | 1.117 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
[11 empty] | WF6_7205 | C207 | NO | 0.042883 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
[11 empty] | WF6_2630 | C207 | NO | 0.8892 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 46 | C207-C209 | 0 | 1 | 0 | 0
[11 empty] | WF6_2785 | C207 | NO | 0.58415 |  | Harvest Processing | Non-Mulch |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
[11 empty] | WF6_2783 | C207 | NO | 0.22042 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
[11 empty] | WF6_2787 | C207 | NO | 0.20903 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
[11 empty] | WF6_7736 | C207 | NO | 0.17393 |  | Harvest Disposal | Mulch |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
[11 empty] | WF6_2630 | C208 | NO | 0.25656 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 46 | C207-C209 | 0 | 1 | 0 | 0
[11 empty] | WF6_2785 | C208 | NO | 1.7764 |  | Harvest Processing | Non-Mulch |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
[11 empty] | WF6_2790 | C208 | NO | 0.097509 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
[11 empty] | WF6_2804 | C208 | NO | 0.12906 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
[11 empty] | WF6_2794 | C209 | NO | 0.072397 |  | Harvest Disposal | Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
[11 empty] | WF6_6352 | C209 | NO | 0.040312 |  | Harvest Disposal | Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
[11 empty] | WF6_7157 | C209 | NO | 0.62155 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
[11 empty] | WF6_2785 | C209 | NO | 0.10847 |  | Harvest Processing | Non-Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
[11 empty] | WF6_2798 | C209 | NO | 0.6887 |  | Harvest Processing | Non-Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
[11 empty] | WF6_2810 | C209 | NO | 0.23183 |  | Retention | Retention |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 8
[11 empty] | WF6_2798 | C210 | NO | 1.2793 |  | Harvest Processing | Non-Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
[11 empty] | WF6_2816 | C211 | YES | 0.096861 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2825 | C211 | YES | 0.13383 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2830 | C211 | YES | 0.037706 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_7206 | C211 | NO | 0.38585 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_7210 | C211 | NO | 0.020712 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2844 | C211 | NO | 0.15784 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_2844 | C211 | NO | 0.37754 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_2798 | C211 | NO | 0.4338 |  | Harvest Processing | Non-Mulch |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2827 | C211 | NO | 0.14627 |  | Harvest Processing | Non-Mulch |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2817 | C211 | NO | 0.047377 |  | Non Productive | Non-Treed |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2821 | C211 | NO | 0.052202 |  | Non Productive | Non-Treed |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2814 | C211 | NO | 0.038987 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2815 | C211 | YES | 0.060226 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2820 | C211 | YES | 0.035832 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2824 | C211 | YES | 0.046208 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2835 | C211 | NO | 0.21599 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2838 | C211 | YES | 0.07958 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_7211 | C212 | NO | 0.28505 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2791 | C212 | NO | 0.51524 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_2844 | C212 | NO | 0.24985 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_2844 | C212 | NO | 0.33683 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_2827 | C212 | NO | 1.2328 |  | Harvest Processing | Non-Mulch |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
[11 empty] | WF6_2829 | C212 | NO | 0.174 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2839 | C212 | NO | 0.21178 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
[11 empty] | WF6_2844 | C212 | NO | 0.012404 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_2844 | C212 | NO | 0.012404 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
[11 empty] | WF6_6301 | C213 | YES | 0.061761 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_6462 | C213 | NO | 0.012775 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_7062 | C213 | YES | 0.090278 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_7063 | C213 | YES | 0.021627 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_7207 | C213 | NO | 0.12435 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_7208 | C213 | NO | 0.02246 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_7209 | C213 | NO | 0.022764 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2802 | C213 | NO | 0.33799 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 49 | C213-C215 | 0 | 1 | 0 | 0
[11 empty] | WF6_2848 | C213 | NO | 0.16365 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 49 | C213-C215 | 0 | 1 | 0 | 0
[11 empty] | WF6_2848 | C213 | NO | 0.35993 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 49 | C213-C215 | 0 | 1 | 0 | 0
[11 empty] | WF6_2801 | C213 | NO | 1.8465 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2827 | C213 | NO | 0.17084 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2795 | C213 | YES | 0.28983 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2831 | C213 | NO | 0.29417 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2811 | C213 | YES | 1.3655 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_7881 | C213 | NO | 0.44607 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2809 | C214 | YES | 0.034237 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2812 | C214 | YES | 0.15242 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2846 | C214 | NO | 0.054855 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2799 | C214 | YES | 0.048165 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_7156 | C214 | NO | 0.031466 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2788 | C214 | NO | 0.33314 |  | Harvest Disposal | Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2788 | C214 | NO | 0.051841 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2801 | C214 | NO | 0.1363 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2795 | C214 | YES | 2.3244 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2807 | C214 | NO | 0.28748 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2807 | C214 | NO | 0.051429 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2789 | C214 | NO | 0.13722 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2796 | C214 | YES | 0.022253 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2797 | C214 | NO | 0.153 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2806 | C214 | NO | 0.15123 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2811 | C214 | YES | 0.1502 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2832 | C214 | NO | 0.01013 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2836 | C214 | NO | 0.85022 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
[11 empty] | WF6_2836 | C214 | NO | 0.19821 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_7854 | C214 | YES | 0.18109 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
[11 empty] | WF6_2841 | C215 | NO | 0.27446 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2841 | C215 | NO | 0.083279 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_6351 | C215 | NO | 0.98071 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7152 | C215 | NO | 0.062943 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7153 | C215 | NO | 0.13393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7154 | C215 | NO | 0.36816 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7158 | C215 | NO | 0.10351 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2788 | C215 | NO | 0.80476 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2851 | C215 | NO | 1.1144 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 50 | C215-C217 | 0 | 1 | 0 | 0
[11 empty] | WF6_2807 | C215 | NO | 1.0765 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2834 | C215 | YES | 0.011412 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2793 | C215 | NO | 0.080706 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_2833 | C215 | NO | 0.18981 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_2836 | C215 | NO | 0.45381 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_2843 | C215 | NO | 0.2063 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_2845 | C215 | NO | 1.3377 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_7269 | C215 | NO | 0.021981 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7867 | C215 | NO | 0.43393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2847 | C216 | NO | 0.25346 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7155 | C216 | NO | 1.0333 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7159 | C216 | NO | 0.56574 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7160 | C216 | NO | 0.097424 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7161 | C216 | NO | 0.049234 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7162 | C216 | NO | 0.036104 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2859 | C216 | NO | 0.11815 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 50 | C215-C217 | 0 | 1 | 0 | 0
[11 empty] | WF6_2859 | C216 | NO | 0.069818 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 50 | C215-C217 | 0 | 1 | 0 | 0
[11 empty] | WF6_2807 | C216 | NO | 0.6649 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2845 | C216 | NO | 0.68719 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_2849 | C216 | NO | 0.13214 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
[11 empty] | WF6_7268 | C216 | NO | 0.020583 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7269 | C216 | NO | 0.050675 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7270 | C216 | NO | 0.026734 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_7869 | C216 | NO | 0.087417 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
[11 empty] | WF6_2853 | C217 | NO | 0.023538 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_7064 | C217 | NO | 0.36558 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_7164 | C217 | NO | 0.012351 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_6118 | C217 | NO | 0.080169 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 51 | C217-C219 | 0 | 1 | 0 | 0
[11 empty] | WF6_2842 | C217 | NO | 0.26774 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 51 | C217-C219 | 0 | 1 | 0 | 0
[11 empty] | WF6_2860 | C217 | NO | 0.28909 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2861 | C217 | NO | 0.15743 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2857 | C217 | NO | 0.081267 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2852 | C217 | NO | 0.30003 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2855 | C217 | YES | 0.36481 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2858 | C217 | NO | 0.036844 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2850 | C217 | NO | 0.21363 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_2854 | C217 | NO | 0.25325 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_2856 | C217 | NO | 0.5854 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_7280 | C217 | NO | 0.10686 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_7281 | C217 | NO | 0.01086 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_7534 | C217 | NO | 0.046215 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_7868 | C217 | NO | 0.018091 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_7870 | C217 | NO | 0.18121 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_7163 | C218 | NO | 0.4179 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2860 | C218 | NO | 0.49078 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2866 | C218 | NO | 0.30473 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2865 | C218 | NO | 0.10352 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
[11 empty] | WF6_2862 | C218 | NO | 0.62522 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_2863 | C218 | NO | 0.63541 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_2867 | C218 | NO | 0.093109 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_2871 | C218 | NO | 0.053398 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
[11 empty] | WF6_7212 | C219 | NO | 0.046917 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
[11 empty] | WF6_2866 | C219 | NO | 0.7203 |  | Harvest Disposal | Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
[11 empty] | WF6_2869 | C219 | NO | 0.4375 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 52 | C219-C221 | 0 | 1 | 0 | 0
[11 empty] | WF6_2872 | C219 | NO | 0.86979 |  | Harvest Processing | Non-Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
[11 empty] | WF6_2870 | C219 | NO | 0.15675 |  | Retention | Retention |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 8
[11 empty] | WF6_2873 | C219 | NO | 0.12562 |  | Retention | Retention |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 8
[11 empty] | WF6_2874 | C219 | NO | 0.22247 |  | Retention | Retention |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 8
[11 empty] | WF6_2869 | C220 | NO | 0.33277 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 52 | C219-C221 | 0 | 1 | 0 | 0
[11 empty] | WF6_2876 | C220 | NO | 0.011456 |  | Non-Merch Disposal | Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
[11 empty] | WF6_2872 | C220 | NO | 1.7577 |  | Harvest Processing | Non-Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
[11 empty] | WF6_7213 | C221 | NO | 0.081061 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_2885 | C221 | NO | 0.16757 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2885 | C221 | NO | 0.16182 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2885 | C221 | NO | 0.14239 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2887 | C221 | NO | 0.13582 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2872 | C221 | NO | 1.179 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_2881 | C221 | NO | 0.22347 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_2878 | C221 | NO | 0.58045 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
[11 empty] | WF6_2879 | C221 | NO | 0.23932 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
[11 empty] | WF6_6463 | C222 | NO | 0.011131 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_7214 | C222 | NO | 0.13215 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_7215 | C222 | NO | 0.40984 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_7216 | C222 | NO | 0.11076 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_2887 | C222 | NO | 0.041164 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2887 | C222 | NO | 0.16478 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2887 | C222 | NO | 0.50541 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
[11 empty] | WF6_2881 | C222 | NO | 0.38525 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_2882 | C222 | NO | 0.050837 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
[11 empty] | WF6_2884 | C222 | NO | 0.085209 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
[11 empty] | WF6_7774 | C222 | NO | 0.31874 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
[11 empty] | WF6_6464 | C223 | NO | 0.92708 |  | Harvest Processing | Non-Mulch |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
[11 empty] | WF6_7219 | C223 | NO | 0.10374 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
[11 empty] | WF6_2883 | C223 | NO | 0.32035 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 54 | C223-C225 | 0 | 1 | 0 | 0
[11 empty] | WF6_2887 | C223 | NO | 0.10435 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 54 | C223-C225 | 0 | 1 | 0 | 0
[11 empty] | WF6_2886 | C223 | NO | 0.095537 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
[11 empty] | WF6_2889 | C223 | NO | 0.10326 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
[11 empty] | WF6_7775 | C223 | NO | 0.37235 |  | Harvest Processing | Non-Mulch |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
[11 empty] | WF6_6465 | C224 | NO | 1.7559 |  | Harvest Processing | Non-Mulch |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
[11 empty] | WF6_7217 | C224 | NO | 0.033227 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
[11 empty] | WF6_2883 | C224 | NO | 0.61874 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 54 | C223-C225 | 0 | 1 | 0 | 0
[11 empty] | WF6_2888 | C224 | NO | 0.087495 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
[11 empty] | WF6_2891 | C224 | NO | 0.12342 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
[11 empty] | WF6_7218 | C225 | NO | 1.0837 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
[11 empty] | WF6_2892 | C225 | NO | 0.27456 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_2897 | C225 | NO | 0.11015 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_7727 | C225 | NO | 0.97472 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
[11 empty] | WF6_2910 | C226 | NO | 0.039258 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 55 | C225-C227 | 0 | 1 | 0 | 0
[11 empty] | WF6_2898 | C226 | NO | 0.013619 |  | Non-Merch Disposal | Mulch |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
[11 empty] | WF6_2893 | C226 | NO | 0.25148 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
[11 empty] | WF6_7165 | C226 | NO | 0.68468 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
[11 empty] | WF6_2894 | C226 | NO | 0.24585 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 55 | C225-C227 | 0 | 1 | 0 | 0
[11 empty] | WF6_2910 | C226 | NO | 0.32764 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 55 | C225-C227 | 0 | 1 | 0 | 0
[11 empty] | WF6_2902 | C226 | NO | 0.32272 |  | Non Productive | Non-Treed |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
[11 empty] | WF6_2896 | C226 | NO | 0.10586 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_2900 | C226 | NO | 0.078745 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_2901 | C226 | NO | 0.030668 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_2903 | C226 | NO | 0.093863 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_2906 | C226 | NO | 0.092965 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
[11 empty] | WF6_2910 | C227 | NO | 1.0557 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 57 | C225-C227 | 0 | 1 | 0 | 0
[11 empty] | WF6_2905 | C227 | NO | 0.23936 |  | Non-Merch Disposal | Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_6354 | C227 | NO | 0.027233 |  | Non-Merch Disposal | Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_7166 | C227 | NO | 1.7743 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_6119 | C227 | NO | 9.2591 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 56 | C225-C227 | 0 | 1 | 0 | 0
[11 empty] | WF6_2910 | C227 | NO | 1.1023 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 56 | C225-C227 | 0 | 1 | 0 | 0
[11 empty] | WF6_2910 | C227 | NO | 0.1443 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 58 | C227-C229 | 0 | 1 | 0 | 0
[11 empty] | WF6_2910 | C227 | NO | 0.15098 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 58 | C227-C229 | 0 | 1 | 0 | 0
[11 empty] | WF6_2902 | C227 | NO | 0.17083 |  | Non Productive | Non-Treed |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_2904 | C227 | NO | 0.15017 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
[11 empty] | WF6_2907 | C227 | NO | 0.15588 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
[11 empty] | WF6_6354 | C228 | NO | 0.27086 |  | Non-Merch Disposal | Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_7220 | C228 | NO | 0.063975 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_2913 | C228 | NO | 0.13668 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 58 | C227-C229 | 0 | 1 | 0 | 0
[11 empty] | WF6_2908 | C228 | NO | 0.31116 |  | Harvest Processing | Non-Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_2909 | C228 | NO | 0.17998 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
[11 empty] | WF6_2911 | C228 | NO | 0.26848 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
[11 empty] | WF6_7777 | C228 | NO | 0.6504 |  | Harvest Processing | Non-Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
[11 empty] | WF6_6466 | C229 | NO | 1.3713 |  | Harvest Processing | Non-Mulch |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
[11 empty] | WF6_2913 | C229 | NO | 0.24711 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
[11 empty] | WF6_6120 | C229 | NO | 0.073332 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
[11 empty] | WF6_6121 | C229 | NO | 0.021666 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
[11 empty] | WF6_7221 | C230 | NO | 0.24066 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
[11 empty] | WF6_2916 | C230 | NO | 0.062852 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
[11 empty] | WF6_2918 | C230 | NO | 0.13624 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
[11 empty] | WF6_6121 | C230 | NO | 0.033391 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
[11 empty] | WF6_7776 | C230 | NO | 0.4253 |  | Harvest Processing | Non-Mulch |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
[11 empty] | WF6_7778 | C230 | NO | 0.90655 |  | Harvest Processing | Non-Mulch |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
[11 empty] | WF6_7779 | C231 | NO | 1.7245 |  | Harvest Processing | Non-Mulch |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_2922 | C232 | YES | 0.027973 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_2924 | C232 | YES | 0.067492 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_2926 | C232 | YES | 0.01242 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_6467 | C232 | NO | 1.4284 |  | Harvest Processing | Non-Mulch |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_7065 | C232 | YES | 0.081416 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_7066 | C232 | YES | 0.064749 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_7222 | C232 | NO | 0.017759 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_7223 | C232 | NO | 0.08437 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_7224 | C232 | NO | 0.036338 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_7225 | C232 | NO | 0.03305 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_6355 | C232 | NO | 0.04768 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
[11 empty] | WF6_6355 | C232 | NO | 0.050886 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
[11 empty] | WF6_2929 | C232 | NO | 0.054618 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
[11 empty] | WF6_2929 | C232 | NO | 0.05474 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
[11 empty] | WF6_2925 | C232 | NO | 0.56513 |  | Harvest Processing | Non-Mulch |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_2921 | C232 | YES | 0.70595 |  | Non Productive | Non-Treed |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
[11 empty] | WF6_2919 | C232 | NO | 0.027114 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
[11 empty] | WF6_2920 | C232 | YES | 0.046296 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
[11 empty] | WF6_2923 | C232 | NO | 0.075276 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
[11 empty] | WF6_2927 | C232 | NO | 0.71352 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
[11 empty] | WF6_6355 | C233 | NO | 0.059781 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_6355 | C233 | NO | 0.027804 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2928 | C233 | NO | 0.030638 |  | Non-Merch Disposal | Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2929 | C233 | NO | 0.064074 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2929 | C233 | NO | 0.027774 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2925 | C233 | NO | 2.5836 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2927 | C233 | NO | 0.55556 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
[11 empty] | WF6_2932 | C233 | NO | 0.074281 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
[11 empty] | WF6_2935 | C234 | NO | 0.066353 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2936 | C234 | YES | 0.078551 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2938 | C234 | YES | 0.068967 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_7226 | C234 | NO | 0.16102 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_7227 | C234 | NO | 0.097821 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_7229 | C234 | NO | 0.020543 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2914 | C234 | NO | 0.24499 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2914 | C234 | NO | 0.1144 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2915 | C234 | NO | 0.22555 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2915 | C234 | NO | 0.32393 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
[11 empty] | WF6_2915 | C234 | NO | 0.015282 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
[11 empty] | WF6_2925 | C234 | NO | 0.38957 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2933 | C234 | NO | 0.016299 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2937 | C234 | NO | 0.24791 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2940 | C234 | NO | 0.012402 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
[11 empty] | WF6_2931 | C234 | NO | 0.090334 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
[11 empty] | WF6_2934 | C234 | NO | 0.44717 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
[11 empty] | WF6_6468 | C235 | NO | 0.73498 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_7228 | C235 | NO | 0.14113 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2915 | C235 | NO | 0.040752 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
[11 empty] | WF6_2917 | C235 | NO | 0.81043 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
[11 empty] | WF6_2937 | C235 | NO | 0.88499 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2917 | C235 | NO | 0.015691 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
[11 empty] | WF6_2947 | C236 | YES | 0.10368 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2948 | C236 | YES | 0.12929 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2951 | C236 | YES | 0.069652 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_7067 | C236 | YES | 0.080531 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_7230 | C236 | NO | 0.016278 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_7231 | C236 | NO | 0.016734 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2917 | C236 | NO | 0.90709 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
[11 empty] | WF6_2945 | C236 | NO | 1.0085 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2950 | C236 | NO | 0.42376 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2944 | C236 | NO | 0.04736 |  | Non Productive | Non-Treed |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_7780 | C236 | NO | 0.17234 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
[11 empty] | WF6_2917 | C236 | NO | 0.015691 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
[11 empty] | WF6_2950 | C237 | NO | 1.4179 |  | Harvest Processing | Non-Mulch |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 0
[11 empty] | WF6_7232 | C238 | NO | 0.10616 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 0
[11 empty] | WF6_2949 | C238 | NO | 0.29372 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 63 | C237-C239 | 0 | 1 | 0 | 0
[11 empty] | WF6_2950 | C238 | NO | 1.8929 |  | Harvest Processing | Non-Mulch |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 0
[11 empty] | WF6_2956 | C238 | NO | 0.11067 |  | Retention | Retention |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 8
[11 empty] | WF6_7233 | C239 | NO | 0.067676 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
[11 empty] | WF6_7234 | C239 | NO | 0.25502 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
[11 empty] | WF6_2950 | C239 | NO | 1.8014 |  | Harvest Processing | Non-Mulch |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
[11 empty] | WF6_7235 | C240 | NO | 0.049572 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
[11 empty] | WF6_6122 | C240 | NO | 0.22012 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
[11 empty] | WF6_6122 | C240 | NO | 0.040396 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
[11 empty] | WF6_2950 | C240 | NO | 1.8933 |  | Harvest Processing | Non-Mulch |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
[11 empty] | WF6_2946 | C240 | NO | 0.38756 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
[11 empty] | WF6_2946 | C240 | NO | 0.059514 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
[11 empty] | WF6_7167 | C241 | NO | 0.50145 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_7236 | C241 | NO | 0.017285 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_7237 | C241 | NO | 0.021178 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_7317 | C241 | NO | 0.27503 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_7317 | C241 | NO | 0.10576 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_7317 | C241 | NO | 0.12939 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2959 | C241 | NO | 0.066074 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2950 | C241 | NO | 0.73583 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2960 | C241 | NO | 0.13847 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
[11 empty] | WF6_7535 | C241 | NO | 0.22431 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_7871 | C241 | NO | 0.01827 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_6356 | C242 | NO | 0.23654 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 67 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2980 | C242 | NO | 0.24011 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 67 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2962 | C242 | NO | 0.15279 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2964 | C242 | NO | 0.011702 |  | Non-Merch Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2965 | C242 | NO | 0.020632 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2975 | C242 | NO | 0.010189 |  | Non-Merch Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_7168 | C242 | NO | 0.071271 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_7238 | C242 | NO | 0.13214 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_6356 | C242 | NO | 0.32739 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_7317 | C242 | NO | 0.23059 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2952 | C242 | NO | 0.30611 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2952 | C242 | NO | 0.51797 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2978 | C242 | NO | 0.18411 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2980 | C242 | NO | 0.3384 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_6123 | C242 | NO | 0.51989 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
[11 empty] | WF6_2967 | C242 | NO | 0.11957 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2971 | C242 | NO | 0.030463 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2973 | C242 | NO | 0.3901 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2972 | C242 | NO | 0.044389 |  | Non Productive | Non-Treed |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
[11 empty] | WF6_2963 | C242 | NO | 0.32534 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
[11 empty] | WF6_2966 | C242 | NO | 0.095548 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
[11 empty] | WF6_2970 | C242 | NO | 0.3036 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
[11 empty] | WF6_2976 | C242 | NO | 0.25296 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
[11 empty] | WF6_7282 | C242 | NO | 0.75295 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
[11 empty] | WF6_7069 | C243 | NO | 0.29648 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_7239 | C243 | NO | 0.53892 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2973 | C243 | NO | 0.23861 |  | Harvest Processing | Non-Mulch |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2979 | C243 | NO | 0.096897 |  | Non Productive | Non-Treed |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2982 | C243 | NO | 0.10886 |  | Non Productive | Non-Treed |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2977 | C243 | NO | 1.0703 |  | Retention | Retention |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 8
[11 empty] | WF6_2981 | C243 | YES | 0.087267 |  | Retention | Retention |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 8
[11 empty] | WF6_7502 | C243 | NO | 0.012786 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2984 | C244 | NO | 0.05115 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_7068 | C244 | NO | 0.025465 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_7240 | C244 | NO | 0.078826 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_7241 | C244 | NO | 0.090862 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2987 | C244 | NO | 0.23493 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 68 | C243-C245 | 0 | 1 | 0 | 0
[11 empty] | WF6_2987 | C244 | NO | 0.95649 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 68 | C243-C245 | 0 | 1 | 0 | 0
[11 empty] | WF6_2985 | C244 | NO | 1.6075 |  | Harvest Processing | Non-Mulch |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_2986 | C244 | NO | 0.030029 |  | Harvest Processing | Non-Mulch |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
[11 empty] | WF6_7169 | C245 | NO | 0.5655 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2990 | C245 | NO | 0.015246 |  | Harvest Disposal | Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2995 | C245 | NO | 0.37808 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
[11 empty] | WF6_2985 | C245 | NO | 1.5453 |  | Harvest Processing | Non-Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2989 | C245 | NO | 0.029925 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2974 | C245 | NO | 0.25594 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
[11 empty] | WF6_2974 | C245 | NO | 0.31287 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
[11 empty] | WF6_2974 | C245 | NO | 0.32745 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
[11 empty] | WF6_2988 | C245 | NO | 0.119 |  | Retention | Retention |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 8
[11 empty] | WF6_2991 | C245 | NO | 0.18283 |  | Retention | Retention |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 8
[11 empty] | WF6_6357 | C246 | NO | 0.055017 |  | Harvest Disposal | Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_7242 | C246 | NO | 0.12842 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2995 | C246 | NO | 0.15317 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
[11 empty] | WF6_2992 | C246 | NO | 0.032053 |  | Harvest Processing | Non-Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2993 | C246 | NO | 1.5404 |  | Harvest Processing | Non-Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_7872 | C246 | NO | 0.35416 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
[11 empty] | WF6_2999 | C247 | NO | 0.055453 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_2996 | C247 | NO | 0.23628 |  | Harvest Disposal | Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_2997 | C247 | NO | 0.12492 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_7070 | C247 | NO | 0.16781 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_7170 | C247 | NO | 0.38758 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_2942 | C247 | NO | 1.9641 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2958 | C247 | NO | 0.29565 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2958 | C247 | NO | 0.8218 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2958 | C247 | NO | 0.31796 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2993 | C247 | NO | 0.22407 |  | Harvest Processing | Non-Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_2998 | C247 | NO | 0.55483 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8