[11 empty] | WF6_2958 | C247 | NO | 0.011688 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_3001 | C248 | YES | 0.10687 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3009 | C248 | YES | 0.084072 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3011 | C248 | NO | 0.17658 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_7171 | C248 | NO | 0.017446 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3010 | C248 | NO | 0.23504 |  | Harvest Disposal | Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3003 | C248 | NO | 1.2176 |  | Non Productive | Non-Treed |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3000 | C248 | YES | 0.0566 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_3006 | C248 | NO | 0.24969 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_3007 | C248 | YES | 0.034938 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_3012 | C248 | NO | 0.24434 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_7855 | C248 | NO | 0.17318 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_2958 | C248 | NO | 0.011688 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_3013 | C249 | NO | 0.12578 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7172 | C249 | NO | 0.020875 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7173 | C249 | NO | 0.42735 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_2942 | C249 | NO | 0.32899 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2968 | C249 | NO | 0.02996 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2968 | C249 | NO | 0.71442 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_2968 | C249 | NO | 0.767 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_3010 | C249 | NO | 0.64808 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3014 | C249 | NO | 0.53263 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3015 | C249 | NO | 0.093906 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_6516 | C249 | NO | 0.01259 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7283 | C249 | NO | 0.021136 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7284 | C249 | NO | 0.058701 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7174 | C250 | NO | 1.1359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7175 | C250 | NO | 0.054772 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3014 | C250 | NO | 0.39443 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3017 | C250 | NO | 0.15519 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_3025 | C250 | NO | 0.26099 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_3020 | C250 | NO | 0.26188 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7737 | C250 | NO | 0.54869 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7873 | C250 | NO | 0.029525 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3021 | C251 | NO | 0.030383 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6302 | C251 | NO | 0.019707 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6303 | C251 | NO | 0.028065 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6358 | C251 | NO | 0.2456 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6359 | C251 | NO | 0.032567 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7071 | C251 | NO | 0.63388 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7176 | C251 | NO | 0.037882 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7177 | C251 | NO | 0.028593 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7178 | C251 | NO | 0.23923 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7244 | C251 | NO | 0.023615 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3017 | C251 | NO | 0.45314 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3022 | C251 | NO | 0.5587 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3019 | C251 | NO | 0.056078 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3023 | C251 | NO | 0.13838 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3024 | C251 | NO | 0.030306 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3027 | C251 | NO | 0.096388 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7285 | C251 | NO | 0.016608 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3035 | C252 | NO | 0.041736 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7243 | C252 | NO | 0.049184 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7245 | C252 | NO | 0.023093 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7246 | C252 | NO | 0.052251 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7247 | C252 | NO | 0.013689 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.3271 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.29116 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.734 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3028 | C252 | NO | 1.3814 |  | Harvest Processing | Non-Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3033 | C252 | NO | 0.11157 |  | Harvest Processing | Non-Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3030 | C252 | NO | 0.37947 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3031 | C252 | NO | 0.056496 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_6517 | C252 | NO | 0.05309 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7286 | C252 | NO | 0.090153 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7287 | C252 | NO | 0.068876 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7738 | C252 | NO | 0.090328 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7874 | C252 | NO | 0.16385 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7882 | C252 | NO | 0.075291 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.015367 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3039 | C253 | NO | 0.047705 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3043 | C253 | NO | 0.013592 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3038 | C253 | NO | 0.029533 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3042 | C253 | YES | 0.11722 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3037 | C253 | NO | 0.032564 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7248 | C253 | NO | 0.011782 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7249 | C253 | NO | 0.05737 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.18485 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.1091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.49732 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.11953 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3034 | C253 | NO | 0.12847 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_6198 | C253 | NO | 0.22835 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3033 | C253 | NO | 1.0471 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3036 | C253 | NO | 0.32301 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3041 | C253 | NO | 0.29741 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3004 | C253 | NO | 0.015367 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3046 | C254 | NO | 0.22395 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3040 | C254 | NO | 1.4545 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3034 | C254 | NO | 0.10611 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_6198 | C254 | NO | 0.29671 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_6198 | C254 | NO | 0.52547 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3044 | C254 | NO | 0.067405 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3045 | C254 | NO | 0.083102 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3048 | C254 | NO | 0.069259 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_8197 | C254 | NO | 0.057505 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7661 | C254 | NO | 0.036359 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7536 | C254 | NO | 0.053333 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_8228 | C254 | NO | 0.037762 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_8229 | C254 | NO | 0.095963 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7538 | C255 | NO | 1.4538 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_8230 | C255 | NO | 0.16305 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3049 | C256 | NO | 0.22973 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3052 | C256 | NO | 0.44079 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3056 | C256 | NO | 0.16953 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3055 | C256 | NO | 0.10409 |  | Non Productive | Non-Treed |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3050 | C256 | NO | 0.5416 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
[11 empty] | WF6_3054 | C256 | NO | 0.39417 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
[11 empty] | WF6_3057 | C256 | NO | 0.032888 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
[11 empty] | WF6_8198 | C256 | NO | 0.17061 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_7537 | C256 | NO | 0.058296 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_7179 | C257 | NO | 0.79644 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3053 | C257 | NO | 0.34647 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
[11 empty] | WF6_3056 | C257 | NO | 0.54854 |  | Harvest Disposal | Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7875 | C257 | NO | 0.029992 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3062 | C258 | YES | 0.03107 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_6304 | C258 | YES | 0.03026 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_6360 | C258 | NO | 0.33292 |  | Harvest Disposal | Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7072 | C258 | YES | 0.40191 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7180 | C258 | NO | 0.92001 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7250 | C258 | NO | 0.079551 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3053 | C258 | NO | 0.16918 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
[11 empty] | WF6_3060 | C258 | NO | 0.14208 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
[11 empty] | WF6_3063 | C258 | NO | 0.23088 |  | Harvest Processing | Non-Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3059 | C258 | NO | 0.13929 |  | Retention | Retention |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 8
[11 empty] | WF6_3070 | C259 | YES | 0.40056 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3064 | C259 | YES | 0.20371 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3066 | C259 | YES | 0.94426 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3069 | C259 | YES | 0.02957 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7251 | C259 | NO | 0.10634 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3058 | C259 | NO | 0.70497 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 77 | C259-C261 | 0 | 1 | 0 | 0
[11 empty] | WF6_3063 | C259 | NO | 0.17497 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3072 | C259 | NO | 0.039219 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3065 | C259 | YES | 0.059874 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3068 | C259 | YES | 0.24989 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7271 | C259 | YES | 0.023112 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7272 | C259 | YES | 0.012546 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7273 | C259 | YES | 0.016072 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3077 | C260 | YES | 0.33676 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3085 | C260 | YES | 0.02669 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7252 | C260 | NO | 0.14151 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3071 | C260 | NO | 0.47146 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 77 | C259-C261 | 0 | 1 | 0 | 0
[11 empty] | WF6_3072 | C260 | NO | 0.16536 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3078 | C260 | NO | 0.14023 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3074 | C260 | YES | 0.10437 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3075 | C260 | YES | 0.032662 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3073 | C260 | YES | 0.033663 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
[11 empty] | WF6_3076 | C260 | YES | 0.086622 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
[11 empty] | WF6_3084 | C260 | YES | 0.1256 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
[11 empty] | WF6_7274 | C260 | YES | 0.035372 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7503 | C260 | YES | 0.35282 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7253 | C261 | NO | 0.17724 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_6197 | C261 | NO | 0.16646 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_6197 | C261 | NO | 0.015932 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3071 | C261 | NO | 0.016644 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3088 | C261 | NO | 0.21985 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3088 | C261 | NO | 0.026751 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3078 | C261 | NO | 0.26599 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3083 | C261 | NO | 0.53253 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3067 | C261 | NO | 0.71685 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3082 | C261 | NO | 0.047519 |  | Non Productive | Non-Treed |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3061 | C261 | NO | 0.31596 |  | Retention | Retention |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 8
[11 empty] | WF6_7254 | C262 | NO | 0.37557 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 1 | 0 | 0
[11 empty] | WF6_3083 | C262 | NO | 1.8222 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3086 | C262 | NO | 0.6513 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3087 | C262 | NO | 0.38347 |  | Retention | Retention |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 8
[11 empty] | WF6_3083 | C263 | NO | 2.2285 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6207 | C264 | NO | 0.017191 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6361 | C264 | NO | 0.18422 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6409 | C264 | NO | 0.017019 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3080 | C264 | NO | 0.17974 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.15804 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.03102 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.033998 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.34847 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.34471 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3094 | C264 | NO | 0.058585 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3095 | C264 | NO | 0.60782 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6124 | C264 | NO | 0.060172 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C264 | NO | 2.2328 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3093 | C264 | NO | 0.075216 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 1 | 0 | 0 | 0
[11 empty] | WF6_3095 | C265 | NO | 0.080845 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3095 | C265 | NO | 0.51692 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C265 | NO | 0.023785 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C265 | NO | 1.8436 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3093 | C265 | NO | 0.020131 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3096 | C265 | NO | 0.95963 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3097 | C266 | YES | 0.02262 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_6469 | C266 | NO | 0.65416 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_7073 | C266 | YES | 0.42019 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_7255 | C266 | NO | 0.29261 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_7256 | C266 | NO | 0.083269 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3101 | C266 | NO | 0.61653 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3101 | C266 | NO | 0.20267 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C266 | NO | 0.078606 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3098 | C266 | NO | 0.014504 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3099 | C266 | NO | 1.7293 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3101 | C267 | NO | 0.069658 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3102 | C267 | NO | 0.087093 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3099 | C267 | NO | 2.5336 |  | Harvest Processing | Non-Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
[11 empty] | WF6_6195 | C268 | NO | 0.21282 |  | Harvest Disposal | Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
[11 empty] | WF6_6195 | C268 | NO | 0.011131 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.28329 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.26696 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.26019 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3099 | C268 | NO | 1.466 |  | Harvest Processing | Non-Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
[11 empty] | WF6_3104 | C268 | NO | 0.13755 |  | Retention | Retention |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 8
[11 empty] | WF6_3105 | C268 | NO | 0.21727 |  | Retention | Retention |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 8
[11 empty] | WF6_3103 | C268 | NO | 0.024094 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.024094 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_7182 | C269 | NO | 0.48098 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3103 | C269 | NO | 0.053912 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C269 | NO | 0.59699 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 83 | C269-C271 | 0 | 1 | 0 | 0
[11 empty] | WF6_3110 | C269 | NO | 0.15953 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3107 | C269 | NO | 0.2147 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3108 | C269 | NO | 0.41261 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3109 | C269 | NO | 0.81964 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3111 | C269 | NO | 0.022662 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_7615 | C269 | NO | 0.12929 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7616 | C269 | NO | 0.018186 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7765 | C269 | NO | 0.57172 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_6196 | C270 | NO | 0.31075 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_6421 | C270 | NO | 0.017417 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_6422 | C270 | NO | 0.12563 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7183 | C270 | NO | 1.0783 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3113 | C270 | NO | 0.35994 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3114 | C270 | NO | 0.24303 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3116 | C270 | NO | 0.082095 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_7275 | C270 | NO | 0.23762 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7288 | C270 | NO | 0.32583 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3106 | C271 | NO | 0.49092 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_6362 | C271 | NO | 0.12061 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_7181 | C271 | NO | 0.5471 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_3115 | C271 | NO | 0.53343 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 84 | C271-C273 | 0 | 1 | 0 | 0
[11 empty] | WF6_3117 | C271 | NO | 0.19151 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_3118 | C271 | NO | 0.45362 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_3120 | C272 | NO | 0.10097 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 84 | C271-C273 | 0 | 1 | 0 | 0
[11 empty] | WF6_3122 | C272 | NO | 0.18017 |  | Harvest Processing | Non-Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_3121 | C272 | NO | 0.079516 |  | Non Productive | Non-Treed |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_3119 | C272 | NO | 0.1461 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_3123 | C272 | NO | 0.064273 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_7739 | C272 | NO | 1.1881 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_7257 | C273 | NO | 0.013831 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3122 | C273 | NO | 1.8311 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3124 | C274 | NO | 0.012373 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_6470 | C274 | NO | 1.9185 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_7257 | C274 | NO | 0.14013 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3132 | C274 | NO | 0.1021 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 85 | C273-C275 | 0 | 1 | 0 | 0
[11 empty] | WF6_3132 | C274 | NO | 0.013908 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3122 | C274 | NO | 0.092615 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3127 | C275 | YES | 0.019357 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3130 | C275 | YES | 0.14847 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_6305 | C275 | YES | 0.014823 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7074 | C275 | YES | 0.12057 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7075 | C275 | YES | 0.31229 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3132 | C275 | NO | 0.26398 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3132 | C275 | NO | 0.082492 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3132 | C275 | NO | 0.31487 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3131 | C275 | NO | 0.27063 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3128 | C275 | YES | 0.45816 |  | Non Productive | Non-Treed |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3126 | C275 | YES | 0.070916 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3129 | C275 | NO | 0.18307 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3133 | C275 | YES | 0.11685 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7781 | C275 | NO | 0.27489 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3134 | C276 | YES | 0.010882 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3136 | C276 | YES | 0.012829 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3139 | C276 | YES | 0.030908 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_6306 | C276 | YES | 0.012393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7076 | C276 | YES | 0.058264 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7077 | C276 | YES | 0.011946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7078 | C276 | YES | 0.031975 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7258 | C276 | NO | 0.18039 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3131 | C276 | NO | 0.90316 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3137 | C276 | NO | 0.038344 |  | Non Productive | Non-Treed |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3135 | C276 | YES | 0.054518 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3138 | C276 | NO | 0.1826 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3140 | C276 | YES | 0.063172 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3142 | C276 | NO | 0.018262 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_6518 | C276 | NO | 0.22935 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7289 | C276 | YES | 0.034153 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7290 | C276 | NO | 0.066229 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7504 | C276 | YES | 0.12355 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7663 | C276 | NO | 0.39784 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7856 | C276 | YES | 0.02 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3143 | C277 | NO | 0.10915 |  | Retention | Retention |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 8
[11 empty] | WF6_3144 | C277 | NO | 0.10831 |  | Retention | Retention |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 8
[11 empty] | WF6_7662 | C277 | NO | 1.9486 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3150 | C278 | NO |  |  | Harvest Disposal | Mulch |  | 6 | 87 | C277-C279 | 0 | 0 | 1 | 0
[11 empty] | WF6_3145 | C278 | NO |  |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 0 | 0 | 1 | 0
[11 empty] | WF6_3166 | C278 | NO | 0.074562 |  | Non-Merch Disposal | Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3141 | C278 | NO | 1.8761 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3141 | C278 | NO | 0.019042 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3163 | C278 | NO | 0.26685 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
[11 empty] | WF5_2229 | C99 | NO | 0.35204 |  | Non-Merch Disposal | Mulch | AN | 5 | 50 | C098-C100 | 0 | 1 | 0 | 0
[11 empty] | WF6_3163 | D001 | NO | 0.01782 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
[11 empty] | WF6_6363 | D001 | NO | 0.072539 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
[11 empty] | WF7_3176 | D001 | NO | 1.3699 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3171 | D001 | NO | 0.10132 |  | Non Productive | Non-Treed | AU1 | 7 | 1 | D001-D003 | 0 | 1 | 0 | 0
[11 empty] | WF7_3172 | D001 | NO | 0.17643 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3173 | D001 | NO | 0.029811 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3174 | D001 | NO | 0.08557 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3176 | D002 | NO | 0.11827 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3195 | D002 | NO | 0.27858 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D002 | NO | 0.72927 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3191 | D002 | NO | 1.0039 |  | Harvest Processing | Non-Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3204 | D002 | NO | 0.026577 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3220 | D002 | NO | 0.052054 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D003 | NO | 2.1972 |  | Harvest Disposal | Mulch |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
[11 empty] | WF7_3220 | D003 | NO | 0.067981 |  | Non Productive | Non-Treed |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D004 | NO | 2.0651 |  | Harvest Disposal | Mulch |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
[11 empty] | WF7_3247 | D005 | YES | 0.13641 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3263 | D005 | NO | 1.0938 |  | Non-Merch Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D005 | NO | 0.085957 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3273 | D005 | NO | 0.16566 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3253 | D005 | NO | 0.18753 |  | Non Productive | Non-Treed |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3259 | D005 | NO | 0.038073 |  | Non Productive | Non-Treed |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3252 | D005 | YES | 0.044357 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3257 | D005 | YES | 0.40222 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3261 | D005 | NO | 0.22573 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3263 | D006 | NO | 0.31932 |  | Non-Merch Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3273 | D006 | NO | 0.046389 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3278 | D006 | NO | 1.8431 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3277 | D006 | NO | 0.1295 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3288 | D006 | NO | 0.066637 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3278 | D007 | NO | 2.2746 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3335 | D007 | NO | 0.45876 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3336 | D007 | NO | 0.59486 |  | Retention | Retention |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 8
[11 empty] | WF7_3343 | D008 | NO | 0.27328 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3278 | D008 | NO | 1.2785 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3303 | D008 | NO | 0.020756 |  | Harvest Disposal | Mulch | AU1 | 7 | 4 | D007-D009 | 0 | 1 | 0 | 0
[11 empty] | WF7_3331 | D008 | NO | 0.41397 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3334 | D008 | NO | 0.11616 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3332 | D008 | NO | 0.044431 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3333 | D008 | NO | 0.29159 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3344 | D008 | NO | 0.78034 |  | Retention | Retention |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 8
[11 empty] | WF7_3297 | D009 | YES | 0.1792 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_6290 | D009 | YES | 0.046524 |  | Hand Fall / Lop and Scatter | Handfall | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3309 | D009 | YES | 0.011045 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3300 | D009 | NO | 0.041697 |  | Harvest Disposal | Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3304 | D009 | NO | 0.034203 |  | Harvest Processing | Non-Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3299 | D009 | YES | 0.021816 |  | Hand Fall / Lop and Scatter | Handfall | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3322 | D009 | YES | 0.15226 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3323 | D009 | YES | 0.029681 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3325 | D009 | YES | 0.55089 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3327 | D009 | YES | 0.1775 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3303 | D009 | NO | 0.032974 |  | Harvest Disposal | Mulch | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3329 | D009 | NO | 0.013761 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3331 | D009 | NO | 0.48319 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_7351 | D009 | NO | 0.02267 |  | Harvest Disposal | Mulch | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3301 | D009 | NO | 0.011418 |  | Non Productive | Non-Treed | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3324 | D009 | NO | 0.58798 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3326 | D009 | YES | 0.058755 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3328 | D009 | NO | 0.063501 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3330 | D009 | NO | 0.017735 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3338 | D009 | NO | 0.067409 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3340 | D010 | NO | 0.18787 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3342 | D010 | NO | 0.038113 |  | Harvest Processing | Non-Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3318 | D010 | YES | 0.22758 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3320 | D010 | YES | 0.21445 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3322 | D010 | YES | 0.018414 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3341 | D010 | YES | 0.037262 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3317 | D010 | NO | 0.1902 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3315 | D010 | NO | 1.2374 |  | Harvest Processing | Non-Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3321 | D010 | NO | 0.14346 |  | Harvest Processing | Non-Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3319 | D010 | NO | 0.14316 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3314 | D011 | NO | 0.12385 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3315 | D011 | NO | 2.1363 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3313 | D012 | NO | 0.049608 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3314 | D012 | NO | 1.5133 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3312 | D012 | NO | 0.67475 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3315 | D012 | NO | 0.048987 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3311 | D013 | NO | 0.72063 |  | Harvest Disposal | Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3313 | D013 | NO | 0.18812 |  | Harvest Disposal | Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3310 | D013 | NO | 0.47753 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3312 | D013 | NO | 0.48046 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3306 | D014 | YES | 0.1399 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3308 | D014 | YES | 0.60324 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3307 | D014 | NO | 1.2711 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3307 | D014 | NO | 0.010131 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3310 | D014 | NO | 0.26137 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3306 | D015 | YES | 0.012141 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3306 | D015 | YES | 0.069951 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3339 | D015 | YES | 0.047754 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3346 | D015 | NO | 0.22201 |  | Harvest Disposal | Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3307 | D015 | NO | 1.3685 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3346 | D016 | NO | 1.0702 |  | Harvest Disposal | Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3351 | D016 | NO | 0.74447 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3352 | D017 | YES | 0.16355 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3356 | D017 | YES | 0.379 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3358 | D017 | YES | 0.20448 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3359 | D017 | NO | 0.66055 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3361 | D017 | YES | 0.43021 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3351 | D017 | NO | 0.15427 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3362 | D017 | NO | 0.47973 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3357 | D017 | NO | 0.43698 |  | Non Productive | Non-Treed |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3376 | D018 | YES | 0.069121 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3362 | D018 | NO | 1.7834 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3387 | D019 | YES | 0.06869 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3376 | D019 | YES | 0.39 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3384 | D019 | YES | 0.27113 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3379 | D019 | NO | 0.82082 |  | Harvest Disposal | Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3383 | D019 | NO | 0.26456 |  | Harvest Disposal | Mulch | AN | 7 | 10 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3383 | D019 | NO | 0.21773 |  | Harvest Disposal | Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3446 | D019 | NO | 0.35981 |  | Harvest Disposal | Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3477 | D019 | NO | 0.079373 |  | Harvest Disposal | Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3362 | D019 | NO | 0.26256 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3386 | D019 | NO | 0.069076 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3389 | D019 | NO | 0.35206 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3399 | D019 | NO | 0.3394 |  | Harvest Processing | Non-Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3504 | D019 | NO | 0.14296 |  | Harvest Processing | Non-Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_7354 | D019 | NO | 0.081421 |  | Harvest Disposal | Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_7405 | D019 | NO | 0.1427 |  | Harvest Processing | Non-Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3392 | D020 | YES | 0.33644 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3397 | D020 | NO | 0.43296 |  | Harvest Disposal | Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3389 | D020 | NO | 1.1281 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_7335 | D021 |  | 0.010345 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 0 | 1 | 0 | 0
[11 empty] | WF7_7336 | D021 |  | 0.11933 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 0 | 1 | 0 | 0
[11 empty] | WF7_3397 | D021 | NO | 1.8592 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3405 | D022 | NO |  |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3438 | D022 | NO | 0.019552 |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3461 | D022 | NO | 0.064955 |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3418 | D022 | NO | 0.47244 |  | Harvest Processing | Non-Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3443 | D022 | NO |  |  | Harvest Processing | Non-Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3397 | D022 | NO | 0.41637 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3453 | D022 | NO | 0.47634 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3430 | D022 | NO | 1.1681 |  | Harvest Processing | Non-Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 1 | 0
[11 empty] | WF7_3462 | D022 | NO | 0.11683 |  | Harvest Processing | Non-Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_8202 | D022 | NO | 0.084341 |  | Hand Fall / Lop and Scatter | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3493 | D023 | NO | 0.10803 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3453 | D023 | NO | 0.039471 |  | Harvest Disposal | Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3462 | D023 | NO | 1.6491 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3492 | D023 | NO | 0.15343 |  | Non Productive | Non-Treed | AN | 7 | 13 | D023-D025 | 0 | 1 | 0 | 0
[11 empty] | WF7_3493 | D024 | NO | 0.90819 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3462 | D024 | NO | 0.31829 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3513 | D024 | NO | 0.3877 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3492 | D024 | NO | 0.091003 |  | Non Productive | Non-Treed | AN | 7 | 13 | D023-D025 | 0 | 1 | 0 | 0
Filter full clearing into "OffROW" clearing only
Given 84.5ha requires seeding, calculate the number of Mix Seed Bags required and the purchase cost
Given seeding is required across 84 ha (or ~$57km), a crew with two labours will require at least one full shift to complete the planned scope
1
2
3

## All Season Access - Removal
All-season Access Removal Forecast
Item |  | All-season Road (km) | Road Reclamation | Wetland Road (km) | Wetland Removal | Mat Removal* | Total Forecast
Actual all-season Roads |  | 37.7724 | 469990.5141 | 4.4253 | 0 | #REF! | #REF!
*Est. mat removal cost will be similar to install cost with an approximate increase of 20% arriving from additional requirements associated with disposal (i.e., the requirement of Triaxle trucks to extract broken and additional support required to dispose of mats).
The following crew compositions are used to calculate the remaining forecasted scope
Road Reclamation
|  | Daily Hours |  | 11
Equipment | Rate | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | 1 | 1 | 1616.56
Excavator Operator - Mon - Fri or Sat | 73.08 | 1 | 1 | 803.88
Pickups | 243.75 | 2 | 1 | 487.5
Dozer D6D | 131.48 | 1 | 1 | 1446.28
Operator - Principle - After Jan 10 | 75 | 1 | 1 | 825
LOA | 210 | LS | LS | 420 | 2
|  | Total Cost |  | 5599.22
|  | Productivity (m/day) |  | 450
|  | Average $ per day |  | 5599.22
|  | Cost ($/km) |  | 12442.7111
Bridge Removal
|  | Daily Hours |  | 11
Equipment | Rate | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | 2 | 2 | 6466.24
Excavator Operator - Mon - Fri or Sat | 73.08 | 2 | 2 | 3215.52
Pickups | 243.75 | 2 | 2 | 975
Labourer - General | 60 | 1 | 2 | 1320
LOA | 210 | LS | LS | 1260 | 6
|  | Total Cost |  | 13236.76
Wetland Removal
|  | Daily Hours |  | 11
Equipment | Rate | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | 1 | 1 | 1616.56
Excavator Operator - Mon - Fri or Sat | 73.08 | 1 | 1 | 803.88
Dump - Triaxle- After Jan 10 | 55.2 | 5 | 1 | 3036
Driver - AZ - After Jan 10 | 70 | 5 | 1 | 3850
Pickups | 243.75 | 2 | 1 | 487.5
Labourer - General | 60 | 2 | 1 | 1320
LOA | 210 | LS | LS | 1680 | 8
|  | Total Cost |  | 12793.94
Road Maintenance
|  |  | Daily Hours |  | 11
Equipment | Rate | UofM | Qty per Crew | # of Crews | Daily Cost
Grader | 126.98 | HR | 1 | 2 | 2793.56
Operator - Principle - After Jan 10 | 75 | HR | 1 | 2 | 1650
Pick ups | 243.75 | HR | 1 | 2 | 487.5
LOA | 210 | DAY | LS | LS | 420 | 2
|  |  |  | Total Cost | 5351.06
|  |  |  | Per unit | 2675.53
|  |  |  | 20 days worth of Grader time | 53510.6
Bridge Install Crew
|  |  | Daily Hours |  | 11
Equipment | Rate | UofM | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | HR | 2 | 3 | 9699.36
Excavator Operator - Mon - Fri or Sat | 73.08 | HR | 2 | 3 | 4823.28
Labourer - General | 60 | HR | 1 | 3 | 1980
Pickups | 243.75 | DAY | 2 | 3 | 1462.5
LOA | 210 | LS | LS | LS | 1890 | 9
Foreman | 95 | H | 1 | 1 | 1045
Pickups | 243.75 | DAY | 1 | 1 | 243.75
0
21143.89
|  |  | Average per day |  | 7047.9633
|  |  | 19 bridges required to be re-installed |  | 66955.6517 | 2 bridges per day