## Sheet1
|  | Comperable Projects Totals / Average (ACTUAL) | East-West Tie Transmission Line Project (ACTUAL) | East-West Tie Transmission Line - (MANHOURS CALCULATED AT MM RATES) | East-West Tie Transmission Line Project - (PRODUCTIVITY LOSS COMPARED TO MM RATES)
ASSEMBLY | Manhours | 785975.4282 | 639591 | 360643.4434 | 43.61%
| Weight | 41065631.9 | 18842893 | 18842893
| Assembly (kg per manhour) | 52.248 | 29.4608 | 52.248
ERECTION | Manhours | 264939.8736 | 285221 | 121422.6915 | 57.43%
| Weight (kg) | 41114503.6382 | 18842893 | 18842893
| Erection (kg per manhour) | 155.1843 | 66.0642 | 155.1843
STRINGING | Stringing Hours | 748957.6773 | 310984 | 187179.6136 | 39.81%
| Line length (m) | 1590652.729 | 445403 | 445403
| conductor length (m) | 14257441.937 | 3563222 | 3563222
| Stringing (meters per manhour by conductor length) | 19.0364 | 11.4579 | 19.0364
|  |  |  | Average | 45.84%