## Conventional Costs
Note on M7: From Contract Exhibit: Appendix A-13 "Soil Profile Schedule"
Note on N7: Exhibit B Pricing Includes Material

## ROW - Support
12-month rental

## All Labour Summary
Lodging Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
135700 | Blair White | Surveyor | 00677 - Valard | 2020-08-09 | KAMA-ROW - Kama Cliffs - ROW | Flag clearing limits | 57010120 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B155...B158 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-08-09 | KAMA-ROW - Kama Cliffs - ROW | Flag clearing limits | 57010120 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B155...B158 |  | mVolts
135700 | Blair White | Surveyor | 00677 - Valard | 2020-08-10 | KAMA-ROW - Kama Cliffs - ROW | B150 to B155 Kama cliffs clearing limit flagging | 57010120 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B150...B155 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-08-10 | KAMA-ROW - Kama Cliffs - ROW | B150 to B155 Kama cliffs clearing limit flagging | 57010120 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B150...B155 |  | mVolts
146992 | Noah Pierre-Lesage | Surveyor | 00677 - Valard | 2020-08-13 | KAMA-ROW - Kama Cliffs - ROW | FLAGGED R.O.W BETWEEN B153.5 AND B155.5 | 57010120 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B153 |  | mVolts
156106 | Patrick Stewart | Surveyor | 00677 - Valard | 2020-08-13 | KAMA-ROW - Kama Cliffs - ROW | FLAGGED R.O.W BETWEEN B153.5 AND B155.5 | 57010120 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B153 |  | mVolts
0
0
0
0
0
0
0
0
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-09-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-09-07 | KAMA-FDN - Kama Cliffs - Foundations | Rough anchor staking kama falls for hand cutters | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B153...B158 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
175289 | Andrew Belanger | Surveyor | 00677 - Valard | 2020-09-08 | KAMA-FDN - Kama Cliffs - Foundations | Set up base for Kama Cliffs work | 57010121 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 | WF3 | B153 |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-09-08 | KAMA-FDN - Kama Cliffs - Foundations | Set up base for Kama Cliffs work | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150...B153 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-09-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
135700 | Blair White | Surveyor | 00677 - Valard | 2020-09-13 | KAMA-FDN - Kama Cliffs - Foundations | IFCR staking | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151...B157 | IFCR Staking | mVolts
146994 | Sylvio Pelletier | Surveyor | 00677 - Valard | 2020-09-13 | KAMA-FDN - Kama Cliffs - Foundations | IFCR staking | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151...B157 | IFCR Staking | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
135700 | Blair White | Surveyor | 00677 - Valard | 2020-09-14 | KAMA-FDN - Kama Cliffs - Foundations | IFCR stake | 57010121 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150, B158 | IFCR Staking | mVolts
146994 | Sylvio Pelletier | Surveyor | 00677 - Valard | 2020-09-14 | KAMA-FDN - Kama Cliffs - Foundations | IFCR stake | 57010121 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150, B158 | IFCR Staking | mVolts
187392 | Carl Boyle | Lineman / Electrician | 00677 - Valard | 2020-09-14 | KAMA-FDN - Kama Cliffs - Foundations | foundation work | 57010121 | 16 | 132.15 | 2114.4 | 210 | 210 | 2324.4
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
187392 | Carl Boyle | Lineman / Electrician | 00677 - Valard | 2020-09-15 | KAMA-FDN - Kama Cliffs - Foundations | foundation work | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-15 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-15 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
187392 | Carl Boyle | Lineman / Electrician | 00677 - Valard | 2020-09-16 | KAMA-FDN - Kama Cliffs - Foundations | foundation work | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-16 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-16 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118699 | Bradley Peckford | Labourer | 00677 - Valard | 2020-09-17 | KAMA-FDN - Kama Cliffs - Foundations | Marathon to pick up poilet | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 |  |  |  | mVolts
187392 | Carl Boyle | Lineman / Electrician | 00677 - Valard | 2020-09-17 | KAMA-FDN - Kama Cliffs - Foundations | foundation work | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-17 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-17 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118699 | Bradley Peckford | Labourer | 00677 - Valard | 2020-09-18 | KAMA-FDN - Kama Cliffs - Foundations | Loading equipment and clen up | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 |  |  |  | mVolts
176227 | Craig McKay | Surveyor | 00677 - Valard | 2020-09-18 | KAMA-FDN - Kama Cliffs - Foundations | IFCR staking | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 | IFCR Staking | mVolts
187392 | Carl Boyle | Lineman / Electrician | 00677 - Valard | 2020-09-18 | KAMA-FDN - Kama Cliffs - Foundations | foundation work | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-18 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-19 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 6 | 150.59 | 903.54 | 114.5455 | 114.55 | 1018.09 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-09-19 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
146994 | Sylvio Pelletier | Surveyor | 00677 - Valard | 2020-09-22 | KAMA-FDN - Kama Cliffs - Foundations | IFCR staking | 57010121 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B158...B161 |  | mVolts
176227 | Craig McKay | Surveyor | 00677 - Valard | 2020-09-22 | KAMA-FDN - Kama Cliffs - Foundations | IFCR staking | 57010121 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B158...B161 |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-09-26 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-09-27 | KAMA-FDN - Kama Cliffs - Foundations | IFC STAKED AND OFFSETS | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150...B153 | IFC Staking | mVolts
176227 | Craig McKay | Surveyor | 00677 - Valard | 2020-09-27 | KAMA-FDN - Kama Cliffs - Foundations | IFC STAKED AND OFFSETS | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150...B153 | IFC Staking | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-09-28 | KAMA-FDN - Kama Cliffs - Foundations | IFC STAKING KAMA CLIFFS | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  | IFC Staking | mVolts
176227 | Craig McKay | Surveyor | 00677 - Valard | 2020-09-28 | KAMA-FDN - Kama Cliffs - Foundations | IFC STAKING KAMA CLIFFS | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  | IFC Staking | mVolts
0
0
0
0
0
0
0
0
0
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-30 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-09-30 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
146994 | Sylvio Pelletier | Surveyor | 00677 - Valard | 2020-10-03 | KAMA-FDN - Kama Cliffs - Foundations | IFCR Staking | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  | IFCR Staking,As-Builts | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-10-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118103 | Darcy Hutchings | Labourer | 00677 - Valard | 2020-10-07 | KAMA-FDN - Kama Cliffs - Foundations | Placeing rig matts for dave carrondo | 57010121 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B146 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Did Helicopter briefing with pilots and Crux crew. Went up to STR B149 with a few crux guys and prepped drill legs for leg A. Tarped water tanks on trailer brougt over heaters and genset. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Did Helicopter briefing with pilots and Crux crew. Went up to STR B149 with a few crux guys and prepped drill legs for leg A. Tarped water tanks on trailer brougt over heaters and genset. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
175289 | Andrew Belanger | Surveyor | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | IFC Staking | 57010121 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  | IFC Staking | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Did Helicopter briefing with pilots and Crux crew. Went up to STR B149 with a few crux guys and prepped drill legs for leg A. Tarped water tanks on trailer brougt over heaters and genset. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178159 | Ryan Beaucage | Labourer | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Did Helicopter briefing with pilots and Crux crew. Went up to STR B149 with a few crux guys and prepped drill legs for leg A. Tarped water tanks on trailer brougt over heaters and genset. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Did Helicopter briefing with pilots and Crux crew. Went up to STR B149 with a few crux guys and prepped drill legs for leg A. Tarped water tanks on trailer brougt over heaters and genset. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Did Helicopter briefing with pilots and Crux crew. Went up to STR B149 with a few crux guys and prepped drill legs for leg A. Tarped water tanks on trailer brougt over heaters and genset. | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Did fly yard prep/layout with cruxs. Unload material and prepp drills | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Did fly yard prep/layout with cruxs. Unload material and prepp drills | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Did fly yard prep/layout with cruxs. Unload material and prepp drills | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178159 | Ryan Beaucage | Labourer | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Did fly yard prep/layout with cruxs. Unload material and prepp drills | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Did fly yard prep/layout with cruxs. Unload material and prepp drills | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Did fly yard prep/layout with cruxs. Unload material and prepp drills | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | 2 hrs fly, yard and prep lay out. Worked at STR B151 Drill deck and preparations for drilling legs A and C. Unload truck with material also prepp drill decks for picks with the helicopter. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | 2 hrs fly, yard and prep lay out. Worked at STR B151 Drill deck and preparations for drilling legs A and C. Unload truck with material also prepp drill decks for picks with the helicopter. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | 2 hrs fly, yard and prep lay out. Worked at STR B151 Drill deck and preparations for drilling legs A and C. Unload truck with material also prepp drill decks for picks with the helicopter. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178159 | Ryan Beaucage | Labourer | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | 2 hrs fly, yard and prep lay out. Worked at STR B151 Drill deck and preparations for drilling legs A and C. Unload truck with material also prepp drill decks for picks with the helicopter. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | 2 hrs fly, yard and prep lay out. Worked at STR B151 Drill deck and preparations for drilling legs A and C. Unload truck with material also prepp drill decks for picks with the helicopter. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | 2 hrs fly, yard and prep lay out. Worked at STR B151 Drill deck and preparations for drilling legs A and C. Unload truck with material also prepp drill decks for picks with the helicopter. | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-10-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Observe drill set up Kama hill with Crux | 57010121 | 5 | 91.26 | 456.3 | 95.4545 | 95.45 | 551.75 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Prep and lay out fly yard also prep drill and deck drill. Drilled firs pile on legs A and started a second pile on leg C STR B151. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Prep and lay out fly yard also prep drill and deck drill. Drilled firs pile on legs A and started a second pile on leg C STR B151. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
146994 | Sylvio Pelletier | Surveyor | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Stake P1 for all legs | 57010121 | 5.5 | 132.15 | 726.825 | 105 | 105 | 831.825 | WF3 | B150, B154, B158 | IFC Staking | mVolts
175289 | Andrew Belanger | Surveyor | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Stake P1 for all legs | 57010121 | 5.5 | 132.15 | 726.825 | 105 | 105 | 831.825 | WF3 | B150, B154, B158 | IFC Staking | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Prep and lay out fly yard also prep drill and deck drill. Drilled firs pile on legs A and started a second pile on leg C STR B151. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178159 | Ryan Beaucage | Labourer | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Prep and lay out fly yard also prep drill and deck drill. Drilled firs pile on legs A and started a second pile on leg C STR B151. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Prep and lay out fly yard also prep drill and deck drill. Drilled firs pile on legs A and started a second pile on leg C STR B151. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Prep and lay out fly yard also prep drill and deck drill. Drilled firs pile on legs A and started a second pile on leg C STR B151. | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | drilled piles on legs A+C STR B151. Drilling pile hub at STR B152. Material prep layout at heli lay down yard. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | drilled piles on legs A+C STR B151. Drilling pile hub at STR B152. Material prep layout at heli lay down yard. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-10-13 | KAMA-ERT - Kama Cliffs - Erection | Welding Project- Jody MacDonald | 57010123 | 6 | 132.15 | 792.9 | 114.5455 | 114.55 | 907.45 |  |  |  | Multi-Project,mVolts,Field Approved
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | drilled piles on legs A+C STR B151. Drilling pile hub at STR B152. Material prep layout at heli lay down yard. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178159 | Ryan Beaucage | Labourer | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | drilled piles on legs A+C STR B151. Drilling pile hub at STR B152. Material prep layout at heli lay down yard. | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | drilled piles on legs A+C STR B151. Drilling pile hub at STR B152. Material prep layout at heli lay down yard. | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | drilled piles on legs A+C STR B151. Drilling pile hub at STR B152. Material prep layout at heli lay down yard. | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-10-15 | KAMA-ERT - Kama Cliffs - Erection | Welding Job for Jody MacDonald | 57010123 | 9 | 132.15 | 1189.35 | 171.8182 | 171.82 | 1361.17 |  |  |  | Multi-Project,mVolts,Field Approved
176227 | Craig McKay | Surveyor | 00677 - Valard | 2020-10-15 | KAMA-FDN - Kama Cliffs - Foundations | IFC Staking | 57010121 | 4 | 132.15 | 528.6 | 76.3636 | 76.36 | 604.96 |  |  | IFC Staking | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-15 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-15 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Observe&verify drilling procedure on kama cliffs,measure bevel washer,verify centralizer on bar | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Working with helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Working with helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
176227 | Craig McKay | Project Assistant | 00677 - Valard | 2020-10-16 | KAMA-ROW - Kama Cliffs - ROW | Layout camp 81 laydown. | 57010120 | 6 | 91.26 | 547.56 | 114.5455 | 114.55 | 662.11 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Working with helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Working with helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
184392 | Tyler Paiha | Project Assistant | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Quality Control | 57010121 | 9 | 91.26 | 821.34 | 171.8182 | 171.82 | 993.16 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Working with helicopters | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-16 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Verify on drilling completed,verify no ground wire,no lock nut.grout pour mud balance and took samples | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Helping helicopter | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Helping helicopter | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Helping helicopter | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Helping helicopter | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
184392 | Tyler Paiha | Project Assistant | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Quality Control | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Helping helicopter | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-10-17 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Observe drilling and casing complete,measured and verify form and stub anchors | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Helped out on helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Helped out on helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Helped out on helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Helped out on helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
184392 | Tyler Paiha | Project Assistant | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Quality Control | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Helped out on helicopters | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-18 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Helped chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Helped chopers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Helping with helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Helped chopers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Helping with helicopters | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-19 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
117745 | Bradley Eagle | Equipment Operator | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Take samples for grout pour,observe drilling for micropile,grouted anchor with Crux | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
118325 | Dakota Lloyd | Labourer | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 |  |  |  | mVolts,mV Revision
118578 | Zachary Myles | Labourer | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
118615 | Gary O'Brien | Equipment Operator | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Haul heater for chopper | 57010121 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF2 |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
129349 | Robyn Hart | Labourer | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Haul heater for chopper | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF2 |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Helping choppers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-20 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Worked with chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Inspect and measure grout pad,observe drilling on Kama cliff ,pick up grout samples | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Worked with chopers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Worked with chopers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Worked with chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Worked with chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-21 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 6 | 150.59 | 903.54 | 114.5455 | 114.55 | 1018.09 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-22 | KAMA-FDN - Kama Cliffs - Foundations | Helping chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-22 | KAMA-FDN - Kama Cliffs - Foundations | Observe drilling and casing installed,took grout samples for Crux,pick up grout samples | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-22 | KAMA-FDN - Kama Cliffs - Foundations | Helping chopers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-22 | KAMA-FDN - Kama Cliffs - Foundations | Helping chopers | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,mV Revision
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-22 | KAMA-FDN - Kama Cliffs - Foundations | Helping chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-22 | KAMA-FDN - Kama Cliffs - Foundations | Helping chopers | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,mV Revision
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts,mV Revision
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Observe drilling and casing installed,on Kama cliff for grout pour,picked up cubes | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Leg B micro-piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts,mV Revision
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Drilling micro-piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
138224 | Gavin Olson | Surveyor | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Crux support. Set Pco's | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B151...B153, B155 | Extra Work,FDN Support | mVolts,mV Revision
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Leg D micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,mV Revision
175289 | Andrew Belanger | Surveyor | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Crux support. Set Pco's | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B151...B153, B155 | Extra Work,FDN Support | mVolts,mV Revision
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Leg A and C grouting | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,mV Revision
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-23 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts,mV Revision
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchor | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Leg B micro-pile | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Leg D micro- pile | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Leg D micro- pile | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Grouting anchors and micro- piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchor | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
190344 | Alexandre Young | Equipment Operator | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Worked on chopper pad mixing grout | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-10-24 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Drilled anchor,grouted and prepped site B155 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Drilled anchor,grouted and prepped site B155 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B153 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Prepped for str B150 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles str 150 and 151 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles str 150 and 151 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Prepped for str B150 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
190344 | Alexandre Young | Equipment Operator | 00677 - Valard | 2020-10-25 | KAMA-FDN - Kama Cliffs - Foundations | Mixing grout on chopper pad | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Final inspections,verify pull test,measure forms,verify putting centralizers on | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B155 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Prep work | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Verify heating and Hoarding | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Prep work | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
190344 | Alexandre Young | Equipment Operator | 00677 - Valard | 2020-10-26 | KAMA-FDN - Kama Cliffs - Foundations | Mixing grout on chopper pad | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Drilled anchor and grouted them and micro-piles and mobed gear to str B156 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Drilled anchor and grouted them and micro-piles and mobed gear to str B156 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B155 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles then went to help grout strB155 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Micro- piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Verify work progress , heating and hoarding , verify work progress at sites , place recording thermometer at B155 | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Micro- piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Micro- piles | 57010121 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
190344 | Alexandre Young | Equipment Operator | 00677 - Valard | 2020-10-27 | KAMA-FDN - Kama Cliffs - Foundations | Worked in the yard mixing grout and cleaning hoppers at camp 81 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-29 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-30 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-30 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
0
0
0
0
0
0
0
0
0
0
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-31 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-10-31 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-10-31 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-02 | KAMA-FDN - Kama Cliffs - Foundations | Drained water tanks and folded up tarps at camp 81 laydown | 57010121 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B151 |  | mVolts
117906 | Keith Goodyear | Equipment Operator | 00677 - Valard | 2020-11-02 | KAMA-FDN - Kama Cliffs - Foundations | Drained water tanks and folded up tarps at camp 81 laydown | 57010121 | 2 | 111.7 | 223.4 | 38.1818 | 38.18 | 261.58 | WF3 | B151 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-02 | KAMA-FDN - Kama Cliffs - Foundations | Drained water tanks and folded up tarps at camp 81 laydown | 57010121 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B151 |  | mVolts
190344 | Alexandre Young | Equipment Operator | 00677 - Valard | 2020-11-02 | KAMA-FDN - Kama Cliffs - Foundations | Drained water tanks and folded up tarps at camp 81 laydown | 57010121 | 2 | 111.7 | 223.4 | 38.1818 | 38.18 | 261.58 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
89710 | John Goertzen | Project Assistant | 00677 - Valard | 2020-11-03 | KAMA-ROW - Kama Cliffs - ROW | Pick up material at Thunder Bay and delivered to Camp 81 rd at Crux's yard. | 57010120 | 8 | 91.26 | 730.08 | 152.7273 | 152.73 | 882.81 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Anchor drilling | 57010121 | 3.5 | 81.03 | 283.605 | 66.8182 | 66.82 | 350.425 | WF3 | B156 |  | mVolts,SubstituteSupervisor
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Grout test prep | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,SubstituteSupervisor
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Inspect grout pads,verify B&C bar installed and surveyed,observe grout pour ,make grout samples, | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Anchor drilling | 57010121 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B156 |  | mVolts,SubstituteSupervisor
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
184993 | Matthew Shepard | Equipment Operator | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Anchor drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B156 |  | mVolts,SubstituteSupervisor
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts,SubstituteSupervisor
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Verify heating and hoarding of micropile,pick up samples,took grout samples,mud balance | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B156 |  | mVolts,SubstituteSupervisor
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Grouting | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,SubstituteSupervisor
184993 | Matthew Shepard | Equipment Operator | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Micro-piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Working in camp 81 heli yard | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Drill micro-piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts,SubstituteSupervisor
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Micro- piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Verify Crux drilling of micropiles on Kama cliff,observe proof test of guy anchors and micro pile 1 | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Drill micro-piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B156 |  | mVolts,SubstituteSupervisor
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Micro- piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,SubstituteSupervisor
178474 | James Campbell | Labourer | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Micro- piles | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B150 |  | mVolts,SubstituteSupervisor
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Working in the Heli laydown at camp 81 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-11-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Drill micro-piles,then prepped for str B176 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts,SubstituteSupervisor
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Micro-pile | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Verify grouted anchors,pick up sample cubes,verify drilling completed anchors,final inspections | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Drill micro-piles,then prepped for str B176 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B156 |  | mVolts,SubstituteSupervisor
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Micro-pile | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
138224 | Gavin Olson | Surveyor | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | MP thread bar as builts | 57010121 | 7 | 132.15 | 925.05 | 133.6364 | 133.64 | 1058.69 |  |  | As-Builts | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Micro-pile | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts,SubstituteSupervisor
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Pull test,cap | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,SubstituteSupervisor
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Working in the yard | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
186557 | Evan Fequet | Surveyor | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | MP thread bar as builts | 57010121 | 7 | 132.15 | 925.05 | 133.6364 | 133.64 | 1058.69 |  |  | As-Builts | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Verify tower shoe installed,Verify grout top up,tighten lock nuts,on Kama cliff observe grout pour,take sample cubes | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Set up | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Set up | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Grouting anchors and micropiles and trimming at B151 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Working in the yard with jake | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Verify drilling of micropile,verify grout pour on Kama Cliff,retrieve grout samples,verify carbozinc applied | 57010121 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchors | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and setting cap | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and setting cap | 57010121 | 5.5 | 111.7 | 614.35 | 105 | 105 | 719.35 | WF3 | B151 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Worked in the yard then went to str B151 and worked | 57010121 | 5.5 | 111.7 | 614.35 | 105 | 105 | 719.35 | WF3 |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchor and set up for micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
116873 | Wayne Squires | Truck Driver / Picker Op. | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Hauled tower steel | 57010122 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 | WF3 | B157 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Observe deadman anchor install,verify grouted anchors install,retrieved sample cubes put in curing tank.verifyed heating and hoarding | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Drill anchor and set up for micro piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | MP as-builts | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  | As-Builts | mVolts
176089 | Justin McGuire | Labourer | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Kama cliff observe dilling leg D,verify deadman anchors hit rock #1,Backfill photo taken.walked cooler up to site | 57010121 | 8 | 91.26 | 730.08 | 152.7273 | 152.73 | 882.81 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
118286 | Kyle Lawson | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
118406 | Enrique Martinez Morales | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
118787 | Rogelio Ramos | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
118801 | Paul Reimer | Foreman | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B152 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
118871 | Wade Rumbolt | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
118872 | William Rumbolt | Equipment Operator | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
118918 | Darren Scott | Foreman | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B152 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B149 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Finished micro pile and moved to str B149 | 57010121 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | As-builts. Mark PCOs | 57010121 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  | As-Builts | mVolts
163292 | Cyrus Desmoulin | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
174660 | Robert Favel | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Cleaning up sites | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
176089 | Justin McGuire | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Micro piles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176914 | January Collins | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 9 | 81.03 | 729.27 | 171.8182 | 171.82 | 901.09 | WF3 | B152 |  | mVolts
176915 | Samantha Collins | Labourer | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 9 | 81.03 | 729.27 | 171.8182 | 171.82 | 901.09 | WF3 | B152 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Grout anchors and micropiles.Prepped for str B158 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-13 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Grout anchors and micropiles.Prepped for str B158 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Rough stake tie-backs. Topo survey for tie-backs. | 57010121 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  | Extra Work,IFCR Staking | mVolts,mV Revision
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Working in laydown yard | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Prepped and started drilling micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Ple cap inspection,remove soil for weld inspection,verify cap installed,wire brushed and sprayed galv | 57010121 | 9 | 91.26 | 821.34 | 171.8182 | 171.82 | 993.16 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-14 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Prepped and started drilling micropiles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Set washers | 57010121 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B151 | FDN Support | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping for 8 hrs and 3hrs prepping at strB150 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and capping for 8 hrs and 3hrs prepping at strB150 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-11-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B158 |  | mVolts
117530 | David Chew | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B149 |  | mVolts
118286 | Kyle Lawson | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-15 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118406 | Enrique Martinez Morales | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118787 | Rogelio Ramos | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118801 | Paul Reimer | Foreman | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B153 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 7 | 111.7 | 781.9 | 133.6364 | 133.64 | 915.54 | WF3 | B158 |  | mVolts
118871 | Wade Rumbolt | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Towern assembl6 | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118872 | William Rumbolt | Equipment Operator | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B153 |  | mVolts
118918 | Darren Scott | Foreman | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B153 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B149 |  | mVolts
155056 | Bryan Spence | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
163292 | Cyrus Desmoulin | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
174660 | Robert Favel | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Cleaning up sites Delivered parts to Marathon Delivered tower steel | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Set FDN caps | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B149 |  | mVolts
176914 | January Collins | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176915 | Samantha Collins | Labourer | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B150 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-15 | KAMA-FDN - Kama Cliffs - Foundations | Torquing caps | 57010121 | 7 | 111.7 | 781.9 | 133.6364 | 133.64 | 915.54 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B153 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Verify rock anchors grouted heating and hoarding,verify pad formwork grout pads poured,verify guy anchors installed | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-16 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and grouting template | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-16 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and grouting template | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B155 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B149 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Prepped site for work | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B154 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Verify Heating and hoarding,pour grout pads,pick up sample cubes,crux grouting on Kama Cliff,spray galv on mast | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-17 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B149 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | As-built pile bolts requested by crux | 57010121 | 6 | 132.15 | 792.9 | 114.5455 | 114.55 | 907.45 | WF3 | B150 | FDN Support | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Grouting | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-17 | KAMA-FDN - Kama Cliffs - Foundations | Grouting | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117530 | David Chew | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B152 |  | mVolts
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B155 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Verify heating and hoarding,fix loose tarps,observe installing deadman anchors,verify carbozinc | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-18 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Stake pile locations, mark pco, and tie back locations | 57010121 | 9 | 132.15 | 1189.35 | 171.8182 | 171.82 | 1361.17 | WF3 | B157, B158 | FDN Support | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Micropile and moved to strB154 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Micropile and moved to strB154 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-18 | KAMA-FDN - Kama Cliffs - Foundations | Worked in the laydown at camp 81 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
117255 | Dylan Austin | Foreman | 00677 - Valard | 2020-11-19 | KAMA-ERT - Kama Cliffs - Erection | Sarens Crane | 57010123 | 2 | 146.89 | 293.78 | 38.1818 | 38.18 | 331.96 |  |  |  | Multi-Project,mVolts,Field Approved
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B156 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Icropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Inspected grout pads,measured and inspected pile caps and beveled washers,verify drilling on Kama Cliff | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
117871 | David Genaille | Journeyman Mechanic | 00677 - Valard | 2020-11-19 | KAMA-ERT - Kama Cliffs - Erection | Sarens Crane | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | Multi-Project,mVolts,Field Approved
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-19 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Verify work progress at B152,B154 Final inspection at B151 . | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Marked pco's and staked tie backs | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B149 | FDN Support | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Icropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and grouting | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-19 | KAMA-FDN - Kama Cliffs - Foundations | Working in the laydown yard at camp 81 helping with materials | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-19 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-20 | KAMA-FDN - Kama Cliffs - Foundations | Heli fdn,got shut down because of weather conditions | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B156 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-20 | KAMA-FDN - Kama Cliffs - Foundations | Heli fdn,got shut down because of weather conditions | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-20 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-20 | KAMA-FDN - Kama Cliffs - Foundations | Heli fdn,got shut down because of weather conditions | 57010121 | 3 | 111.7 | 335.1 | 57.2727 | 57.27 | 392.37 | WF3 |  |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-11-20 | KAMA-ERT - Kama Cliffs - Erection | Weld Fly Crew Stops/Proto Types | 57010123 | 5.5 | 132.15 | 726.825 | 105 | 105 | 831.825 |  |  |  | Multi-Project,mVolts,Field Approved
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-20 | KAMA-FDN - Kama Cliffs - Foundations | Heli fdn,got shut down because of weather conditions | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-20 | KAMA-FDN - Kama Cliffs - Foundations | Heli fdn,got shut down because of weather conditions | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-20 | KAMA-FDN - Kama Cliffs - Foundations | Heli fdn,got shut down because of weather conditions | 57010121 | 3 | 111.7 | 335.1 | 57.2727 | 57.27 | 392.37 | WF3 |  |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-20 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
116889 | Guildo Theriault | Foreman | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Site Inspections | 57010121 | 6 | 146.89 | 881.34 | 114.5455 | 114.55 | 995.89 |  |  |  | mVolts,SubstituteSupervisor
117036 | Karl Kenny | Project Assistant | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Kama cliff inspections | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 |  |  |  | mVolts
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 146.89 | 881.34 | 114.5455 | 114.55 | 995.89 | WF3 | B157 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117716 | Jordie Douglas | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | On Kama cliff observe pull test procedure,observe drilling of micropile, install lock nuts | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts,SubstituteSupervisor
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-21 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | TIE BACKS | 57010121 | 4 | 132.15 | 528.6 | 76.3636 | 76.36 | 604.96 | WF3 | B149 | FDN Support | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing at str B152 and B153 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Worked in the laydown yard all day | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-21 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B157 |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-11-21 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling and install anchor bar | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
116660 | Richard Hickey | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117591 | Dylon Constant | Foreman | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B157 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B154 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Measured angle on anchors are in spec,Observe drilling on Kama cliff | 57010121 | 9 | 91.26 | 821.34 | 171.8182 | 171.82 | 993.16 |  |  |  | mVolts
118119 | Darryl Jacobson | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-22 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling and install anchor bar | 57010121 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B158 |  | mVolts
119196 | Joseph Wells Jr | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
153108 | Lynden Jonski | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
176475 | Fabian Grandy | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
176479 | Robert Plummber | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B154 |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Pull tested and moved to B156 | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B155 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-22 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B152 |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2020-11-22 | KAMA-ASY - Kama Cliffs - Assembly | Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Drill micropiles | 57010121 | 9 | 81.03 | 729.27 | 171.8182 | 171.82 | 901.09 | WF3 | B158 |  | mVolts
117709 | Jason Donahue | Labourer | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Drill micropiles | 57010121 | 9 | 81.03 | 729.27 | 171.8182 | 171.82 | 901.09 | WF3 | B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-23 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Drill micropiles | 57010121 | 9 | 111.7 | 1005.3 | 171.8182 | 171.82 | 1177.12 | WF3 | B158 |  | mVolts
146992 | Noah Pierre-Lesage | Surveyor | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Marked hub pco's | 57010121 | 4 | 132.15 | 528.6 | 76.3636 | 76.36 | 604.96 | WF3 | B156 | FDN Support | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-11-23 | KAMA-ERT - Kama Cliffs - Erection | Welding | 57010123 | 9 | 132.15 | 1189.35 | 171.8182 | 171.82 | 1361.17 |  |  |  | Multi-Project,mVolts,Field Approved
175614 | Jordan Ball | Surveyor | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Marked hub pco's | 57010121 | 4 | 132.15 | 528.6 | 76.3636 | 76.36 | 604.96 | WF3 | B156 | FDN Support | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Drill micropiles | 57010121 | 9 | 81.03 | 729.27 | 171.8182 | 171.82 | 901.09 | WF3 | B154 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Pull tested anchors and moved to B157 | 57010121 | 9 | 81.03 | 729.27 | 171.8182 | 171.82 | 901.09 | WF3 | B156 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-11-23 | KAMA-FDN - Kama Cliffs - Foundations | Anchor pull test and moved equipment to B153 | 57010121 | 9 | 111.7 | 1005.3 | 171.8182 | 171.82 | 1177.12 | WF3 | B152 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-24 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-25 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-26 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-26 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-27 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-27 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-27 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-28 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-28 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-28 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-11-28 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-29 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-29 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-29 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
0
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-11-30 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
0
0
0
0
0
0
0
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2020-11-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-30 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-11-30 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-01 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 6.5 | 81.03 | 526.695 | 124.0909 | 124.09 | 650.785 | WF3 | B154 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 6.5 | 81.03 | 526.695 | 124.0909 | 124.09 | 650.785 | WF3 | B154 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Pull test and capping andgrout and template at strB150 | 57010121 | 6.5 | 81.03 | 526.695 | 124.0909 | 124.09 | 650.785 | WF3 | B157 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-01 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B158 |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-02 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B158 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 6 | 111.7 | 670.2 | 114.5455 | 114.55 | 784.75 | WF3 | B153 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B158 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B153 |  | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | final inspections at B152,B153,B155,B156,B157 | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Capping at strs B1156,B152,B153 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Micropiles | 57010121 | 6 | 111.7 | 670.2 | 114.5455 | 114.55 | 784.75 | WF3 | B158 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B153 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing anchors | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-03 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-12-03 | KAMA-ERT - Kama Cliffs - Erection | Jody MacDonald | 57010123 | 1 | 132.15 | 132.15 | 19.0909 | 19.09 | 151.24 |  |  |  | Multi-Project,mVolts,Field Approved
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Check hub cap elevations. | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B152...B157 | Extra Work | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | witness pulltest at B153 G3, verify work progress at B154 | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Finished up micropile and mobed to strB158 | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Prepped for cap at B150 and prepped for grout at B149 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-03 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing anchors at str B153 and B155 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-04 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-12-04 | KAMA-ERT - Kama Cliffs - Erection | Jody MacDonald | 57010123 | 1 | 132.15 | 132.15 | 19.0909 | 19.09 | 151.24 |  |  |  | Multi-Project,mVolts,Field Approved
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Micropile drilling | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and install templates | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Trimming and install templates | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-05 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 7 | 111.7 | 781.9 | 133.6364 | 133.64 | 915.54 | WF3 | B149 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B149 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Mark PCOs - Did not get done...helicopter was held up due to fog | 57010121 | 3.5 | 132.15 | 462.525 | 66.8182 | 66.82 | 529.345 | WF3 | B154 | Standby | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Trimming | 57010121 | 3 | 111.7 | 335.1 | 57.2727 | 57.27 | 392.37 | WF3 | B149 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-12-05 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-06 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Torquing and levelling plates | 57010121 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B152 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Torquing and levelling plates | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B152 |  | mVolts
138229 | Udaydeep Bajwa | Surveyor | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | As built MPs at B152. | 57010121 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B152 | As-Builts | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Mark PCOs | 57010121 | 4.5 | 132.15 | 594.675 | 85.9091 | 85.91 | 680.585 | WF3 | B154 | FDN Support | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Mobing equipment to laydown | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Prep work for grouting | 57010121 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Working in the laydown | 57010121 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B149 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-06 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Capping and trimming bar at strs 152,153,155,156,157 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-07 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
138229 | Udaydeep Bajwa | Surveyor | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | as Built MPs, As built hub and anchors & Plumb refs from B155-B157 | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B153, B155...B157 | As-Builts | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Mark PCOs (B158) Asbuilts and plumb reference nails (B152 and B153) | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B152...B158 | As-Builts | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Final inspection at B152,B153 and B155 | 57010121 | 6 | 91.26 | 547.56 | 114.5455 | 114.55 | 662.11 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Grouting | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Working in the yard mixing grout and cleaning hoppers for str149 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing anchors at B155,B156 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-08 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
156993 | John Young | Project Assistant | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 6 | 91.26 | 547.56 | 114.5455 | 114.55 | 662.11 |  |  |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing and capping | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Grouting at B149 and prep work for grouting at B154 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Worked in heli laydown loading hoppers and cleaning | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B156 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Pile cap inspections on kama cliff,anchor pull-test | 57010121 | 6 | 91.26 | 547.56 | 114.5455 | 114.55 | 662.11 | WF3 | B156, B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-09 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | As-built MPs | 57010121 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B150 | As-Builts | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Set plates | 57010121 | 4.5 | 132.15 | 594.675 | 85.9091 | 85.91 | 680.585 | WF3 | B150 | FDN Support | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-12-09 | KAMA-ERT - Kama Cliffs - Erection | Jody MacDonald | 57010123 | 3 | 132.15 | 396.45 | 57.2727 | 57.27 | 453.72 |  |  |  | Multi-Project,mVolts,Field Approved
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | As-built MPs | 57010121 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B150 | As-Builts | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Set plates | 57010121 | 4.5 | 132.15 | 594.675 | 85.9091 | 85.91 | 680.585 | WF3 | B150 | FDN Support | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Capping | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Trimming at str B154 and B158 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Working in the yard | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Waited in yard to see if weather would clear | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-10 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Stake tie-back anchors and offsets | 57010121 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B149 | Extra Work,FDN Support | mVolts,mV Revision
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Prep welding trucks for kama cliff welding. Work on repairs for crux | 57010121 | 7 | 127.04 | 889.28 | 133.6364 | 133.64 | 1022.92 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Prep welding trucks for kama cliff welding. Work on repairs for crux | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Stake tie-back anchors and offsets | 57010121 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B149 | Extra Work,FDN Support | mVolts,mV Revision
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Waited in yard to see if weather would clear | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Waited in yard to see if weather would clear | 57010121 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Waited in yard to see if weather would clear | 57010121 | 3 | 111.7 | 335.1 | 57.2727 | 57.27 | 392.37 | WF3 |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Pull tests | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2020-12-11 | KAMA-ERT - Kama Cliffs - Erection | Began moving equipment to structure | 57010123 | 4 | 111.7 | 446.8 | 76.3636 | 76.36 | 523.16 | WF3 | B089 |  | mVolts
118106 | Derek Hynes | Equipment Operator | 00677 - Valard | 2020-12-11 | KAMA-ERT - Kama Cliffs - Erection | Began moving equipment to structure | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B089 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-11 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2020-12-11 | KAMA-ERT - Kama Cliffs - Erection | Began moving equipment to structure | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B089 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Stake tie-back anchors and offsets (B150 and B151). Set shoes and final as-builts (B151). | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150, B151 | Extra Work,FDN Support | mVolts,mV Revision
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | B-151. Weld on tower shoes. Weld hole covers on tower shoes | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | B-151. Weld on tower shoes. Weld hole covers on tower shoes | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2020-12-11 | KAMA-ERT - Kama Cliffs - Erection | Jody MacDonald | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | Multi-Project,mVolts,Field Approved
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Stake tie-back anchors and offsets (B150 and B151). Set shoes and final as-builts (B151). | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150, B151 | Extra Work,FDN Support | mVolts,mV Revision
175289 | Andrew Belanger | Surveyor | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Tie Back staking | 57010121 | 6 | 132.15 | 792.9 | 114.5455 | 114.55 | 907.45 | WF3 | B154, B158 | IFC Staking | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Capping at B150 and prepping for pull test at B149 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Grouting and hoarding | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Filling hoppers and working in the yard | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Pull test anchor | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
117346 | Robert Bjerkelund | Labourer | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117446 | Samuel Burnett | Labourer | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117562 | Jordan Clair | Apprentice - 4th Year | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Observe drilling and installing of rebar and forming,measure bevel washer on kama cliff | 57010121 | 7 | 91.26 | 638.82 | 133.6364 | 133.64 | 772.46 |  |  |  | mVolts
117855 | Gregory Gagnon | Apprentice - 4th Year | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118087 | Thomas Howes | Foreman | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Move equipment for helecopter mock up. | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B089 |  | mVolts
118106 | Derek Hynes | Equipment Operator | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Building guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118623 | Kenneth O'Dea | Labourer | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
118962 | Caleb Sladen | Lineman / Electrician | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B089 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Re-stake tie back anchors and offsets to be 2.8m off of plates. | 57010121 | 3 | 132.15 | 396.45 | 57.2727 | 57.27 | 453.72 | WF3 | B151...B158 | Rework,FDN Support | mVolts,mV Revision
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Set plates and final as-builts for B150. | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 | FDN Support | mVolts,mV Revision
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | B-150 weld stub legs and hole covers | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 | WF3 |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | B-150 weld stub legs and hole covers | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 | WF3 |  |  | mVolts
155637 | Judidiah Prince | Labourer | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Re-stake tie back anchors and offsets to be 2.8m off of plates. | 57010121 | 3 | 132.15 | 396.45 | 57.2727 | 57.27 | 453.72 | WF3 | B151...B158 | Rework,FDN Support | mVolts,mV Revision
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Set plates and final as-builts for B150. | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 | FDN Support | mVolts,mV Revision
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B089 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Pull testing | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Grouting | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Fill hoppers and clean in the heli laydown | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2020-12-12 | KAMA-ERT - Kama Cliffs - Erection | Mob'd equipment from landfill rd to maata's rd, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-12-12 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Capping and rock busting,started to mob drill into B151 but got called due to fog | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
117346 | Robert Bjerkelund | Labourer | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117446 | Samuel Burnett | Labourer | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117562 | Jordan Clair | Apprentice - 4th Year | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117855 | Gregory Gagnon | Apprentice - 4th Year | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118087 | Thomas Howes | Foreman | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Box in and set leg extensions. | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B089 |  | mVolts
118106 | Derek Hynes | Equipment Operator | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Testing guides | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118623 | Kenneth O'Dea | Labourer | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
118962 | Caleb Sladen | Lineman / Electrician | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B089 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | As-built MPs. Set plates | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 | FDN Support,As-Builts | mVolts,mV Revision
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Welding grounding tabs at B-150 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Welding grounding tabs at B-150 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
155637 | Judidiah Prince | Labourer | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | As-built MPs. Set plates | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 | FDN Support,As-Builts | mVolts,mV Revision
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B089 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Capping and rock busting,started to mob drill into B151 but got called due to fog | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Working in the heli laydown flying in material to 149 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Working in the heli laydown flying in material to 149 | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2020-12-13 | KAMA-ERT - Kama Cliffs - Erection | Finished moving equipment, shuffled steel, prepped for mock chopper test, boxed in, and stood leg extensions, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116651 | Sheldon Hardiman | Labourer | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
117346 | Robert Bjerkelund | Labourer | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117446 | Samuel Burnett | Labourer | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117562 | Jordan Clair | Apprentice - 4th Year | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
117855 | Gregory Gagnon | Apprentice - 4th Year | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118087 | Thomas Howes | Foreman | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Preping tower for mock run. Set leg extensions. | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B089 |  | mVolts
118106 | Derek Hynes | Equipment Operator | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B089 |  | mVolts
118623 | Kenneth O'Dea | Labourer | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
118853 | Bradley Rose | Equipment Operator | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118962 | Caleb Sladen | Lineman / Electrician | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B089 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Set shoes at legs A, C and D. Set plate at leg B. | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B149 | FDN Support | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Weld foundation B-149 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Weld foundation B-149 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
155637 | Judidiah Prince | Labourer | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Set shoes at legs A, C and D. Set plate at leg B. | 57010121 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B149 | FDN Support | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B089 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2020-12-14 | KAMA-ERT - Kama Cliffs - Erection | Winded out most the day, (55km/hr), Prepped for mock chopper lift, Stood body extensions | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B089 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-14 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B089 |  | mVolts
117346 | Robert Bjerkelund | Labourer | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B089 |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Grouted leg D at STR B063 with crux's | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117446 | Samuel Burnett | Labourer | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B089 |  | mVolts
117466 | Coleman Cadigan | Lineman / Electrician | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B089 |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Final Inspection of pile cap,grouting at B158 on Kama cliff,backfilled put data recorder on | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150, B158 |  | mVolts
117855 | Gregory Gagnon | Apprentice - 4th Year | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B089 |  | mVolts
118087 | Thomas Howes | Foreman | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Finish setting str B089 for heli mock-up. | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B089 |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B089 |  | mVolts
118282 | Lorne Lavhey | Equipment Operator | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B089 |  | mVolts
118962 | Caleb Sladen | Lineman / Electrician | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B089 |  | mVolts
119055 | Keith Taylor | Equipment Operator | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B089 |  | mVolts
130124 | Tyler Pinkerton | Labourer | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
134110 | Teemo Toykkala | Apprentice - 2nd Year | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B089 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Set shoe. Final as-builts. | 57010121 | 6 | 132.15 | 792.9 | 114.5455 | 114.55 | 907.45 | WF3 | B149 | FDN Support | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Welding at B-149 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Welding at B-149 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
155637 | Judidiah Prince | Labourer | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B089 |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Set shoe. Final as-builts. | 57010121 | 6 | 132.15 | 792.9 | 114.5455 | 114.55 | 907.45 | WF3 | B149 | FDN Support | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B089 |  | mVolts
176607 | James Ashton | Labourer | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178159 | Ryan Beaucage | Labourer | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Grouted leg D at STR B063 with crux's | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185056 | Mohammad (Max) Khalifa | Equipment Operator | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Helping crux | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2020-12-15 | KAMA-ERT - Kama Cliffs - Erection | Performed mock chopper test on b089 then completed tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B089 |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-15 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2020-12-16 | KAMA-FDN - Kama Cliffs - Foundations | Final inspection on Kama cliff,put pile cap on | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B154, B156, B157 |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-16 | KAMA-FDN - Kama Cliffs - Foundations | MP as-builts. Set btm washers for plates. | 57010121 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B154 | FDN Support,As-Builts | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-16 | KAMA-FDN - Kama Cliffs - Foundations | Welding foundation caps, stub legs, stiffeners and grounding tabs | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-16 | KAMA-FDN - Kama Cliffs - Foundations | Welding foundation caps, stub legs, stiffeners and grounding tabs | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-16 | KAMA-FDN - Kama Cliffs - Foundations | MP as-builts. Set btm washers for plates. | 57010121 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B154 | FDN Support,As-Builts | mVolts
118231 | Kteily, Mark | Supervisor | 00677 - Valard | 2020-12-16 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-17 | KAMA-FDN - Kama Cliffs - Foundations | Foundation support/As-builts | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154...B158 | FDN Support,As-Builts | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-17 | KAMA-FDN - Kama Cliffs - Foundations | Welding at B-154 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-17 | KAMA-FDN - Kama Cliffs - Foundations | Welding at B-154 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-17 | KAMA-FDN - Kama Cliffs - Foundations | Foundation support/As-builts | 57010121 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154...B158 | FDN Support,As-Builts | mVolts
146993 | Stuart Anishinabie | Surveyor | 00677 - Valard | 2020-12-18 | KAMA-FDN - Kama Cliffs - Foundations | Set plates for legs A and B. Set shoes. Final as-builts. | 57010121 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B158 | FDN Support | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2020-12-18 | KAMA-FDN - Kama Cliffs - Foundations | Foundation welding at B-158 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
152366 | Cory Breau | Carpenter | 00677 - Valard | 2020-12-18 | KAMA-FDN - Kama Cliffs - Foundations | Foundation welding at B-158 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
156936 | Stacy Snowden | Surveyor | 00677 - Valard | 2020-12-18 | KAMA-FDN - Kama Cliffs - Foundations | Set plates for legs A and B. Set shoes. Final as-builts. | 57010121 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B158 | FDN Support | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-12-19 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
117487 | Carrondo, David | Supervisor | 00677 - Valard | 2020-12-26 | KAMA-FDN - Kama Cliffs - Foundations | Foundations supervision | 57010121 | 40 | 150.59 | 6023.6 | 1050 | 1050 | 7073.6 |  |  |  | mVolts
0
0
0
0
0
0
0
0
116889 | Guildo Theriault | Foreman | 00677 - Valard | 2021-01-09 | KAMA-FDN - Kama Cliffs - Foundations | Site inspections | 57010121 | 9 | 146.89 | 1322.01 | 171.8182 | 171.82 | 1493.83 | WF3 | B149...B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116889 | Guildo Theriault | Foreman | 00677 - Valard | 2021-01-11 | KAMA-FDN - Kama Cliffs - Foundations | Site Inspections | 57010121 | 1 | 146.89 | 146.89 | 19.0909 | 19.09 | 165.98 | WF3 | B158 |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-01-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B152, B153, B155...B157 |  | mVolts
117716 | Jordie Douglas | Labourer | 00677 - Valard | 2021-01-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B152, B153, B155...B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-01-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B152 |  | mVolts
117716 | Jordie Douglas | Labourer | 00677 - Valard | 2021-01-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B152 |  | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2021-01-12 | KAMA-FDN - Kama Cliffs - Foundations | Weld gussets at B-151 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2021-01-13 | KAMA-FDN - Kama Cliffs - Foundations | Weld stiffeners at B-151 | 57010121 | 6 | 127.04 | 762.24 | 114.5455 | 114.55 | 876.79 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-01-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B153, B156 |  | mVolts
117716 | Jordie Douglas | Labourer | 00677 - Valard | 2021-01-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B153, B156 |  | mVolts
184392 | Tyler Paiha | Project Assistant | 00677 - Valard | 2021-01-14 | KAMA-FDN - Kama Cliffs - Foundations | Quality Control | 57010121 | 5 | 91.26 | 456.3 | 95.4545 | 95.45 | 551.75 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-01-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B153, B156, B157 |  | mVolts
117716 | Jordie Douglas | Labourer | 00677 - Valard | 2021-01-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B153, B156, B157 |  | mVolts
154415 | Boe Geislinger | Journeyman Mechanic | 00677 - Valard | 2021-01-15 | KAMA-ERT - Kama Cliffs - Erection | Welding | 57010123 | 9 | 132.15 | 1189.35 | 171.8182 | 171.82 | 1361.17 |  |  |  | Multi-Project,mVolts,Field Approved
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117808 | Ernest Foisey | Project Assistant | 00677 - Valard | 2021-01-16 | KAMA-FDN - Kama Cliffs - Foundations | Kama cliff take measurements and photos | 57010121 | 6 | 91.26 | 547.56 | 114.5455 | 114.55 | 662.11 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 13 | 150.59 | 1957.67 | 210 | 210 | 2167.67 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-01-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155, B157 |  | mVolts
117716 | Jordie Douglas | Labourer | 00677 - Valard | 2021-01-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155, B157 |  | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2021-01-19 | KAMA-FDN - Kama Cliffs - Foundations | Welding stiffeners at B-156, 153 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2021-01-22 | KAMA-FDN - Kama Cliffs - Foundations | Gussets at B-151, 153 | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2021-01-22 | KAMA-FDN - Kama Cliffs - Foundations | Jack hammer and shovel snow for foundation reveal,,and 2 legs at str 151 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-01-22 | KAMA-FDN - Kama Cliffs - Foundations | Jack hammer and shovel snow for foundation reveal,,and 2 legs at str 151 | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2021-01-23 | KAMA-FDN - Kama Cliffs - Foundations | Jack hammer rock for reveal,then bumped equipment to str 150 and removed snow from leg A,B and D | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-01-23 | KAMA-FDN - Kama Cliffs - Foundations | Jack hammer rock for reveal,then bumped equipment to str 150 and removed snow from leg A,B and D | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2021-01-24 | KAMA-FDN - Kama Cliffs - Foundations | Foundation welding | 57010121 | 5 | 127.04 | 635.2 | 95.4545 | 95.45 | 730.65 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2021-01-24 | KAMA-FDN - Kama Cliffs - Foundations | Heatng and hoarding at str B150 in order to do reveal | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B150 |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-01-24 | KAMA-FDN - Kama Cliffs - Foundations | Heatng and hoarding at str B150 in order to do reveal | 57010121 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B150 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
150993 | Dustin Holmes | Carpenter | 00677 - Valard | 2021-01-25 | KAMA-FDN - Kama Cliffs - Foundations | Weld stiffeners at B-151 | 57010121 | 6 | 127.04 | 762.24 | 114.5455 | 114.55 | 876.79 |  |  |  | mVolts
178171 | Jay Hoover | Labourer | 00677 - Valard | 2021-01-25 | KAMA-FDN - Kama Cliffs - Foundations | Heating and hoarding to prep for rock hammering for reveal on legs A and C | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-01-25 | KAMA-FDN - Kama Cliffs - Foundations | Heating and hoarding to prep for rock hammering for reveal on legs A and C | 57010121 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
0
0
0
0
0
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-01-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-05-13 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing (tavelled in covid testing) | 57010123 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-05-14 | KAMA-ERT - Kama Cliffs - Erection | Testing tower guides/stoppers D33 (SRF) | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116726 | Wilbert Legge | Labourer | 00677 - Valard | 2021-05-28 | KAMA-ERT - Kama Cliffs - Erection | Pull cut and press guy wires | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B152, B153, B155 |  | mVolts,mV Revision
117819 | Daniel Forsey | Equipment Operator | 00677 - Valard | 2021-05-28 | KAMA-ERT - Kama Cliffs - Erection | Pull cut and press guy wires | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B152, B153, B155 |  | mVolts,mV Revision
118760 | Dave Price | Foreman | 00677 - Valard | 2021-05-28 | KAMA-ERT - Kama Cliffs - Erection | Pull cut and press guy wires | 57010123 | 5 | 146.89 | 734.45 | 95.4545 | 95.45 | 829.9 | WF3 | B152, B153, B155 |  | mVolts,mV Revision
116726 | Wilbert Legge | Labourer | 00677 - Valard | 2021-05-29 | KAMA-ERT - Kama Cliffs - Erection | Cut and press guy wires | 57010123 | 6 | 81.03 | 486.18 | 114.5455 | 114.55 | 600.73 | WF3 | B156, B157 |  | mVolts,mV Revision
117819 | Daniel Forsey | Equipment Operator | 00677 - Valard | 2021-05-29 | KAMA-ERT - Kama Cliffs - Erection | Cut and press guy wires | 57010123 | 6 | 111.7 | 670.2 | 114.5455 | 114.55 | 784.75 | WF3 | B156, B157 |  | mVolts,mV Revision
118760 | Dave Price | Foreman | 00677 - Valard | 2021-05-29 | KAMA-ERT - Kama Cliffs - Erection | Cut and press guy wires | 57010123 | 6 | 146.89 | 881.34 | 114.5455 | 114.55 | 995.89 | WF3 | B156, B157 |  | mVolts,mV Revision
0
0
0
0
0
0
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116726 | Wilbert Legge | Labourer | 00677 - Valard | 2021-06-03 | KAMA-ERT - Kama Cliffs - Erection | Delivered guy wires and hardware to site | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B152, B153, B155...B157 |  | mVolts
117819 | Daniel Forsey | Equipment Operator | 00677 - Valard | 2021-06-03 | KAMA-ERT - Kama Cliffs - Erection | Delivered guy wires and hardware to site | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B152, B153, B155...B157 |  | mVolts
118760 | Dave Price | Foreman | 00677 - Valard | 2021-06-03 | KAMA-ERT - Kama Cliffs - Erection | Delivered guy wires and hardware to site | 57010123 | 5 | 146.89 | 734.45 | 95.4545 | 95.45 | 829.9 | WF3 | B152, B153, B155...B157 |  | mVolts
185363 | Brian Pittman | Labourer | 00677 - Valard | 2021-06-03 | KAMA-ERT - Kama Cliffs - Erection | Delivered guy wires and hardware to site | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B152, B153, B155...B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-22 | KAMA-FDN - Kama Cliffs - Foundations | Planning and organizing | 57010121 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-22 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151
187615 | Zachary Granberg | Equipment Operator | 00677 - Valard | 2021-06-22 | KAMA-ERT - Kama Cliffs - Erection | Gathering tools and rigging | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-23 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151
187615 | Zachary Granberg | Equipment Operator | 00677 - Valard | 2021-06-23 | KAMA-ERT - Kama Cliffs - Erection | Gathering tools and rigging | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116634 | James Griffiths | Apprentice - 4th Year | 00677 - Valard | 2021-06-24 | KAMA-ERT - Kama Cliffs - Erection | Rigging / flying material to kama cliffs / prep heli pads | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-24 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118959 | Jordan Skanes | Labourer | 00677 - Valard | 2021-06-24 | KAMA-ERT - Kama Cliffs - Erection | Rigging / flying material to kama cliffs / prep heli pads | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-24 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7
187615 | Zachary Granberg | Equipment Operator | 00677 - Valard | 2021-06-24 | KAMA-ERT - Kama Cliffs - Erection | Rigging / flying material to kama cliffs / prep heli pads | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
196694 | Brandon Duncan | Carpenter | 00677 - Valard | 2021-06-24 | KAMA-FDN - Kama Cliffs - Foundations | Welding stiffeners for foundation | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
196694 | Brandon Duncan | Carpenter | 00677 - Valard | 2021-06-24 | KAMA-FDN - Kama Cliffs - Foundations | Welding stiffeners on kama cliffs | 57010121 | 2 | 127.04 | 254.08 | 0 | 0 | 254.08 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-24 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-25 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-25 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154
196694 | Brandon Duncan | Carpenter | 00677 - Valard | 2021-06-25 | KAMA-FDN - Kama Cliffs - Foundations | Welding stiffeners on kama cliff sites | 57010121 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-25 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116634 | James Griffiths | Apprentice - 4th Year | 00677 - Valard | 2021-06-26 | KAMA-FDN - Kama Cliffs - Foundations | Preping heli pads / flying machines / clear sites | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117493 | Kent Caravan | Labourer | 00677 - Valard | 2021-06-26 | KAMA-ERT - Kama Cliffs - Erection | Heli pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B148 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-26 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118959 | Jordan Skanes | Labourer | 00677 - Valard | 2021-06-26 | KAMA-FDN - Kama Cliffs - Foundations | Preping heli pads / flying machines / clear sites | 57010121 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-26 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151
187615 | Zachary Granberg | Equipment Operator | 00677 - Valard | 2021-06-26 | KAMA-ERT - Kama Cliffs - Erection | Leaving job | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 |  |  |  | mVolts
196694 | Brandon Duncan | Carpenter | 00677 - Valard | 2021-06-26 | KAMA-FDN - Kama Cliffs - Foundations | Stiffeners on kama cliffs | 57010121 | 12.5 | 127.04 | 1588 | 210 | 210 | 1798 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-26 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150, B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116634 | James Griffiths | Apprentice - 4th Year | 00677 - Valard | 2021-06-27 | KAMA-ERT - Kama Cliffs - Erection | Install take off plates - apply carbonzinc - flying skids | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117493 | Kent Caravan | Labourer | 00677 - Valard | 2021-06-27 | KAMA-ERT - Kama Cliffs - Erection | Building heli pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-27 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118959 | Jordan Skanes | Labourer | 00677 - Valard | 2021-06-27 | KAMA-ERT - Kama Cliffs - Erection | Install take off plates - apply carbonzinc - flying skids | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-27 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151
196694 | Brandon Duncan | Carpenter | 00677 - Valard | 2021-06-27 | KAMA-FDN - Kama Cliffs - Foundations | welding stiffeners and grounding tabs | 57010121 | 12 | 127.04 | 1524.48 | 210 | 210 | 1734.48 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-27 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116634 | James Griffiths | Apprentice - 4th Year | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Flying skids / flying equipment | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117493 | Kent Caravan | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Heli pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118599 | Peter Norman | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149
118959 | Jordan Skanes | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Flying skids / flying equipment | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
157037 | Clayton Kwissiwa | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
182705 | Devin Courcelles | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
196694 | Brandon Duncan | Carpenter | 00677 - Valard | 2021-06-28 | KAMA-FDN - Kama Cliffs - Foundations | Weld stiffeners on foundation | 57010121 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
202967 | Chad Binguis | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Clearing brush | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151...B155 |  | mVolts
204116 | Stephen Bustard | Labourer | 00677 - Valard | 2021-06-28 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116634 | James Griffiths | Apprentice - 4th Year | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Flying skids / installing take off plates / applying carbonzinc | 57010123 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
117493 | Kent Caravan | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Heli pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118599 | Peter Norman | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B159
118959 | Jordan Skanes | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Flying skids / installing take off plates / applying carbonzinc | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
157037 | Clayton Kwissiwa | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
182705 | Devin Courcelles | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B159
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
202967 | Chad Binguis | Labourer | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Clearing pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-29 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149, B155...B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-06-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117435 | Stephen Budel | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Grounding strs / flying skids | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117493 | Kent Caravan | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Heli Pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
0
0
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118599 | Peter Norman | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149
0
0
0
0
0
0
157037 | Clayton Kwissiwa | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
175195 | Mark Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-06-30 | KAMA-ASY - Kama Cliffs - Assembly | Deliver tower steel. Drop trailer in Thunder Bay. | 57010122 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 | WF3 | B150 |  | mVolts
176480 | Brandon Kwandibens | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
182705 | Devin Courcelles | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
202967 | Chad Binguis | Labourer | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Build pas | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
203810 | Eric Morrison | Project Assistant | 00677 - Valard | 2021-06-30 | KAMA-ERT - Kama Cliffs - Erection | Site inspection | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149 |  | mVolts
117036 | Karl Kenny | Project Assistant | 00677 - Valard | 2021-07-01 | KAMA-FDN - Kama Cliffs - Foundations | Welding inspections on Kama ciff. | 57010121 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 | WF3 | B150 |  | mVolts
117435 | Stephen Budel | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ERT - Kama Cliffs - Erection | Grounding / flying skids | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117493 | Kent Caravan | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ERT - Kama Cliffs - Erection | Heli pads | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts,mV Revision
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-01 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
157037 | Clayton Kwissiwa | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-01 | KAMA-ERT - Kama Cliffs - Erection | Erection Crew | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-01 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117036 | Karl Kenny | Project Assistant | 00677 - Valard | 2021-07-02 | KAMA-FDN - Kama Cliffs - Foundations | Welding inspections on Kama cliff. | 57010121 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 | WF3 | B150 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117435 | Stephen Budel | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ERT - Kama Cliffs - Erection | Grounding towers / flying skids | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-02 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
157037 | Clayton Kwissiwa | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-02 | KAMA-FDN - Kama Cliffs - Foundations | Foundation Crew | 57010121 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117036 | Karl Kenny | Project Assistant | 00677 - Valard | 2021-07-03 | KAMA-FDN - Kama Cliffs - Foundations | Welding inspections on welded braces for Leg A and B. | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-03 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
157037 | Clayton Kwissiwa | Labourer | 00677 - Valard | 2021-07-03 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-03 | KAMA-FDN - Kama Cliffs - Foundations | Grout 149 & 150 | 57010121 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
117616 | Shannon Courtorielle | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to structure B158. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-04 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-04 | KAMA-FDN - Kama Cliffs - Foundations | Foundation Crew | 57010121 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 3 | 111.7 | 335.1 | 57.2727 | 57.27 | 392.37 | WF3 | B154 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B158 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-04 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-05 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 111.7 | 614.35 | 105 | 105 | 719.35 | WF3 | B154 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 111.7 | 614.35 | 105 | 105 | 719.35 | WF3 | B151 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B154 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117616 | Shannon Courtorielle | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to structure B154. | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
117616 | Shannon Courtorielle | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocks at structure B154. | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to structure B154. | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocks at structure B154. | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 111.7 | 614.35 | 105 | 105 | 719.35 | WF3 | B151 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 111.7 | 614.35 | 105 | 105 | 719.35 | WF3 | B150 |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to structure B154. | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocks at structure B154. | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B154 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B151 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 5.5 | 81.03 | 445.665 | 105 | 105 | 550.665 | WF3 | B150 |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-09 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151, B154, B158 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-09 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151, B154, B158 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-09 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151, B154, B158 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-09 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151, B154, B158 |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | QA/QC | 57010122 | 1 | 91.26 | 91.26 | 19.0909 | 19.09 | 110.35 | WF3 | B150 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B151, B154, B158 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | QA/QC | 57010122 | 1 | 91.26 | 91.26 | 19.0909 | 19.09 | 110.35 | WF3 | B150 |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B151, B154, B158 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151, B154, B158 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | QA/QC | 57010122 | 1 | 91.26 | 91.26 | 19.0909 | 19.09 | 110.35 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-10 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B151, B154, B158 |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
116910 | Doyle Walsh | Equipment Operator | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 111.7 | 223.4 | 38.1818 | 38.18 | 261.58 |  |  |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117616 | Shannon Courtorielle | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocks. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B154, B158 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-12 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
118191 | Jason Kelly | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 146.89 | 293.78 | 38.1818 | 38.18 | 331.96 |  |  |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-12 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-12 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocks. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B154, B158 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-12 | KAMA-ERT - Kama Cliffs - Erection | Prepare for erecting | 57010123 | 2 | 111.7 | 223.4 | 38.1818 | 38.18 | 261.58 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-12 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B150 |  | mVolts,SubstituteSupervisor
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
116910 | Doyle Walsh | Equipment Operator | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118191 | Jason Kelly | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185237 | Robert Phillips | Equipment Operator | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-13 | KAMA-ERT - Kama Cliffs - Erection | Review procedures | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-14 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-14 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-14 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocking and loaded garbage from B150, fly yard. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-14 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
205223 | Gary Walle | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Dropped blocking and loaded garbage from B150, fly yard. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B150 |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-15 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B150 |  | mVolts,SubstituteSupervisor
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-15 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B150 |  | mVolts,SubstituteSupervisor
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-15 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B150 |  | mVolts,SubstituteSupervisor
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ERT - Kama Cliffs - Erection | Swap trucks | 57010123 | 2.5 | 81.03 | 202.575 | 47.7273 | 47.73 | 250.305 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ERT - Kama Cliffs - Erection | Swap trucks | 57010123 | 2.5 | 81.03 | 202.575 | 47.7273 | 47.73 | 250.305 |  |  |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to B150. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-15 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 3 | 91.26 | 273.78 | 57.2727 | 57.27 | 331.05 | WF3 | B150 |  | mVolts,SubstituteSupervisor
205223 | Gary Walle | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to B150. | 57010122 | 2 | 81.03 | 162.06 | 38.1818 | 38.18 | 200.24 | WF3 | B150 |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-16 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts,SubstituteSupervisor
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-16 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-16 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 |  |  |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-16 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B149, B150 |  | mVolts,SubstituteSupervisor
203781 | Owen Shaw | Lineman / Electrician | 00677 - Valard | 2021-07-16 | KAMA-ERT - Kama Cliffs - Erection | Install boom on jlg 80' lift | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
205274 | Kevin Hurst | Labourer | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts,SubstituteSupervisor
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Delivered steel to B150, B151 and B158. (Fly yard) | 57010122 | 3 | 81.03 | 243.09 | 57.2727 | 57.27 | 300.36 | WF3 | B150, B151, B158 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
203781 | Owen Shaw | Lineman / Electrician | 00677 - Valard | 2021-07-17 | KAMA-ERT - Kama Cliffs - Erection | Prepare for kamil cliff erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts,SubstituteSupervisor
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B149, B158 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B149, B158 |  | mVolts
203240 | Matthew French | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | lifting for tower fitting leg ext. | 57010123 | 11 | 127.04 | 1397.44 | 210 | 210 | 1607.44 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
203781 | Owen Shaw | Lineman / Electrician | 00677 - Valard | 2021-07-18 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149, B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-19 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-19 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-19 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-07-19 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 8 | 91.26 | 730.08 | 152.7273 | 152.73 | 882.81 | WF3 | B149...B151, B154, B158 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-07-19 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 8 | 91.26 | 730.08 | 152.7273 | 152.73 | 882.81 | WF3 | B149...B151, B154, B158 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-19 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
203781 | Owen Shaw | Lineman / Electrician | 00677 - Valard | 2021-07-19 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
117369 | Maxwell Bolt | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149...B151, B154, B158 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-20 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
118178 | Bradley Kearley | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149...B151, B154, B158 |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-20 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
118646 | Orren Osmond | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-20 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
174869 | Karl Bouchard | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149...B151, B154, B158 |  | mVolts
176485 | Jeremy Sgambelluri | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
177494 | Keith Cheesequay | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
185960 | Dwight Mullins | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
186065 | Skylar Seifried | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
203259 | Jared Kearley | Labourer | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-20 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
203781 | Owen Shaw | Lineman / Electrician | 00677 - Valard | 2021-07-20 | KAMA-ERT - Kama Cliffs - Erection | Prepare for heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116511 | Marc Belanger | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118268 | Craig Laturnas | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118357 | Ramil Mabalot | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts
118394 | Rommel Mallari | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118503 | Mark Miller | Foreman | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118711 | Bobby Peters | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
203781 | Owen Shaw | Lineman / Electrician | 00677 - Valard | 2021-07-21 | KAMA-ERT - Kama Cliffs - Erection | Prepare for job shut down | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-07-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-07-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151, B154, B158 |  | mVolts
197856 | Lucas Price | Labourer | 00677 - Valard | 2021-07-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151, B154, B158 |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-07-26 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
118606 | Rodney Nugent | Project Assistant | 00677 - Valard | 2021-07-26 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
157011 | Stephanie Shedler | Project Assistant | 00677 - Valard | 2021-07-26 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
203395 | Bryan Patterson | Project Assistant | 00677 - Valard | 2021-07-26 | KAMA-FDN - Kama Cliffs - Foundations | QA/QC | 57010121 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B149...B151, B154, B158 |  | mVolts
117431 | Joshua Budel | Labourer | 00677 - Valard | 2021-07-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B150, B151, B193 |  | mVolts,SubstituteSupervisor
197856 | Lucas Price | Labourer | 00677 - Valard | 2021-07-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B150, B151, B193 |  | mVolts,SubstituteSupervisor
0
0
0
0
0
0
0
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-06 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-07 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-08 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-08-12 | KAMA-ERT - Kama Cliffs - Erection | Pick up crews gear | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-12 | KAMA-ERT - Kama Cliffs - Erection | Travelled from t-bay to marathon | 57010123 | 5 | 150.59 | 752.95 | 95.4545 | 95.45 | 848.4 |  |  |  | mVolts,SubstituteSupervisor
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-13 | KAMA-ERT - Kama Cliffs - Erection | Organize crews and equipment for EWT project | 57010123 | 4 | 146.89 | 587.56 | 76.3636 | 76.36 | 663.92
117456 | Dyson Byron-Smith | Lineman / Electrician | 00677 - Valard | 2021-08-13 | KAMA-ERT - Kama Cliffs - Erection | Return from Nipigon | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-14 | KAMA-ERT - Kama Cliffs - Erection | Organize crews and equipment for EWT project | 57010123 | 4 | 146.89 | 587.56 | 76.3636 | 76.36 | 663.92
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-15 | KAMA-ERT - Kama Cliffs - Erection | Organize crews and equipment for EWT project | 57010123 | 4 | 146.89 | 587.56 | 76.3636 | 76.36 | 663.92
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-17 | KAMA-ERT - Kama Cliffs - Erection | Missing time for Dave Smyth, Pat Green, Tyler Chisholm | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-17 | KAMA-ERT - Kama Cliffs - Erection | Missing time for Dave Smyth, Pat Green, Tyler Chisholm | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-17 | KAMA-ERT - Kama Cliffs - Erection | Missing time for Dave Smyth, Pat Green, Tyler Chisholm | 57010123 | 2 | 146.89 | 293.78 | 38.1818 | 38.18 | 331.96 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-17 | KAMA-ERT - Kama Cliffs - Erection | Missing time for Dave Smyth, Pat Green, Tyler Chisholm | 57010123 | 2 | 132.15 | 264.3 | 38.1818 | 38.18 | 302.48 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-17 | KAMA-ERT - Kama Cliffs - Erection | Missing time for Dave Smyth, Pat Green, Tyler Chisholm | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-18 | KAMA-ERT - Kama Cliffs - Erection | Layover | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Layover | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 |  |  |  | mVolts
116588 | Clayton Favel | Apprentice - 1st Year | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
116854 | Evan Seymour | Apprentice - 1st Year | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Missing time Guy Drinkwalter forgot to add him | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Flagging | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-19 | KAMA-ERT - Kama Cliffs - Erection | Went through jsa sop swp for heli erection picked up stoppers banana guides delivered to kama fly yard picked up juan romero from white river spray painted flower pots | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
116588 | Clayton Favel | Apprentice - 1st Year | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
116854 | Evan Seymour | Apprentice - 1st Year | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Travel in/ covid test drive to nipigon | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Flagging Training | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Picked out steel for stiffeners lifeted cage 1 and 2 and tops with crane to get the weight went over prints did inventory of tools | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-20 | KAMA-ERT - Kama Cliffs - Erection | Missing time for juan romero mendez | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Missing time for jeremiah mistakenchief He was just added to the project | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-21 | KAMA-ERT - Kama Cliffs - Erection | Installed bracing on panels, take booms off man lifts put mock up rigging for heli installed stoppers and banana guides on srf tower | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliffs flagging | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-22 | KAMA-ERT - Kama Cliffs - Erection | Erected str 100 installed stiffeners on panels broke apart srx cages to box in installed rigging on tower legs | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-23 | KAMA-ERT - Kama Cliffs - Erection | Flew to sites to look at for setting, finished installing stiffeners, made up bolt bags, cleaned up garbage, | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Bundling and installing steel in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Bundling and installing steel in fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Bundling and installing steel in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Bundling and installing steel in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Bundling and installing steel in fly yard | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Bundling and installing steel in fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-24 | KAMA-ERT - Kama Cliffs - Erection | Prepped fly yard did helicopter briefing with puma and 407 flew equipment and some tools to 158 painted legs at sites cleared brush away from legs | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B154 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | On site with the Fly crew | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | Multi-Project,mVolts,Field Approved
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-25 | KAMA-ERT - Kama Cliffs - Erection | Flew manlifts to 158, flew mini hoes from 151-158, flew tool baskets, manlift booms, flew legs A,D,C,B to 158 started putting boom on manlift and tying in the 4 sides of the tower | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts,SubstituteSupervisor
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts,SubstituteSupervisor
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,SubstituteSupervisor
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,SubstituteSupervisor
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,SubstituteSupervisor
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts,SubstituteSupervisor
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts,SubstituteSupervisor
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Missing time | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,SubstituteSupervisor
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts,SubstituteSupervisor
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts,SubstituteSupervisor
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B154 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,SubstituteSupervisor
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Supply Mechanic | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | Multi-Project,mVolts,Field Approved
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts,SubstituteSupervisor
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts,SubstituteSupervisor
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-26 | KAMA-ERT - Kama Cliffs - Erection | Boxed in legs installed trash rack steel in 158 prepped in fly yard flew blocks to 154 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts,SubstituteSupervisor
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts,SubstituteSupervisor
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts,SubstituteSupervisor
117243 | Robert Arnott | Project Assistant | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Added cuts as per RFI | 57010122 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts,SubstituteSupervisor
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts,SubstituteSupervisor
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts,SubstituteSupervisor
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts,SubstituteSupervisor
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts,SubstituteSupervisor
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Missing Time | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts,SubstituteSupervisor
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts,SubstituteSupervisor
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts,SubstituteSupervisor
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B154 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts,SubstituteSupervisor
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Supply mechanic for the fly crew | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | Multi-Project,mVolts,Field Approved
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly/boxing in | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts,SubstituteSupervisor
177368 | Ryan Arnold | Project Assistant | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Added cuts as per RFI | 57010122 | 2 | 91.26 | 182.52 | 38.1818 | 38.18 | 220.7 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts,SubstituteSupervisor
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-27 | KAMA-ERT - Kama Cliffs - Erection | Flew tools and equipment from 158-154 flew jersey barriers to 154 flew A,B,C,D legs for 154 pinned splices | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts,SubstituteSupervisor
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
116671 | Lucas Howardson | Foreman | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Missing Time | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
131309 | Dane Harrison | Foreman | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-28 | KAMA-ERT - Kama Cliffs - Erection | Finished boxing in 154, flew mini hoes to 150 installed banana guides and stoppers flew blocks back to yard | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-29 | KAMA-ERT - Kama Cliffs - Erection | Kama Cliff Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-29 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B154 |  | mVolts,mV Revision
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B154 |  | mVolts,mV Revision
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B154 |  | mVolts,mV Revision
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B154 |  | mVolts,mV Revision
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B154 |  | mVolts,mV Revision
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts,mV Revision
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts,mV Revision
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-30 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and testing | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts,mV Revision
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-30 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B154 |  | mVolts,mV Revision
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B154 |  | mVolts,mV Revision
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B153 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B154 |  | mVolts,mV Revision
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B154 |  | mVolts,mV Revision
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B154 |  | mVolts,mV Revision
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
0
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B154 |  | mVolts,mV Revision
117967 | Leeland Halleran | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B154 |  | mVolts,mV Revision
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B154 |  | mVolts,mV Revision
0
0
0
0
0
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B154 |  | mVolts,mV Revision
153100 | Axel Beaulieu | Apprentice - 1st Year | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B153 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B154 |  | mVolts,mV Revision
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
175347 | Norman Renaud | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B154 |  | mVolts,mV Revision
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B154 |  | mVolts,mV Revision
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-08-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard, and row stuff | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B154 |  | mVolts,mV Revision
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-08-31 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B154 |  | mVolts,mV Revision
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts,mV Revision
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts,mV Revision
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts,mV Revision
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B154 |  | mVolts,mV Revision
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Tower erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts,mV Revision
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts,mV Revision
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts,mV Revision
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts,mV Revision
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts,mV Revision
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Tower erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts,mV Revision
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts,mV Revision
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts,mV Revision
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B154 |  | mVolts,mV Revision
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B154 |  | mVolts,mV Revision
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B154 |  | mVolts,mV Revision
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B154 |  | mVolts,mV Revision
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B154 |  | mVolts,mV Revision
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts,mV Revision
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
156263 | James Young | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts,mV Revision
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts,mV Revision
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts,mV Revision
206863 | Steven Lesperance | Labourer | 00677 - Valard | 2021-09-02 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B154, B158 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B154, B158 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154, B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154, B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Supply mechanic for the fly crew | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 |  |  |  | Multi-Project,mVolts,Field Approved
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154, B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154, B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-03 | KAMA-ERT - Kama Cliffs - Erection | Installing wings | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154, B158 |  | mVolts
206863 | Steven Lesperance | Labourer | 00677 - Valard | 2021-09-03 | KAMA-ASY - Kama Cliffs - Assembly | Tower Assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B153, B155 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 | WF3 | B158 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B158 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 | WF3 | B158 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Tower erection | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Tower erection | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B158 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-04 | KAMA-ASY - Kama Cliffs - Assembly | Split gtl shafts | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-04 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B158 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Tower erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Tower erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-05 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B158 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 | WF3 | B158 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B158 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Tower Erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B158 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Tower Erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-06 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B158 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Tower Erection | 57010123 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B158 |  | mVolts
117935 | Patrick Green | Equipment Operator | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Tower Erection | 57010123 | 4 | 81.03 | 324.12 | 76.3636 | 76.36 | 400.48 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-07 | KAMA-ERT - Kama Cliffs - Erection | Heli yard clean up | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-09 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-10 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 1 | 150.59 | 150.59 | 19.0909 | 19.09 | 169.68 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama cliffs fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-11 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
116725 | Colin Legge | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117459 | Mark Byrd | Equipment Operator | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117569 | Samuel Clarke | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152, B153, B155...B157 |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly in kama fly yard | 57010122 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152, B153, B155...B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-12 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-13 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-14 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-15 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-16 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-16 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-17 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151, B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B151, B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B151, B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B151, B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B151, B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B151, B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B151, B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B151, B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-18 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-19 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 | WF3 | B153 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 4 | 146.89 | 587.56 | 57.2727 | 57.27 | 644.83 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B153 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 81.03 | 283.605 | 57.2727 | 57.27 | 340.875 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B153 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 111.7 | 390.95 | 57.2727 | 57.27 | 448.22 | WF3 | B158 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B153 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 81.03 | 283.605 | 57.2727 | 57.27 | 340.875 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B153 |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 81.03 | 283.605 | 57.2727 | 57.27 | 340.875 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B153 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 81.03 | 283.605 | 57.2727 | 57.27 | 340.875 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B153 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 132.15 | 462.525 | 57.2727 | 57.27 | 519.795 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B153 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 81.03 | 283.605 | 57.2727 | 57.27 | 340.875 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B153 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-20 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 3.5 | 132.15 | 462.525 | 57.2727 | 57.27 | 519.795 | WF3 | B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-20 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 146.89 | 1028.23 | 133.6364 | 133.64 | 1161.87 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 5 | 146.89 | 734.45 | 76.3636 | 76.36 | 810.81 | WF3 | B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 81.03 | 364.635 | 76.3636 | 76.36 | 440.995 | WF3 | B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 111.7 | 781.9 | 133.6364 | 133.64 | 915.54 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 111.7 | 502.65 | 76.3636 | 76.36 | 579.01 | WF3 | B158 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 146.89 | 1028.23 | 133.6364 | 133.64 | 1161.87 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 5 | 146.89 | 734.45 | 76.3636 | 76.36 | 810.81 | WF3 | B158 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 81.03 | 364.635 | 76.3636 | 76.36 | 440.995 | WF3 | B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 81.03 | 364.635 | 76.3636 | 76.36 | 440.995 | WF3 | B158 |  | mVolts
118716 | Micheal Phillips | Foreman | 00677 - Valard | 2021-09-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly | 57010122 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 81.03 | 364.635 | 76.3636 | 76.36 | 440.995 | WF3 | B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 132.15 | 925.05 | 133.6364 | 133.64 | 1058.69 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 132.15 | 594.675 | 76.3636 | 76.36 | 671.035 | WF3 | B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 81.03 | 567.21 | 133.6364 | 133.64 | 700.85 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 81.03 | 364.635 | 76.3636 | 76.36 | 440.995 | WF3 | B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 7 | 132.15 | 925.05 | 133.6364 | 133.64 | 1058.69 | WF3 | B152, B153, B155, B157, B165 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-21 | KAMA-ERT - Kama Cliffs - Erection | Backbolting | 57010123 | 4.5 | 132.15 | 594.675 | 76.3636 | 76.36 | 671.035 | WF3 | B158 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-21 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B152, B153, B155 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B152, B153, B155 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B152, B153, B155 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B152, B153, B155 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B152, B153, B155 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-22 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B155...B157 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B155...B157 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B155...B157 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B155...B157 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B155...B157 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B155...B157 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B155...B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B155...B157 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B155...B157 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B155...B157 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B155...B157 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B155...B157 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B155...B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-23 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B157 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B157 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B157 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B157 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B157 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-24 | KAMA-ERT - Kama Cliffs - Erection | Plumbing | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B157 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 3 | 150.59 | 451.77 | 57.2727 | 57.27 | 509.04 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-24 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B152, B153 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 146.89 | 1542.345 | 200.4545 | 200.45 | 1742.795 | WF3 | B152, B153 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 81.03 | 850.815 | 200.4545 | 200.45 | 1051.265 | WF3 | B152, B153 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 111.7 | 1172.85 | 200.4545 | 200.45 | 1373.3 | WF3 | B152, B153 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 111.7 | 1172.85 | 200.4545 | 200.45 | 1373.3 | WF3 | B152, B153 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 146.89 | 1542.345 | 200.4545 | 200.45 | 1742.795 | WF3 | B152, B153 |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 81.03 | 850.815 | 200.4545 | 200.45 | 1051.265 | WF3 | B152, B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 81.03 | 850.815 | 200.4545 | 200.45 | 1051.265 | WF3 | B152, B153 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 81.03 | 850.815 | 200.4545 | 200.45 | 1051.265 | WF3 | B152, B153 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B152, B153 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 81.03 | 850.815 | 200.4545 | 200.45 | 1051.265 | WF3 | B152, B153 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B152, B153 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-25 | KAMA-ERT - Kama Cliffs - Erection | K-frame and bridge prep | 57010123 | 10.5 | 132.15 | 1387.575 | 200.4545 | 200.45 | 1588.025 | WF3 | B152, B153 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-25 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B152 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B152 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B152 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B152 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B152 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B152 |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Fly crew support | 57010123 | 4 | 132.15 | 528.6 | 76.3636 | 76.36 | 604.96 |  |  |  | Multi-Project,mVolts,Field Approved
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B152 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B152 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-26 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B153 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B153 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B153 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B153 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B153 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B153 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B153 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B153 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B153 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B153 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B153 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-27 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B152, B153 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B152, B153 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B152, B153 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B152, B153 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B152, B153 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B152, B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B152, B153 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B152, B153 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B152, B153 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B152, B153 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B152, B153 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B152, B153 |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 4 | 150.59 | 602.36 | 76.3636 | 76.36 | 678.72 |  |  |  | mVolts
117561 | Joseph Clarke | Supervisor | 00677 - Valard | 2021-09-28 | KAMA-ASY - Kama Cliffs - Assembly | Tower assembly supervision | 57010122 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B152, B153, B155 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B152, B153, B155 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B152, B153, B155 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B152, B153, B155 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B152, B153, B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B152, B153, B155 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B152, B153, B155 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B152, B153, B155 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B152, B153, B155 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B155 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Preping tie back sies with mini hoes | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B155 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B155 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B155 |  | mVolts
0
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
0
0
119108 | Robert Tremblett | Equipment Operator | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Preping tie back sies with mini hoes | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
0
0
0
0
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B155 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155 |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly crew Support | 57010123 | 4 | 132.15 | 528.6 | 76.3636 | 76.36 | 604.96 |  |  |  | Multi-Project,mVolts,Field Approved
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B155 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B155 |  | mVolts
203539 | Michael Shea | Equipment Operator | 00677 - Valard | 2021-09-30 | KAMA-ERT - Kama Cliffs - Erection | Preping tie back sies with mini hoes | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-01 | KAMA-ERT - Kama Cliffs - Erection | Built pads for man lifts on north and south side of foundations with mini hoes | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149 |  | mVolts
119108 | Robert Tremblett | Equipment Operator | 00677 - Valard | 2021-10-01 | KAMA-ERT - Kama Cliffs - Erection | Built pads for man lifts on north and south side of foundations with mini hoes | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
203539 | Michael Shea | Equipment Operator | 00677 - Valard | 2021-10-01 | KAMA-ERT - Kama Cliffs - Erection | Built pads for man lifts on north and south side of foundations with mini hoes | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-02 | KAMA-ERT - Kama Cliffs - Erection | Built acsses to tie back on the south side and acsses to leg C tie back and pad for lego blocks | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149 |  | mVolts
119108 | Robert Tremblett | Equipment Operator | 00677 - Valard | 2021-10-02 | KAMA-ERT - Kama Cliffs - Erection | Built acsses to tie back on the south side and acsses to leg C tie back and pad for lego blocks | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
203539 | Michael Shea | Equipment Operator | 00677 - Valard | 2021-10-02 | KAMA-ERT - Kama Cliffs - Erection | Built acsses to tie back on the south side and acsses to leg C tie back and pad for lego blocks | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-03 | KAMA-ERT - Kama Cliffs - Erection | Finished str 149 flew up to str.151 built pad on southside of tower.cut of tempory anchors on str. 158 lonlined steel and cut offs to staging | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149 |  | mVolts
119108 | Robert Tremblett | Equipment Operator | 00677 - Valard | 2021-10-03 | KAMA-ERT - Kama Cliffs - Erection | Finished str 149 flew up to str.151 built pad on southside of tower.cut of tempory anchors on str. 158 lonlined steel and cut offs to staging | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
203539 | Michael Shea | Equipment Operator | 00677 - Valard | 2021-10-03 | KAMA-ERT - Kama Cliffs - Erection | Finished str 149 flew up to str.151 built pad on southside of tower.cut of tempory anchors on str. 158 lonlined steel and cut offs to staging | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-08 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-10-08 | KAMA-ERT - Kama Cliffs - Erection | Fly Crew Support | 57010123 | 6 | 132.15 | 792.9 | 114.5455 | 114.55 | 907.45 |  |  |  | Multi-Project,mVolts,Field Approved
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-08 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-09 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
196534 | Darryl McLeod | Journeyman Mechanic | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly crew Support | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 |  |  |  | Multi-Project,mVolts,Field Approved
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-10 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B155, B156, B158 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B155, B156, B158 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B155, B156, B158 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 | WF3 | B155, B156, B158 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 | WF3 | B155, B156, B158 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 | WF3 | B155, B156, B158 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12.5 | 150.59 | 1882.375 | 210 | 210 | 2092.375 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B155, B156, B158 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B155, B156, B158 |  | mVolts
138224 | Gavin Olson | Surveyor | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | stake tie backs and panel tie backs | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B149 | Extra Work,FDN Support | mVolts,mV Revision
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B155, B156, B158 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 | WF3 | B155, B156, B158 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B155, B156, B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 | WF3 | B155, B156, B158 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting / heli erection | 57010123 | 13 | 70.81 | 920.53 | 210 | 210 | 1130.53 | WF3 | B155, B156, B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B156, B157 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B156, B157 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B156, B157 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B156, B157 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B156, B157 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B156, B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B156, B157 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B156, B157 |  | mVolts
119105 | Brodie Trenholm | Labourer | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B156, B157 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B156, B157 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B156, B157 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B156, B157 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B156, B157 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-12 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B156, B157 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B157 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B157 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B157 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B157 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B157 |  | mVolts
119105 | Brodie Trenholm | Labourer | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B157 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B157 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B157 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B157 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-13 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B157 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150, B156, B157 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150, B156, B157 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150, B156, B157 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150, B156, B157 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150, B156, B157 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150, B156, B157 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150, B156, B157 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150, B156, B157 |  | mVolts
126752 | Andrew Laidlaw | Surveyor | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Tieback anchor layout support | 57010123 | 6.5 | 132.15 | 858.975 | 124.0909 | 124.09 | 983.065 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150, B156, B157 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150, B156, B157 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150, B156, B157 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150, B156, B157 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-14 | KAMA-ERT - Kama Cliffs - Erection | Rock anchors and back bolting | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149, B150, B156, B157 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150, B152, B153, B155 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150, B152, B153, B155 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150, B152, B153, B155 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150, B152, B153, B155 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150, B152, B153, B155 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150, B152, B153, B155 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150, B152, B153, B155 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150, B152, B153, B155 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150, B152, B153, B155 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150, B152, B153, B155 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150, B152, B153, B155 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150, B152, B153, B155 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-15 | KAMA-ERT - Kama Cliffs - Erection | Back bolting and pad building | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B150, B152, B153, B155 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-16 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149, B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-17 | KAMA-ERT - Kama Cliffs - Erection | Heli reection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
118850 | Francisco Roque-Alvarenga | Apprentice - 2nd Year | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149, B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149, B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B151 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B151 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erertion | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erertion | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erertion | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erertion | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erertion | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erertion | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149, B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149...B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149...B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149...B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149...B151 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149...B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149...B151 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149...B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149...B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149...B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149...B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erecction | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149...B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
117819 | Daniel Forsey | Equipment Operator | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Dlivered steel and bolts to fly yard | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B153 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
185363 | Brian Pittman | Labourer | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Dlivered steel and bolts to fly yard | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B153 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10.5 | 146.89 | 1542.345 | 200.4545 | 200.45 | 1742.795 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection prep | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B149 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Set legs on str 149 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Set legs on str 149 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Set legs on str 149 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
174881 | Terry Jean | Journeyman Mechanic | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Support for Fly Crew | 57010123 | 3 | 132.15 | 396.45 | 57.2727 | 57.27 | 453.72 |  |  |  | Multi-Project,mVolts,Field Approved
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Set legs on str 149 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Set legs on str 149 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Set legs on str 149 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-23 | KAMA-ERT - Kama Cliffs - Erection | Yard prep and heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B151 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Back bolting str 149 | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B154 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Back bolting str 149 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Back bolting str 149 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts
138438 | Jacob Palmer | Project Assistant | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B155, B156, B157 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B155...B157 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B155, B156, B157 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B155...B157 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Back bolting str 149 | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B154 |  | mVolts
189100 | Michael Moroso | Project Assistant | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B155, B156, B157 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B155...B157 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Back bolting str 149 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts
197055 | Elie Sutton Deschenes | Labourer | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B155, B156, B157 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B155...B157 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Back bolting str 149 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B154 |  | mVolts
205193 | Tommy Collin | Apprentice - 3rd Year | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B155, B156, B157 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B155...B157 |  | mVolts
208927 | Xavier Girard | Apprentice - 3rd Year | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B155, B156, B157 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B155...B157 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B149, B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B149, B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
138438 | Jacob Palmer | Project Assistant | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str. B157, B158 | 57010123 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B157, B158 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B149, B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str. B157, B158 | 57010123 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B157, B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B149, B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
189100 | Michael Moroso | Project Assistant | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str. B157, B158 | 57010123 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B157, B158 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
197055 | Elie Sutton Deschenes | Labourer | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str. B157, B158 | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B157, B158 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
205193 | Tommy Collin | Apprentice - 3rd Year | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str. B157, B158 | 57010123 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B157, B158 |  | mVolts
208927 | Xavier Girard | Apprentice - 3rd Year | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str. B157, B158 | 57010123 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 | WF3 | B157, B158 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-25 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B149, B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Back bolting on str 151 | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Back bolting on str 151 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Back bolting on str 151 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B150, B151, B152, B153 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150...B153 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Back bolting on str 151 | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Back bolting on str 151 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
197055 | Elie Sutton Deschenes | Labourer | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B150, B151, B152, B153 | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150...B153 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B150, B151, B152, B153 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150...B153 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Back bolting on str 151 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
205193 | Tommy Collin | Apprentice - 3rd Year | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B150, B151, B152, B153 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150...B153 |  | mVolts
208927 | Xavier Girard | Apprentice - 3rd Year | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspections at Str.B150, B151, B152, B153 | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B150...B153 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | backbolting | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | backbolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | backbolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | backbolting | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | backbolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
197055 | Elie Sutton Deschenes | Labourer | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | QA/QC | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | QA/QC | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | backbolting | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts
205193 | Tommy Collin | Apprentice - 3rd Year | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | QA/QC | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151 |  | mVolts
208927 | Xavier Girard | Apprentice - 3rd Year | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | QA/QC | 57010123 | 11 | 91.26 | 1003.86 | 210 | 210 | 1213.86 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
155056 | Bryan Spence | Labourer | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
163292 | Cyrus Desmoulin | Labourer | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B149 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing floor | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-28 | KAMA-ERT - Kama Cliffs - Erection | Installing the floor | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 | WF3 | B151 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B151 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
155056 | Bryan Spence | Labourer | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B151 |  | mVolts
163292 | Cyrus Desmoulin | Labourer | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 | WF3 | B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B151 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Standing panels on 151 | 57010123 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 70.81 | 885.125 | 210 | 210 | 1095.125 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
155056 | Bryan Spence | Labourer | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
163292 | Cyrus Desmoulin | Labourer | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-30 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
0
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
0
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
0
0
0
0
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
0
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
155056 | Bryan Spence | Labourer | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
163292 | Cyrus Desmoulin | Labourer | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B149 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-10-31 | KAMA-ERT - Kama Cliffs - Erection | Fly yard prep | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B151 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B151 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B151 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B151 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B149 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-01 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B150 |  | mVolts
117725 | Guy Drinkwalter | Foreman | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
118970 | Edward Smith | Labourer | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-03 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-03 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-03 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-03 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B151 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-04 | KAMA-ERT - Kama Cliffs - Erection | Oblique BB1/2 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-04 | KAMA-ERT - Kama Cliffs - Erection | Oblique BB1/2 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-04 | KAMA-ERT - Kama Cliffs - Erection | Oblique BB1/2 | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B151 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-04 | KAMA-ERT - Kama Cliffs - Erection | Oblique BB1/2 | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-05 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts,SubstituteSupervisor
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-05 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts,SubstituteSupervisor
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-05 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts,SubstituteSupervisor
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-05 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts,SubstituteSupervisor
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-06 | KAMA-ERT - Kama Cliffs - Erection | Oblique 151 | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B151 |  | mVolts,SubstituteSupervisor
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-06 | KAMA-ERT - Kama Cliffs - Erection | Oblique 151 | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts,SubstituteSupervisor
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-06 | KAMA-ERT - Kama Cliffs - Erection | Oblique 151 | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B151 |  | mVolts,SubstituteSupervisor
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-06 | KAMA-ERT - Kama Cliffs - Erection | Oblique 151 | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B151 |  | mVolts,SubstituteSupervisor
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-06 | KAMA-ERT - Kama Cliffs - Erection | Oblique 151 | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B151 |  | mVolts,SubstituteSupervisor
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-07 | KAMA-ERT - Kama Cliffs - Erection | Bolting 151 | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts,SubstituteSupervisor
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-07 | KAMA-ERT - Kama Cliffs - Erection | Bolting 151 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts,SubstituteSupervisor
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-07 | KAMA-ERT - Kama Cliffs - Erection | Bolting 151 | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B151 |  | mVolts,SubstituteSupervisor
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-07 | KAMA-ERT - Kama Cliffs - Erection | Bolting 151 | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B151 |  | mVolts,SubstituteSupervisor
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-07 | KAMA-ERT - Kama Cliffs - Erection | Bolting 151 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B151 |  | mVolts,SubstituteSupervisor
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-08 | KAMA-ERT - Kama Cliffs - Erection | Flew webbing on str 150 | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-08 | KAMA-ERT - Kama Cliffs - Erection | Flew webbing on str 150 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-08 | KAMA-ERT - Kama Cliffs - Erection | Flew webbing on str 150 | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-08 | KAMA-ERT - Kama Cliffs - Erection | Flew webbing on str 150 | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-08 | KAMA-ERT - Kama Cliffs - Erection | Flew webbing on str 150 | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-09 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-09 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-09 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-09 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-09 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-10 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-10 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-10 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-10 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 9 | 146.89 | 1322.01 | 171.8182 | 171.82 | 1493.83 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 8 | 150.59 | 1204.72 | 152.7273 | 152.73 | 1357.45 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 9 | 146.89 | 1322.01 | 171.8182 | 171.82 | 1493.83 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-11 | KAMA-ERT - Kama Cliffs - Erection | Erection kama cliffs | 57010123 | 8 | 70.81 | 566.48 | 152.7273 | 152.73 | 719.21 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 146.89 | 734.45 | 95.4545 | 95.45 | 829.9 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 111.7 | 558.5 | 95.4545 | 95.45 | 653.95 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 81.03 | 405.15 | 95.4545 | 95.45 | 500.6 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5.5 | 146.89 | 807.895 | 105 | 105 | 912.895 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 132.15 | 660.75 | 95.4545 | 95.45 | 756.2 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-12 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 5 | 70.81 | 354.05 | 95.4545 | 95.45 | 449.5 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-13 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-14 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-15 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 12 | 70.81 | 849.72 | 210 | 210 | 1059.72 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
116787 | Shamus Myers | Foreman | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
180376 | David Smyth | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-16 | KAMA-ERT - Kama Cliffs - Erection | Erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150, B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150, B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B150, B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B150, B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150, B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150, B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150, B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150, B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150, B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150, B151 |  | mVolts
188896 | Decker MacLean | Foreman | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Mobb out | 57010123 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 | WF3 | B150 |  | mVolts
196040 | Jason Delaurier | Lineman / Electrician | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Mobb out | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
201359 | Kevin Blanchette | Lineman / Electrician | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Mobb out | 57010123 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-17 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B150, B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B154 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B154 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B154 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B154 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 |  |  |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-18 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B150 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-19 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B150 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 12 | 150.59 | 1807.08 | 210 | 210 | 2017.08 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B150 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-20 | KAMA-ERT - Kama Cliffs - Erection | Heli erecton | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-21 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B150 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-22 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B150, B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150, B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B150, B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150, B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150, B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150, B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B150, B151 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B150, B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-23 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B150, B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-24 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 | WF3 | B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 | WF3 | B151 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | 210 | 210 | 1101.33 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-25 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 70.81 | 778.91 | 210 | 210 | 988.91 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-26 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-27 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-28 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | 210 | 210 | 1866.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-29 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | 210 | 210 | 1024.315 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
0
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | 190.9091 | 190.91 | 1696.81 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
0
0
0
0
0
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
0
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-11-30 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 10 | 70.81 | 708.1 | 190.9091 | 190.91 | 899.01 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 146.89 | 1468.9 | Nipigon Camp | 0 | 1468.9 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 111.7 | 1117 | Nipigon Camp | 0 | 1117 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 111.7 | 1117 | Nipigon Camp | 0 | 1117 |  |  |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | Nipigon Camp | 0 | 1505.9 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 |  |  |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 |  |  |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-01 | KAMA-ERT - Kama Cliffs - Erection | Yard work | 57010123 | 10 | 70.81 | 708.1 | Nipigon Camp | 0 | 708.1 |  |  |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 146.89 | 1468.9 | Nipigon Camp | 0 | 1468.9 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 111.7 | 1117 | Nipigon Camp | 0 | 1117 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 111.7 | 1117 | Nipigon Camp | 0 | 1117 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 10 | 150.59 | 1505.9 | Nipigon Camp | 0 | 1505.9 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-02 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 10 | 70.81 | 708.1 | Nipigon Camp | 0 | 708.1 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 146.89 | 1689.235 | Nipigon Camp | 0 | 1689.235 | WF3 | B149 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-03 | KAMA-ERT - Kama Cliffs - Erection | Heli erection | 57010123 | 11.5 | 70.81 | 814.315 | Nipigon Camp | 0 | 814.315 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 146.89 | 1689.235 | Nipigon Camp | 0 | 1689.235 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts,SubstituteSupervisor
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 6.5 | 81.03 | 526.695 | Nipigon Camp | 0 | 526.695 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 6.5 | 132.15 | 858.975 | Nipigon Camp | 0 | 858.975 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 6.5 | 132.15 | 858.975 | Nipigon Camp | 0 | 858.975 | WF3 | B151 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-04 | KAMA-ERT - Kama Cliffs - Erection | Back bolting tower | 57010123 | 11.5 | 70.81 | 814.315 | Nipigon Camp | 0 | 814.315 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 146.89 | 1615.79 | Nipigon Camp | 0 | 1615.79 | WF3 | B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 | WF3 | B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 | WF3 | B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Climbing and foundatin inspections Str.B149. | 57010123 | 11 | 91.26 | 1003.86 | Nipigon Camp | 0 | 1003.86 | WF3 | B149 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Climbing and foundatin inspections Str.B149. | 57010123 | 11 | 91.26 | 1003.86 | Nipigon Camp | 0 | 1003.86 | WF3 | B149 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Climbing and foundatin inspections Str.B149. | 57010123 | 11 | 91.26 | 1003.86 | Nipigon Camp | 0 | 1003.86 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Hand wings with chopper | 57010123 | 11 | 70.81 | 778.91 | Nipigon Camp | 0 | 778.91 | WF3 | B151 |  | mVolts
211348 | Michael Dicks | Apprentice - 2nd Year | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Climbing and foundatin inspections Str.B149. | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B149 |  | mVolts
212437 | Gintaras Gaputis | Lineman / Electrician | 00677 - Valard | 2021-12-05 | KAMA-ERT - Kama Cliffs - Erection | Climbing and foundatin inspections Str.B149. | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B149 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 146.89 | 1615.79 | Nipigon Camp | 0 | 1615.79 | WF3 | B151, B154 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151, B154 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 | WF3 | B151, B154 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 | WF3 | B151, B154 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151, B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151, B154 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151, B154 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151, B154 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151, B154 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151, B154 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspection Str.B154 | 57010123 | 11 | 91.26 | 1003.86 | Nipigon Camp | 0 | 1003.86 | WF3 | B154 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspection Str.B154 | 57010123 | 11 | 91.26 | 1003.86 | Nipigon Camp | 0 | 1003.86 | WF3 | B154 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B151, B154 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspection Str.B154 | 57010123 | 11 | 91.26 | 1003.86 | Nipigon Camp | 0 | 1003.86 | WF3 | B154 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B151, B154 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 70.81 | 778.91 | Nipigon Camp | 0 | 778.91 | WF3 | B151, B154 |  | mVolts
211348 | Michael Dicks | Apprentice - 2nd Year | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspection Str.B154 | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B154 |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-06 | KAMA-ERT - Kama Cliffs - Erection | Climbing inspection Str.B154 | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 146.89 | 1615.79 | Nipigon Camp | 0 | 1615.79 | WF3 | B150, B154 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B150, B154 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 | WF3 | B150, B154 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 | WF3 | B150, B154 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B150, B154 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B150, B154 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B150, B154 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B150, B154 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B150, B154 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B150, B154 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151, B154 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151, B154 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 132.15 | 1453.65 | Nipigon Camp | 0 | 1453.65 | WF3 | B150, B154 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151, B154 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 81.03 | 891.33 | Nipigon Camp | 0 | 891.33 | WF3 | B150, B154 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-07 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11 | 70.81 | 778.91 | Nipigon Camp | 0 | 778.91 | WF3 | B150, B154 |  | mVolts
211348 | Michael Dicks | Apprentice - 2nd Year | 00677 - Valard | 2021-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 81.03 | 972.36 | Nipigon Camp | 0 | 972.36 | WF3 | B151, B154 |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-07 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B151, B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 146.89 | 1689.235 | Nipigon Camp | 0 | 1689.235 | WF3 | B150, B151 |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B150, B151 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B150, B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B150, B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B150, B151 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B150, B151 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B150, B151 |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B150, B151 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B150, B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B150, B151 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151, B154 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151, B154 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B150, B151 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151, B154 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B150, B151 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-08 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 11.5 | 70.81 | 814.315 | Nipigon Camp | 0 | 814.315 | WF3 | B150, B151 |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-08 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B151, B154 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 146.89 | 881.34 | Nipigon Camp | 0 | 881.34 |  |  |  | mVolts
117367 | Juan Bolanos Henriquez | Apprentice - 2nd Year | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 111.7 | 670.2 | Nipigon Camp | 0 | 670.2 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 10 | 111.7 | 1117 | Nipigon Camp | 0 | 1117 |  |  |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 9 | 150.59 | 1355.31 | Nipigon Camp | 0 | 1355.31 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 |  |  |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 132.15 | 792.9 | Nipigon Camp | 0 | 792.9 |  |  |  | mVolts
136050 | Michael Pond | Lineman / Electrician | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 132.15 | 792.9 | Nipigon Camp | 0 | 792.9 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 10 | 132.15 | 1321.5 | Nipigon Camp | 0 | 1321.5 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 |  |  |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundation QC | 57010121 | 5 | 91.26 | 456.3 | Nipigon Camp | 0 | 456.3 | WF3 | B151 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundation QC | 57010121 | 5 | 91.26 | 456.3 | Nipigon Camp | 0 | 456.3 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 6 | 132.15 | 792.9 | Nipigon Camp | 0 | 792.9 |  |  |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundation QC | 57010121 | 5 | 91.26 | 456.3 | Nipigon Camp | 0 | 456.3 | WF3 | B151 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 |  |  |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-09 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 10 | 70.81 | 708.1 | Nipigon Camp | 0 | 708.1 |  |  |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-09 | KAMA-FDN - Kama Cliffs - Foundations | Foundation QC | 57010121 | 5 | 132.15 | 660.75 | Nipigon Camp | 0 | 660.75 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 146.89 | 1689.235 | Nipigon Camp | 0 | 1689.235 | WF3 | B149, B150 |  | mVolts,mV Revision
117441 | Cyric Burt | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 12 | 111.7 | 1340.4 | Nipigon Camp | 0 | 1340.4 | WF3 | B150 |  | mVolts
117466 | Coleman Cadigan | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 132.15 | 1717.95 | Nipigon Camp | 0 | 1717.95 | WF3 | B150 |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 12 | 127.04 | 1524.48 | Nipigon Camp | 0 | 1524.48 | WF3 | B150 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B149, B150 |  | mVolts,mV Revision
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 | WF3 | B149, B150 |  | mVolts,mV Revision
117631 | Stephen Crossley | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 111.7 | 1452.1 | Nipigon Camp | 0 | 1452.1 | WF3 | B150 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149, B150 |  | mVolts,mV Revision
118179 | Chad Kearley | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 81.03 | 1053.39 | Nipigon Camp | 0 | 1053.39 | WF3 | B150 |  | mVolts
118282 | Lorne Lavhey | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 111.7 | 1452.1 | Nipigon Camp | 0 | 1452.1 | WF3 | B150 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118433 | Bradley McCullough | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 132.15 | 1717.95 | Nipigon Camp | 0 | 1717.95 | WF3 | B150 |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149, B150 |  | mVolts,mV Revision
119105 | Brodie Trenholm | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 81.03 | 1053.39 | Nipigon Camp | 0 | 1053.39 | WF3 | B150 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149, B150 |  | mVolts,mV Revision
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 81.03 | 1053.39 | Nipigon Camp | 0 | 1053.39 | WF3 | B150 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149, B150 |  | mVolts,mV Revision
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149, B150 |  | mVolts,mV Revision
175342 | Patrick Bananish | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 81.03 | 1053.39 | Nipigon Camp | 0 | 1053.39 | WF3 | B150 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 | WF3 | B149, B150 |  | mVolts,mV Revision
191181 | Roland Bruce | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 111.7 | 1452.1 | Nipigon Camp | 0 | 1452.1 | WF3 | B150 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151 |  | mVolts
201825 | Craig Bolt | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 81.03 | 1053.39 | Nipigon Camp | 0 | 1053.39 | WF3 | B150 |  | mVolts
202793 | Kenneth Mullett | Equipment Operator | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 12 | 111.7 | 1340.4 | Nipigon Camp | 0 | 1340.4 | WF3 | B150 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 | WF3 | B149, B150 |  | mVolts,mV Revision
208965 | William Wellwood | Labourer | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 81.03 | 1053.39 | Nipigon Camp | 0 | 1053.39 | WF3 | B150 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolt | 57010123 | 11.5 | 70.81 | 814.315 | Nipigon Camp | 0 | 814.315 | WF3 | B149, B150 |  | mVolts,mV Revision
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel QC the whole structure Move everything to structure B149 | 57010123 | 13 | 132.15 | 1717.95 | Nipigon Camp | 0 | 1717.95 | WF3 | B150 |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-10 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B151 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 146.89 | 1762.68 | Nipigon Camp | 0 | 1762.68 | WF3 | B149 |  | mVolts
117441 | Cyric Burt | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 111.7 | 670.2 | Nipigon Camp | 0 | 670.2 | WF3 | B149 |  | mVolts
117466 | Coleman Cadigan | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 132.15 | 792.9 | Nipigon Camp | 0 | 792.9 | WF3 | B149 |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 111.7 | 1340.4 | Nipigon Camp | 0 | 1340.4 | WF3 | B149 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 111.7 | 1340.4 | Nipigon Camp | 0 | 1340.4 | WF3 | B149 |  | mVolts
117631 | Stephen Crossley | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6.5 | 111.7 | 726.05 | Nipigon Camp | 0 | 726.05 | WF3 | B149 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 81.03 | 972.36 | Nipigon Camp | 0 | 972.36 | WF3 | B149 |  | mVolts
118179 | Chad Kearley | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 | WF3 | B149 |  | mVolts
118282 | Lorne Lavhey | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6.5 | 111.7 | 726.05 | Nipigon Camp | 0 | 726.05 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118433 | Bradley McCullough | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 132.15 | 792.9 | Nipigon Camp | 0 | 792.9 | WF3 | B149 |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 81.03 | 972.36 | Nipigon Camp | 0 | 972.36 | WF3 | B149 |  | mVolts
119105 | Brodie Trenholm | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 | WF3 | B149 |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B149 |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 | WF3 | B149 |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B149 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 81.03 | 972.36 | Nipigon Camp | 0 | 972.36 | WF3 | B149 |  | mVolts
175342 | Patrick Bananish | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6.5 | 81.03 | 526.695 | Nipigon Camp | 0 | 526.695 | WF3 | B149 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151...B153, B155...B158 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151...B153, B155...B158 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B149 |  | mVolts
191181 | Roland Bruce | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 111.7 | 670.2 | Nipigon Camp | 0 | 670.2 | WF3 | B149 |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B151...B153, B155...B158 |  | mVolts
201825 | Craig Bolt | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6.5 | 81.03 | 526.695 | Nipigon Camp | 0 | 526.695 | WF3 | B149 |  | mVolts
202793 | Kenneth Mullett | Equipment Operator | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 111.7 | 670.2 | Nipigon Camp | 0 | 670.2 | WF3 | B149 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 81.03 | 972.36 | Nipigon Camp | 0 | 972.36 | WF3 | B149 |  | mVolts
208965 | William Wellwood | Labourer | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 81.03 | 486.18 | Nipigon Camp | 0 | 486.18 | WF3 | B149 |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolting | 57010123 | 12 | 70.81 | 849.72 | Nipigon Camp | 0 | 849.72 | WF3 | B149 |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-ERT - Kama Cliffs - Erection | Back bolted structure Installed missing steel | 57010123 | 6 | 132.15 | 792.9 | Nipigon Camp | 0 | 792.9 | WF3 | B149 |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-11 | KAMA-FDN - Kama Cliffs - Foundations | Erection/Foundation QC | 57010121 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B151...B153, B155...B158 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 146.89 | 1689.235 | Nipigon Camp | 0 | 1689.235 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 111.7 | 1284.55 | Nipigon Camp | 0 | 1284.55 |  |  |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 |  |  |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 |  |  |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 |  |  |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-12-12 | KAMA-ROW - Kama Cliffs - ROW | ROW tasks | 57010120 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B154 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Erection QC | 57010123 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Erection QC | 57010123 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 132.15 | 1519.725 | Nipigon Camp | 0 | 1519.725 |  |  |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Erection QC | 57010123 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 81.03 | 931.845 | Nipigon Camp | 0 | 931.845 |  |  |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11.5 | 70.81 | 814.315 | Nipigon Camp | 0 | 814.315 |  |  |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-12 | KAMA-ERT - Kama Cliffs - Erection | Erection QC | 57010123 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B150 |  | mVolts
116532 | Jesse Broadfoot | Foreman | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 146.89 | 587.56 | Nipigon Camp | 0 | 587.56 |  |  |  | mVolts
117537 | Jeremiah Mistaken Chief | Equipment Operator | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 111.7 | 446.8 | Nipigon Camp | 0 | 446.8 |  |  |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 111.7 | 446.8 | Nipigon Camp | 0 | 446.8 |  |  |  | mVolts
117685 | Corey Derksen | Project Assistant | 00677 - Valard | 2021-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Erection/ Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150, B151 |  | mVolts
117741 | Brandon Dyke | Labourer | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 81.03 | 324.12 | Nipigon Camp | 0 | 324.12 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
118488 | Felix Mendoza | Apprentice - 2nd Year | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 81.03 | 324.12 | Nipigon Camp | 0 | 324.12 |  |  |  | mVolts
119238 | Kyle Willetts | Lineman / Electrician | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 132.15 | 528.6 | Nipigon Camp | 0 | 528.6 |  |  |  | mVolts
139162 | Malcolm Newton | Lineman / Electrician | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 132.15 | 528.6 | Nipigon Camp | 0 | 528.6 |  |  |  | mVolts
155056 | Bryan Spence | Labourer | 00677 - Valard | 2021-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Erection/ Foundation QC | 57010121 | 12 | 81.03 | 972.36 | Nipigon Camp | 0 | 972.36 | WF3 | B150, B151 |  | mVolts
156150 | Elijah Kwissiwa | Labourer | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 81.03 | 324.12 | Nipigon Camp | 0 | 324.12 |  |  |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-12-13 | KAMA-ROW - Kama Cliffs - ROW | ROW tasks | 57010120 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B155 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Erection/ Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150, B151 |  | mVolts
186426 | Cole Eldridge | Project Assistant | 00677 - Valard | 2021-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Erection/ Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150, B151 |  | mVolts
188879 | Juan Romero Mendez | Lineman / Electrician | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 132.15 | 528.6 | Nipigon Camp | 0 | 528.6 |  |  |  | mVolts
197658 | Cody Hull | Project Assistant | 00677 - Valard | 2021-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Erection/ Foundation QC | 57010121 | 12 | 91.26 | 1095.12 | Nipigon Camp | 0 | 1095.12 | WF3 | B150, B151 |  | mVolts
202852 | Campbell Sturge-Anderson | Labourer | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 81.03 | 324.12 | Nipigon Camp | 0 | 324.12 |  |  |  | mVolts
210604 | Greg Ripley | Apprentice - 1st Year | 00677 - Valard | 2021-12-13 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 4 | 70.81 | 283.24 | Nipigon Camp | 0 | 283.24 |  |  |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-13 | KAMA-FDN - Kama Cliffs - Foundations | Erection/ Foundation QC | 57010121 | 12 | 132.15 | 1585.8 | Nipigon Camp | 0 | 1585.8 | WF3 | B150, B151 |  | mVolts
117541 | Tyler Chisholm | Equipment Operator | 00677 - Valard | 2021-12-14 | KAMA-ERT - Kama Cliffs - Erection | Yard clean up | 57010123 | 11 | 111.7 | 1228.7 | Nipigon Camp | 0 | 1228.7 |  |  |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-14 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
185078 | Reese Schmidt | Labourer | 00677 - Valard | 2021-12-14 | KAMA-ROW - Kama Cliffs - ROW | ROW tasks. | 57010120 | 10 | 81.03 | 810.3 | Nipigon Camp | 0 | 810.3 | WF3 | B155 |  | mVolts
185549 | Jackson Pond | Project Assistant | 00677 - Valard | 2021-12-14 | KAMA-ERT - Kama Cliffs - Erection | Installed grounds. | 57010123 | 3 | 91.26 | 273.78 | Nipigon Camp | 0 | 273.78 | WF3 | B149 |  | mVolts
211851 | Cody Tucker | Lineman / Electrician | 00677 - Valard | 2021-12-14 | KAMA-ERT - Kama Cliffs - Erection | Installed grounds. | 57010123 | 3 | 132.15 | 396.45 | Nipigon Camp | 0 | 396.45 | WF3 | B149 |  | mVolts
118370 | Jody MacDonald | Supervisor | 00677 - Valard | 2021-12-15 | KAMA-ERT - Kama Cliffs - Erection | Planning and organizing | 57010123 | 11 | 150.59 | 1656.49 | Nipigon Camp | 0 | 1656.49 |  |  |  | mVolts
0
0
0
0
0
0
0
0
0
0
0
0
0
0
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-15 | KAMA-STG - Kama Cliffs - Stringing | - worked on crane pads at str B-148 - cleared access and fibre pad west of str B-147 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-15 | KAMA-STG - Kama Cliffs - Stringing | - worked on crane pads at str B-148 - cleared access and fibre pad west of str B-147 | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-16 | KAMA-STG - Kama Cliffs - Stringing | - worked on crane pads at B-148 - worked on puller pad at B-160 - cleared all access and sites on camp 81 RD. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-16 | KAMA-STG - Kama Cliffs - Stringing | - worked on crane pads at B-148 - worked on puller pad at B-160 - cleared all access and sites on camp 81 RD. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-17 | KAMA-STG - Kama Cliffs - Stringing | - cleared jackpine access into B-159/160 - cleared existing crane pads - unloaded tower materials in the fly yard/laydown - worked on puller pad - worked on crane pads at B-159/160 | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-17 | KAMA-STG - Kama Cliffs - Stringing | - cleared jackpine access into B-159/160 - cleared existing crane pads - unloaded tower materials in the fly yard/laydown - worked on puller pad - worked on crane pads at B-159/160 | 57010124 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-18 | KAMA-STG - Kama Cliffs - Stringing | Prepping hardware for pull | 57010124 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-18 | KAMA-STG - Kama Cliffs - Stringing | Prepping hardware for pull | 57010124 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-18 | KAMA-STG - Kama Cliffs - Stringing | Prepping hardware for pull | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 9 | 111.7 | 1005.3 | 171.8182 | 171.82 | 1177.12 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | set up pull site at b160. | 57010124 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | - unloadeded hardline/rope reels at entrance to jackpine RD. - delivered hardline/rope reels into str -B-160 puller site. - delivered fly stand to jackpine puller site from km 17 henson. - assisted tractor and flystand into puller site with loader. | 57010124 | 12 | 127.04 | 1524.48 | 210 | 210 | 1734.48 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | - unloadeded hardline/rope reels at entrance to jackpine RD. - delivered hardline/rope reels into str -B-160 puller site. - delivered fly stand to jackpine puller site from km 17 henson. - assisted tractor and flystand into puller site with loader. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | - unloadeded hardline/rope reels at entrance to jackpine RD. - delivered hardline/rope reels into str -B-160 puller site. - delivered fly stand to jackpine puller site from km 17 henson. - assisted tractor and flystand into puller site with loader. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep for śtringing. | 57010124 | 11.5 | 111.7 | 1284.55 | 210 | 210 | 1494.55 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep for śtringing. | 57010124 | 11.5 | 146.89 | 1689.235 | 210 | 210 | 1899.235 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-19 | KAMA-STG - Kama Cliffs - Stringing | Prep for śtringing. | 57010124 | 11.5 | 81.03 | 931.845 | 210 | 210 | 1141.845 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 11.5 | 132.15 | 1519.725 | 210 | 210 | 1729.725 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 11.5 | 91.26 | 1049.49 | 210 | 210 | 1259.49 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 4 | 111.7 | 446.8 | 76.3636 | 76.36 | 523.16 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 91.26 | 912.6 | 190.9091 | 190.91 | 1103.51 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10.5 | 146.89 | 1542.345 | 200.4545 | 200.45 | 1742.795 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | - fuelled excavator at str 160 - travelled 744 loader down to camp 81 RD from jackpine RD. | 57010124 | 8 | 127.04 | 1016.32 | 152.7273 | 152.73 | 1169.05 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | - fuelled excavator at str 160 - travelled 744 loader down to camp 81 RD from jackpine RD. | 57010124 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | - fuelled excavator at str 160 - travelled 744 loader down to camp 81 RD from jackpine RD. | 57010124 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Building glass for dead end towers. | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Building glass for dead end towers. | 57010124 | 10 | 146.89 | 1468.9 | 190.9091 | 190.91 | 1659.81 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-20 | KAMA-STG - Kama Cliffs - Stringing | Building glass for dead end towers. | 57010124 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Set up puller site at str B160. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | - plowed fly yard and cleared extra laydown area for helicopters - cleared tension site - bobtailed to wawa and hauled PT-40 puller down to jackpine str 160. - moved reel trailer and tensioner onto tension site at str 148. | 57010124 | 14 | 127.04 | 1778.56 | 210 | 210 | 1988.56 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | - plowed fly yard and cleared extra laydown area for helicopters - cleared tension site - bobtailed to wawa and hauled PT-40 puller down to jackpine str 160. - moved reel trailer and tensioner onto tension site at str 148. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | - plowed fly yard and cleared extra laydown area for helicopters - cleared tension site - bobtailed to wawa and hauled PT-40 puller down to jackpine str 160. - moved reel trailer and tensioner onto tension site at str 148. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Building hardware for stringing activities. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Building hardware for stringing activities. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-21 | KAMA-STG - Kama Cliffs - Stringing | Building hardware for stringing activities. | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prepped material to hang travellers | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Site prep | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep material,prep jumpers,hang travellers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Cleared snow Assested other crews where needed Unloaded equipment Prepped site for pull Placed equipment | 57010124 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Cleared snow Assested other crews where needed Unloaded equipment Prepped site for pull Placed equipment | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Cleared snow Assested other crews where needed Unloaded equipment Prepped site for pull Placed equipment | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Prep to string from B160 to B 148. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Building D.E hardware and flysite materials | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Building D.E hardware and flysite materials | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-22 | KAMA-STG - Kama Cliffs - Stringing | Building D.E hardware and flysite materials | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 10 | 132.15 | 1321.5 | 190.9091 | 190.91 | 1512.41 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Unload trailer/prep material/set up site | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Preppped for pull Cleared snow Spotten equipment Assested other crews where needed | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Preppped for pull Cleared snow Spotten equipment Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Preppped for pull Cleared snow Spotten equipment Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 91.26 | 1140.75 | 210 | 210 | 1350.75 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 91.26 | 1140.75 | 210 | 210 | 1350.75 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hung conductor and static travellers from B148-B160 Hung fiber travellers from B147-B160 | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | prep sites to pull from b148 to b160. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | hag travellers between b148 and b160. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Hang travellers,prep material, | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Stringing kama cliffs | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | - plowed fibre site at str B-147. - cleared extra space in fly yard for c-cans and parking. - widened all access from fly yard to highway on camp 81 RD. - unload fibre tensioner and reel stands in fly yard. -bump fuel bowser into the heli LZ. | 57010124 | 4 | 127.04 | 508.16 | 76.3636 | 76.36 | 584.52 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | - plowed fibre site at str B-147. - cleared extra space in fly yard for c-cans and parking. - widened all access from fly yard to highway on camp 81 RD. - unload fibre tensioner and reel stands in fly yard. -bump fuel bowser into the heli LZ. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | - plowed fibre site at str B-147. - cleared extra space in fly yard for c-cans and parking. - widened all access from fly yard to highway on camp 81 RD. - unload fibre tensioner and reel stands in fly yard. -bump fuel bowser into the heli LZ. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Site prep and cleanup | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Site prep and cleanup | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-23 | KAMA-STG - Kama Cliffs - Stringing | Site prep and cleanup | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118032 | Dwayne Hickey | Labourer | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Puller site | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly rope | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13.5 | 146.89 | 1983.015 | 210 | 210 | 2193.015 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly hardline,pull conductor | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Flew 6 hardlines and 2 ropes Prepped puller for pull Broke down moved equipment Winded ropes and hardlines | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Flew 6 hardlines and 2 ropes Prepped puller for pull Broke down moved equipment Winded ropes and hardlines | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Flew 6 hardlines and 2 ropes Prepped puller for pull Broke down moved equipment Winded ropes and hardlines | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly all hard lines and rope from b160 to b148. Set up to pull conductor. | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Fly all hard lines and rope from b160 to b148. Set up to pull conductor. | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Prepped material for conductor and static tie in B148-B160 Prepped fiber material for tie in B147-B160 Prepped hold down blocks for B149,151,156 | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | stringing kama cliffs | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116584 | Justin Fancey | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | - cleared snow with dozer - washed/cleaned trucks - travelled to Thunder Bay | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119126 | Derwin Upshall | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | - cleared snow with dozer - washed/cleaned trucks - travelled to Thunder Bay | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing Support | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep and cleanup of material in wawa | 57010124 | 14 | 81.03 | 1134.42 | 210 | 210 | 1344.42 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep and cleanup of material in wawa | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-24 | KAMA-STG - Kama Cliffs - Stringing | Stringing prep and cleanup of material in wawa | 57010124 | 14 | 111.7 | 1563.8 | 210 | 210 | 1773.8 |  |  |  | mVolts
118032 | Dwayne Hickey | Labourer | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Puller site | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull opgw | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 91.26 | 1140.75 | 210 | 210 | 1350.75 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 91.26 | 1140.75 | 210 | 210 | 1350.75 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 Ground work for helicopters | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled 4 phases of wire | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled 4 phases of wire | 57010124 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled 4 phases of wire | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled 4 phases of wire | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled 4 phases of wire | 57010124 | 12.5 | 81.03 | 1012.875 | 210 | 210 | 1222.875 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled 4 phases of wire | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | stringing str 148-160 | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13.5 | 146.89 | 1983.015 | 210 | 210 | 2193.015 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled phases 1,2,3,4 Assested with fiber pull Swapped reels | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled phases 1,2,3,4 Assested with fiber pull Swapped reels | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pulled phases 1,2,3,4 Assested with fiber pull Swapped reels | 57010124 | 12.5 | 111.7 | 1396.25 | 210 | 210 | 1606.25 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull conductor from B148 to B160. | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Pull conductor from B148 to B160. | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Organizing material and cleanup | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
117571 | Travis Clarke | Foreman | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Organizing material and cleanup | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Organizing material and cleanup | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-02-25 | KAMA-STG - Kama Cliffs - Stringing | Stringing Support | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13.5 | 146.89 | 1983.015 | 210 | 210 | 2193.015 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Deadending conductor str 149 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
118032 | Dwayne Hickey | Labourer | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Puller site | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Stringing | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Stringing | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Stringing | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Stringing | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Stringing | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Stringing | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Hold downs B149,B151,B156 Gripping B148,B160 | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Pulled phase 5,6,7 Load/ unload reels on pt 40 Break down site Prepped for sagging | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Pulled phase 5,6,7 Load/ unload reels on pt 40 Break down site Prepped for sagging | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Pulled phase 5,6,7 Load/ unload reels on pt 40 Break down site Prepped for sagging | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | pull conductor from F148 to F160. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | pull conductor from F148 to F160. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | stringing str B148-B160 | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Sag opgw and deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
157024 | Joseph Thompson | Labourer | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Finish cleanup and head to Thunderbay | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117996 | Terrance Hardiman | Equipment Operator | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | Finish cleanup and head to Thunderbay | 57010124 | 10 | 111.7 | 1117 | 190.9091 | 190.91 | 1307.91 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-02-26 | KAMA-STG - Kama Cliffs - Stringing | OPGW Sagging | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag/deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Packed up rest of site and brought stuff back to the c cans Assested in moving equipment to the laydown yard Assested other crews where needed | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Packed up rest of site and brought stuff back to the c cans Assested in moving equipment to the laydown yard Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Packed up rest of site and brought stuff back to the c cans Assested in moving equipment to the laydown yard Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Tied in fiber pull B147-B160 | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 127.04 | 1524.48 | 210 | 210 | 1734.48 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Break down puller site equipment and get it ready for mobe. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | help with deadending conductor at str b148. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | stringing | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118032 | Dwayne Hickey | Labourer | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Puller site | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-02-27 | KAMA-STG - Kama Cliffs - Stringing | Sagging OPGW and Conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor,install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag and deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sagged wire Moved reels from site to end of access road Assested other crews where needed | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sagged wire Moved reels from site to end of access road Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sagged wire Moved reels from site to end of access road Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 127.04 | 1524.48 | 210 | 210 | 1734.48 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag conductor and shield wire between B149 and B151. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sag conductor and shield wire between B149 and B151. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | stringing | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
118032 | Dwayne Hickey | Labourer | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Puller site | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-02-28 | KAMA-STG - Kama Cliffs - Stringing | Sagging Support | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Installed jumper on B148 Ground work for heicopter Prep material | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | sag conductor from B160 to B151. Clean up excess wire. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | sag conductor from B160 to B151. Clean up excess wire. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
203383 | Derek Millar | Apprentice - 3rd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 8 | 91.26 | 730.08 | 152.7273 | 152.73 | 882.81 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagged wire Assested other crews where needed | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagged wire Assested other crews where needed | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
119291 | Mitchell Young | Equipment Operator | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagged wire Assested other crews where needed | 57010124 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118196 | Bowin Kerbrat | Labourer | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging | 57010124 | 10 | 81.03 | 810.3 | 190.9091 | 190.91 | 1001.21 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | stringing | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-03-01 | KAMA-STG - Kama Cliffs - Stringing | Sagging Support | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 13.5 | 127.04 | 1715.04 | 210 | 210 | 1925.04 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Tie in B152 B154 b158 half sides of B153 b155 b156 B157 | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | stringing | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | sag conductor from B160 to b 151 and clean up wire. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | sag conductor from B160 to b 151 and clean up wire. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | sag conductor from B160 to b 151 and clean up wire. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | sag conductor from B160 to b 151 and clean up wire. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-03-02 | KAMA-STG - Kama Cliffs - Stringing | Sagging Support | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Haul equipment from site to thunderbay yard. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Haul equipment from site to thunderbay yard. | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend str b159. | 57010124 | 12.5 | 132.15 | 1651.875 | 210 | 210 | 1861.875 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend str b159. | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | stringing | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Clean up prep | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Clean up prep | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
187804 | Steven Hrushka | Equipment Operator | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Clean up prep | 57010124 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 |  |  |  | mVolts
204378 | Kenneth Bennett | Equipment Operator | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Clean up prep | 57010124 | 8 | 111.7 | 893.6 | 152.7273 | 152.73 | 1046.33 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Clean up prep | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 91.26 | 1186.38 | 210 | 210 | 1396.38 |  |  |  | mVolts
209527 | Alex-Antoine Gilot | Apprentice - 4th Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
184649 | Gregory Baggs | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
211145 | Daniel Rideout | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
183141 | Jovaun Meekis | Apprentice - 2nd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 81.03 | 1053.39 | 210 | 210 | 1263.39 |  |  |  | mVolts
204055 | Brady Budgell | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116628 | Christopher Gray | Apprentice - 4th Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Finished tie in B148-B160 Installed bird diverters B158-159,160,161 Installed pendulums B156-B157 | 57010124 | 13.5 | 146.89 | 1983.015 | 210 | 210 | 2193.015 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend,jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend,jumpers | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend,jumpers | 57010124 | 13 | 146.89 | 1909.57 | 210 | 210 | 2119.57 |  |  |  | mVolts
137794 | Austin Atatise-Morriseau | Apprentice - 2nd Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend,jumpers | 57010124 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend,jumpers | 57010124 | 13 | 111.7 | 1452.1 | 210 | 210 | 1662.1 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Deadend,jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
174682 | Nolan Martens | Surveyor | 00677 - Valard | 2022-03-03 | KAMA-STG - Kama Cliffs - Stringing | Sagging Support | 57010124 | 13 | 132.15 | 1717.95 | 210 | 210 | 1927.95 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116828 | Joshua Price | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12.5 | 146.89 | 1836.125 | 210 | 210 | 2046.125 |  |  |  | mVolts
116663 | Tyrone Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
205605 | Alexander Temple | Apprentice - 2nd Year | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 81.03 | 972.36 | 210 | 210 | 1182.36 |  |  |  | mVolts
204381 | Grant Guy | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116662 | Tyson Hickey | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend conductor | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116641 | Wayne Guest | Equipment Operator | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | prep equipment for mobe and clean up site. | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | prep equipment for mobe and clean up site. | 57010124 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
119201 | Mark Wells | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | prep equipment for mobe and clean up site. | 57010124 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
118338 | Joshua Lowery | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | install jumpers on str b159 and move equipment to a2. | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
185538 | Brett Beam | Apprentice - 2nd Year | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 8 | 81.03 | 648.24 | 152.7273 | 152.73 | 800.97 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Site clean up | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116777 | John Mitchell Jr | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | stringing | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend opgw and ohsw/jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend opgw and ohsw/jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend opgw and ohsw/jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend opgw and ohsw/jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-04 | KAMA-STG - Kama Cliffs - Stringing | Deadend opgw and ohsw/jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Equiptment haul | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
117688 | Brett Desjarlais | Foreman | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Equiptment haul | 57010124 | 8 | 146.89 | 1175.12 | 152.7273 | 152.73 | 1327.85 |  |  |  | mVolts
118362 | Craig MacKinnon | Lineman / Electrician | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Site cleanup | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
180170 | Craig Canal | Apprentice - 3rd Year | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Site cleanup | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
203354 | Ryan Maye | Apprentice - 4th Year | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Site cleanup | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
184683 | Richard Dicks | Apprentice - 3rd Year | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Site cleanup | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
116826 | Joseph Power | Foreman | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Site cleanup | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
119206 | James West | Lineman / Electrician | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Site cleanup | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
197057 | David Grenier | Lineman / Electrician | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Prep jumpers | 57010124 | 8 | 132.15 | 1057.2 | 152.7273 | 152.73 | 1209.93 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Prep jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116849 | Joshua Schiestel | Foreman | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Prep jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Prep jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Prep jumpers | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-05 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Hauling | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Prep materail for jumpers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Prep materail for jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Prep materail for jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Prep materail for jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Load trailer/fly crew | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Load trailer/fly crew | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-06 | KAMA-STG - Kama Cliffs - Stringing | Load trailer/fly crew | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Jumpers,yard work | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Jumpers,yard work | 57010124 | 12 | 146.89 | 1762.68 | 210 | 210 | 1972.68 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Jumpers,yard work | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-07 | KAMA-STG - Kama Cliffs - Stringing | Hauling | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
203358 | Loran Whittle | Apprentice - 3rd Year | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 91.26 | 1095.12 | 210 | 210 | 1305.12 |  |  |  | mVolts
117628 | Matthew Crossley | Equipment Operator | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 111.7 | 1340.4 | 210 | 210 | 1550.4 |  |  |  | mVolts
116815 | Daniel Pelley | Lineman / Electrician | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
116864 | James Smith | Journeyman Mechanic | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Install jumpers | 57010124 | 12 | 132.15 | 1585.8 | 210 | 210 | 1795.8 |  |  |  | mVolts
153300 | David Ginter | Truck Driver / Picker Op. | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Hauling | 57010124 | 13 | 127.04 | 1651.52 | 210 | 210 | 1861.52 |  |  |  | mVolts
210614 | Christian Sirois | Lineman / Electrician | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Yard work | 57010124 | 11 | 132.15 | 1453.65 | 210 | 210 | 1663.65 |  |  |  | mVolts
116555 | Jonathan Clarke | Foreman | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Yard work | 57010124 | 11 | 146.89 | 1615.79 | 210 | 210 | 1825.79 |  |  |  | mVolts
213753 | Jadon Elliott | Apprentice - 4th Year | 00677 - Valard | 2022-03-08 | KAMA-STG - Kama Cliffs - Stringing | Yard work | 57010124 | 11 | 111.7 | 1228.7 | 210 | 210 | 1438.7 |  |  |  | mVolts