## 2-AA
Projects | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 Bridge Year | 2024 Test Year
Reporting Basis
SA-01 - Capital Poles | 620437 | 460555 | 863086.7 | 726784.46 | 1582976.63 | 516001 | 810423.4
SA-06 - New Subdivisions | 507509.3 | 454982.38 | 235303 | 338635.46 | 264729.61 | 481455.61 | 436986.04
SA-03 - New UG Service | 280141.44 | 197412.67 | 170596 | 196111.72 | 333013 | 255238 | 268524.18
SA-07- Service Upgrades | 62893.12 | 71694.56 | 109226 | 135415 | 193965.87 | 524683 | 79985.2
SA-05 - 3-Phase Customer Connections | 112956.33 | 116174 | 122418 | 115188 | 319963 | 214834 | 148218.23
New O/H Service Connections | 10992.24 | 6529.55 | 2051.7 | 6844.83 | 51496.58 | 51584 | 16877.53
Microfits | 9597.7 | 7629 | 623.33 | 1470.9 | 1820.64 | 8783.33 | 0
Non-demarcation Customers | 38047.05 | 41012.8 | 24564.41 | 28927.31 | 1106.38 | 0 | 32647.49
System Access Gross Expenditures | 1642574.18 | 1355989.96 | 1527869.14 | 1549377.68 | 2749071.71 | 2052578.94 | 1793662.07
System Access Capital Contributions | -333784 | -380696 | -314737.66 | -479486.67 | -538856.88 | -1231946 | -850267
Sub-Total | 1308790.18 | 975293.96 | 1213131.48 | 1069891.01 | 2210214.83 | 820632.94 | 943395.07
System Renewal
SR-04 - Decrepit Pole Replacement | 674069 | 920915 | 1086293.19 | 2045865.27 | 998984.05 | 1164482 | 1652855.2
SR-02 - Substation Upgrades | 1350783.09 | 1025882.24 | 1063358 | 856613 | 1052559.35 | 1928976.26 | 1294515.27
SR-05C - Kincardine Load Balancing | 0 | 0 | 0 | 0 | 0 | 80538.34 | 1090213.66
SR-05D- Fibreglass Transformer Base Replacement | 0 | 0 | 0 | 0 | 0 | 277308 | 230321.12
SR-05 - Distribution Transformer Replacement | 174253 | 279728 | 160608 | 118615.82 | 63179.01 | 78769.6 | 242718.75
SR-06 - Infrastructure Upgrade | 87440.98 | 54886 | 320450 | 39050 | 418138.59 | 1039682.67 | 136659.17
SR-07- Pole Line Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 335000
Poletran Conversion | 587918.78 | 582180.79 | 0 | 0 | 0 | 0 | 0
#6 Copper Replacement | 345035.87 | 187664.64 | 134540.37 | 0 | 0 | 0 | 0
PME/Metering Replacement | 0 | 0 | 210532 | 0 | 2447 | 0 | 0
SR-04 - Decrepit Pole Replacement Emergent | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Renewal Gross Expenditures | 3219500.72 | 3051256.67 | 2975781.56 | 3060144.09 | 2535308 | 4569756.87 | 4982283.17
System Renewal Capital Contributions |  | -32558 | -98609
Sub-Total | 3219500.72 | 3018698.67 | 2877172.56 | 3060144.09 | 2535308 | 4569756.87 | 4982283.17
System Service
Meters | 224096.17 | 112537 | 224140 | 65923 | 109156 | 99996 | 310493.68
SCADA | 212571.53 | 363.8 | 0 | 0 | 0 | 0 | 0
Automatic Switch | 0 | 46996.62 | 8322.57 | 0 | 160761.16 | 138303 | 42800.91
Micellaneous Metering | 0 | 0 | 2696.71 | 0 | 0 | 0 | 0
CYME & GIS Integration | 0 | 0 | 0 | 0 | 71777.57 | 0 | 0
System Service Gross Expenditures | 436667.7 | 159897.42 | 235159.28 | 65923 | 341694.73 | 238299 | 353294.59
System Service Capital Contributions | 0 | -21632 | -4326 | 0 | 0 | 0 | -30873
Sub-Total | 436667.7 | 138265.42 | 230833.28 | 65923 | 341694.73 | 238299 | 322421.59
General Plant
Technology | 117083.7 | 16145 | 0 | 30311 | 2875 | 125654 | 144196
Vehicle Replacement | 541413.5 | 11688 | 112200 | 371220 | 490809 | 506754.94 | 250000
Tools and Equipment | 15694.37 | 172600 | 0 | 75571 | 31588 | 52610.07 | 61000
Facilities Enhancements | 57681.9 | 17319.75 | 161260.53 | 21135.89 | 0 | 172434.52 | 20000
Office Furniture and Equipment | 19648.99 | 10123.34 | 0 | 31769 | 0 | 9253.16 | 15000
Communication Equipment | 18972.99 | 0 | 0 | 0 | 0 | 0 | 0
General Plant Gross Expenditures | 770495.45 | 227876.09 | 273460.53 | 530006.89 | 525272 | 866706.69 | 490196
General Plant Capital Contributions
Sub-Total | 770495.45 | 227876.09 | 273460.53 | 530006.89 | 525272 | 866706.69 | 490196
HONI LTLT Asset Purchase | 49742 | 0 | 0 | 0 | 0
Other Capitl Projects | 128261.57 | 131465.3 | 45604.65 | 40686 | 224498.91 | 128919.89
Miscellaneous
Total | 5913457.62 | 4491599.44 | 4640202.5 | 4766650.99 | 5836988.47 | 6624315.39 | 6738295.83
Less Renewable Generation Facility Assets and Other Non-Rate-Regulated Utility Assets (input as negative)
Total | 5913457.62 | 4491599.44 | 4640202.5 | 4766650.99 | 5836988.47 | 6624315.39 | 6738295.83
| 5913457.43 | 4491599.32 | 4640203 | 4766651 | 5836988 | 6624315 | 6738296
| -0.19 | -0.12 | 0.5 | 0.01 | -0.47 | -0.39 | 0.17
Work in Progress (WIP) at the end of 2023 consists of the following project categories:
Oth-03 Service Upgrades | 24428
SA-01 Capital Poles | 48103
SA-03 New U/G Service Connections | 6041
SA-05 3 Phase Customers | 7373
SA-06 New Subdivision | 7283
SR-02 Substation Upgrades | 1269981
Total | 1363209
It relates to the following assets:
1820 | 1265236
1830 | 40181
1835 | 33283
1840 | 300
1845 | 4123
1850 | 6064
1855 | 2141
1860 | 11881
Total | 1363209

## 2-AB
Appendix 2-AB
Table 2 - Capital Expenditure Summary from Chapter 5 Consolidated Distribution System Plan Filing Requirements
First year of Forecast Period: | 2023
CATEGORY | Historical Period (previous plan1 & actual) | [14 empty] | Forecast Period (planned)
| 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 | 2024 | 2025 | 2026 | 2027
| Plan | Actual | Var | Plan | Actual | Var | Plan | Actual | Var | Plan | Actual | Var | Plan | Actual2 | Var
| $ '000 |  | % | $ '000 |  | % | $ '000 |  | % | $ '000 |  | % | $ '000 |  | % | $ '000
System Access | 3231509 | 1643000 | -49.16% | 2963562 | 1356000 | -54.24% | 3158679 | 1528000 | -51.63% | 3449520 | 1588000 | -53.96% | 3466927 | 0 | -100% | 2052579 | 1793662
System Renewal | 382000 | 3158000 | 726.7% | 66750 | 3051000 | 4471% | 69690 | 2897000 | 4057% | 69690 | 3125000 | 4384% | 69690 | 0 | -100% | 4569757 | 4982283
System Service | 642734 | 437000 | -32.01% | 664635 | 203000 | -69.46% | 671006 | 206000 | -69.3% | 677481 | 14000 | -97.93% | 686893 | 0 | -100% | 367219 | 322422
General Plant | 635000 | 948 | -99.85% | 350000 | 350000 | 0% | 590000 | 425000 | -27.97% | 95000 | 476000 | 401.1% | 570000 | 0 | -100% | 866707 | 490196
Capital Contribution | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -1231946 | -850267
TOTAL EXPENDITURE | 4891243 | 5238948 | 7.109% | 4044947 | 4960000 | 22.62% | 4489375 | 5056000 | 12.62% | 4291691 | 5203000 | 21.23% | 4793510 | 0 | -100% | 6624316 | 6738296 | 0 | 0 | 0
System O&M (exclude Admin) |  |  | -- |  |  | -- |  |  | -- |  |  | -- |  |  | --
Continuity Schedule Integrigy Check |  | 5641528.29 |  |  | 4481881.72 |  |  | 4630628.23 |  |  | 4777951.79 |  |  | 5879973 |  | 6624316 | 6738296
Notes to the Table:
1. Historical “previous plan” data is not required unless a plan has previously been filed. However, use the last Board-approved, at least on a Total (Capital) Expenditure basis for the last cost of service rebasing year, and the applicant should include their planned budget in each subsequent historical year up to and including the Bridge Year.
2. Indicate the number of months of 'actual' data included in the last year of the Historical Period (normally a 'bridge' year):
Explanatory Notes on Variances (complete only if applicable)
Notes on shifts in forecast vs. historical budgets by category
Notes on year over year Plan vs. Actual variances for Total Expenditures
Notes on Plan vs. Actual variance trends for individual expenditure categories