## Forecast and Actual Units
CIR Parent Program | Program | Asset Type | Unit of Measure | 2020-2024 Total Forecast (as filed) | 2020-2024 Total Actual (includes Forecasted 2024)
Metering |  | Residential & Small C&I | Units | 311978 | 104791
Metering |  | Large Customer & Interval | Units | 60 | 22
Metering |  | Remote Disconnect | Units | - | 11168
Metering |  | Suite Metering | Units | 27500 | 16614
Metering |  | Samp./Meter Repl. | Units | - | 56156
Load Demand |  | Load Transfers – Bus | MVA | 105 | 187.06
Load Demand |  | Feeder Transfers | # | 16 | 7
Load Demand |  | Cable Upgrades | # | 18 | 11
Load Demand |  | Network Equipment Upgrades | # | 6 | 3
Load Demand |  | Civil Enhancements | # areas targeted | 2.5 | 2.68
Area Conversion | Box Construction Conversion | Poles | Units | 3800 | 3368
Area Conversion | Rear Lot Conversion | No. of Customers Converted | Rear Lot Customers Converted | 2350 | 683
Network System Renewal | Network Unit Renewal | Network Units | Units | 200 | 173
Network System Renewal | Legacy Network Units | ATS & RPB | Units | 13 | 15
Network System Renewal | Network Vault Renewal | Vault Rebuilds | Units | 33 | 32
Network System Renewal | Network Vault Renewal | Roof Rebuilds | Units |  | 9
Network System Renewal | Network Vault Renewal | Vault Decommission | Units |  | 1
Network Circuit Reconfiguration | Network Circuit Reconfiguration | Reconfiguration | Units | 5 | 3
Network Circuit Reconfiguration | Network Circuit Reconfiguration | Network Unit | Units | 14 | 14
Overhead Renewal | Overhead System Renewal | Poles | Units | 11530 | 7803
Overhead Renewal | Overhead System Renewal | Transformers | Units | 6700 | 3499
Overhead Renewal | Overhead System Renewal | OH Switches | Units | 710 | 748
Overhead Renewal | Overhead System Renewal | Conductors (Primary) | km | 350 | 277
Stations Renewal | Stations TS | TS Switchgear | Units | 5 | 2
Stations Renewal | Stations TS | TS Breakers (Outdoor) | Units | 9 | 12
Stations Renewal | Stations TS | TS Switch (Outdoor) | Units | 61 | 69
Stations Renewal | Stations MS | MS Switchgear | Units | 12 | 11
Stations Renewal | Stations MS | Power Transformer | Units | 10 | 12
Stations Renewal | Stations MS | MS Primary Supply | Units | 11 | 3
Stations Renewal | Stations Control & Monitoring | RTU Renewal TS | Units | 43 | 12
Stations Renewal | Stations Control & Monitoring | RTU Renewal MS | Units |  | 48
Stations Renewal | Stations Control & Monitoring | Relay Renewal (including Pilot-wire Protection Renewal) | Units/Locations | 5 | 39
Stations Renewal | Stations Control & Monitoring | Interstation Control Wiring Renewal | km | 45 | 16
Stations Renewal | Stations Ancillary and Battery | Battery units | Units | 67 | 53
Stations Renewal | Stations Ancillary and Battery | Charger units | Units | 67 | 37
Stations Renewal | Stations Ancillary and Battery | Air Compressor Replacements | Units | 2 | 0
Stations Renewal | Stations Ancillary and Battery | Sump Pump Installations | Units | 3 | 1
Stations Renewal | Stations Ancillary and Battery | SST | Units | 6 | 6
Stations Renewal | Stations Ancillary and Battery | AC Panels | Units | N/A | 1
Underground Renewal - Horseshoe | Underground Circuit Renewal - Horseshoe | Total Cable | km | 340 | 184
Underground Renewal - Horseshoe | Underground Circuit Renewal - Horseshoe | Transformers | Units | 2478 | 1999
Underground Renewal - Horseshoe | Underground Circuit Renewal - Horseshoe | UG Switches | Units | 116 | 144
Underground Renewal - Downtown | Underground Cable Renewal | PILC Cable | km | 27.5 | 28.9
Underground Renewal - Downtown | Underground Cable Renewal | AILC Cable | km | 53.5 | 6.3
Underground Renewal - Downtown | Underground Cable Renewal | Fiber Optic Cable | km | - | 0
Underground Renewal - Downtown | Cable Chamber Renewal | Cable Chamber | Units | 75 | 25
Underground Renewal - Downtown | Cable Chamber Renewal | Cable Chamber Roof | Units | 120 | 33
Underground Renewal - Downtown | Cable Chamber Renewal | Cable Chamber Abandonment | Units | 15 | 2
Underground Renewal - Downtown | Cable Chamber Renewal | Cable Chamber Lid | Units | 1000 | 1491
Underground Renewal - Downtown | Underground Residential Distribution Renewal | URD Submersible Switches | Units | 17 | 8
Underground Renewal - Downtown | Underground Residential Distribution Renewal | URD Transformers | Units | 3 | 7
Underground Renewal - Downtown | Underground Residential Distribution Renewal | URD Vault Roof | Units | 18 | 9
Underground Renewal - Downtown | Underground Residential Distribution Renewal | FCIs | Units | - | -
Reactive and Corrective Capital |  | Transformers | Units | 2834 | 1867
Reactive and Corrective Capital |  | Pole | Units | 1209 | 1105
Reactive and Corrective Capital |  | Switches | Units | 124 | 220
Reactive and Corrective Capital |  | Switchgear | Units | 137 | 101
Non-Wires Alternatives | Energy Storage (ESS) | Battery Energy Storage System | Units | 4 | 0
Network Condition and Monitoring | NCMC | Commissioned Vaults | Units | 705 | 705
System Enhancements | Contingency Enhancement | SCADA Switches | Units | 40 | 32
System Enhancements | Contingency Enhancement | Reclosers | Units | 26 | 26
System Enhancements | Contingency Enhancement | Undersized circuit replaced | km | 27.1 | 26.9
System Enhancements | Downtown Contingency | # of Station Ties | Units | 1 | 1
System Enhancements | Customer-Owned Substation Protection | Switch Units | Units | 23 | 47
IT-OT Systems | Core Backend Infrastructure Assets (Capacity) | Unix Virtual Servers | Units | 560 | 560
IT-OT Systems | Core Backend Infrastructure Assets (Capacity) | Linux x86 Virtual Servers | Units | 350 | 349
IT-OT Systems | Core Backend Infrastructure Assets (Capacity) | Windows Virtual Servers | Units | 2660 | 2656
IT-OT Systems | Endpoint Assets | Personal Computing Devices | Units | 2640 | 2308
IT-OT Systems | Endpoint Assets | Printers & Plotters | Units | 190 | 180
IT-OT Systems | IT Hardware - Cybersecurity Systems and Controls | OEB CSF Controls & Compliance | Units | - | 545
IT-OT Systems | IT Hardware - Cybersecurity Systems and Controls | Asset Security: Systems/Applications | Units | - | 1600
IT-OT Systems | IT Hardware - Cybersecurity Systems and Controls | Asset Security: Endpoints | Units | - | 30265
IT-OT Systems | Communication Infrastructure | SONET Migration and Decommissioning | Units | 45 | 31
IT-OT Systems | Communication Infrastructure | Fibre-Optic Cable | Units | 10 | 15
IT-OT Systems | Communication Infrastructure | SCADA High-Site Capacity Upgrade | Units | 12 | 12
IT-OT Systems | Communication Infrastructure | Wireless SCADA Endpoint Radio Migration | Units | 885 | 1103
IT-OT Systems | Communication Infrastructure | Radio Installation | Units | 46 | 0
IT-OT Systems | Communication Infrastructure | Underground Radio Sites | Units | 42 | 0
Fleet and Equipment |  | LD - Pickup Trucks | Units | 73 | 44
Fleet and Equipment |  | HD - Cubevan (2020 sprinter & 2020 Command unit) | Units | 18 | 9
Fleet and Equipment |  | HD - Linetruck (welder 2020) | Units | 3 | 6
Fleet and Equipment |  | HD - Large Digger Derrick | Units | 4 | 6
Fleet and Equipment |  | HD - Single Bucket | Units | 32 | 13
Fleet and Equipment |  | LD - SUV's | Units | 25 | 26
Fleet and Equipment |  | HD - Double Bucket | Units | 23 | 34
Fleet and Equipment |  | HD - Van with Aerial | Units | 6 | 3
Fleet and Equipment |  | HD - Cable Truck | Units | 2 | 0
Fleet and Equipment |  | HD - Small Crane truck | Units | 4 | 0
Fleet and Equipment |  | HD - Large Crane truck | Units | 1 | 0
Fleet and Equipment |  | HD - Small Digger Derrick | Units | 4 | 0
Fleet and Equipment |  | HD - Dump Truck | Units | 6 | 0
Fleet and Equipment |  | LD - Passenger Minivan | Units | 3 | 0
Fleet and Equipment |  | LD - Cargo Minivans | Units | 20 | 29
Fleet and Equipment |  | LD - Fullsize Van | Units | 38 | 24
Fleet and Equipment |  | LD - Cars | Units | 0 | 5
Fleet and Equipment |  | HD - Pick-up | Units | 0 | 1
Fleet and Equipment |  | EV - Cargo Van | Units | 0 | 1
Fleet and Equipment |  | EV - Double Bucket | Units | 0 | 1
Fleet and Equipment |  | EQ - Forklift | Units | 0 | 11
Fleet and Equipment |  | EQ - Stringing Trailer | Units | 0 | 2
Fleet and Equipment |  | EQ - ePTO units | Units | 0 | 5
Fleet and Equipment |  | EV - Pick-up Truck | Units | 0 | 7
Fleet and Equipment |  | EQ - Cable Reels | Units | 0 | 2
Fleet and Equipment |  | EQ - Float Trailer | Units | 0 | 1