## Appendix 2-AB
[18 empty] | File Number: |  | EB-2023-0195
[18 empty] | Exhibit: |  | Settlement Proposal
Tab:
[18 empty] | Schedule: |  | 10.2
[18 empty] | Page: |  | 1
[18 empty] | Date: |  | 2024-08-16
Capital Expenditures = In Service Additions |  | No
Appendix 2-AB
Table 2 - Capital Expenditure Summary from Chapter 5 Consolidated Distribution System Plan Filing Requirements
First year of Forecast Period:
2025
CATEGORY | Historical Period (previous plan1 & actual) | [14 empty] | Forecast Period (planned)
| 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 | 2026 | 2027 | 2028 | 2029
| OEB approved | Actual | Var | OEB approved | Actual | Var | OEB approved | Actual | Var | OEB approved | Actual | Var | OEB approved | Bridge | Var
| $M |  | % | $M |  | % | $ '000 |  | % | $M |  | % | $M |  | % | $M
System Access | 164931646.703 | 225222919.689 | 36.56% | 192958839.8289 | 240677101.7301 | 24.73% | 184703184.989 | 244289280.5937 | 32.26% | 197434824.29 | 278158875.1016 | 40.89% | 211147327.9924 | 306170469.3893 | 45% | 382214138.5824 | 377734778.8177 | 362571535.6767 | 342932509.8487 | 337547726.2197
System Renewal | 290470091.8958 | 261657814.1654 | -9.919% | 307188155.2274 | 247314177.948 | -19.49% | 304729281.4981 | 276629517.8221 | -9.221% | 319440881.3915 | 305410081.7525 | -4.392% | 309474149.7831 | 367021436.8342 | 18.6% | 312478929.4464 | 318456135.7682 | 339964593.4478 | 368105897.6214 | 372794443.7162
System Service | 34613033.7955 | 33446693.2621 | -3.37% | 60090728.7388 | 68043939.1777 | 13.24% | 71271494.4824 | 67066126.244 | -5.9% | 33586716.8262 | 27658633.4664 | -17.65% | 38524677.4384 | 29847175.7458 | -22.52% | 33860002.8193 | 30593859.9473 | 59165183.5937 | 71772373.3367 | 76704966.8911
General Plant | 78773778.0131 | 56084960.4418 | -28.8% | 92819412.918 | 72420972.03 | -21.98% | 88121647.7176 | 112900815.13 | 28.12% | 76795210.1593 | 93482728.04 | 21.73% | 84441088.4364 | 84369189.55 | -0.08515% | 92559906.9239 | 107386899.1655 | 113284782.5272 | 104358577.2871 | 87895406.6568
Other | 5277467.9177 | 17496676.7517 | 231.5% | 6544047.8715 | 4837075.6218 | -26.08% | 8912261.8095 | 12791738.7457 | 43.53% | 6266297.5076 | 43211010.1075 | 589.6% | 5723501.4625 | 7900080.3261 | 38.03% | 5314495.3268 | 5952547.7097 | 6792274.7862 | 7484625.4698 | 8297536.9187
TOTAL EXPENDITURE | 574066018.325 | 593909064.31 | 3.457% | 659601184.5847 | 633293266.5076 | -3.988% | 657737870.4966 | 713677478.5355 | 8.505% | 633523930.1746 | 747921328.4681 | 18.06% | 649310745.1128 | 795308351.8454 | 22.49% | 826427473.0987 | 840124221.4084 | 881778370.0315 | 894653983.5637 | 883240080.4026
Capital Contributions | -74846844.5654 | -145770420.46 | 94.76% | -102653618.4852 | -100106422.8121 | -2.481% | -93911558.4669 | -115826061.4955 | 23.34% | -94468028.5711 | -141838843.2681 | 50.14% | -97630132.8623 | -147501521.1964 | 51.08% | -164003394.0748 | -150732772.0574 | -140734970.3455 | -147200624.0931 | -154894660.3524
NET CAPITAL EXPENDITURES | 499219173.7596 | 448138643.85 | -10.23% | 556947566.0995 | 533186843.6955 | -4.266% | 563826312.0297 | 597851417.04 | 6.035% | 539055901.6034 | 606082485.2 | 12.43% | 551680612.2505 | 647806830.6489 | 17.42% | 662424079.024 | 689391449.3511 | 741043399.686 | 747453359.4706 | 728345420.0503
System O&M | 126329488.0592 | 117104150.94 | -7.303% |  | 117495650.42 | -- |  | 124054430.49 | -- |  | 119400000 | -- |  | 133500000 | -- | 135897487.9
Notes to the Table:
1. Historical “previous plan” data is not required unless a plan has previously been filed. However, use the last OEB-approved, at least on a Total (Capital) Expenditure basis for the last cost of service rebasing year, and the applicant should include their planned budget in each subsequent historical year up to and including the Bridge Year.
2. Indicate the number of months of 'actual' data included in the last year of the Historical Period (normally a 'bridge' year):
3. System O&M contains the following accounts: 5005, 5010, 5012, 5014, 5015, 5016, 5017, 5020, 5025, 5030, 5035, 5040, 5045, 5050, 5055, 5060, 5065, 5070, 5075, 5085, 5090, 5095, 5096, 5105, 5110, 5112, 5114, 5120, 5125, 5130, 5135, 5145, 5150, 5155, 5160, 5165, 5170, 5172, 5175, 5178, 5195
Explanatory Notes on Variances (complete only if applicable)
Notes on shifts in forecast vs. historical budgets by category
Refer to respective category sections for discussion on historical vs forecast shifts. Section E5 for System Access, Section E6 for System Renewal, Section E7 for System Service and Section E8 for General Plant.
Notes on year over year Plan vs. Actual variances for Total Expenditures
Refer to Section E4 on Variance analysis between Plan vs Actuals.
Notes on Plan vs. Actual variance trends for individual expenditure categories
Refer to Section E4 on Variance analysis between Plan vs Actuals. Note that System OEB Approved 2020 O&M figure of $126.3M is based on the updated filing requirements for System O&M specified in Note 3. The OEB Approved 2020 System O&M figure documented in the 2020 - 2024 CIR DRO of $129.4M used a methodology that is not comparable to the actuals presented in the 2-AB table above