## Sheet1
ATTACHMENT 1: Overhead and AFUDC Cost Estimate Calculation – SCTL Project
|  | Total | 2021 | [9 empty] | 2022 | [12 empty] | 2023 | [12 empty] | 2024 | [12 empty] | 2025 | [12 empty] | 2026 | [12 empty] | 2027 | [12 empty] | 2028
|  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Table 1 - Line Cost
| Direct Capital Expenditure (Direct + Contingency) | 286244454.8324 | 5114 | 31420 | 55227.56 | 156697.77 | 54858.61 | 60468.82 | 126955.66 | 263211.36 | 165073.74 |  | 332918.67 | 274389.72 | 291701.79 | 235659.76 | 320128.11 | 678794.47 | 361598.74 | 483213.54 | 1126327.6 | 529659.83 | 411656.56 | 361411.92 |  | 405430.27 | 432157.51 | 526155.26 | 467298.68 | 1541933.8 | 453634.13 | 581075.49 | 1393023.77 | 666223.15 | 687503.51 | 1672013.73 | 831364.71 |  | 9045708.0786 | 9596902.0786 | 1583353.0786 | 1652574.7486 | 2583335.0786 | 1640492.0786 | 1638435.0786 | 1225353.0786 | 1925353.0786 | 1225353.0786 | 1225353.0786 | 11998641.0786 |  | 4733470.501 | 4587470.501 | 4662170.501 | 4587470.501 | 5087470.501 | 4668420.501 | 4587470.501 | 5177060.501 | 5421637.171 | 4587470.501 | 6845655.501 | 16312034.501 |  | 6743929.4232 | 769098.4232 | 917098.4232 | 3573240.4232 | 21250932.4232 | 1691499.4232 | 15180342.4232 | 23583678.4232 | 3055827.4232 | 1126127.4232 | 1294581.4232 | 14795708.4232 |  | 806594.4232 | 665124.0232 | 1718124.0232 | 670124.0232 | 2697302.0232 | 719374.0232 | 9814850.0232 | 665124.0232 | 9188508.6932 | 7009654.0232 | 2970234.0232 | 11469950.0232 |  | 468593.8704 | 402593.8704 | 420593.8704 | 356515.1667 | 356515.1667 | 356515.1667 | 374515.1667 | 356515.1667 | 356515.1667 | 356515.1667 | 356515.1667 | 7122566.9267
| AFUDC (Cost) | 41802550.457 | 8.82 | 71.83 | 221.26 | 444.55 | 900.69 | 1087.73 | 1414.49 | 2012.27 | 2772.56 |  | 3681.44 | 4508.38 | 5359.07 | 6135.86 | 6922.37 | 7880.64 | 9468.25 | 10850.6 | 13457.45 | 15903.23 | 19759.66 | 21420.16 |  | 22943.05 | 25662.14 | 27462.85 | 29032.94 | 33007.64 | 37965.6 | 39576.46 | 42631.01 | 47147.99 | 49717.14 | 53767.87 | 59945.67 |  | 65319.1262 | 99345.3836 | 135555.0337 | 141965.4833 | 148657.9606 | 158851.4733 | 165560.655 | 172286.7219 | 177494.4964 | 185335.9454 | 190591.505 | 195866.31 |  | 248650.7729 | 267799.9032 | 286459.5512 | 305476.9774 | 324278.7394 | 345075.0871 | 364337.6508 | 383361.4292 | 404725.3134 | 427110.7483 | 446371.3003 | 474392.4947 |  | 545753.0544 | 574111.7709 | 579301.0244 | 585086.7028 | 601242.738 | 686332.2965 | 695543.8351 | 757342.7285 | 852116.8395 | 867276.991 | 874976.9884 | 883362.6889 |  | 944780.0355 | 951522.739 | 957741.7894 | 968074.0636 | 974375.778 | 980828.1285 | 987369.8474 | 1029260.003 | 1035776.1029 | 1075418.752 | 1106751.024 | 1122515.4206 |  | 1170587.0508 | 1176875.8416 | 1182932.4951 | 1189082.1369 | 1195006.5666 | 1200953.62 | 1206923.3835 | 1212985.8035 | 1219001.5144 | 1225040.1975 | 1231101.9406 | 1237186.8318
| Overhead (Cost) | 6444444 | 460.26 | 2827.8 | 4970.48 | 12535.82 | 4388.69 | 4837.51 | 12695.57 | 26321.14 | 20320.35 |  | 39950.24 | 31844.43 | 35004.21 | 23565.98 | 32012.81 | 67879.45 | 36159.87 | 48321.35 | 112632.76 | 52965.98 | 41165.66 | 56386.95 |  | 28380.12 | 30251.03 | 36830.87 | 32710.91 | 107935.37 | 31754.39 | 46486.04 | 111441.9 | 19986.69 | 20625.11 | 50160.41 | 66190.8 |  | 180914.1616 | 191938.0416 | 31667.0616 | 33051.495 | 51666.7016 | 32809.8416 | 32768.7016 | 24507.0616 | 38507.0616 | 24507.0616 | 24507.0616 | 239972.8216 |  | 94669.41 | 91749.41 | 93243.41 | 91749.41 | 101749.41 | 93368.41 | 91749.41 | 103541.21 | 108432.7434 | 91749.41 | 136913.11 | 326240.69 |  | 134878.5885 | 15381.9685 | 18341.9685 | 71464.8085 | 425018.6485 | 33829.9885 | 303606.8485 | 471673.5685 | 61116.5485 | 22522.5485 | 25891.6285 | 295914.1685 |  | 13177.9183 | 10866.6138 | 28070.2388 | 10948.3024 | 44067.7802 | 11752.9354 | 160352.3262 | 10866.6138 | 150119.3334 | 114521.8038 | 48526.8683 | 187392.8958 |  | 7655.7581 | 6577.4682 | 6871.5472 | 5824.647 | 5824.647 | 5824.647 | 6118.726 | 5824.647 | 5824.647 | 5824.647 | 5824.647 | 124169.0043
| Cumulative Capital Expenditure |  | 5583.08 | 39902.71 | 100322.01 | 270000.15 | 330148.14 | 396542.2 | 537607.92 | 829152.69 | 1017319.34 |  | 1393869.69 | 1704612.22 | 2036677.29 | 2302038.89 | 2661102.18 | 3415656.74 | 3822883.6 | 4365269.09 | 5617686.9 | 6216215.94 | 6688797.82 | 7128016.85 |  | 7584770.29 | 8072840.97 | 8663289.95 | 9192332.48 | 10875209.29 | 11398563.41 | 12065701.4 | 13612798.08 | 14346155.91 | 15104001.67 | 16879943.68 | 17837444.86 | 0 | 27129386.2264 | 37017571.7301 | 38768146.904 | 40595738.6308 | 43379398.3716 | 45211551.7651 | 47048316.2003 | 48470463.0624 | 50611817.699 | 52047013.7846 | 53487465.4297 | 65921945.6399 | 0 | 70998736.3238 | 75945756.138 | 80987629.6003 | 85972326.4887 | 91485825.1391 | 96592689.1372 | 101636246.699 | 107300209.8393 | 113235005.0671 | 118341335.7264 | 125770275.6378 | 142882943.3235 | 0 | 150307504.3895 | 151666096.552 | 153180837.9681 | 157410629.9025 | 179687823.7122 | 182099485.4204 | 198278978.5271 | 223091673.2473 | 227060734.0584 | 229076661.021 | 231272111.0611 | 247247096.3416 | 0 | 249011648.7186 | 250639162.0946 | 253343098.1459 | 254992244.535 | 258707990.1164 | 260419945.2035 | 271382517.4002 | 273087768.0402 | 283462172.1696 | 291661766.7486 | 295787278.6641 | 308567137.0036 | 0 | 310213973.6828 | 311800020.863 | 313410418.7757 | 314961840.7262 | 316519187.1064 | 318082480.54 | 319670037.8161 | 321245363.4332 | 322826704.7612 | 324414084.7723 | 326007526.5266 | 334491449.2894
* Note - ECI-EPC overhead rate implemented in September 2023
Table 2 - Station Cost
| Direct Capital Expenditure (Direct + Contingency) | 116217449.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272222 | 14030.5 | 27714.56 | 0 | 211.69 | 10592 | 675.5 | 0 | 21622.15 | 8457.5 | 55103.1 | 0 | 12292.11 | -173 | 12369.95 | 39635.75 | 72734.41 | 105369.08 | 201687.49 | 117148.49 | 57494.8 | 134559.42 | 168155.07 | 180945.82 | 0 | 147636.7 | 147636.7 | 254408.7769 | 254408.7769 | 4200116.4404 | 997278.4187 | 4169330.4187 | 997278.4187 | 3899236.4187 | 997278.4187 | 6121515.4188 | 5548604.0854 | 0 | 5631938.5301 | 908028.5301 | 13650085.2994 | 906381.7777 | 3649011.7777 | 906381.7777 | 2019181.7777 | 906381.7777 | 1800580.7777 | 7470181.7777 | 2167014.7777 | 6198706.4444 |  | 3253827.2842 | 1732560.2842 | 4675962.2842 | 1732560.2842 | 1732560.2842 | 1732560.2842 | 3769219.3956 | 503044.163 | 6507940.163 | 503044.163 | 1244043.163 | 6010021.7994 | 0 | 163512.1359 | 163512.1359 | 163512.1359 | 163512.1359 | 73053.3667 | 73053.3667 | 73053.3667 | 73053.3667 | 73053.3667 | 73053.3667 | 73053.3667 | 73053.3667 | 0 | 62636.7 | 1399771.2 | 1399771.2 | 1399771.2 | 1409771.2 | 72636.7 | 62636.7 | 62636.7 | 62636.7 | 62636.7 | 62636.7 | 62636.7
| AFUDC (Cost) | 13866677.2211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864.67 | 466.69 | 543.31 | 588.54 | 588.54 | 1050.76 | 1069.14 | 1070.25 | 1105.53 | 1288.95 | 1315.48 | 0 | 1452.55 | 1596.2 | 1632.99 | 1727.62 | 1899.05 | 2304.43 | 2886.3 | 3483.49 | 3870.54 | 4232.51 | 4817.53 | 5526.88 | 0 | 6200.1557 | 6795.9304 | 7393.8868 | 8408.4821 | 9426.7927 | 24230.9218 | 28190.7142 | 44477.7237 | 48511.6581 | 63824.6774 | 67929.4586 | 91939.6381 | 0 | 108724.6607 | 131263.9428 | 135001.0538 | 198205.3656 | 202576.881 | 217930.4975 | 222376.414 | 231288.3088 | 235784.6096 | 243873.0659 | 274660.2896 | 284360.4612 | 0 | 314138.5728 | 328636.6875 | 336972.8333 | 357370.3631 | 365816.2595 | 374294.4157 | 374297.2762 | 207243.3552 | 210117.823 | 237544.9935 | 240535.2009 | 246565.2572 |  | 280581.9239 | 282322.6319 | 284069.9916 | 285824.0282 | 287584.7674 | 288982.3776 | 290385.3283 | 291793.64 | 293207.3332 | 294626.4283 | 296050.9461 | 297480.9072 |  | 298721.6905 | 300120.7485 | 307039.7676 | 313985.2084 | 320957.1718 | 327997.0012 | 329549.0952 | 331065.8741 | 332588.4452 | 334116.8305 | 335651.0523 | 328683.454
| Overhead (Cost) | 7297665.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 28254.38 | 1683.66 | 2771.46 | 0 | 21.17 | 1059.2 | 67.55 | 0 | 2162.22 | 845.75 | 5610.32 | 0 | 860.45 | -12.11 | 865.9 | 2774.5 | 5091.41 | 7375.85 | 16135.01 | 9371.85 | 2742.96 | 10681.58 | 11922.36 | 23632.22 | 0 | 8858.202 | 8858.202 | 15264.5266 | 15264.5266 | 233189.952 | 59836.7051 | 250159.8251 | 59836.7051 | 233954.1851 | 59836.7051 | 367290.9251 | 332916.2451 | 0 | 319099.2774 | 35664.6774 | 800188.0836 | 54382.9067 | 218940.7067 | 54382.9067 | 121150.9067 | 54382.9067 | 108034.8467 | 448210.9067 | 130020.8867 | 371922.3867 | 0 | 227767.9099 | 121279.2199 | 327317.3599 | 121279.2199 | 121279.2199 | 121279.2199 | 245174.9889 | 16542.7226 | 436885.4426 | 16542.7226 | 68412.6526 | 402031.1571 |  | 11445.8495 | 11445.8495 | 11445.8495 | 11445.8495 | 5113.7357 | 5113.7357 | 5113.7357 | 5113.7357 | 5113.7357 | 5113.7357 | 5113.7357 | 5113.7357 |  | 5010.936 | 111981.696 | 111981.696 | 111981.696 | 112781.696 | 5810.936 | 5010.936 | 5010.936 | 5010.936 | 5010.936 | 5010.936 | 5010.936
| Cumulative Capital Expenditure |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 302341.05 | 318521.9 | 349551.23 | 350139.77 | 350961.17 | 363663.13 | 365475.32 | 366545.57 | 391435.47 | 402027.67 | 464056.57 |  | 478661.68 | 480072.77 | 494941.61 | 539079.48 | 618804.35 | 733853.71 | 954562.51 | 1084566.34 | 1148674.64 | 1298148.15 | 1483043.11 | 1693148.03 | 0 | 1855843.0877 | 2019133.9201 | 2296201.1104 | 2574282.896 | 7017016.0811 | 8098362.1268 | 12546043.0848 | 13647635.9324 | 17829338.1944 | 18950277.9957 | 25507013.7981 | 31480473.7668 | 0 | 37540236.2351 | 38615193.3854 | 53200467.8222 | 54359437.8722 | 58429967.2376 | 59608662.4195 | 61971371.5179 | 63163424.5111 | 65307824.7451 | 73470090.4954 | 76041786.4494 | 82896775.7417 | 0 | 86692509.5086 | 88874985.7002 | 94215238.1776 | 96426448.0448 | 98646103.8085 | 100874237.7283 | 105262929.3889 | 105989759.6297 | 113144703.0583 | 113901834.9373 | 115454825.9537 | 122113444.1675 | 0 | 122568984.0767 | 123026264.6941 | 123485292.6711 | 123946074.6847 | 124311826.5544 | 124678976.0344 | 125047528.465 | 125417489.2074 | 125788863.6429 | 126161657.1736 | 126535875.222 | 126911523.2316 | 0 | 127277892.5581 | 129089766.2026 | 130908558.8661 | 132734296.9705 | 134577807.0383 | 134984251.6755 | 135381448.4067 | 135780161.9168 | 136180397.998 | 136582162.4645 | 136985461.1527 | 137381792.2428
* Note - AFUDC calculation includes the in-service of the Wallaceburg station assets in 2026