## Scenario A
Scenario Details
Project Alternative: Scenario A - Full Replacement
The scenaio cost analysis covers up to 61 years asset life starting from In-Service date: 2026
Costs are based on 2024 dollars
NPV as of: | 2024
Scenario Details
This scenario involves the replacement of the SLP pipeline with: - Approximately 10.0 km of Nominal Pipe Size (NPS) 12 Extra High Pressure (XHP) Steel Coated (ST) natural gas pipeline; - Approximately 2.5 km of NPS 16 XHP ST natural gas pipeline; - Approximately 0.3 km of NPS 6 XHP ST natural gas pipeline; - Approximately 0.9 km of NPS 6 Intermediate Pressure (IP) Polyethylene (PE) natural gas pipeline; and - Approximately 3.9 km of NPS 4 IP PE natural gas pipeline.
- Discount rate is based on 2024 Enbridge WACC
- Cost escalation of 4% based on estimated provided by construction contractor
Cost/Benefit Category | Cost/Benefit Type | Scenario Tasks | Assumptions | Type | Activity | Year | Quantity | Unit Cost (2024 $) | Cost (2024 $) | Discount Rate (%) | Cost Escalation (%) | Cost in year spent ($)
Cost | Upfront | Full Replacement of the SLP | Class 3 estimate prepared by Capital Development | Capital | Replacement Work | 2024 | 1 | 2515000 | -2515000 | 5.75% | 4% | -2515000
Cost | Upfront |  |  | Capital | Replacement Work | 2025 | 1 | 68699826.1538 | -68699826.1538 | 5.75% | 4% | -71447819.2
Cost | Upfront |  |  | Capital | Replacement Work | 2026 | 1 | 67110044.1712 | -67110044.1712 | 5.75% | 4% | -72586223.7756
Cost | Upfront |  |  | Capital | Replacement Work | 2027 | 1 | 12996943 | -12996943 | 5.75% | 4% | -14619793.2908
Cost | Upfront | Interest During Construction | Based on estimates prepared by Capital Development | Capital | IDC | 2024 | N/A | 483724.5768 | -483724.5768 | N/A | N/A | -483724.5768
Cost | Upfront |  |  | Capital | IDC | 2025 | N/A | 1814188.0223 | -1814188.0223 | N/A | N/A | -1886755.5432
Cost | Upfront |  |  | Capital | IDC | 2026 | N/A | 1352294.9303 | -1352294.9303 | N/A | N/A | -1462642.1966

## Scenario B
Scenario Details
Project Alternative: Scenario B - Extensive Inspection and Repair
The scenaio cost analysis covers up to 61 years asset life starting from In-Service date: 2026
Costs are based on 2024 dollars
NPV as of: | 2024
Scenario Details
- Expand Crawler Inspection and Integrity Dig activities to mitigate current corrosion risks on the St. Laurent pipeline (where required) - This includes 13 additional ILI runs through 12 additional launch points - 4.6km needs short-term inspection, 7.8km will be inspected indefinitely.
Add additional TPD barriers to mitigate TPD risk including: - Adding SLP to Vital Mains program providing on-site supervision during third-party excavtion activities - Increasing response time notifications to same day - Locating pipeline using mechanical methods - Installation of High Visibility Slabbing, where feasible
- 1.9KM targeted replacements to address imeedate Third-Party damage risks
- Accelerated ROW Patrol required until slabbing and replacements completed
- Discount rate is based on 2024 Enbridge WACC
- General inflation rate of 3% applied broadly for most cost categories. Integrity Dig costs increased at an escalation rate of 6% based on cost trending over the previous 10 years
Cost/Benefit Category | Cost/Benefit Type | Scenario Tasks | Assumptions | Type | Activity | Year | Quantity | Unit Cost (2024 $) | Cost (2024 $) | Discount Rate (%) | Cost Escalation (%) | Cost in year spent ($)
Cost | Upfront | Inspect and mitigate remaining critical features identified from the inspected sections of the pipeline (40% of pipeline) | Integrity has identified the need for 19 additional digs based on the proposed EDIMP dig criteria and probability of sizing of the inspection tool. Based on the 2 year timeframe for Phase 2 digs in the proposed Dig Criteria, these dig would be required to be completed by 2025. Dig costs is determined based the weighted average of the 19 known dig sites and their specified accessibility through Engineering Construction review. | Capital | Integrity Digs + Mitigation | 2025 | 19 | 657894.7368 | -12500000 | 5.75% | 6% | -13250000
Cost | Upfront | Replacement @ NPS16 LRT crossing with identified corrosion issue | Estimate based on a cut out and replacements of the above grade NPS16 pipe with Corrosion that requires repair. Based on the Engineer Assessment of corrosion on this segment, mitigation must occur by 2027. Estimate provided by Capital Development (CD). | Capital | Replacement | 2026 | 1 | 2741043 | -2741043 | 5.75% | 3% | -2907972.5187
Cost | Upfront | Inspect the uninspected portion of the pipeline with crawler inspection tool (only where required - 4.56km) | Integrity has created an inspection plan for remaining segments of SLP that will require inspection. CD has assessed the feasibility and costs of launch points in the plan. | O&M | Launch Site Retrofits | 2025 | 12 | 200000 | -2400000 | 5.75% | 3% | -2472000
Cost | Upfront |  |  | Capital | Launch Site Retrofits | 2025 | 12 | 40000 | -480000 | 5.75% | 3% | -494400
Cost | Upfront |  |  | O&M | Crawler Tool Inspection | 2025 | 13 | 81500 | -1059500 | 5.75% | 3% | -1091285
Cost | Upfront | ROW Patrol for pipeline and pubic awareness campaign as temporary TPD mitigation measures | Assume daily patrol to reduce TPD risks (as per CFER TPD Fault tree model). Cost is based on 2023 actual costs related to daily patrols and additional targeted public awareness campaign. | O&M | Row Patrol + Public Awareness | 2025 | 1 | 140000 | -140000 | 5.75% | 3% | -144200
Cost | Upfront | ROW Patrol for pipeline and pubic awareness campaign as temporary TPD mitigation measures | Assume daily patrol to reduce TPD risks (as per CFER TPD Fault tree model). Cost is based on 2023 actual costs related to daily patrols and additional targeted public awareness campaign. | O&M | Row Patrol + Public Awareness | 2026 | 1 | 140000 | -140000 | 5.75% | 3% | -148526
Cost | Upfront | Implement additional TPD barriers to reduce the TPD threat. Install protective slabbing with high visibility marker tape on portions of the pipeline that are deemed feasible. | Based on slabbing feasibility assessment and updated costs estimates provided by CD in Feb 2024 | Capital | Install High Visibility Slabs | 2025 | 4.937 | 2329349.8 | -11499999.9626 | 5.75% | 3% | -11844999.9615
Cost | Upfront | Inspect and mitigate critical features identified from the uninspected portion of the pipeline | Assumed that the uninspected portion of the pipelines will require similar post-inspection mitigation as the inspected portion. Inspected and uninspected sections have same proportions, hence, 1:1 multiplier used for uninspected sections. | Capital | Integrity Digs + Mitigation | 2026 | 24 | 680420.045 | -16330081.0811 | 5.75% | 6% | -18348479.1027
Cost | Upfront | Additional Replacements required to meet risk criteria | 2 segments have been identified for replacement to meet Risk targets. These segments were strategically selected to also remove any uninspected segments of vintage pipe.(1828m) | Capital | Replacement | 2025 | 1 | 41500000 | -41500000 | 5.75% | 3% | -42745000
Cost | Upfront | Uncertainty where continued inspections can result in stuck ILI tools | Assume 1 in 500 chance of the tool getting stuck and requiring a cut-out to retrieve. | O&M | Stuck Crawler Tool Retrieval | 2025 | 13 | 10000 | -130000 | 5.75% | 3% | -133900
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2029 | 19 | 10000 | -190000 | 5.75% | 3% | -220262.0741
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2036 | 19 | 10000 | -190000 | 5.75% | 3% | -270894.5685
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2043 | 19 | 10000 | -190000 | 5.75% | 3% | -333166.1501
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2050 | 19 | 10000 | -190000 | 5.75% | 3% | -409752.3408
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2057 | 19 | 10000 | -190000 | 5.75% | 3% | -503943.6953
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2064 | 19 | 10000 | -190000 | 5.75% | 3% | -619787.1805
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2071 | 19 | 10000 | -190000 | 5.75% | 3% | -762260.0554
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2078 | 19 | 10000 | -190000 | 5.75% | 3% | -937483.7208
Cost | On-going |  |  | O&M | Stuck Crawler Tool Retrieval | 2085 | 19 | 10000 | -190000 | 5.75% | 3% | -1152986.7275
Cost | On-going | Continued inspection of the St. Laurent pipeline system to maintain a risk/reliability that meets our thresholds | Assume a 7-year re-inspection interval (consistent with company standards) with additional construction costs to excavate and prepare launch locations. | O&M | Crawler Tool Inspection | 2029 | 19 | 81500 | -1548500 | 5.75% | 3% | -1795135.9041
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2036 | 19 | 81500 | -1548500 | 5.75% | 3% | -2207790.7333
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2043 | 19 | 81500 | -1548500 | 5.75% | 3% | -2715304.1232
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2050 | 19 | 81500 | -1548500 | 5.75% | 3% | -3339481.5778
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2057 | 19 | 81500 | -1548500 | 5.75% | 3% | -4107141.1166
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2064 | 19 | 81500 | -1548500 | 5.75% | 3% | -5051265.5209
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2071 | 19 | 81500 | -1548500 | 5.75% | 3% | -6212419.4515
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2078 | 19 | 81500 | -1548500 | 5.75% | 3% | -7640492.3244
Cost | On-going |  |  | O&M | Crawler Tool Inspection | 2085 | 19 | 81500 | -1548500 | 5.75% | 3% | -9396841.8288
Cost | On-going |  |  | O&M | Launch Site Preparation | 2029 | 16 | 200000 | -3200000 | 5.75% | 3% | -3709677.0378
Cost | On-going |  |  | O&M | Launch Site Preparation | 2036 | 16 | 200000 | -3200000 | 5.75% | 3% | -4562434.8379
Cost | On-going |  |  | O&M | Launch Site Preparation | 2043 | 16 | 200000 | -3200000 | 5.75% | 3% | -5611219.3698
Cost | On-going |  |  | O&M | Launch Site Preparation | 2050 | 16 | 200000 | -3200000 | 5.75% | 3% | -6901092.0561
Cost | On-going |  |  | O&M | Launch Site Preparation | 2057 | 16 | 200000 | -3200000 | 5.75% | 3% | -8487472.7627
Cost | On-going |  |  | O&M | Launch Site Preparation | 2064 | 16 | 200000 | -3200000 | 5.75% | 3% | -10438520.9344
Cost | On-going |  |  | O&M | Launch Site Preparation | 2071 | 16 | 200000 | -3200000 | 5.75% | 3% | -12838064.0909
Cost | On-going |  |  | O&M | Launch Site Preparation | 2078 | 16 | 200000 | -3200000 | 5.75% | 3% | -15789199.5081
Cost | On-going |  |  | O&M | Launch Site Preparation | 2085 | 16 | 200000 | -3200000 | 5.75% | 3% | -19418723.8309
Cost | On-going | Inspect and mitigate identified critical features identified from the ILI tool inspections | Digs in second inspection campaign estimated based on growth of ILI data. Digs in 3rd and later ILI campaign estimated based on TIMP ILI campaign trending. | Capital | Integrity Digs + Mitigation | 2030 | 17 | 683420.045 | -11618140.7658 | 5.75% | 6% | -16480554.7251
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2037 | 19 | 683420.045 | -12984980.8559 | 5.75% | 6% | -27696032.6249
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2044 | 21 | 683420.045 | -14351820.9459 | 5.75% | 6% | -46028234.0466
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2051 | 23 | 683420.045 | -15718661.036 | 5.75% | 6% | -75800821.2404
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2058 | 25 | 683420.045 | -17085501.1261 | 5.75% | 6% | -123887400.5147
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2065 | 28 | 683420.045 | -19135761.2613 | 5.75% | 6% | -208634545.4162
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2072 | 31 | 683421.045 | -21186052.3964 | 5.75% | 6% | -347321425.4358
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2079 | 34 | 683422.045 | -23236349.5315 | 5.75% | 6% | -572783488.6259
Cost | On-going |  |  | Capital | Integrity Digs + Mitigation | 2086 | 37 | 683422.045 | -25286615.6667 | 5.75% | 6% | -937247636.9969
Cost | Upfront | Interest During Construction | Assume 8 months of construction per year (construction period) and all work will be completed in the given year. 5.48% interest rate on debt. | Capital | IDC | 2025 | N/A | 1205234.666 | -1205234.666 | N/A | N/A | -1248241.706
Cost | Upfront |  |  | Capital | IDC | 2026 | N/A | 348365.8665 | -348365.8665 | N/A | N/A | -388284.5163
Cost | On-going |  |  | Capital | IDC | 2030 | N/A | 212224.7047 | -212224.7047 | N/A | N/A | -301044.7996
Cost | On-going |  |  | Capital | IDC | 2037 | N/A | 237192.317 | -237192.317 | N/A | N/A | -505914.1959
Cost | On-going |  |  | Capital | IDC | 2044 | N/A | 262159.9293 | -262159.9293 | N/A | N/A | -840782.4086
Cost | On-going |  |  | Capital | IDC | 2051 | N/A | 287127.5416 | -287127.5416 | N/A | N/A | -1384628.3347
Cost | On-going |  |  | Capital | IDC | 2058 | N/A | 312095.1539 | -312095.1539 | N/A | N/A | -2263009.8494
Cost | On-going |  |  | Capital | IDC | 2065 | N/A | 349546.5724 | -349546.5724 | N/A | N/A | -3811057.6963
Cost | On-going |  |  | Capital | IDC | 2072 | N/A | 386998.5571 | -386998.5571 | N/A | N/A | -6344404.7046
Cost | On-going |  |  | Capital | IDC | 2079 | N/A | 424450.6514 | -424450.6514 | N/A | N/A | -10462845.0589
Cost | On-going |  |  | Capital | IDC | 2086 | N/A | 461902.1795 | -461902.1795 | N/A | N/A | -17120390.1691

## Scenario B.2 (hidden)
Scenario Details |  | NOT UPDATED
Project Alternative: Scenario B.2 - Full Replacement
The analysis covers 40 year asset life starting from In-Service date: 2026
Scenario Details
- Replace / Relocation of St. Laurent, Tremblay Lateral, and Sandridge Lateral XHP ST
- General inflation rate of 3% applied broadly for more cost categories. Integrity Dig costs increases based on 10 year historical spend increase assessment
- No periodic corrosion or leak survey carried out
- Assume a 15% contingency of cost estimates in all scenarios and +60%/-30% uncertainty of constuction related costs
- TPD threat will be temporarily mitigated as Enbridge will have a large presence in the area during construction and would know if any other construction activies are started.
Cost/Benefit Category | Cost/Benefit Type | Scenario Tasks | Assumptions | Type | Activity | Year | Quantity | Unit Cost (2023 $) | Cost (2023 $) | Discount Rate (%) | Cost Escalation (%) | Cost in year spent ($)
Cost | Upfront | Replace all portions of St. Laurent Pipeline (St. Laurent, Tremblay, Sandridge) | The steel scope is consistent with what was filed to the OEB as part of the original LTC application, but the PE components were removed north of Brittany, and removed on Coventry/Ogilvie between Belfast to Cummings. This option maximized the number of services that could be relayed to the new steel main, but would need to be confirmed as a feasible solution by DOE. Replacement estimates refreshed in November 2023. | Capital | Replacement | 2023 | 1 | 2142244 | -2142244 | 0% | 0% | -2142244
Cost | Upfront |  |  | Capital | Replacement | 2024 | 1 | 39199152.4272 | -39199152.4272 | 5.75% | 3% | -40375127
Cost | Upfront |  |  | Capital | Replacement | 2025 | 1 | 93182544.0664 | -93182544.0664 | 5.75% | 3% | -98857361
Cost | Upfront |  |  | Capital | Replacement | 2026 | 1 | 33868972.7626 | -33868972.7626 | 5.75% | 3% | -37009541
Cost | Upfront |  |  | Capital | Replacement | 2027 | 1 | 4906610.1935 | -4906610.1935 | 5.75% | 3% | -5522433
Cost | On-going | Interest During Construction | Assume 8 months of construction per year (construction period) and all work will be completed in the given year. 5.48% interest rate on debt. | Capital | IDC | 2023 | 1 | 111632.2854 | -111632.2854 | 5.75% | 0% | -111632.2854
Cost | On-going |  |  | Capital | IDC | 2024 | 1 | 1111958.5637 | -1111958.5637 | 5.75% | 0% | -1111958.5637
Cost | On-going |  |  | Capital | IDC | 2025 | 1 | 2073392.6067 | -2073392.6067 | 5.75% | 0% | -2073392.6067
Cost | On-going |  |  | Capital | IDC | 2026 | 1 | 491614.4035 | -491614.4035 | 5.75% | 0% | -491614.4035