## 1-Intervenor-4a
Description | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Explanation
As per the Business Plan | 14032622.65 | 16658342.6197 | 22087878.7116 | 22431377.1893 | 19195320.7543 | 16777234.9428 | 15561725.1692
Difference:
Buildings | -265511.2 | 150000 | 15300 | 0 | 0 | 0 | 0 | To reflect lower actual costs in 2024; carry-over of receiving dock replacement from 2024 to 2025; increased cost for security in 2025/2026
Standby Generator, 1340 Brant Street | -60000 | 0 | 0 | 0 | 0 | 0 | 0 | Replacement shifted to 2024
Poles and Transformers Replacements | 488809.59 | 0 | 0 | 0 | 0 | 0 | 0 | Higher actual cost in 2024 due to additional proactive and reactive replacements
General Services | 1017575.53 | 1230000 | 918000 | 936000 | 954900 | 973800 | 993600 | Higher number of customer requests for connections and upgrades in 2024; forecast updated based on historical costs and expected increase in customer demands and connections
Major Transit Area Developments | 0 | 364476 | 1250666.6623 | 1492804.4126 | -816532.674 | 3767798.8133 | 2665449.1519 | Costs were updated based on revised estimates provided by the consultant. Capital contribution assumptions were also adjusted to reflect an extended revenue horizon
Subdivision Buybacks | -362813.34 | 0 | 0 | 0 | 0 | 0 | 0 | To reflect lower actual cost in 2024 as developers in process to rectify defects for buyback
Waterdown Rd. | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 2 additional pole replacements required to address safety clearance issue
OMS | 39065.19 | 0 | 0 | 0 | 0 | 0 | 0 | Higher implementation cost than planned
Other | 29722.91 | 0 | 0 | 0 | 0 | 0 | 0 | Misc. items including office equipment, EV charges etc.
As per the Application submission | 14919471.33 | 18502818.6197 | 24271845.374 | 24860181.6019 | 19333688.0803 | 21518833.7561 | 19220774.3211
Dundas Street Rd. Widening | 0 | -783042 | 554960 | 0 | 0 | 0 | 0 | Northampton Blvd to Guelph line section delayed from 2025 to 2026 based on new timelines and updated cost
Poles Replacements | 0 | 1242647 | 0 | 0 | 0 | 0 | 0 | Forecast updated to address higher number of poles in poor/very poor condition based on ACA results
OMS and Website | 0 | 72081.69 | 44000 | 0 | 0 | 0 | 0 | To reflect updated cost estimate for OMS Phase 2 and website development
Substation Transformer Replacement | 0 | -400000 | 0 | 0 | 0 | 0 | 0 | Deferred from 2025 to 2026 to mitigate other increases
Standby Generator, 1340 Brant Street | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Carry-over from 2024 to 2025
Buildings | 0 | 28693 | 0 | 0 | 0 | 0 | 0 | Increase HVAC and dock replacement costs
Major Transit Area Developments | 0 | -243906 | 0 | 0 | 0 | 0 | 0 | Design scope reduced
CCRA Tremaine and Bronte TS | 0 | -364100 | 0 | 0 | 0 | 0 | 0 | To reflect CCRA true-ups from Hydro One for Tremaine and Bronte TS
Circuit Breakers Replacement | 0 | -100000 | 0 | 0 | 0 | 0 | 0 | Deferred to mitigate other increases
Underground Rebuilds | 0 | -256333 | 0 | 0 | 0 | 0 | 0 | Deferred to mitigate other increases
Switch Replacement | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | Reactive replacements
Switchgear Replacement | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | Reactive replacements
Primary and Secondary -overhead wires | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | Reactive
As per the IR submission (updated) | 14919471.33 | 17903859.3097 | 24870805.374 | 24860181.6019 | 19333688.0803 | 21518833.7561 | 19220774.3211