## 2-SEC-42
Project Code | Program Type | Project Type | Planning Portfolio | Project Name | HOL Value | Capacity | Compliance | Environmental | Financial Risk | Reliability Risk | Reliability Risk - Resiliency | Safety | Distributed Generation | Financial Benefits And Costs | Program Effects | Reliability | Technological Innovation | Replacement Cost | Total Investment Cost | Initial Estimate | 2025 Project Cost | Variance | Post-2025 Submitted Spend | In DSP | Completion Year
AIP003933 | Distribution | System Renewal | Pole Renewal | Storm Hardening | 1418.9 | 0 | 0 | 0 | 0 | 3165.1 | 313.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2060 | 1501563 | 2167046.62 | 665483.62 | 0 |  | 2025
AIP003778 | Distribution | System Renewal | Vault Renewal | Vault Renewal 2025 | 1587.4 | 0 | 0 | 0 | 0 | 0 | 44.6 | 9.4 | 0 | 2014.4 | 0 | 0 | 0 | 0 | -481 | 506000 | 499964.02 | -6035.98 | 0 |  | 2025
AIP003519 | Stations | System Renewal | Station Battery Renewal | Station Battery Renewal | 264.1 | 0 | 0 | 0 | 526.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -262 | 84169 | 84168 | -1 | 199727 | Yes | 2026
AIP004042 | Distribution | System Renewal | UG Switchgear Renewal | SC7717 Replacement | 72 | 0 | 0 | 0 | 234 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -162 | 166667 | 166759.01 | 92.01 | 0 |  | 2025
AIP004041 | Distribution | System Renewal | UG Switchgear Renewal | SC21 Replacement | 84 | 0 | 0 | 0 | 243 | 90 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -250 | 166667 | 259861 | 93194 | 0 |  | 2025
AIP004031 | Distribution | System Renewal | Pole Renewal | Broadview Ave. Pole Renewal | 98 | 0 | 0 | 0 | 113 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -380 | 349733 | 388146.89 | 38413.89 | 0 |  | 2025
AIP003149 | Distribution | System Renewal | UG Switchgear Renewal | SC14 UG SWG Renewal | 277 | 0 | 0 | 0 | 218 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -128 | 118028 | 129522.13 | 11494.13 | 0 |  | 2025
AIP004040 | Distribution | System Renewal | UG Switchgear Renewal | SC81 Replacement | 570 | 0 | 0 | 0 | 319 | 411 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -161 | 166667 | 167814 | 1147 | 0 |  | 2025
AIP003974 | Distribution | System Renewal | Pole Renewal | Dagmar Phase 1 | 1228 | 0 | 0 | 0 | 0 | 1832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -603 | 618500 | 618508.41 | 8.41 | 0 |  | 2025
AIP003396 | Distribution | System Renewal | Pole Renewal | Centretown Pole Ren. 1.8-Percy | 2020 | 0 | 0 | 11 | 452 | 2465 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | -910 | 400000 | 950211.83 | 550211.83 | 0 |  | 2025
AIP003464 | Distribution | System Renewal | Cable Replacement | Fortune Cable Renewal - P1.2 | 2829 | 0 | 0 | 73 | 3577 | 2967 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | -3792 | 5394174 | 3977031.3 | -1417142.7 | 0 |  | 2025
AIP003900 | Distribution | System Service | Dist. System Reliability | LTM04 Loop | 5020 | 0 | 0 | 0 | 0 | 8738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3718 | 2668449 | 0 | -2668449 | 0 |  | 2025
AIP003491 | Distribution | System Renewal | Cable Replacement | Fortune Cable Renewal - P1.1 | 7023 | 0 | 0 | 58 | 5205 | 3851 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | -2095 | 3546936 | 2196310.17 | -1350625.83 | 0 |  | 2025
AIP003728 | Stations | System Renewal | Stations Transformer Renewal | Longfields T2 XFMR Renewal | 9590 | 0 | 0 | 56 | 2056 | 9815 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | -2346 | 62000 | 623559.54 | 561559.54 | 1930462.45 | Yes | 2026
AIP003716 | Distribution | System Service | Distribution Capacity Upgrades | RHS-CBN Tie (Barnsdale) Ph2 | 14184 | 0 | 0 | 0 | 0 | 14444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -259 | 20000 | 264710.44 | 244710.44 | 0 |  | 2025
AIP003467 | Stations | System Service | Stations Capacity Upgrades | Piperville MTS | 31188 | 57956 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28187 | 21421006 | 27302721.41 | 5881715.41 | 1987054.47 | Yes | 2026
AIP004027 | Distribution | System Service | Distribution Capacity Upgrades | Bells Corners New Feeder | 38864 | 30122 | 0 | 0 | 59 | 9774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1090 | 2605000 | 1129374.95 | -1475625.05 | 0 |  | 2025
AIP003076 | Stations | System Service | Stations Capacity Upgrades | Riverdale Switchgear Upgrade | 55265 | 59473 | 0 | 0 | 0 | 14555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18763 | 10452836 | 7554639.68 | -2898196.32 | 12331462.14 | Yes | 2027
AIP004033 | Distribution | System Service | Distribution Capacity Upgrades | Piperville MTS Egress | 56482 | 57956 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2893 | 3318644 | 2979990.8 | -338653.2 | 0 |  | 2025
AIP004029 | Distribution | System Service | Dist. System Reliability | FAL02 CBN05 tie | 62948 | 57023 | 0 | 0 | 0 | 6064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -139 | 144237 | 144467 | 230 | 0 |  | 2025
AIP003853 | Stations | System Service | Stations Capacity Upgrades | Mer Bleue Station | 73738 | 5782 | 0 | 0 | 5461 | 94805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32310 | 6979131 | 7518582.41 | 539451.41 | 22929260.98 | Yes | 2028
AIP004039 | Stations | System Service | Stations Capacity Upgrades | Greenbank MTS Capacity Upgrade | 75171 | 105312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30141 | 250000 | 1922247.5 | 1672247.5 | 6642211.61 | Yes | 2028
AIP001962 | Distribution | System Service | Dist. System Reliability | Worst Feeder Betterment 13-20 | 82170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441 | 0 | 82568 | 0 | 0 | -839 | 500000 | 302489.04 | -197510.96 | 602022 | Yes | 2026
AIP003969 | Distribution | System Service | Distribution Capacity Upgrades | Westboro Capacity - Hinchey Ext | 128201 | 87185 | 0 | 0 | 0 | 43596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2579 | 2003498 | 2644314.94 | 640816.94 | 0 |  | 2025
AIP002164 | Stations | System Service | Stations Capacity Upgrades | New Kanata North MTS | 182867 | 129053 | 0 | 0 | 0 | 88242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34428 | 347837 | 1415033.04 | 1067196.04 | 9100000 | Yes | 2028