## Accessibility Disclaimer Public
This is a locked, fillable form and not all of the content in this document may be captured by a screen-reading device. If you require additional assistance to complete and submit this form, please contact innovation@OEB.ca

## Project Proposal Part B Cover
Project Proposal Part B Cover
Applicant:
Project Title:
| I. Document Checklist | Not Complete
| II. Funding Summary | Not Complete
| III. OEB Funding (Supported by Government of Canada) Summary by Milestone | Not Complete
I. Document Checklist
Document ID | Worksheet Title | Description | Checklist (drop down selection)
1 | Budget | This document is the project budget that provides a detailed breakdown of activities within each task in every milestone, the associated costs for each activity and the contribution between partners, proponent and OEB towards the project. | Not Complete
2 | Work Plan | The work plan is a Gantt chart that provides a description of specific milestones, outcomes, tasks, and deliverables that will be taking place during the course of the project timeline. | Not Complete
3 | Measuring Results | "Measuring Results" aims to capture the performance indicators of key tasks, its associated performance results and the timeframe of the results. This is also reflected in Section 7, Part A of the Project Proposal Template. | Not Complete
4 | Project Risk Profile | This document captures the risks and associated mitigation strategies | Not Complete
II. Funding Summary
Row ID | Organization Structure (drop down selection) | Company Name | Industry (drop down selection) | Applicant / Project Partner (drop down selection) | In-Kind / Cash Contribution (drop down selection) | Status (drop down selection) | Amount (Numeric Value)
1
2
3
4
|  | Total |  |  |  |  | 0
III. OEB Funding (Supported by Government of Canada) Summary by Milestone
Milestone ID | Milestone Completion Month (Numeric Value) | Brief Milestone Description | OEB Contribution Amount (Supported by Government of Canada) (Numeric Value) | Total Milestone Amount (Numeric Value)
1
2
3
4
5
|  | Total | 0 | 0

## 1. Budget
1. Detailed Project Budget
Project Name:
Organization Name:
Summary | Expected Submission Date (Months from project start date) | OEB Contribution (Supported by Government of Canada) | Total Partner Contribution (Confirmed) | Total Milestone Value
Milestone 1 |  | 0 | 0 | 0
Milestone 2 |  | 0 | 0 | 0
Milestone 3 |  | 0 | 0 | 0
Milestone 4 |  | 0 | 0 | 0
Milestone 5 |  | 0 | 0 | 0
Total |  | 0 | 0 | 0
Click red triangles on cells for important notes that will help you accurately complete this template.
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
1.1 | 1 |  | 1 | [18 empty] | 0
1. | 1 | [20 empty] | 0
1. | 1 | [20 empty] | 0
1. | 1 | [20 empty] | 0
1. | 1 | [10 empty] | 0 | [9 empty] | 0
1. | 1 | [10 empty] | 0 | [9 empty] | 0
1. | 1 | [10 empty] | 0 | [9 empty] | 0
1. | 1 | [10 empty] | 0 | [9 empty] | 0
Milestone 1 Summary | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
2.1 | 2 |  | 1 |  | 1 | [6 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
2. | 2 | [10 empty] | 0 | [9 empty] | 0
Milestone 2 Summary | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
3.1 | 3 |  | 1 |  | 1 | [6 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
3. | 3 | [10 empty] | 0 | [9 empty] | 0
Milestone 3 Summary | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
4.1 | 4 |  | 1 |  | 1 | [6 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
4. | 4 | [10 empty] | 0 | [9 empty] | 0
Milestone 4 Summary | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (Cash) | Applicant Company (In-Kind) | Partner A (In-Kind) | Partner A (Cash) | Partner B (In-Kind) | Partner B (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
5.1 | 5 |  | 1 |  | 1 | [6 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
5. | 5 | [10 empty] | 0 | [9 empty] | 0
Milestone 5 Summary | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLEASE NOTE:
Please refer to spreadsheet titled "1. Budget Example" for example content to demonstrate format.
The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column.
Unless specifically directed otherwise, do not include OEB services as an in-kind contribution.
Please refer to appendice C of the Proponent Guideline available on Innovation Sandbox Engage with Us site for more information on eligible project costs.
Final project milestone value must represent a minimum of 10% of Fund grant.
In-kind and cash contributions consist of auditable, substantiated cash and non-cash contributions to the project that contribute substantially to the completion of the project.
Add/Remove Milestones as required
Note on E14: Multiple tasks can be mapped to a single milestone.
Note on F14: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on G14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on I14: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J14: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K14: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L14: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Q14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X14: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F25: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I25: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J25: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K25: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L25: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Q25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X25: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F36: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I36: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J36: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K36: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L36: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Q36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X36: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F47: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I47: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J47: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K47: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L47: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Q47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X47: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F58: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I58: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J58: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K58: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L58: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Q58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on W58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on X58: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)

## 2. Work Plan
2. Work Plan
Project Name:
Organization Name:
Project Month # (Maximum project length is 24 months)
Milestone | Outcome by Milestone | Task Area | Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
E.g., Milestone 1 | E.g., Milestone 1 Outcome | E.g., Task Area 1 | E.g., Deliverable 1 | bar: Project Month # (Maximum project length is 24 months) 1 to Project Month # (Maximum project length is 24 months) 3
E.g., Deliverable 2 | bar: Project Month # (Maximum project length is 24 months) 3
E.g., Deliverable 3 | bar: Project Month # (Maximum project length is 24 months) 4 to Project Month # (Maximum project length is 24 months) 7
E.g., Deliverable 4 | bar: Project Month # (Maximum project length is 24 months) 6 to Project Month # (Maximum project length is 24 months) 10
|  | E.g., Task Area 2 | E.g., Deliverable 1 | bar: Project Month # (Maximum project length is 24 months) 3
E.g., Deliverable 2 | bar: Project Month # (Maximum project length is 24 months) 3 to Project Month # (Maximum project length is 24 months) 4
E.g., Deliverable 3 | bar: Project Month # (Maximum project length is 24 months) 5 to Project Month # (Maximum project length is 24 months) 14
E.g., Deliverable 4 | bar: Project Month # (Maximum project length is 24 months) 12 to Project Month # (Maximum project length is 24 months) 14
E.g., Deliverable 5 | bar: Project Month # (Maximum project length is 24 months) 14 to Project Month # (Maximum project length is 24 months) 15
E.g., Milestone 2 |  | E.g., Task Area 1 | E.g., Deliverable 1 | bar: Project Month # (Maximum project length is 24 months) 12 to Project Month # (Maximum project length is 24 months) 13
E.g., Deliverable 2 | bar: Project Month # (Maximum project length is 24 months) 13 to Project Month # (Maximum project length is 24 months) 14
|  | E.g., Task Area 2 | E.g., Deliverable 1 | bar: Project Month # (Maximum project length is 24 months) 14 to Project Month # (Maximum project length is 24 months) 18
E.g., Deliverable 2 | bar: Project Month # (Maximum project length is 24 months) 15 to Project Month # (Maximum project length is 24 months) 21
E.g., Deliverable 3 | bar: Project Month # (Maximum project length is 24 months) 14
|  | E.g., Task Area 3 | E.g., Deliverable 1 | bar: Project Month # (Maximum project length is 24 months) 14 to Project Month # (Maximum project length is 24 months) 19
E.g., Deliverable 2 | bar: Project Month # (Maximum project length is 24 months) 16 to Project Month # (Maximum project length is 24 months) 23
E.g., Deliverable 3 | bar: Project Month # (Maximum project length is 24 months) 23 to Project Month # (Maximum project length is 24 months) 24
E.g., Milestone 3 |  | E.g., Task Area 1 | E.g., Deliverable 1
E.g., Deliverable 2 | bar: Project Month # (Maximum project length is 24 months) 24
E.g., Deliverable 3 | bar: Project Month # (Maximum project length is 24 months) 24

## 3. Measuring Results
3. Measuring Results
Project Name:
Organization Name:
Click red triangles on cells for important notes that will help you accurately complete this template.
Milestone | Milestone Outcome | Task | Performance Indicator | Method of Measurement | Performance Results | Performance Achievement Date/Month
Milestone 1
Milestone 2
Milestone 3
Milestone 4
Project | Project Outcome | Performance Indicator | Method of Measurement | Performance Results | Performance Achievement Date/Month
E.g., Project outcome 1
E.g., Project outcome 2
E.g., Project outcome 3
Note on E7: Measuring results requires a performance indicator to be established for EACH project task as well as plan for how and when it will be measured.
Note on F7: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on G7: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on H7: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.
Note on D20: Measuring results requires a performance indicator to be established for EACH project outcome as well as plan for how and when it will be measured.
Note on E20: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on F20: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on G20: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.

## 4. Project Risk Profile
4. Project Risk Profile
Project Name:
Organization Name:
Risk ID | Description of Risk | Severity of Risk (drop down selection) | Likelihood of Risk (drop down selection) | Risk Mitigation Strategy

## Examples-->
This spreadsheet is left intentionally blank. Examples of each deliverable can be found in subsequent worksheets. Please note that each worksheet example is an independant example.
Good luck!

## Proj. Prop. Pt. B Cover EXAMPLE
Project Proposal Part B Cover (EXAMPLE)
| Applicant: | XYZ Inc.
| Project Title: | Pilot Scale Up Project
| I. Document Checklist | Complete
| II. Funding Summary | Complete
| III. OEB Funding Summary (Supported by NRCan) by Milestone | Complete
I. Document Checklist
Document ID | Title | Description | Checklist
1 | Budget | This document is the project budget that provides a detailed breakdown of activities within each task in every milestone, the associated costs for each activity and the contribution between partners, proponent and OEB towards the project. | Complete
2 | Work Plan | The work plan is a Gantt chart that provides a description of specific milestones, outcomes, tasks, and deliverables that will be taking place during the course of the project timeline. | Complete
3 | Measuring Results | "Measuring Results" aims to capture the performance indicators of key tasks, its associated performance results and the timeframe of the results. This is also reflected in Section 7, Part A of the Project Proposal Template. | Complete
4 | Project Risk Profile | This document captures the risks and associated mitigation strategies | Complete
II. Funding Summary
ID | Organization Structure | Company Name | Industry | Applicant / Project Partner | In-Kind / Cash Contribution | Status | Amount
1 | Private - For Profit | XYZ Inc. | Manufacturing | Applicant | In Kind | Confirmed | 100000
2 | Private - For Profit | XYZ Inc. | Manufacturing | Applicant | Cash | Confirmed | 80000
3 | Local Distribution Company | Utility ABC | Utilities | Project Partner | In Kind | Confirmed | 95000
4 | Private - For Profit | Gadget Co. | Consultants | Project Partner | In Kind | Confirmed | 50000
5 | Private - For Profit | Meter Inc. | Research | Project Partner | In Kind | Unconfirmed | 85000
6 | Private - For Profit | Meter Inc. | Research | Project Partner | Cash | Confirmed | 45000
|  | Total |  |  |  |  | 455000
III. OEB Funding (Supported by NRCan) Summary by Milestone
Milestone ID | Milestone Completion Month (Numeric Value) | Brief Milestone Description | OEB Contribution Amount (Supported by NRCan) (Numeric Value) | Total Milestone Amount (Numeric Value)
1 | 5 | Project Design | 22500 | 87000
2 | 8 | Project Implementation | 35000 | 203000
3 | 15 | Analysis | 39500 | 116000
4 | 36 | M&V Results and Reporting | 28000 | 174000
|  | Total | 125000 | 580000

## 1. Budget EXAMPLE
1. Detailed Project Budget (EXAMPLE)
Project Name: | Pilot Scale Up Project
Organization Name: | XYZ Inc.
Summary | Expected Submission Date (Months from project start date) | OEB Contribution | Total Partner Contribution (Confirmed) | Total Milestone Value
Milestone 1 | 5 | 22500 | 64500 | 87000
Milestone 2 | 8 | 35000 | 168000 | 203000
Milestone 3 | 15 | 39500 | 76500 | 116000
Milestone 4 | 36 | 28000 | 146000 | 174000
|  | 0 | 0 | 0
Total |  | 125000 | 455000 | 580000
Click red triangles on cells for important notes that will help you accurately complete this template.
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (In-Kind) | Applicant Company (Cash) | Gadget Co. (In-Kind) | Gadget Co. (Cash) | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
1.1 | 1 | Milestone 1: Project Design | 1 | Task 1: Project Design & Work Plan | 1 | Activity 1: Develop detailed M&V Plan | Month 1 | Labour | Applicant Company / LDC | 154 | 18 | 2772 | 2079 | 0 | 0 | 0 | 0 | 0 | 693 | 2772
1.2 | 1 | Milestone 1: Project Design | 2 | Task 2: Review Project Design & Work Plan with OEB | 2 | Activity 2: Review detailed M&V Plan with IESO | Month 2 | Labour | Applicant Company | 154 | 2 | 308 | 231 | 0 | 0 | 0 | 0 | 0 | 77 | 308
1.3 | 1 | Milestone 1: Project Design | 3 | Task 3: Finalize Project Design & Work Plan | 1 | Activity 1: Develop metering plan | Month 2 | Labour | Applicant Company | 154 | 5 | 770 | 577.5 | 0 | 0 | 0 | 0 | 0 | 192.5 | 770
1. | 1 |  |  |  | 2 | Activity 2: Acquire submeters | [5 empty] | 0
1. | 1 | [10 empty] | 0
1. | 1 | [10 empty] | 0
1. | 1 | [10 empty] | 0
1. | 1 | [10 empty] | 0
Milestone 1 Summary | [10 empty] | 25 | 3850 | 2887.5 | 0 | 0 | 0 | 0 | 0 | 962.5 | 3850
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
2.1 | 2 |  | 1 |  | 1 |  |  | Labour |  |  |  | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
2. | 2 | [10 empty] | 0 | [7 empty] | 0
Milestone 2 Summary | [10 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
3.1 | 3 |  | 1 |  | 1 | [6 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
3. | 3 | [10 empty] | 0 | [7 empty] | 0
Milestone 3 Summary | [10 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
4.1 | 4 |  | 1 |  | 1 | [6 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
4. | 4 | [10 empty] | 0 | [7 empty] | 0
Milestone 4 Summary | [10 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Unique Line Item ID [Milestone].[Task] (Autogenerated-DO NOT ENTER) | Milestone ID | Milestone Description | Task ID | Task Areas | Activity ID | Activity Detail | Due Date | Cost Classification (drop down selection) | Service Provider [Product or Service Provider] | Rate/Cost [$/hr] or [$/unit] | Units | Total Cost (Calculated) | Total Contribution (OEB, Supported by Government of Canada) | Applicant Company (In-Kind) |  |  |  | Demonstration Facility (In-Kind) | Local Distribution Company (LDC) partner (In-Kind) | Total Contribution (All Funders)
5.1 | 5 |  | 1 |  | 1 | [6 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
5. | 5 | [10 empty] | 0 | [7 empty] | 0
Milestone 5 Summary | [10 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
PLEASE NOTE:
Please refer to spreadsheet titled "1. Budget Example" for example content to demonstrate format.
The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column.
Unless specifically directed otherwise, do not include OEB services as an in-kind contribution.
Please refer to appendice C of the Proponent Guideline available on Innovation Sandbox Engage with Us site for more information on eligible project costs.
Final project milestone value must represent a minimum of 10% of Fund grant.
In-kind and cash contributions consist of auditable, substantiated cash and non-cash contributions to the project that contribute substantially to the completion of the project.
Add/Remove Milestones as required
Note on C14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on E14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on F14: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on G14: Multiple activities can be mapped to a single task. Multiple tasks can be mapped to a single milestone.
Note on I14: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J14: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K14: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L14: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on Q14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on R14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on S14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U14: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V14: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F25: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I25: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J25: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K25: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L25: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U25: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V25: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F36: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I36: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J36: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K36: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L36: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U36: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V36: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F47: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I47: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J47: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K47: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L47: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U47: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V47: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on F58: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on I58: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on J58: Classification of cost for this project activity either as: - labour cost including salaries and studies. - material, hardware or equipment cost for this project - licensing fees including cost of administration fees - 3rd party M&V costs
Note on K58: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on L58: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on P58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on T58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on U58: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on V58: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)

## 2. Work Plan EXAMPLE
2. Work Plan (EXAMPLE)
| Project Name: | Pilot Scale Up Project
| Organization Name: | XYZ Inc.
Project Month # (Maximum project length is 24 months)
Milestone | Outcome by Milestone | Task Area | Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
E.g., Milestone 1 |  | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 24 months) 1 to Project Month # (Maximum project length is 24 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 24 months) 3
E.g., Activity 3 | bar: Project Month # (Maximum project length is 24 months) 4 to Project Month # (Maximum project length is 24 months) 7
E.g., Activity 4 | bar: Project Month # (Maximum project length is 24 months) 6 to Project Month # (Maximum project length is 24 months) 10
|  | E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 24 months) 3
E.g., Activity 2 | bar: Project Month # (Maximum project length is 24 months) 3 to Project Month # (Maximum project length is 24 months) 4
E.g., Activity 3 | bar: Project Month # (Maximum project length is 24 months) 5 to Project Month # (Maximum project length is 24 months) 14
E.g., Activity 4 | bar: Project Month # (Maximum project length is 24 months) 12 to Project Month # (Maximum project length is 24 months) 14
E.g., Activity 5 | bar: Project Month # (Maximum project length is 24 months) 14 to Project Month # (Maximum project length is 24 months) 15
E.g., Milestone 2 |  | E.g., Task Area 1 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 24 months) 12 to Project Month # (Maximum project length is 24 months) 13
E.g., Activity 2 | bar: Project Month # (Maximum project length is 24 months) 13 to Project Month # (Maximum project length is 24 months) 14
|  | E.g., Task Area 2 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 24 months) 14 to Project Month # (Maximum project length is 24 months) 18
E.g., Activity 2 | bar: Project Month # (Maximum project length is 24 months) 15 to Project Month # (Maximum project length is 24 months) 21
E.g., Activity 3 | bar: Project Month # (Maximum project length is 24 months) 14
|  | E.g., Task Area 3 | E.g., Activity 1 | bar: Project Month # (Maximum project length is 24 months) 14 to Project Month # (Maximum project length is 24 months) 19
E.g., Activity 2 | bar: Project Month # (Maximum project length is 24 months) 16 to Project Month # (Maximum project length is 24 months) 23
E.g., Activity 3 | bar: Project Month # (Maximum project length is 24 months) 23 to Project Month # (Maximum project length is 24 months) 24
E.g., Milestone 3 |  | E.g., Task Area 1 | E.g., Activity 1
E.g., Activity 2 | bar: Project Month # (Maximum project length is 24 months) 24
E.g., Activity 3 | bar: Project Month # (Maximum project length is 24 months) 24

## 3. Measuring Results EXAMPLE
3. Measuring Results (EXAMPLE)
Project Name: | Pilot Scale Up Project
Organization Name: | XYZ Inc.
Click red triangles on cells for important notes that will help you accurately complete this template.
Milestone | Milestone Outcome | Task | Performance Indicator | Method of Measurement | Performance Results | Performance Achievement Date/Month
Milestone 1 | Finalize Project Design & Work Plan with OEB | Project Design & Work Plan | Design & Work Plan submitted to OEB | Confirmation of receipt from OEB | Received | Month 1
|  | Discuss Project Design & Work Plan with OEB | Receive oral or written feedback from OEB | Agreement from OEB on approach | Approach to address feedback confirmed | Month 2
|  | Finalize Project Design & Work Plan | Final Design & Work Plan submitted to OEB | OEB approval | Approved | Month 2
Milestone 2 | Project Implementation
Milestone 3 | Analysis
Milestone 4 | M&V Results and Reporting
Project | Project Outcome | Performance Indicator | Method of Measurement | Performance Results | Performance Achievement Date/Month
Pilot Scale Up Project | Detailed understanding of hurdles faced implementing pilot scale ups | Detailed description in Final Report | Process Evaluation | Detailed description of hurdles regarding design, implementation, budget, provincial roll-out in Final Report | Month 24
| Identification of enabling mechanisms that promote successful project scale up | Detailed description in Final Report | Process Evaluation | Prioritized set of recommendations for enabling mechanisms for effective provincial roll-out in Final Report | Month 24
| Enhanced customers' understanding of their role in the energy transition through innovative strategy | Increase in understanding at post-project compared to pre-project | Pre- and Post- Surveys/Interviews | Statistically significant increase in customers' understanding | Month 24
| Estimated impact of project scale up in designated markets across Ontario | Quantitative assessment of relative impacts, with assumptions stated | Impact Assessment and Forecast | Adequate information on which to base recommendation for provincial scale up | Month 24
Note on E7: Measuring results requires a performance indicator to be established for EACH project task as well as plan for how and when it will be measured.
Note on F7: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on G7: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on H7: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.
Note on D29: Measuring results requires a performance indicator to be established for EACH project outcome as well as plan for how and when it will be measured.
Note on E29: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on F29: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on G29: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.

## 4. Project Risk Profile EXAMPLE
4. Project Risk Profile (EXAMPLE)
| Project Name: | Pilot Scale Up Project
| Organization Name: | XYZ Inc.
Risk ID | Description of Risk | Severity of Risk (drop down selection) | Likelihood of Risk (drop down selection) | Risk Mitigation Strategy
1 | Project partners sever partnership prior to project kick-off | Significant | Unlikely | Engage with partners frequently throughout the process to ensure that all parties are aligned with the defined roles and responsibilities, and contributions to project costs
2 | Delays in delivery of equipment | Moderate | Possible | Add a buffer to the expected lead delivery time to account for uncertainties in equipment delivery. Identify alternative equipment suppliers and shipping options to help reduce lead time.
3 | Lower than forecast participation | Significant | Possible | Identify potential participants prior to the project kick-off. Engage with relevant associations to assist with participant recruitment. Adjust engagement strategies to encourage higher participant enrollment.
4 | Project schedule and timeline is not met | Significant | Unlikely | Include critical contingencies in project work plan, and track progress at the individual task level. If the project schedule shows signs of duress, advice OEB and take action to bring in additonal resources or reallocate resources in a timely manner to course correct.
5 | Inadequate communication between project team and OEB | Moderate | Unlikely | Key personnel will participate in weekly meetings during the project setup and launch, followed by monthly meetings with the OEB during ongoing operations once a steady-state of operations has been achieved. The project lead will also maintain informal communications with the OEB. This will ensure timely and effective communication throughout the project setup and ongoing operations.
6 | Work product not to OEB expectations | Significant | Unlikely | Project lead will meet at least quarterly with the OEB to review the project team performance, discuss lessons learned, identify opportunities for improvement, and develop an agreed upon implementation plan for course correction, whose implementation the project lead will oversee and report on to the OEB.

## Options (hidden)
Severity | Almost Certain | Likely | Possible | Unlikely | Rare
Critical | 1 | 1 | 1 | 2 | 3
Significant | 1 | 1 | 2 | 3 | 4
Moderate | 1 | 2 | 3 | 4 | 5
Minor | 2 | 3 | 4 | 5 | 5
Insignificant | 3 | 4 | 5 | 5 | 5
Scope
Budget
Timeline
Material / Equipment / Hardware
Labour
License Fees
Participant Incentives
3rd Party M&V
Accommodation and food services
Agriculture
Business, building and other support services
Construction
Educational services
Finance, insurance, real estate, rental and leasing
Forestry, fishing, mining, quarrying, oil and gas
Goods-producing sector
Health care and social assistance
Information, culture and recreation
Manufacturing
Other services (except public administration)
Professional, scientific and technical services
Public administration
Services-producing sector
Transportation and warehousing
Utilities
Wholesale and retail trade
Complete
Not Complete
Academia / University
Crown Corporation
Government - Federal Entity
Government - Municipal Entity
Government - Provincial Entity
Local Distribution Company
NGO
Private - For Profit
Private - Not For Profit
Transmission Company
Academia, University Research
Accommodation and Food Services
Administrative and Support, Waste Management and Remediation Services
Agriculture, Forestry, Fishing and Hunting
Arts, Entertainment and Recreation
Construction
Consultants
Educational Services
Electricity System Operator
Energy
Finance and Insurance
Health Care and Social Assistance
Information and Cultural Industries
Manufacturing
Mining, Quarrying, and Oil and Gas Extraction
Public Administration
Real Estate and Rental and Leasing
Research
Retail Trade
Technology
Transportation and Warehousing
Utilities
Wholesale Trade
In Kind
Cash
Applicant
Project Partner
Confirmed
Unconfirmed