## Quanity
2-AMPCO-38
Alectra Asset Condition Assessment - Quantity of Assets Replaced - All Investments Excluding Reactive Capital B05
Ref: Ex 2A-1-1 Investments Summaries B1-B4; B6-B14
Distribution Assets | Unit | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Estimate Assumptions
Pad-mounted Transformer | each | 498 | 318 | 423 | 364 | 340 | 446 | 590 | 590 | 682 | 848 | 968 | 1091 | 1201 | Program actuals only 2019-2025, Forecast for the total investment in 2026-2031
Pole-Mounted Transformer | each
Vault Transformer | each
Pad-mounted Switchgear | each | 34 | 50 | 58 | 52 | 58 | 73 | 66 | 56 | 56 | 56 | 56 | 88 | 88 | Program actuals for 2019-2025, Forecast program replacements for 2026-2031
Overhead Switch (LIS) | each | 15 | 13 | 25 | 27 | 30 | 36 | 31 | 51 | 51 | 51 | 51 | 51 | 51 | Program actuals for 2019-2025, Forecast program replacements for 2026-2031
Overhead Conductor | km | 49.853 | 77.267 | 120.039 | 87.671 | 98.376 | 118.7 | 108.431 | 9.353 | N/A | N/A | N/A | N/A | N/A | Change in total overhead conductor population, yearly forecast breakout possible
Wood Pole | each | 588 | 682 | 772 | 836 | 942 | 709 | 746 | 746 | 826 | 925 | 1025 | 1180 | 1300 | Program actuals for 2019-2025, Forecast program replacements for 2026-2031
Concrete pole | each
UG Primary XLPE Cable | km | 45 | 67 | 47 | 37 | 62.316 | 64.2114 | 76.026 | 36 | 42 | 59 | 66 | 102 | 113 | Cable replacement actual projects only 2019-2025, Forecasted replacement for cable replacement projects only 2026-2031
UG Primary PILC Cable | km | 0 | 0 | 3.3 | 0 | 3.9 | 7.1 | 5.1 | N/A | N/A | N/A | N/A | N/A | N/A | Change in total cable population for 2019-2025, no estimated forecast
U/G Primary EPR Cable | km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change in total cable population for 2019-2025, no planned replacements in 2026-2031
Station Assets
Station Power Transformer | each | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
Station Switchgear | each | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 6 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
Station Circuit Breaker | each | 0 | 5 | 21 | 11 | 0 | 5 | 2 | 0 | 0 | 9 | 14 | 13 | 31 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
Protection & Control Systems
Electromechanical Relays | each | 22 | 46 | 8 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 18 | 39 | 115 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
Solid State Relays | each | 8 | 55 | 0 | 4 | 0 | 18 | 15 | 10 | 30 | 51 | 186 | 6 | 79 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
Microprocessor-based Relays | each | 4 | 16 | 0 | 3 | 12 | 19 | 12 | 9 | 5 | 6 | 34 | 13 | 30 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
Fleet Asset Inventory
Heavy-Duty Vehicles | each | 10 | 9 | 12 | 9 | 5 | 3 | 25 | 9 | 11 | 10 | 14 | 17 | 13 | Based on vehicle deliveries in 2019-2025 and Forecasted delivery in 2026-2031
Medium-Duty Vehicles | each | 0 | 3 | 0 | 0 | 1 | 4 | 6 | 3 | 8 | 5 | 1 | 0 | 1 | Based on vehicle deliveries in 2019-2025 and Forecasted delivery in 2026-2031
Light-Duty Vehicles | each | 20 | 59 | 6 | 11 | 26 | 52 | 41 | 63 | 60 | 55 | 28 | 28 | 50 | Based on vehicle deliveries in 2019-2025 and Forecasted delivery in 2026-2031
Trailers | each | 9 | 0 | 1 | 4 | 9 | 9 | 10 | 14 | 2 | 8 | 2 | 5 | 23 | Based on vehicle deliveries in 2019-2025 and Forecasted delivery in 2026-2031
Fleet Equipment | each | 1 | 2 | 1 | 2 | 0 | 4 | 5 | 1 | 5 | 2 | 3 | 1 | 1 | Based on vehicle deliveries in 2019-2025 and Forecasted delivery in 2026-2031
Other
Porcelain Insulators | each | 925 | 1300 | 827 | 257 | N/A | N/A | N/A | N/A | N/A | N/A | 477 | 482 | 496 | Based on actual projects for 2019-2025 and Forecasted projects in 2026-2031
First Generation Polymer Insulators | each
25 kV Air-Insulated "Live Front" Switchgear | each | 28 | 42 | 51 | 36 | 46 | 45 | 54 | 46 | 43 | 34 | 29 | 59 | 67 | Based on replacements under the program only for 2019-2031, and Forecasted program replacements for 2026-2031
First Generation Solid Switchgear | each | 0 | 0 | 0 | 3 | 0 | 1 | 2 | 2 | 1 | 0 | 5 | 2 | 1 | Based on replacements under the program only for 2019-2031, and Forecasted program replacements for 2026-2031
Oil-Insulated Switchgear | each | 0 | 2 | 0 | 1 | 8 | 20 | 9 | 6 | 8 | 18 | 17 | 20 | 19 | Based on replacements under the program only for 2019-2031, and Forecasted program replacements for 2026-2031
SF6 Switchgear | each | 6 | 6 | 7 | 12 | 4 | 7 | 1 | 2 | 4 | 4 | 5 | 7 | 1 | Based on replacements under the program only for 2019-2031, and Forecasted program replacements for 2026-2031