## HE Capital
D1-AMPCO-13
Ref: D1-1-2 Table 1
Capital Project Listing - Hydroelectric
| Projects ≥ $30M Total Project Cost (Allocated) | [20 empty] | Drivers of Variance to First Execution BCS
| Region | Facility | Project Name | Project # | BCS Tab # | Category | Start Date | Final In-Service Date | Total Project Cost ($M) | Cost at First Exceution BCS ($M) | Final In-Service Date at First Exceution BCS | Total In-Service ($ M) | In-Service LTD ($M) | In-Service IR Term ($ M) | In-Service 2025 ($M) | In-Service 2026 ($M) | SPI = EV/PV | Schedule Variance (SV) = PV-EV | CPI = EV/AC | Cost Variance = EV-AC | Cost Varinace to First Execution BCS ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | Eastern | Calabogie | Calabogie GS - Redevelopment | 82089 | 6 | Value Enhancing (Redevelopment) | 2017-01-31 | 2023-10-25 | 167.204 | 136.5 |  | 165.552 | 165.682 | 0 | -0.13 | 0 |  |  |  |  | 30.704
2 | Niagara | DeCew Falls 2 | G2 Overhaul & Upgrade | 80851 | 4 | Sustaining (Refurbishment) | 2015-02-05 | 2019-07-01 | 35.5 | 38.1 |  | 34.944 | 34.944 | 0 | 0 | 0 |  |  |  |  | -2.6
3 | Niagara | Sir Adam Beck 1 | BK1 G1/G2 Replacement | 84185 |  | Value Enhancing (Expansion) | 2019-02-25 | 2022-10-05 | 122.765 | 115.753 |  | 112.851 | 112.851 | 0 | 0 | 0 |  |  |  |  | 7.012
4 | Niagara | Sir Adam Beck 1 | SAB1 Canal Isolation Preparedness Phase 1 (SAB1 CIP1) | 89252 |  | Sustaining (Canal Rehabilitation) | 2025-07-11 | 2029-12-01 | 65 | n/a |  | 65 | 0 | 65 | 0 | 0
5 | Niagara | Sir Adam Beck Pump Generating Station | Sir Adam Beck Pump GS - Reservoir Refurbishment | 80583 | 2 | Sustaining | 2011-09-19 | 2017-04-01 | 48.689 | 58.2 |  | 48.689 | 48.689 | 0 | 0 | 0 |  |  |  |  | -9.511
6 | Niagara | Sir Adam Beck 1 | Sir Adam Beck I GS - G10 Major Overhaul & Upgrade | 80649 | 3 | Sustaining (Refurbishment) | 2013-10-18 | 2017-06-09 | 30.81 | 27 |  | 30.165 | 30.165 | 0 | 0 | 0 |  |  |  |  | 3.81
7 | Western | Ranney Falls | Ranney Falls Expansion Project | 80581 | 1 | Value Enhancing (Expansion) | 2011-09-19 | 2022-06-01 | 74.5 | 77.3 |  | 74.496 | 74.496 | 0 | 0 | 0 |  |  |  |  | -2.8
8 | Niagara | Sir Adam Beck 1 | Sir Adam Beck 1 GS - Unit G5 Upgrade | 82777 | 10 | Sustaining (Refurbishment) | 2018-05-03 | 2021-09-23 | 44.675 | 19.771 |  | 43.393 | 43.393 | 0 | 0 | 0 |  |  |  |  | 24.904
9 | Eastern | Abitibi Canyon | Abitibi - G2 Capital Upgrades/HG | 83155 |  | Sustaining (Refurbishment) | 2019-02-01 | 2022-03-01 | 30.105 | 27.5 |  | 29.508 | 29.233 | 0 | 0.275 | 0 |  |  |  |  | 2.605
10 | Eastern | Otter Rapids | Otter Project Camp | 84907 |  | Sustaining | 2020-06-08 | 2024-07-16 | 39.47 | 39.472 |  | 38.954 | 38.554 | 0 | 0.4 | 0 |  |  |  |  | -0.002
11 | Eastern | Frederick House6 | Frederick House Lake Dam Upgrades | 83194 |  | Sustaining | 2021-10-29 | 2025-12-31 | 90 | 90 |  | 79.9 | 35.3 | 0 | 37.4 | 7.2 |  |  |  |  | 0
12 | Eastern | R.H. Saunders | SAU - G9 Capital Refurbishment | 83495 |  | Sustaining (Refurbishment) | 2020-12-16 | 2025-08-22 | 42.688 | 17.2 |  | 38.4 | 0 | 0 | 37 | 1.4 |  |  |  |  | 25.488
13 | Eastern | Chenaux | CHE - Limerick Isl. Spr Structure Sluice Gate Hoist | 84494 |  | Regulatory | 2019-05-27 | 2023-11-30 | 32.7 | 32.701 |  | 28.84 | 28.84 | 0 | 0 | 0 |  |  |  |  | -0.001
14 | Eastern | Otter Rapids | Otter G2 Capital Upgrade | 82543 | 9 | Sustaining (Refurbishment) | 2020-08-14 | 2025-12-15 | 78.05 | 43.11 |  | 70.069 | 7.769 | 0 | 61.9 | 0.4 |  |  |  |  | 34.94
15 | Eastern | Coniston/Stinson | Coniston/Stinson GS Redevelopment | 82087 | 5 | Value Enhancing (Redevelopment) | 2019-03-28 | 2027-04-01 | 177.99 | 178 |  | 176.4 | 0 | 45.9 | 0 | 130.5 |  |  |  |  | -0.01
16 | Western | Kakabeka Falls | Kakabeka Falls GS Redevelopment | 86386 |  | Value Enhancing (Redevelopment) | 2021-03-22 | 2028-05-05 | 519 | 519 |  | 511 | 0 | 487.1 | 12.7 | 11.2 |  |  |  |  | 0
17 | Niagara | Sir Adam Beck 2 | BK2 G20/G19 Refurbishment | 87768 |  | Sustaining (Refurbishment) | 2019-10-31 | 2029-02-10 | 377.5 | n/a |  | 353 | 0 | 353 | 0 | 0
18 | Eastern | Matabitchuan | Matabitchuan GS Redevelopment | 86387 |  | Value Enhancing (Redevelopment) | 2022-11-16 | 2028-08-07 | 190 | 190 |  | 187.55 | 0 | 183.4 | 4.2 | 0 |  |  |  |  | 0
19 | Eastern | R.H. Saunders | SAU - G12 Capital Refurbishment | 86587 |  | Sustaining (Refurbishment) | 2022-06-14 | 2026-06-09 | 30.38 | 30.38 |  | 26.9 | 0 | 0 | 0 | 26.9 |  |  |  |  | 0
20 | Eastern | Otter Rapids | Otter G1 Capital Upgrade | 82542 | 8 | Sustaining (Refurbishment) | 2019-02-21 | 2026-12-10 | 40.664 | 40.7 |  | 35.8 | 0 | 1.8 | 0 | 34 |  |  |  |  | -0.036
21 | Eastern | Abitibi Canyon | ABI - G1 Capital Upgrades | 83148 |  | Sustaining (Refurbishment) | 2025-03-06 | 2031-01-30 | 54.67 | n/a |  | 46.8 | 0 | 46.8 | 0 | 0
22 | Eastern | R.H. Saunders | SAU - Long Sault Dam Capital Program (JW)(NYPA) | 86595 |  | Regulatory | 2023-03-01 | 2033-12-31 | 88.01 | n/a |  | 74.8085 | 0 | 45.3 | 0 | 0
23 | Eastern | R.H. Saunders | SAU - Massena Canal Dam (JW)(NYPA)(CAP) | 87142 |  | Regulatory | 2015-05-29 | 2029-12-31 | 47.31 | n/a |  | 39.1 | 0 | 39.1 | 0 | 0
24 | Eastern | Abitibi Canyon | Abitibi Canyon Concrete Repair Zone 7 | 89505 |  | Sustaining (Abitibi Concrete) | 2024-12-10 | 2026-04-30 | 35.6 | 35.6 |  | 26.4 | 1.4 | 0 | 0 | 25 |  |  |  |  | 0
25 | Eastern | Otto Holden | OTO - Refurbish Stop Log Sluice Piers | 89354 |  | Sustaining | 2024-10-10 | 2036-09-30 | 107.95 | n/a |  | 91.7575 | 0 | 51.3 | 0 | 0
26 | Western | Alexander | G1 Capital Refurb | 82391 | 7 | Sustaining (Refurbishment) | 2023-04-30 | 2030-09-23 | 45.8888 | n/a |  | 42 | 0 | 42 | 0 | 0
27 | Western | Silver Falls | Surge Tank Replacement | 83833 |  | Sustaining | 2021-03-15 | 2028-12-15 | 40.6954 | n/a |  | 38.8 | 0 | 38.8 | 0 | 0
28 | Western | Northwest Operations7 | NWO Work Centre Building | 84901 |  | Sustaining | 2020-02-26 | 2027-08-27 | 44.4 | n/a |  | 39.9 | 0 | 39.9 | 0 | 0
29 | Western | Alexander | G2 Capital Refurb | 86792 |  | Sustaining (Refurbishment) | 2023-04-30 | 2027-08-16 | 49.7319 | n/a |  | 43.5 | 0 | 43.5 | 0 | 0
30 | Western | Alexander | G3 Capital Refurb | 86793 |  | Sustaining (Refurbishment) | 2023-06-13 | 2031-12-20 | 43.6394 | n/a |  | 41.5 | 0 | 40 | 0 | 0
31 | Western | Manitou Falls | MAN G3 Capital Refurb | 86860 |  | Sustaining (Refurbishment) | 2024-12-03 | 2029-05-29 | 53.2184 | n/a |  | 48 | 0 | 48 | 0 | 0
32 | Western | Aguasabon | Aguasabon Dam Rehab. Hayes Lake Main Dam | 87217 |  | Sustaining | 2023-08-14 | 2033-12-20 | 116.4634 | n/a |  | 110 | 0 | 70 | 0 | 0
33 | Niagara | Sir Adam Beck 1 | SAB1 Station Service Upgrade | 86364 |  | Sustaining | 2020-12-15 | 2030-01-24 | 33.4359 | n/a |  | 31.8 | 0 | 31.8 | 0 | 0
34 | Niagara | Sir Adam Beck 1 | BK1 G6 G8 Refurbishment | 86372 |  | Sustaining (Refurbishment) | 2024-05-24 | 2030-04-10 | 232.3075 | n/a |  | 226.2 | 0 | 226.2 | 0 | 0
35 | Niagara | Sir Adam Beck 1 | BK1 G4 Refurbishment | 86570 |  | Sustaining (Refurbishment) | 2022-05-20 | 2027-06-08 | 109.129 | 109.1 |  | 96.7 | 0 | 96.7 | 0 | 0 |  |  |  |  | 0.029
36 | Niagara | Sir Adam Beck 2 | BK2 G18 G17 Refurbishment | 87356 |  | Sustaining (Refurbishment) | 2025-05-22 | 2030-11-30 | 361.1 | n/a |  | 344.2 | 0 | 344.2 | 0 | 0
37 | Niagara | Sir Adam Beck 2 | BK2 G14 G13 Refurbishment | 87357 |  | Sustaining (Refurbishment) | 2025-05-25 | 2032-07-08 | 375.5516 | n/a |  | 360.8 | 0 | 0 | 0 | 0
38 | Eastern | R.H. Saunders | SAU - G16 Capital Refurbishment | 86937 |  | Sustaining (Refurbishment) | 2024-11-29 | 2028-02-08 | 49.3 | n/a |  | 38.7 | 0 | 38.7 | 0 | 0
39 | Niagara | Sir Adam Beck 2 | BK2 230kV Conductor Replacement | 87362 |  | Sustaining | 2025-03-25 | 2039-08-12 | 35.9234 | n/a |  | 29.8 | 0 | 9.6 | 0 | 0
40 | Eastern | R.H. Saunders | SAU - Long Sault Dam Downstream Concrete (JW) (NYPA) | 87575 |  | Regulatory | 2024-06-11 | 2038-12-31 | 38.38 | n/a |  | 32.623 | 0 | 20.2 | 0 | 0
|  |  | Total Regulated Hydroelectric | [5 empty] | 4200.3947 |  |  | 3954.8 | 651.316 | 2408.3 | 153.745 | 236.6