## HE Capital
D1-AMPCO-14
Ref: D1-1-2 table 2, Table 2b
Capital Project Listing - Regulated Hydroelectric
Projects $10M - $30M Total Project Cost (Allocated)
Drivers of Variance to First Execution BCS
Line No. | Region | Facility | Project Name | Project Number | Category | Start Date | Final In-Service Date | Total Project Cost ($M) | Cost at First Execution BCS ($M) | Final In-Service Date at Execution BCS | Total In-Service ($M) | In-Service LTD ($M) | In-Service IR Term | In-Service 2025 | In-Service 2026 | SPI = EV/PV | Schedule Variance (SV) = PV-EV | CPI = EV/AC | Cost Variance = EV-AC | Cost Varinace to Execution BCS ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | Eastern | Matabitchuan | Replace Penstocks & Saddles | 80703 | Sustaining | 2009-12-11 | 2013-01-14 | 20.2 | [5 empty] | 0 | 0
2 | Eastern | Otto Holden | Otto Holden GS - Replace Sluicegates & Rehabilitate Sluicegates System | 80717 | Sustaining | 2006-05-25 | 2015-11-04 | 22.05 | [5 empty] | 0 | 0
3 | Niagara | Sir Adam Beck 2 | Sir Adam Beck II GS - Station Service Upgrades | 80666 | Sustaining | 2011-03-31 | 2019-04-29 | 14.12 | [5 empty] | 0 | 0
4 | Eastern | R.H. Saunders | R.H. Saunders GS - Replace Station Service Breakers | 80637 | Sustaining | 2012-02-15 | 2018-12-03 | 16.74 | [5 empty] | 0 | 0
5 | Eastern | R.H. Saunders | R.H Saunders GS - Replace Powerhouse Crane | 80635 | Sustaining | 2008-08-26 | 2015-06-12 | 15.065 | [5 empty] | 0 | 0
6 | Eastern | Lower Notch | Lower Notch GS - Unit G2 Capital Upgrades | 80694 | Sustaining (Refurbishment) | 2012-09-13 | 2018-06-01 | 15.47 | [5 empty] | 0 | 0
7 | Eastern | Lower Notch | Lower Notch GS - G1 Capital Upgrade | 80692 | Sustaining (Refurbishment) | 2011-11-22 | 2016-09-24 | 17.47 | [5 empty] | 0 | 0
8 | Eastern | Des Joachims | Des Joachims GS - Rewind Generators G1, G3, G5 | 80604 | Sustaining (Refurbishment) | 2010-09-07 | 2015-05-08 | 10.738 | [5 empty] | 0 | 0
9 | Eastern | Chenaux | Chenaux GS - Replace Protections and Controls | 80596 | Sustaining | 2008-08-29 | 2019-11-25 | 14.241 | [5 empty] | 0 | 0
10 | Western | Caribou Falls | Caribou Block Dam #2 Rehab | 83029 | Regulatory | 2016-03-14 | 2019-10-30 | 24.649 | [5 empty] | 0 | 0
11 | Western | Manitou Falls | Sluicegate Replacement | 82940 | Sustaining | 2018-04-23 | 2021-09-15 | 25.448 | [5 empty] | 0.7 | 0
12 | Western | Silver Falls | SLV G1 Rewind and New Core | 82385 | Sustaining (Refurbishment) | 2018-01-22 | 2022-12-05 | 21.434 | [5 empty] | 0 | 0
13 | Western | Aguasabon | Surge Tank Replacement | 83610 | Sustaining | 2018-01-22 | 2023-08-31 | 26.36 | [5 empty] | 0 | 0
14 | Western | Whitedog Falls | WHD Sluicegate Replacement | 83031 | Sustaining | 2017-02-27 | 2021-12-03 | 16.88 | [5 empty] | 0 | 0
15 | Eastern | Des Joachims | DEJ - Controls - Repl. Generator Controls | 83353 | Sustaining | 2016-11-04 | 2022-06-17 | 13.125 | [5 empty] | 0 | 0
16 | Eastern | Otto Holden | OTO - Capital Project Scope G7 1st Unit | 84385 | Sustaining (Refurbishment) | 2019-09-18 | 2022-09-21 | 12.459 | [5 empty] | 0 | 0
17 | Eastern | Otter Rapids | OTR -T2/T1 Transformer Replacement | 82255 | Sustaining | 2017-03-13 | 2020-08-28 | 12.68 | [5 empty] | 0 | 0
18 | Western | Pine Portage | PIN Sluicegate Replacement | 82802 | Sustaining | 2016-03-14 | 2021-10-29 | 13.07 | [5 empty] | 0 | 0
19 | Western | Whitedog Falls | WHD Sluicegate Repl. - Dogged #1-#4- #5-#6 | 84446 | Sustaining | 2019-08-12 | 2021-10-16 | 12.77 | [5 empty] | 0 | 0
20 | Western | Caribou Falls | Sluicegate Replacement | 82799 | Sustaining | 2018-04-23 | 2023-10-20 | 17.25 | [5 empty] | 0.1 | 0
21 | Eastern | R.H. Saunders | SAU - Headwork Crane Replacement | 83111 | Sustaining | 2016-04-28 | 2022-12-03 | 10.85 | [5 empty] | 0.4 | 0
22 | Eastern | Des Joachims | Replace Generator Breakers and Station Service Brks. | 80602 | Sustaining | 2011-11-30 | 2020-12-14 | 16.5 | [5 empty] | 0 | 0
23 | Eastern | Barrett Chute | Rewind Generators & Reinsulate Field Poles (G1-4) First Unit (G3) | 80980 | Sustaining (Refurbishment) | 2016-05-10 | 2023-11-30 | 13.682 | [5 empty] | 0 | 0
24 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1-4) Second Unit (G4) | 84587 | Sustaining (Refurbishment) | 2019-07-12 | 2023-11-30 | 11.878 | [5 empty] | 0 | 0
25 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1) | 86082 | Sustaining (Refurbishment) | 2022-05-18 | 2024-05-24 | 11.455 | [5 empty] | 0.7 | 0
26 | Eastern | Otter Rapids | Otter Runner Purchase | 80684 | Value Enhancing (Refurbishment) | 2010-04-10 | 2029-11-28 | 17.9 | [5 empty] | 4.4 | 0
27 | Eastern | Otter Rapids | Otter Sluice Gate Upgrades | 82246 | Sustaining | 2019-03-19 | 2024-12-18 | 23.9 | [5 empty] | 1.3 | 0
28 | Eastern | Abitibi Canyon | Abitibi - Transformer Deck Roof Replacement | 82257 | Sustaining | 2019-02-09 | 2024-12-09 | 26.685 | [5 empty] | 1 | 0
29 | Eastern | Stewartville | Replace AC Station Service Transformers, Switchgear and Distribution Panels | 83763 | Sustaining | 2018-06-25 | 2023-12-01 | 12.3 | [5 empty] | 0 | 0
30 | Eastern | Elliott Chute | Elliott - Service Gate and Gains Upgrade | 84534 | Sustaining | 2021-02-04 | 2024-11-13 | 13.187 | [5 empty] | 0.3 | 0
31 | Eastern | R.H. Saunders | Replacement of Excitation System All 16 Units | 82986 | Sustaining | 2016-07-06 | 2026-12-31 | 17.17 | [5 empty] | 0 | 0.8
32 | Eastern | R.H. Saunders | Install Concrete Plug in Ice Sluice Drum Gate Openings | 84202 | Sustaining | 2017-03-28 | 2026-12-19 | 22.6 | [5 empty] | 0.8 | 3.6
33 | Niagara | DeCew Falls 2 | G1 Runner Shaft Replacement | 84558 | Sustaining (Refurbishment) | 2020-08-04 | 2024-11-29 | 19.5 | [5 empty] | 0 | 0
34 | Niagara | Sir Adam Beck 1 | BK1 Tailrace Deck | 86053 | Sustaining | 2020-11-20 | 2025-05-14 | 18.93 | [5 empty] | 0.314 | 0
35 | Niagara | Sir Adam Beck 2 | SAB2 Headgate Replt. | 86376 | Sustaining | 2021-03-18 | 2024-09-30 | 23.3 | [5 empty] | 0 | 0
36 | Niagara | Sir Adam Beck 2 | SAB2 Rock Cliff Conc. Rehab | 86491 | Sustaining | 2021-07-06 | 2024-12-09 | 22.84 | [5 empty] | 2.4 | 0
37 | Niagara | Sir Adam Beck 2 | Battery Banks and DC System Upgrade | 80812 | Sustaining | 2018-07-27 | 2024-02-27 | 11.9 | [5 empty] | 0 | 0
38 | Western | Alexander | Stn. Switchgear, Protections & Ctrls. Repl. | 82378 | Sustaining | 2018-11-23 | 2023-12-01 | 27.5 | [5 empty] | 1.1 | 0
39 | Western | Cameron Falls | T1 & T2 Replacement | 82390 | Sustaining | 2020-02-05 | 2025-02-24 | 25.05 | [5 empty] | 7 | 0
40 | Niagara | Sir Adam Beck 2 | BK2 Penstock Concrete Restoration | 87951 | Sustaining | 2024-06-14 | 2026-08-25 | 24.7 | [5 empty] | 15.6 | 9
41 | Western | Caribou Falls | CAF 120/208V & Lighting Upgrade | 84432 | Sustaining | 2021-09-15 | 2024-01-23 | 10.225 | [5 empty] | 0.4 | 0
42 | Eastern | R.H. Saunders | SAU - Concrete Rehabilitation | 89543 | Sustaining | 2024-12-17 | 2026-10-01 | 16.55 | [5 empty] | 7 | 0.8
43 | Eastern | Bingham Chute | Bingham Chute GS Redevelopment | 86385 | Value Enhancing (Redevelopment) | 2021-06-24 | 2027-04-15 | 24 | [5 empty] | 0 | 23.5
44 | Eastern | Crystal Falls | Crystal Falls Elect./Controls Upgrade | 82261 | Sustaining | 2020-11-10 | 2026-11-12 | 20.8 | [5 empty] | 0 | 16.2
45 | Eastern | Stewartville | STW - G5 Cap. Refurb. - Rwnd Gen. & Reinsul. | 82351 | Sustaining (Refurbishment) | 2024-10-10 | 2027-05-31 | 19.14 | [5 empty] | 0 | 0
46 | Eastern | Otto Holden | OTO - New Turbine Runners | 83356 | Value Enhancing (Refurbishment) | 2017-01-30 | 2030-04-30 | 15.54 | [5 empty] | 0 | 0
47 | Eastern | R.H. Saunders | SAU - Headgate Control Replacement | 86220 | Sustaining | 2023-11-27 | 2030-12-19 | 19.03 | [5 empty] | 0.82987 | 1.9
48 | Eastern | Coniston | Wanapitei Civil Upgrades | 86310 | Sustaining | 2021-12-21 | 2026-11-27 | 29.1 | [5 empty] | 4.1 | 18.3
49 | Eastern | R.H. Saunders | SAU - Long Sault Dam Superstructure Automation (JW) (NYPA) | 87140 | Regulatory | 2023-03-01 | 2029-12-31 | 19.06 | [5 empty] | 0 | 0
50 | Eastern | R.H. Saunders | SAU - 13.8KV Underground Feeder Eval. (JW) (NYPA) | 87141 | Regulatory | 2023-03-01 | 2025-12-31 | 20.8 | [5 empty] | 0 | 0
51 | Eastern | Otto Holden | OTO - G1 Refurb - Turbine & Generator | 87545 | Sustaining (Refurbishment) | 2025-01-30 | 2027-04-30 | 13.3 | [5 empty] | 0 | 0
52 | Eastern | Abitibi Canyon | ABI - Powerhouse Crane Refurb / Replace | 89078 | Sustaining | 2024-12-12 | 2028-05-15 | 20.5 | [5 empty] | 0 | 0
53 | Eastern | Abitibi Canyon | ABI - Unloading Crane Refurb/Replacement | 89079 | Sustaining | 2024-11-29 | 2028-01-30 | 15.26 | [5 empty] | 0 | 0
54 | Western | Silver Falls | SLV Electrical Infrastructure Replacement | 82005 | Sustaining | 2021-03-18 | 2028-10-18 | 18.7631 | [5 empty] | 0 | 0
55 | Western | Caribou Falls | CAF Electrical Infrastructure Replacement | 84430 | Sustaining | 2021-03-18 | 2027-12-03 | 23.4821 | [5 empty] | 0 | 0
56 | Western | Manitou Falls | MOT T1 Replacement | 84436 | Sustaining | 2022-04-27 | 2027-02-24 | 12.6 | [5 empty] | 0 | 0
57 | Western | Whitedog Falls | WHD Electrical Infrastructure Replacement | 84448 | Sustaining | 2021-03-18 | 2028-10-13 | 23.6306 | [5 empty] | 0 | 0
58 | Western | Pine Portage | Black Sturgeon Dam | 86369 | Sustaining | 2021-02-15 | 2031-12-15 | 17.1353 | [5 empty] | 0 | 0
59 | Western | Aguasabon | G2 Rewind & Core Replacement | 86383 | Sustaining (Refurbishment) | 2021-08-09 | 2025-10-10 | 17.521 | [5 empty] | 16.6 | 0
60 | Western | Cameron Falls | CAM - Block Dam 3-4 Life Extension | 89000 | Sustaining | 2025-06-12 | 2027-12-12 | 15.4239 | [5 empty] | 5 | 0
61 | Niagara | Sir Adam Beck 2 | SAB OH Site Prep and Facility Rehab | 86379 | Sustaining | 2021-08-31 | 2026-02-27 | 17.68 | [5 empty] | 15.7 | 0
62 | Niagara | Sir Adam Beck 2 | BK2 Phse. Cranes Replacement | 89025 | Sustaining | 2025-01-13 | 2031-01-07 | 14.712 | [5 empty] | 0 | 0
63 | Eastern | Arnprior | ARN - Repl. AC Stn. Serv. Switchgear & Brkrs. | 80951 | Sustaining | 2022-07-14 | 2025-09-25 | 14.32 | [5 empty] | 5.4 | 0
64 | Niagara | Sir Adam Beck Pump GS | Hatchcover and Drive System | 82210 | Sustaining | 2024-04-11 | 2026-02-19 | 11.79 | [5 empty] | 5 | 1.3
65 | Eastern | Mountain Chute | MTN - Repl. AC Sta. Serv. Trnsfrmrs Switch | 82987 | Sustaining | 2022-07-14 | 2028-03-30 | 11.7 | [5 empty] | 0 | 7.3
66 | Eastern | Abitibi Canyon | Abitibi - Breaker Roof Replt. | 83153 | Sustaining | 2023-03-20 | 2026-11-07 | 10.8 | [5 empty] | 0.5 | 8
67 | Western | Cameron Falls | CAM G7 Capital Refurb | 83257 | Sustaining (Refurbishment) | 2019-08-12 | 2026-12-08 | 29.4 | [5 empty] | 0 | 25.3
68 | Eastern | R.H. Saunders | SAU - Repl. Iroquois Dam 2 Cranes (JW) (OPG) | 86586 | Sustaining | 2024-05-07 | 2028-12-21 | 20.1 | [5 empty] | 0 | 8.5
69 | Eastern | Barrett Chute | BAR - G2 Cap. Rfrb; Rwnd Gen. Reins. Fld. Pls. | 86077 | Sustaining (Refurbishment) | 2020-07-17 | 2025-04-07 | 10.475 | [5 empty] | 10.5 | 0
70 | Eastern | Chenaux | CHE - PH Cranes 2 - Cntrls & Cndctr Upgrade | 86200 | Sustaining | 2021-12-20 | 2025-09-04 | 11.053 | [5 empty] | 8.5 | 0
71 | Niagara | Sir Adam Beck 2 | SAB2 N and S Phse Cranes | 86438 | Sustaining | 2020-09-25 | 2025-08-29 | 10.544 | [5 empty] | 0.5 | 0
72 | Eastern | Otto Holden | OTO - G8 Refurb - Turbine & Generator | 86477 | Sustaining (Refurbishment) | 2023-02-22 | 2025-04-11 | 13.6 | [5 empty] | 12.1 | 0
73 | Eastern | Otto Holden | OTO - G6 Refurb - Turbine & Generator | 86478 | Sustaining (Refurbishment) | 2024-02-07 | 2026-05-29 | 10.742 | [5 empty] | 0 | 10
74 | Western | Caribou Falls | CAF Block Dam 4 Rehabilitation | 86602 | Sustaining | 2021-07-28 | 2024-10-23 | 10.4 | [5 empty] | 0.9 | 0
75 | Eastern | Stewartville | STW - Access Rd and Bank Stabilization | 89572 | Sustaining | 2025-03-26 | 2026-06-26 | 10.68 | [5 empty] | 6.8 | 0.9
76 | Eastern | Arnprior | ARN - Replace T1 Main Output Transformer | 87513 | Sustaining | 2024-12-16 | 2029-10-16 | 11.95 | [5 empty] | 0 | 0
77 | Niagara | Sir Adam Beck Pump GS | BKP Headworks Crane Replacement | 86920 | Sustaining | 2023-12-19 | 2027-10-22 | 19.6 | [5 empty] | 0 | 0
78 | Eastern | Des Joachims | DEJ - Headpond and Tailrace Booms | 86204 | Regulatory | 2022-08-08 | 2028-09-30 | 10.8 | [5 empty] | 0 | 0
79 | Niagara | Sir Adam Beck 2 | BK2 Hoist Refurbishment G11-18 | 84568 | Sustaining | 2020-09-23 | 2036-09-29 | 17.7 | [5 empty] | 0 | 0
80 | Eastern | R.H. Saunders | Runner Replacement | 83104 | Value Enhancing (Refurbishment) | 2016-08-22 | 2028-03-31 | 17.9 | [5 empty] | 10 | 2.8
81 | Eastern | Abitibi Canyon | Canyon Dam Downstream Concrete Rehab | 87192 | Sustaining | 2023-05-04 | 2026-02-11 | 24.8 | [5 empty] | 1.4 | 2.3
|  |  | Total Regulated Hydroelectric |  |  |  |  | 1396.653 |  |  |  |  | 295.0133 | 147.3439 | 140.5