## Table 1a
D2-AMPCO-28
Ref: D2-1-3 Table 1a
Capital Project Listing - OPG Nuclear Facilities Projects
Projects ≥ $30M Total Project Cost (Allocated)
Drivers of Variance
|  | ONGOING PROJECTS FROM EB-2020-0290 | Project # | BCS Tab # | Category | Start Date | Final In-Service Date | Final In-Service Date from 1st Execution BCS | Total Project Cost 0297 ($M) | Total Project Cost (TPC) 0290 ($M) | Variance $ | Variance % | First Execution BCS ($M) | Variance TPC 0297 to BCS ($M) | First Execution BCS 0290 ($M) | Total In-Service 0297 ($ M) | Total In-Service 0290 ($M) | In-Service LTD ($M) | In-Service 2025 ($M) | In-Service 2026 ($M) | Forecast In-Service IR Term ($M) | SPI = EV/PV | Schedule Variance (SV) = PV-EV | CPI = EV/AC | Cost Variance = EV-AC | Variance TPC 2097 to TPC 0290 ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | DN | DN Class II Uninterruptable Power Supply Replacement | 31412 | 1 | Sustaining | 2011-01-01 | 2027-02-01 |  | 69.3972 | 63.634 | 5.7632 | 9.057% | 38.442 | 30.9552 | 38.442 | 66.927 |  | 57.444 | 0.5 | 6.629 | 2.354 |  |  |  |  | 5.7632
2 | DN | DN Station Roofs Replacement | 31524 | 2 | Sustaining | 2012-11-01 | 2024-10-01 |  | 71.6698 | 116.938 | -45.2682 | -38.71% | 72.2 | -0.53019 | N/A | 71.6068 |  | 70.3768 | 1.23 | 0 | 0 |  |  |  |  | -45.2682
3 | DN | DN Powerhouse Water Air Condition Units Replacement | 31532 | 3 | Sustaining | 2012-10-01 | 2025-07-01 |  | 38.2112 | 38.179 | 0.032196 | 0.08433% | 26.595 | 11.6162 | 26.595 | 37.6759 |  | 35.9067 | 1.7692 | 0 | 0 |  |  |  |  | 0.032196
4 | DN | DN Water Treatment Plant Interconnections - S | 31535 | 4 | Sustaining | 2011-09-01 | 2024-12-01 |  | 94.8918 | 53.155 | 41.7368 | 78.52% | 58.262 | 36.6298 | N/A | 94.9 |  | 94.9 | 0 | 0 | 0 |  |  |  |  | 41.7368
5 | DN | DN Radiation Detection Equipment Obsolescence | 31544 | 5 | Sustaining | 2014-01-01 | 2026-09-01 |  | 65.3028 | 45 | 20.3028 | 45.12% | 58.19 | 7.1128 | N/A | 63.7554 |  | 53.9384 | 6 | 3.817 | 0 |  |  |  |  | 20.3028
6 | DN | DN Air Conditioning Unit Replacement For Secondary Control Area | 33621 | 6 | Sustaining | 2009-02-01 | 2026-01-01 |  | 47.5869 | 35.957 | 11.6299 | 32.34% | 12.291 | 35.2959 | 12.291 | 43.475 |  | 34.123 | 5.868 | 3.484 | 0 |  |  |  |  | 11.6299
7 | DN | DN Major Pump-Sets Vibration Monitoring System Upgrades | 33819 | 7 | Sustaining | 2006-03-01 | 2027-04-01 |  | 60.5698 | 55.385 | 5.1848 | 9.361% | 12.766 | 47.8038 | 12.766 | 54.619 |  | 46.799 | 3.45 | 1.908 | 2.462 |  |  |  |  | 5.1848
8 | DN | DN Standby Generator Controls Replacement | 33973 | 8 | Sustaining | 2006-12-01 | 2025-07-01 |  | 45.9475 | 46.254 | -0.30651 | -0.6627% | 21.768 | 24.1795 | 21.768 | 45.935 |  | 45.866 | 0.069 | 0 | 0 |  |  |  |  | -0.30651
9 | DN | DN OH180 Aging Management Hardware Installation | 80022 | 9 | Sustaining | 2014-12-01 | 2029-11-01 |  | 60.9 | 60.931 | -0.031 | -0.05088% | 60.93 | -0.03 | 60.93 | 36.9042 |  | 27.8443 | 2.55 | 2.319 | 4.1908 |  |  |  |  | -0.031
10 | DN | DN R22 Refrigerant Air Conditioning Unit Replacement | 80036 | 10 | Regulatory | 2015-12-01 | 2027-01-01 |  | 59.7431 | 50.7 |  |  | 50.7 | 9.0431 | 50.7 | 54.9975 |  | 29.5445 | 7.448 | 12.419 | 5.586 |  |  |  |  | 9.0431
11 | DN | DN Digital Control, Common Process And Sequence Of Events Monitoring Computer Aging Management | 80078 | 11 | Regulatory | 2015-11-01 | 2035-03-01 |  | 156.4 | 77.498 | 78.902 | 101.8% | n/a |  | n/a | 124.3 |  | 3.7952 | 0 | 0.462 | 77.129 |  |  |  |  | 78.902
12 | DN | DN Main Power Output Protection System Replacement | 80122 | 12 | Sustaining | 2016-09-01 | 2028-01-01 |  | 124.9038 | 65 | 59.9038 | 92.16% | 124.904 | -0.000215 | n/a | 111.2703 |  | 18.6913 | 42.31 | 17.359 | 32.91 |  |  |  |  | 59.9038
13 | DN | DN Group II Pressure Transmitter Replacement | 80123 | 13 | Sustaining | 2016-01-01 | 2028-12-01 |  | 43.6907 | 47.748 | -4.0573 | -8.497% | 43.69 | 0.000658 | n/a | 32.4267 |  | 11.7319 | 4.9598 | 5 | 10.735 |  |  |  |  | -4.0573
14 | DN | DN Obsolete Controller Replacement | 80124 | 14 | Sustaining | 2017-06-01 | 2028-12-01 |  | 38.0231 | 38.023 | 0.00011 | 0.0002893% | 38.023 | 0.00011 | 38.023 | 28.466 |  | 19.592 | 1.75 | 2.96 | 4.164 |  |  |  |  | 0.00011
15 | DN | DN Emergency Power Generator 1 And 2 Replacement | 80126 | 15 | Regulatory | 2017-02-01 | 2023-11-01 |  | 178.0382 | 203.8 |  |  | 176.239 | 1.7992 | 176.239 | 174.882 |  | 173.515 | 1.367 | 0 | 0 |  |  |  |  | -25.7618
16 | DN | DN Fuel Handling Computer Input/ Output Subsystem Interprocessor Communication Replacement | 80148 | 16 | Sustaining | 2015-12-01 | 2027-12-01 |  | 40.2134 | 23.445 | 16.7684 | 71.52% | n/a |  | n/a | 32.8523 |  | 6.7857 | 6.0776 | 7.245 | 12.744 |  |  |  |  | 16.7684
17 | DN | DN Fire Resistant Fluid Pump Improvement | 80150 | 17 | Sustaining | 2016-01-01 | 2029-12-01 |  | 55 | 30 | 25 | 83.33% | n/a |  | n/a | 40.8928 |  | 16.1648 | 0 | 0 | 24.728 |  |  |  |  | 25
18 | SEC | Security Project B | 82929 |  | Sustaining | 2016-06-01 | 2025-10-01 |  | 44.3 | 32.747 | 11.553 | 35.28% | 32.747 | 11.553 | 32.747 | 43.1995 |  | 37.1012 | 5.0983 | 1 | 0 |  |  |  |  | 11.553
19 | DN | DN Fuel Handling Head Major Component Replacement | 82947 | 18 | Sustaining | 2018-10-01 | 2028-08-01 |  | 120.0908 | 98.041 | 22.0498 | 22.49% | 120.091 | -0.000165 | n/a | 90.3658 |  | 34.2831 | 11.5337 | 14.889 | 29.66 |  |  |  |  | 22.0498
20 | AIM | DN Rapid Delivery Machine | 83039 | 19 | Sustaining | 2014-11-01 | 2029-07-01 |  | 206.7 | 162.2 | 44.5 | 27.44% | 162.2 | 44.5 | n/a | 181.0195 |  | 59.2955 | 9.419 | 104.454 | 7.851 |  |  |  |  | 44.5
21 | DN | DN Main Output Transformer & Unit Service Transformer Replacement | 83296 | 20 | Sustaining | 2018-07-01 | 2027-12-01 |  | 170 | 170.125 | -0.125 | -0.07348% | 170.125 | -0.125 | 170.125 | 151.0993 |  | 101.5653 | 0 | 0 | 49.534 |  |  |  |  | -0.125
22 | DN | DN Large Moderator Temperature Control Valve Replacement | 83297 | 21 | Sustaining | 2018-11-01 | 2030-01-01 |  | 39.8583 | 36.928 | 2.9303 | 7.935% | 39.858 | 0.000307 | n/a | 36.678 |  | 18.507 | 2.351 | 1.815 | 14.005 |  |  |  |  | 2.9303
23 | DN | DN Secondary System Obsolete Control Valve Replacement | 83298 | 22 | Sustaining | 2018-03-01 | 2027-10-01 |  | 38.3519 | 35.433 | 2.9189 | 8.238% | 38.352 | -6.9e-05 | n/a | 31.4643 |  | 12.725 | 4.7353 | 6.2 | 7.804 |  |  |  |  | 2.9189
24 | DN | DN 4KV Motor Refurbishment And Replacement | 83480 | 23 | Sustaining | 2018-10-01 | 2036-06-01 |  | 146.7924 | 278.792 | -131.9996 | -47.35% | 146.792 | 0.000427 | n/a | 116.1437 |  | 6.887 | 3.9707 | 3.9 | 48 |  |  |  |  | -131.9996
25 | DN | DN Isolated Phase Bus Refurbishment | 83484 | 24 | Sustaining | 2020-07-01 | 2028-07-01 |  | 43.966 | 62.408 | -18.442 | -29.55% | 43.966 | 1.2e-05 | n/a | 30.0656 |  | 5.8186 | 0 | 12.148 | 12.099 |  |  |  |  | -18.442
26 | DN | DN Powerhouse Upper Level Service Water Piping Replacement | 83530 | 25 | Sustaining | 2019-05-01 | 2025-11-01 |  | 82.7 | 85.5 |  |  | 55.698 | 27.002 | 55.698 | 79.133 |  | 60.199 | 15.769 | 3.165 | 0 |  |  |  |  | -2.8
27 | DN | DN Unit 2 Turbine Control & Auxiliary Systems Upgrade | 83664 | 26 | Sustaining | 2019-12-01 | 2028-01-01 |  | 194.5632 | 112.681 | 81.8822 | 72.67% | 194.563 | 0.000156 | n/a | 177.162 |  | 0 | 0 | 0 | 177.162 |  |  |  |  | 81.8822
28 | DN | DN Primary Heat Transport Liquid Relief Valve Modifications (Waterhammer) | 84235 | 27 | Regulatory | 2019-01-01 | 2026-01-01 |  | 86.8 | 86.754 | 0.046 | 0.05302% | 85.941 | 0.859 | 85.941 | 72.3415 |  | 58.4963 | 11.0772 | 2.768 | 0 |  |  |  |  | 0.046
29 | DN | DN Motor Operated Valve Replacements | 84551 | 28 | Sustaining | 2020-03-01 | 2029-12-01 |  | 34.2514 | 44.536 | -10.2846 | -23.09% | 34.25 | 0.001421 | n/a | 26.9933 |  | 10.3353 | 2.41 | 5.771 | 8.477 |  |  |  |  | -10.2846
30 | DN | DN Revenue Metering Transformer Replacement | 84939 | 29 | Regulatory | 2020-04-01 | 2028-07-01 |  | 56.6972 | 35.854 | 20.8432 | 58.13% | 56.697 | 0.00018 | n/a | 48.6983 |  | 8.7441 | 8.4882 | 19.245 | 12.221 |  |  |  |  | 20.8432
|  | Total | [6 empty] | 2515.5606 | 2293.646 | 221.9146 |  | 1976.28 | 287.6672 |  | 2200.2498 |  | 1160.9761 | 160.2011 | 238.957 | 543.8158 |  |  |  |  | 221.9146

## Sheet1
Darlington Water Treatment Plant Lease
Darlington Unit 2 Turbine Control and Auxiliary Systems Upgrade
Tritium Removal Facility Major Component Replacement Program | 84764
Darlington Steam Generator Primary Moisture Separators Replacement Projects | 87151
Pickering Extended Operations
Darlington Non-Routine Steam Generator Cleanings
Darlington Unit 1 and 2 Generator Stator Rewind | 89281
Darlington Turbine Rotors Replacement2 | 87707/87811
Pickering Water Treatment Plant Lease1