## Table 1b
D2-AMPCO-30
Ref: D2-1-3 Table 1b
Capital Project Listing - OPG Nuclear Facilities Projects
|  | Projects ≥ $30M Total Project Cost (Allocated) | [25 empty] | Drivers of Variance
|  | ONGOING PROJECTS FROM EB-2020-0290 | Project # | BCS Tab # | Category | Start Date | Final In-Service Date | Final In-Service Date from 1st Execution BCS | Total Project Cost 0297 ($M) | Total Project Cost 0290 ($M) | Variance $ | Variance % | First Execution BCS ($M) | First Execution BCS 0290 ($M) | Total In-Service 0297 ($ M) | Total In-Service 0290 ($M) | In-Service LTD | In-Service 2025 | In-Service 2026 | Forecast In-Service IR Term | SPI = EV/PV | Schedule Variance (SV) = PV-EV | CPI = EV/AC | Cost Variance = EV-AC | Planned Hours | Earned Hours | Variance Total Project Cost to BCS | Variance: Cost Management ($M) | Variance: Project Management ($M) | Variance: Inspection ($M) | Variance: Engineering ($M) | Variance: Procurement ($M) | Variance: Construction ($M) | Variance: Commissioning ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
31 | DN | DN Shutdown Cooling Heat Exchanger Replacement | 31710 | 30 | Sustaining | 2012-11-01 | 2021-11-01 |  | 85.518 | 111.4 | -25.882 |  | 56.085 | 56.085 | 73.8091 |  | 73.8091 | 0 | 0 | 0 | [6 empty] | 29.433
32 | DN | DN Auxiliary Heating System | 34000 | 31 | Regulatory | 2006-03-01 | 2018-06-01 |  | 106.3597 | 107.149 | -0.78935 |  | 45.607 | 45.607 | 102.6442 |  | 102.6442 | 0 | 0 | 0 | [6 empty] | 60.7527
33 | DN | DN Zebra Mussels Mitigation & Improvements | 38948 | 32 | Sustaining | 2012-11-01 | 2021-12-01 |  | 37.1392 | 36.634 | 0.50519 |  | 21.481 | 21.481 | 37.1392 |  | 37.1392 | 0 | 0 | 0 | [6 empty] | 15.6582
34 | DN | DN RS Primary Heat Transport Pump Motor Replacement4 | 73566, 80144, 36001 | 33 | Sustaining | 2015-07-01 | 2022-10-01 |  | 77.8983 | 84 | -6.1017 |  | 26.7 | 26.7 | 72.0935 |  | 72.0935 | 0 | 0 | 0 | [6 empty] | 51.1983
35 | DN | DN Steam Generator Level Control Valve Replacement | 80023 | 34 | Sustaining | 2015-01-01 | Cancelled |  | 9.3298 | 38.6 | -29.2702 |  | n/a | n/a | 0 |  | 0 | 0 | 0 | 0
36 | DN | DN Primary Heat Transport Pump Motor Overhaul | 80144 | 33 | Sustaining | 2015-07-01 | 2021-12-01 |  | 43.5744 | 53.3 | -9.7256 |  | 102.8 | 102.8 | 42.6119 |  | 42.6119 | 0 | 0 | 0 | [6 empty] | -59.2256
37 | DN | DN Copper Piping Replacement | 83049, 83784, 83819 | 35 | Sustaining | 2016-08-01 | 2023-08-01 |  | 44.3056 | 45.072 | -0.7664 |  | 29.334 | 29.334 | 42.8248 |  | 42.8248 | 0 | 0 | 0 | [6 empty] | 14.9716
|  | Total | [6 empty] | 404.1248 | 476.155 | -72.0302 | 0 | 282.007 | 282.007 | 371.1226 |  | 371.1226 | 0 | 0 | 0 | [6 empty] | 112.7881
-33.4302