## Table 1 c
D2-AMPCO-32
Ref: D2-1-3 Table 1c
Capital Project Listing - OPG Nuclear Facilities Projects
|  | Projects ≥ $30M Total Project Cost (Allocated) | [19 empty] | Cost Driver Variance
|  | PROJECTS NOT IN EB-2020-0290 >$30 M | Project # | Category | BCS Tab # | Start Date | Final In-Service Date | Total Project Cost ($M) | Total Project Cost at D2-1-3 Attachment #1 Tabs 36-55 | Total In-Service Date at D2-1-3 Attachment #1 Tabs 36-55 | First Execution Business Case ($M) | Total In-Service ($M) | In-Service LTD ($M) | In-Service 2025 ($M) | In-Service 2026 ($M) | Forecast In-Service IR Term ($M) | SPI = EV/PV | Schedule Variance (SV) = PV-EV | CPI = EV/AC | Cost Variance = EV-AC | Variance to Approved Project Cost at D2-1-3 Attachment #1 ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | DN | DN Public Address System Upgrade | 31708 | Sustaining | 36 | 2021-10-01 | 2027-03-01 | 51.6288 |  |  | n/a | 40.567 |  | 0 | 17.378 | 23.189
2 | DN | DN Breathing, Instrument and Service Air Compressor Replacement | 83933 | Sustaining | 37 | 2023-02-01 | 2030-02-01 | 64.1 |  |  | n/a | 49.479 |  | 0 | 0 | 49.479
3 | DN | DN Powerhouse Elevator Replacement | 86910 | Sustaining | 38 | 2021-08-01 | 2031-06-01 | 49 |  |  | n/a | 38.701 |  | 6.5 | 6 | 26.201
4 | DN | DN Powerhouse Cranes Refurbishment | 84139 | Sustaining | 39 | 2022-12-01 | 2032-12-01 | 93.1 |  |  | n/a | 72.1 |  | 0 | 0 | 59.2973
5 | DN | DN Vacuum Building Outage Power Operated Valves Replacement | 84552 | Sustaining | 40 | 2023-12-01 | 2028-10-01 | 95.2537 |  |  | n/a | 76.934 |  | 0 | 0 | 76.934
6 | DN | Tritium Removal Facility Major Component Replacement Program | 84764 | Sustaining | 41 | 2021-11-01 | 2038-02-01 | 540.9504 |  |  | n/a | 452 |  | 0 | 0 | 157.645
7 | DN | DN Low Pressure Service Water Strainer Backwash Motorized Valves Replacement | 86280 | Sustaining | 42 | 2025-06-01 | 2028-05-01 | 31.9801 |  |  | n/a | 22.204 |  | 0 | 0 | 22.204
8 | DN | Darlington Steam Generator Moisture Separator Replacement | 86693 | Sustaining | 43 | 2021-10-01 | 2025-12-01 | 359.2 |  |  | 380.829 | 278.6123 |  | 107.977 | 0.5 | 0
9 | DN | DN Motor Operated Valve Replacement Innage | 86795 | Sustaining | 44 | 2023-06-01 | 2029-09-01 | 32.8506 |  |  | n/a | 19.304 |  | 0 | 0 | 19.304
10 | DN | DN Lighting Fixtures Light Emitting Diode Replacement | 86910 | Sustaining | 45 | 2023-04-01 | 2029-02-01 | 39.8805 |  |  | 39.881 | 35.503 |  | 6.5 | 5.4 | 15.683
11 | DN | DN Copper Upgrades Phase III | 86915 | Sustaining | 46 | 2024-12-01 | 2031-04-01 | 38.3007 |  |  | n/a | 34.733 |  | 0 | 6.2 | 28.533
12 | DN | DN Unit 2 and 3 Steam Generator Moisture Separator Replacement | 87151 | Sustaining | 47 | 2025-06-01 | 2027-12-01 | 275 |  |  | 275 | 216.6148 |  | 0 | 81.309 | 135.3058
13 | DN | DN Tritium Removal Facility Cryogenic Refrigeration System Turbine Replacement | 87191 | Sustaining | 48 | 2023-10-01 | 2027-10-01 | 50 |  |  | n/a | 37.122 |  | 0 | 0 | 37.122
14 | DN | DN Turbine Rotors Replacement6 | 87807 87811 | Sustaining | 49 | 2025-03-01 | 2032-07-01 | 2589 |  |  | n/a | 2293.3 |  | 0 | 0 | 1692.711
15 | DN | DN Smartops Sensor Integration | 87808 | Sustaining | 50 | 2024-05-01 | 2030-12-01 | 51.0184 |  |  | n/a | 37.818 |  | 0.856 | 1.644 | 35.318
16 | DN | DN Unit 1 and 2 Generator Stator Rewind | 89281 | Sustaining | 51 | 2025-03-01 | 2030-12-01 | 350 |  |  | n/a | 312.3 |  | 0 | 0 | 312.3
17 | DN | DN Steam Generator Soft Chemical Clean | 89462 | Sustaining | 52 | 2024-12-01 | 2029-02-01 | 77.9404 |  |  | n/a | 59.668 |  | 0 | 20 | 39.668
18 | PN | PN 058 Boiler Room and Turbine Hall Crane Upgrade | 89535 | Sustaining | 53 | 2025-01-01 | 2027-07-01 | 59.6669 |  |  | n/a | 47.338 |  | 0 | 14.469 | 32.869
19 | PN | PN 058 Turbine Auxiliary Building, Reactor Auxiliary Building Hoist & Cranes | 89536 | Sustaining | 54 | 2025-03-01 | 2029-12-01 | 47.7 |  |  | n/a | 36.1 |  | 0 | 9.0196 | 27.0804
20 | PN | P58 Second Simulator and Pickering Learning Centre Extension | 89581 | Regulatory | 55 | 2025-05-01 | 2028-03-01 | 39.6924 |  |  | n/a | 28.8959 |  | 0 | 0 | 28.8959
|  | Total | [5 empty] | 4936.2627 |  |  |  | 4189.2941 |  | 121.833 | 161.9196 | 2819.7395