## Table 2a-2g
D2-AMPCO-34
Ref: D2-3-1 Tables 2a-2g
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)
Cost Driver Variance
Line No. | Facility | Project Name | Project Number | Category | Start Date | Final In-Service Date | Total Project Cost ($M) | Final In-Service Date at time of EB-2020-0290 | Project Cost at time of EB-2020-0290 ($M) | Cost at Execution BCS($M) | Final In-Service Date at Execution BCS | Total In-Service ($M) | Total In-Service LTD ($M) | In-Service 2025 ($M) | In-Service 2026 ($M) | In-Service Term ($M) | SPI = EV/PV | Schedule Variance (SV) = PV-EV | CPI = EV/AC | Cost Variance = EV-AC | Cost Variance ($M) | Variance to Approved Project Cost at D2-1-3 Attachment #1 ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Commissioning ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
ONGOING PROJECTS FROM EB-2020-0290
1 | DN | DN Active Liquid Waste System Upgrade | 31403 | Regulatory | 2009-11-01 | 2026-05-01 | 17.86 | [6 empty] | 0 | 10.923 | 0.079
2 | DN | DN Dryer Programmable Logic Controller Replacement | 31420 | Sustaining | 2014-02-01 | 2026-06-01 | 15.1271 | [6 empty] | 1.4999 | 2.045 | 0.816
3 | DN | DN Replacement Of Obsolete Online Chemistry Analyzers | 31520 | Sustaining | 2012-10-01 | 2024-08-01 | 16.2069 | [6 empty] | 0.112 | 0 | 0
4 | DN | DN Feeder Scanner Replacement | 31526 | Sustaining | 2012-12-01 | 2022-12-01 | 15.3489 | [6 empty] | 0.554 | 0 | 0
5 | DN | DN Fuel Handling Obsolete Control Relay Re-Engineer/Replacement | 31704 | Sustaining | 2013-10-01 | 2026-06-01 | 17.1699 | [6 empty] | 2.9797 | 6.735 | 0
6 | DN | DN Vapour Recovery Button-Up Valve Replacements | 31706 | Sustaining | 2013-12-01 | 2026-01-01 | 23.7005 | [6 empty] | 9.033 | 6.118 | 0
7 | DN | DN Neutron Over-Power Ion Chamber & In-Core Flux Detector Amplifier Replacement (Reactor Regulating System, Shutdown System 1 & Shutdown System 2) | 31716 | Sustaining | 2013-07-01 | 2028-11-01 | 23.8465 | [6 empty] | 3.0705 | 3.51 | 6.859
8 | DN | DN Replacement Of Emergency Power Supply Uninterruptible Power Supply | 33258 | Sustaining | 2010-02-01 | 2024-11-01 | 27.2949 | [6 empty] | 0.245 | 0 | 0
9 | DN | Fuel Handling Computer Replacement | 33815 | Sustaining | 2005-08-01 | 2024-08-01 | 16.7372 | [6 empty] | 0 | 0.424 | 0
10 | DN | DN Digital Control Computer Replacement/ Refurbishment/ Upgrades | 33977 | Sustaining | 2003-09-01 | 2025-05-01 | 29.9 | [6 empty] | 1.254 | 0 | 0
11 | DN | DN Standby Generators Protective Relay Replacement | 80063 | Sustaining | 2015-12-01 | 2026-11-01 | 22.0005 | [6 empty] | 5.312 | 3.979 | 2.482
12 | DN | DN Irradiated Fuel Discharge Mechanism Major Component Repla | 82841 | Sustaining | 2015-11-01 | 2028-12-01 | 10.6982 | [6 empty] | 1.99 | 0.899 | 0.77735
13 | DN | DN Fuel Handling Trolley Major Auxiliary Component Replacement | 82842 | Sustaining | 2017-01-01 | 2028-01-01 | 19.1021 | [6 empty] | 1.6625 | 2.998 | 6.238
14 | DN | DN Class 1 Rectifier Replacement | 82883 | Sustaining | 2018-05-01 | 2028-01-01 | 24.6639 | [6 empty] | 2.104 | 3.606 | 3.961
15 | DN | DN Fuel Handling Motor Replacement | 82886 | Sustaining | 2017-01-01 | 2030-12-01 | 14.6003 | [6 empty] | 0.33763 | 0.69 | 8.947
16 | SEC | Security Project C | 82930 | Sustaining | 2016-06-01 | 2025-06-01 | 29.6738 | [6 empty] | 1.313 | 0 | 0
17 | DN | DN Fuel Handling Power & Signal Cable Catenary Replacement | 83052 | Sustaining | 2019-04-01 | 2027-12-01 | 18.3658 | [6 empty] | 0 | 0 | 0.49
18 | DN | DN Phase 2 Station Battery Replacement | 83076 | Sustaining | 2016-08-01 | 2027-11-01 | 27.7356 | [6 empty] | 3.6688 | 3.859 | 3.294
19 | DN | DN Heavy Water Management System Computer Distributed Control Units Replacement | 83288 | Sustaining | 2018-01-01 | 2027-09-01 | 16.5449 | [6 empty] | 0 | 0 | 11.867
20 | DN | DN Irradiated Fuel Bay Cooling and Purification Pump Replacement | 83483 | Sustaining | 2017-12-01 | 2029-01-01 | 29 | [6 empty] | 2.6281 | 0.919 | 18.791
21 | DN | DN Fuel Handling Service Area Bridge F5 Ball Screw Assembly Replacement | 83558 | Sustaining | 2018-03-01 | 2024-11-01 | 16.6924 | [6 empty] | 0.511 | 0 | 0
22 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 83560 | Sustaining | 2018-05-01 | 2025-12-01 | 12.6906 | [6 empty] | 2.3 | 1.139 | 0
23 | DN | Fleet Monitoring Initiative (Monitoring & Diagnostic Centre) | 83828 | Sustaining | 2018-03-01 | 2026-09-01 | 29.9 | [6 empty] | 3.4875 | 4.782 | 0
24 | DN | DN Fuel Handling Replacement of Fuelling Machine Calibration Facility | 83916 | Sustaining | 2019-02-01 | 2027-11-01 | 18.7648 | [6 empty] | 4.141 | 3.554 | 6.77
25 | DN | DN Shutdown System 1 and Reactor Regulating System Ion Chamber Replacements | 83937 | Sustaining | 2018-12-01 | 2033-07-01 | 11.336 | [6 empty] | 0 | 1.37 | 4.388
26 | DN | DN Fuelling Machine Duct & Central Service Area Air Conditioning Unit Replacement | 84006 | Sustaining | 2019-08-01 | 2029-07-01 | 25.1 | [6 empty] | 0 | 0 | 19.382
27 | DN | DN Air Operated Valve Replacements | 84009 | Sustaining | 2020-03-01 | 2025-12-01 | 18.9512 | [6 empty] | 8.1637 | 1.864 | 0
28 | AIM | PN Circumferential Wet Scrape Tool Enhancements | 84140 | Sustaining | 2019-11-01 | 2023-12-01 | 18.6 | [6 empty] | 0 | 0 | 0
29 | DN | DN Radiation Detection Equipment Obsolescence - Moderator Cover Gas Monitors & Fixed Area Alarming Gamma Monitors | 84399 | Sustaining | 2019-11-01 | 2025-05-01 | 19.2856 | [6 empty] | 4.0131 | 0.32 | 0
30 | DN | DN Radiation Detection Obsolescence- Active Liquid Waste and Liquid Effluent Monitor | 84400 | Sustaining | 2019-11-01 | 2026-04-01 | 19.2084 | [6 empty] | 0 | 13 | 0.176
31 | DN | DN Primary Heat Transport Pump Rotor Inspection and Replacement | 84799 | Sustaining | 2020-05-01 | 2024-07-01 | 28.3722 | [6 empty] | 0 | 0 | 0
32 | DN | DN Main Power Output Transformer Fire Containment System Upgrade | 86055 | Sustaining | 2020-07-01 | 2026-09-01 | 29.8634 | [6 empty] | 9.286 | 2.334 | 1.63
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
33 | DN | DN Pressurizer Heaters and Controllers Replacement | 31422 | Sustaining | 2011-04-01 | 2022-10-01 | 12.1027 | [6 empty] | 0 | 0 | 0
34 | DN | DN Fuel Handling Inverter Replacement | 31426 | Sustaining | 2011-11-01 | 2022-03-01 | 25.1315 | [6 empty] | 0 | 0 | 0
35 | DN | DN Station Fluorescent Lighting Fixtures Retrofit | 31516 | Sustaining | 2012-12-01 | 2023-11-01 | 20.1652 | [6 empty] | 0 | 0 | 0
36 | DN | DN Restore Emergency Service Water and Firewater Margins | 31518 | Regulatory | 2012-12-01 | 2021-01-01 | 22.1833 | [6 empty] | 0 | 0 | 0
37 | DN | DN Tritium Removal Facility Deuterium Make-up System Electrolyzer Replacement | 31522 | Sustaining | 2012-11-01 | 2021-11-01 | 13.9382 | [6 empty] | 0 | 0 | 0
38 | DN | DN Transformer Multi-Gas Analyzer Installation | 31542 | Sustaining | 2012-10-01 | 2020-09-01 | 22.4604 | [6 empty] | 0 | 0 | 0
39 | DN | DN Feedwater Chemistry Control Improvements | 31548 | Sustaining | 2013-11-01 | 2020-11-01 | 11.625 | [6 empty] | 0 | 0 | 0
40 | DN | DN Hydrogen Cooling Temperature Control Valve TCV20 Redesign | 33228 | Sustaining | 2012-11-01 | 2021-11-01 | 12.4373 | [6 empty] | 0 | 0 | 0
41 | DN | DN Chiller Replacement to Reduce Chlorofluorocarbon Emissions | 33631 | Regulatory | 2004-01-01 | 2021-12-01 | 24.0491 | [6 empty] | 0 | 0 | 0
42 | PN | PB Emergency Power Generator and Main Output Power Protective Relay Replace | 40691 | Sustaining | 2012-02-01 | 2021-03-01 | 25.6822 | [6 empty] | 0 | 0 | 0
43 | PN | PA Standby Generator Reliability Upgrades | 40972 | Sustaining | 2012-04-01 | 2024-12-01 | 19.6613 | [6 empty] | 0 | 0 | 0
44 | PN | PN Obsolete Online Chemistry Analyzer Replacement | 40985 | Sustaining | 2013-03-01 | 2021-07-01 | 16.3507 | [6 empty] | 0 | 0 | 0
45 | DN | DN Feeder Scanner Replacement | 80070 | Sustaining | 2014-05-01 | 2025-02-01 | 15.1128 | [6 empty] | 0.20692 | 0 | 0
46 | DN | DN Fire Hazard Assessment and Fire Safe Shutdown Analysis Modifications | 80151 | Regulatory | 2015-11-01 | 2022-10-01 | 17.9666 | [6 empty] | 0 | 0 | 0
47 | DN | DN Vault Cooling Coil Replacement | 82816 | Regulatory | n/a | 2020-10-01 | 16.2044 | [6 empty] | 0 | 0 | 0
48 | DN | DN Main Power Output and Class IV Transformer Control Cabinet Wiring Replacement | 82890 | Sustaining | 2019-01-01 | Deferred | 26.8 | [6 empty] | 0 | 0 | 11.7036
49 | PN | PN P58 Buried Blowdown Piping Replacement | 83072 | Sustaining | 2016-11-01 | 2021-09-01 | 21.3103 | [6 empty] | 0 | 0 | 0
50 | PN | PN U14 Low Pressure Feedheater Heat Exchanger Replacement | 83088 | Sustaining | 2016-05-01 | 2021-02-01 | 22.007 | [6 empty] | 0 | 0 | 0
51 | DN | DN Condenser Steam Discharge Valve Control System Replacement | 83299 | Sustaining | 2019-01-01 | Cancelled | 11.5099 | [6 empty] | 0 | 0 | 0
52 | DN | DN Turbine Hall Crane Controls Upgrade | 83556 | Sustaining | 2017-12-01 | 2020-04-01 | 24.2299 | [6 empty] | 0 | 0 | 0
53 | DN | DN Irradiated Fuel Bay Permanent Fuel Inspection Equipment | 83559 | Regulatory | 2018-03-01 | 2023-05-01 | 23.9047 | [6 empty] | 0.37113 | 0 | 0
54 | PN | PN High Pressure Turbine Spindle Capital Spares | 83668 | Sustaining | 2017-11-01 | 2020-06-01 | 21.3356 | [6 empty] | 0 | 0 | 0
55 | AIM | Steam Generator Manipulator & Automated Tube Plug | 84888 | Sustaining | 2020-03-01 | Deferred | 12.5 | [6 empty] | 0 | 0 | 0
PROJECTS NOT IN EB-2020-0290
56 | DN | DN Frazil Ice and Discharge Gate Replacement | 31554 | Sustaining | 2024-08-01 | 2027-08-01 | 27.0141 | [6 empty] | 0 | 0 | 20.532
57 | DN | DN Glycol Chiller Single Point Vulnerability Removal | 80152 | Sustaining | 2024-06-01 | 2027-06-01 | 17.7959 | [6 empty] | 0 | 0 | 7.069
58 | DN | DN Lake Current Monitoring System Replacement | 83289 | Sustaining | 2021-12-01 | 2026-06-01 | 10.9961 | [6 empty] | 0 | 7.423 | 0.217
59 | DN | DN Turbine Lubricating Oil Cooler Replacement | 83300 | Sustaining | 2025-03-01 | 2029-05-01 | 29.1 | [6 empty] | 0 | 4.899 | 14.128
60 | DN | DN Emergency Service Water & Low Pressure Service Water Expansion Joints Replacement | 83665 | Sustaining | 2021-07-01 | 2028-08-01 | 13.9 | [6 empty] | 0 | 0 | 10.538
61 | DN | DN Tritium Removal Facility/ Heavy Water Management Interim Lifecycle Plan Implementation | 83669 | Sustaining | 2021-01-01 | 2026-05-01 | 29.8886 | [6 empty] | 18.108 | 10.044 | 0
62 | DN | DN Active Liquid Waste Tank Liner Replacement | 83918 | Sustaining | 2025-04-01 | 2029-05-01 | 16.9694 | [6 empty] | 0 | 0 | 11.226
63 | DN | DN Condenser Water Box Isolation From Discharge Duct | 84134 | Sustaining | 2020-10-01 | Aug-24 (Complete) | 14.7605 | [6 empty] | 0 | 0 | 0
64 | DN | DN Vault Vapour Recovery System Component Replacement | 84138 | Sustaining | 2021-02-01 | 2025-03-25 | 21.7567 | [6 empty] | 1.5059 | 0 | 0
65 | DN | DN Inactive Drainage Sump Pump Replacement | 84300 | Sustaining | 2024-12-01 | 2029-08-01 | 19.2422 | [6 empty] | 1.563 | 5.4 | 9.442
66 | DN | DN Low Pressure Service Water Heat Exchanger Coil Replacement | 84301 | Sustaining | 2022-05-01 | 2028-02-01 | 11.7911 | [6 empty] | 1.3268 | 2.873 | 5.235
67 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 84308 | Sustaining | 2024-12-01 | 2027-01-01 | 14.8856 | [6 empty] | 0 | 0 | 11.423
68 | DN | DN Emergency Service Water Travelling Screen, Motor and Bubbler Replacement | 84312 | Sustaining | 2025-04-01 | 2028-03-01 | 10.1924 | [6 empty] | 0 | 1 | 7.291
69 | AIM | AIM Advanced Non-Destructive Examination MK3 Inspection Tool | 86043 | Sustaining | 2023-08-01 | 2027-12-01 | 19.0092 | [6 empty] | 0 | 0 | 16.085
70 | DN | DN Steam Generator Waterlancing Optimization | 86086 | Sustaining | 2022-08-01 | 2026-01-01 | 12.9299 | [6 empty] | 1.293 | 7.954 | 0
71 | DN | DN Fuelling Machine Head Gap Air Sensing Package | 86302 | Sustaining | 2021-03-01 | 2029-12-01 | 14.8804 | [6 empty] | 0 | 1.803 | 6.048
72 | AIM | AIM Connectorized Umbilical Cable | 86520 | Sustaining | 2024-06-01 | 2028-09-01 | 11.9518 | [6 empty] | 0 | 0 | 8.235
73 | DN | DN Fuelling Machine Trolley Air Compressor Replacement | 86553 | Sustaining | 2024-03-01 | 2027-09-01 | 17.1379 | [6 empty] | 0 | 0 | 10.102
74 | PN | PN Irradiated Fuel Bay Heat Exchanger Replacement | 86831 | Sustaining | 2022-06-01 | Dec-23 (Complete) | 12.1286 | [6 empty] | 0 | 0 | 0
75 | DN | DN Electrical Signature Analysis Monitoring 13.2KV And 4KV Motors | 87342 | Value Enhancing | 2024-05-01 | 2030-05-01 | 13.7175 | [6 empty] | 0 | 1.495 | 7.301
76 | DN | DN Sensor Development | 87698 | Sustaining | 2024-04-01 | 2026-06-01 | 13.4269 | [6 empty] | 5.9129 | 7.203 | 0
77 | DN | DN Main Control Room and Simulators Renovation | 87806 | Value Enhancing | 2024-12-01 | 2030-06-01 | 16.4868 | [6 empty] | 0 | 0 | 12.807
78 | PN | PN Emergency Response Team Garage | 87809 | Sustaining | 2024-05-01 | 2025-06-01 | 17.5845 | [6 empty] | 9.711 | 0 | 0
79 | PN | PN Polychlorinated Biphenyl Lighting 5-8 | 87845 | Regulatory | 2023-12-01 | 2025-12-01 | 25 | [6 empty] | 7.436 | 0 | 0
80 | DN | DN Turbine Protection Reliability Improvement | 87920 | Sustaining | 2023-12-01 | 2027-08-01 | 19.3065 | [6 empty] | 1.674 | 2.619 | 1.822
81 | DN | Darlington Site Shoreline Protection | 87998 | Sustaining | 2025-03-01 | 2026-08-01 | 12.8335 | [6 empty] | 0 | 9.949 | 0
82 | DN | DN Generator Rotor Refurbishment | 89305 | Sustaining | 2025-03-01 | 2029-08-01 | 25.4 | [6 empty] | 0 | 0 | 18.259
83 | DN | DN Atmospheric Steam Discharge Valve Silencers Replacement | 89591 | Sustaining | 2025-03-01 | 2025-08-27 | 12.674 | [6 empty] | 1.4 | 3.1 | 6.098
84 | PN | PN Class 1 & 2 Battery Bank Replacement | 89865 | Sustaining | 2025-05-01 | 2033-06-01 | 29.7574 | [6 empty] | 0 | 2.5 | 18.4
|  | Total |  |  |  |  | 1615.5273 | [6 empty] | 120.175 | 143.33 | 310.9089