## HE Capital
D1-AMPCO-13 |  |  | Filed: 2026-04-22
EB-2025-0297
Ref: D1-1-2 Table 1 |  |  | Exhibit L
D1-AMPCO-013
| Capital Project Listing - Hydroelectric |  | Attachment 1
| Projects ≥ $30M Total Project Cost (Allocated) | [21 empty] | Drivers of Variance to First Execution BCS
Line No. | Region | Facility | Project Name | Project # | BCS Tab # | Category | Start Date | Final In-Service Date | Total Project Cost ($M) | Cost at First Execution BCS ($M) | Final In-Service Date at First Execution BCS | Total In-Service ($ M) | In-Service LTD ($M) | In-Service IR Term ($ M) | In-Service 2025 ($M) | In-Service 2026 ($M) | SPI = EV/PV | Schedule Variance (SV) = EV-PV (hours) | Schedule Variance (SV) = EV-PV ($M) | CPI = EV/AC | Cost Variance = EV-AC | Cost Variance to First Execution BCS ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | Eastern | Calabogie | Calabogie GS - Redevelopment | 82089 | 6 | Value Enhancing (Redevelopment) | 2017-01-31 | 2023-10-25 | 167.204 | 136.5 | 2022-12-31 | 165.552 | 165.682 | 0 | -0.13 | 0 | n/a | n/a | n/a | n/a | n/a | 30.704 | 7 | 0.9 | 17.3 | -10.6 | -3 | 19.1 | Others: Inspection, Procurement, Commissioning and Closeout
2 | Niagara | DeCew Falls 2 | G2 Overhaul & Upgrade | 80851 | 4 | Sustaining (Refurbishment) | 2015-02-05 | 2019-07-01 | 35.5 | 38.1 | 2018-02-14 | 34.944 | 34.944 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -2.6 | n/a | n/a | n/a | n/a | n/a | n/a
3 | Niagara | Sir Adam Beck 1 | BK1 G1/G2 Replacement | 84185 | 17 | Value Enhancing (Expansion) | 2019-02-25 | 2022-10-05 | 122.765 | 119.708 | 2022-03-07 | 112.851 | 112.851 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 3.057 | n/a | n/a | n/a | n/a | n/a | n/a | Others: Inspection, Procurement, commissioning, Contractor Fees and closeout
4 | Niagara | Sir Adam Beck 1 | SAB1 Canal Isolation Preparedness Phase 1 (SAB1 CIP1) | 89252 | 42 | Sustaining (Canal Rehabilitation) | 2025-07-11 | 2029-12-01 | 65 | n/a | n/a | 65 | 0 | 65 | 0 | 0 | 1.0035 | 72.5 | n/a | 1.1 | 0.43136 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
5 | Niagara | Sir Adam Beck Pump Generating Station | Sir Adam Beck Pump GS - Reservoir Refurbishment | 80583 | 2 | Sustaining | 2011-09-19 | 2017-04-01 | 48.689 | 58.2 | 2017-03-31 | 48.689 | 48.689 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -9.511 | n/a | n/a | n/a | n/a | n/a | n/a
6 | Niagara | Sir Adam Beck 1 | Sir Adam Beck I GS - G10 Major Overhaul & Upgrade | 80649 | 3 | Sustaining (Refurbishment) | 2013-10-18 | 2017-06-09 | 30.81 | 27 | 2016-07-30 | 30.165 | 30.165 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 3.81 | -0.371 | 0.0233 | 5.3277 | -2.427 | 1.1476 | 0.1095 | Others: Procurement
7 | Western | Ranney Falls | Ranney Falls Expansion Project | 80581 | 1 | Value Enhancing (Expansion) | 2011-09-19 | 2022-06-01 | 74.5 | 77.3 | 2019-12-31 | 74.496 | 74.496 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -2.8 | n/a | n/a | n/a | n/a | n/a | n/a | Others: Inspection, Procurement, Commissioning and Closeout
8 | Niagara | Sir Adam Beck 1 | Sir Adam Beck 1 GS - Unit G5 Upgrade | 82777 | 10 | Sustaining (Refurbishment) | 2018-05-03 | 2021-09-23 | 44.675 | 19.971 | 2020-07-29 | 43.393 | 43.393 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 24.704 | 8.8375 | 1.1489 | 20.249 | -2.829 | 1.16 | -3.8625 | Others - Procurement, Consultants, OPG other Costs
9 | Eastern | Abitibi Canyon | Abitibi - G2 Capital Upgrades/HG | 83155 | 12 | Sustaining (Refurbishment) | 2019-02-01 | 2022-03-01 | 30.105 | 37.05 | 2021-05-15 | 29.508 | 29.233 | 0 | 0.275 | 0 | 1 | n/a | 0 | 1 | 0.3 | -6.945 | n/a | n/a | n/a | n/a | n/a | n/a
10 | Eastern | Otter Rapids | Otter Project Camp | 84907 | 21 | Sustaining | 2020-06-08 | 2024-07-16 | 39.47 | 39.472 | 2024-04-07 | 38.954 | 38.554 | 0 | 0.4 | 0 | n/a | n/a | n/a | n/a | n/a | -0.002 | 0 | 0 | 0 | 0 | 0 | 0
11 | Eastern | Frederick House6 | Frederick House Lake Dam Upgrades | 83194 | 14 | Sustaining | 2021-10-29 | 2025-12-31 | 90 | 90 | 2025-09-30 | 79.9 | 35.3 | 0 | 37.4 | 7.2 | 0.96844 | -22280.2876 | n/a | 0.99 | -0.89939 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Eastern | R.H. Saunders | SAU - G9 Capital Refurbishment | 83495 | 15 | Sustaining (Refurbishment) | 2020-12-16 | 2025-08-22 | 42.688 | 17.2 | 2024-02-20 | 38.4 | 0 | 0 | 37 | 1.4 | 0.99 | -1701 | n/a | 1.02 | 0.605 | 25.488 | 2.036 | 3.793 | 6.799 | 1.697 | 1.242 | 9.949 | Others: $2.4M - procurement, commisioning and closeout; $7.5M due to lack of in-sufficient category-level data on first execution BCS.
13 | Eastern | Chenaux | CHE - Limerick Isl. Spr Structure Sluice Gate Hoist | 84494 | 19 | Regulatory | 2019-05-27 | 2023-11-30 | 32.7 | 32.701 | 2023-11-30 | 28.84 | 28.84 | 0 | 0 | 0 | 1 | n/a | -0.074 | 1.01 | 0.26 | -0.001 | n/a | n/a | n/a | n/a | n/a | n/a
14 | Eastern | Otter Rapids | Otter G2 Capital Upgrade | 82543 | 9 | Sustaining (Refurbishment) | 2020-08-14 | 2025-12-15 | 78.05 | 43.1 | 2025-04-30 | 70.069 | 7.769 | 0 | 61.9 | 0.4 | 0.99 | n/a | -0.98 | 0.93 | -5.4 | 34.95 | -0.6 | 1.1 | 31.8 | -3.4 | 0.3 | 5.8
15 | Eastern | Coniston/Stinson | Coniston/Stinson GS Redevelopment | 82087 | 5 | Value Enhancing (Redevelopment) | 2019-03-28 | 2027-04-01 | 177.99 | 178 | 2027-04-01 | 176.4 | 0 | 45.9 | 0 | 130.5 | 0.92652 | -56688.8734 | n/a | 1 | 0.34178 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0
16 | Western | Kakabeka Falls | Kakabeka Falls GS Redevelopment | 86386 | 24 | Value Enhancing (Redevelopment) | 2021-03-22 | 2028-05-05 | 519 | 519 | 2028-05-05 | 511 | 0 | 487.1 | 12.7 | 11.2 | 0.91629 | -113393.0741 | n/a | 0.97 | -6.182 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Niagara | Sir Adam Beck 2 | BK2 G20/G19 Refurbishment | 87768 | 41 | Sustaining (Refurbishment) | 2019-10-31 | 2029-02-10 | 377.5 | n/a | n/a | 353 | 0 | 353 | 0 | 0 | 1.01 | 4833.8815 | n/a | 1.01 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
18 | Eastern | Matabitchuan | Matabitchuan GS Redevelopment | 86387 | 25 | Value Enhancing (Redevelopment) | 2022-11-16 | 2028-08-07 | 190 | 190 | 2028-08-07 | 187.55 | 4.2 | 183.4 | 4.2 | 0 | 1.0008 | 162.5763 | n/a | 1.02 | 0.93082 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
19 | Eastern | R.H. Saunders | SAU - G12 Capital Refurbishment | 86587 | 27 | Sustaining (Refurbishment) | 2022-06-14 | 2026-06-09 | 30.38 | 30.38 | 2026-01-09 | 26.9 | 0 | 0 | 0 | 26.9 | 0.9 | n/a | -2.842 | 0.93 | -1.767 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
20 | Eastern | Otter Rapids | Otter G1 Capital Upgrade | 82542 | 8 | Sustaining (Refurbishment) | 2019-02-21 | 2026-12-10 | 40.664 | 40.7 | 2026-12-10 | 35.8 | 0 | 1.8 | 0 | 34 | 1.12 | n/a | 0.7 | 1.12 | 0.7 | -0.036 | n/a | n/a | n/a | n/a | n/a | n/a
21 | Eastern | Abitibi Canyon | ABI - G1 Capital Upgrades | 83148 | 11 | Sustaining (Refurbishment) | 2025-03-06 | 2031-01-30 | 54.67 | n/a | n/a | 46.8 | 0 | 46.8 | 0 | 0 | 0.98 | n/a | 0 | 0.98 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
22 | Eastern | R.H. Saunders | SAU - Long Sault Dam Capital Program (JW)(NYPA) | 86595 | 28 | Regulatory | 2023-03-01 | 2033-12-31 | 88.01 | n/a | n/a | 74.8085 | 0 | 45.3 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
23 | Eastern | R.H. Saunders | SAU - Massena Canal Dam (JW)(NYPA)(CAP) | 87142 | 33 | Regulatory | 2015-05-29 | 2029-12-31 | 47.31 | n/a | n/a | 39.1 | 0 | 39.1 | 0 | 0 | n/a | n/a | -3 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
24 | Eastern | Abitibi Canyon | Abitibi Canyon Concrete Repair Zone 7 | 89505 | 44 | Sustaining (Abitibi Concrete) | 2024-12-10 | 2026-04-30 | 35.6 | 35.6 | 2026-04-30 | 26.4 | 1.4 | 0 | 0 | 25 | 1.0379 | n/a | 0.85751 | 1.03 | 0.68035 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
25 | Eastern | Otto Holden | OTO - Refurbish Stop Log Sluice Piers | 89354 | 43 | Sustaining | 2024-10-10 | 2036-09-30 | 107.95 | n/a | n/a | 91.7575 | 0 | 51.3 | 0 | 0 | 0.86 | n/a | -0.2 | 0.91 | -0.02 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
26 | Western | Alexander | G1 Capital Refurb | 82391 | 7 | Sustaining (Refurbishment) | 2023-04-30 | 2030-09-23 | 45.8888 | n/a | n/a | 42 | 0 | 42 | 0 | 0 | 0.77 | n/a | -0.022554 | 1.1 | -0.001592 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
27 | Western | Silver Falls | Surge Tank Replacement | 83833 | 16 | Sustaining | 2021-03-15 | 2028-12-15 | 40.6954 | n/a | n/a | 38.8 | 0 | 38.8 | 0 | 0 | 0.44 | n/a | -0.476 | 0.56 | -0.296 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
28 | Western | Northwest Operations7 | NWO Work Centre Building | 84901 | 20 | Sustaining | 2020-02-26 | 2027-08-27 | 44.4 | n/a | n/a | 39.9 | 0 | 39.9 | 0 | 0 | 0.94 | n/a | -0.8 | 1.16 | 1.2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
29 | Western | Alexander | G2 Capital Refurb | 86792 | 29 | Sustaining (Refurbishment) | 2023-04-30 | 2027-08-16 | 49.7319 | n/a | n/a | 43.5 | 0 | 43.5 | 0 | 0 | 0.96 | n/a | -0.14 | 1.31 | 0.72 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
30 | Western | Alexander | G3 Capital Refurb | 86793 | 30 | Sustaining (Refurbishment) | 2023-06-13 | 2031-12-20 | 43.6394 | n/a | n/a | 41.5 | 0 | 40 | 0 | 0 | 0.1 | n/a | -0.12282 | 1 | -4.1e-05 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
31 | Western | Manitou Falls | MAN G3 Capital Refurb | 86860 | 31 | Sustaining (Refurbishment) | 2024-12-03 | 2029-05-29 | 53.2184 | n/a | n/a | 48 | 0 | 48 | 0 | 0 | 0.93 | n/a | -0.06 | 1 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
32 | Western | Aguasabon | Aguasabon Dam Rehab. Hayes Lake Main Dam | 87217 | 35 | Sustaining | 2023-08-14 | 2033-12-20 | 116.4634 | n/a | n/a | 110 | 0 | 70 | 0 | 0 | 0.57 | n/a | -0.33747 | 1 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
33 | Niagara | Sir Adam Beck 1 | SAB1 Station Service Upgrade | 86364 | 22 | Sustaining | 2020-12-15 | 2030-01-24 | 33.4359 | n/a | n/a | 31.8 | 0 | 31.8 | 0 | 0 | 0.94 | -3872.0672 | n/a | 0.88 | -0.88 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
34 | Niagara | Sir Adam Beck 1 | BK1 G6 G8 Refurbishment | 86372 | 23 | Sustaining (Refurbishment) | 2024-05-24 | 2030-04-10 | 232.3075 | n/a | n/a | 226.2 | 0 | 226.2 | 0 | 0 | 0.96 | -2335 | n/a | 1.11 | 1.0128 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
35 | Niagara | Sir Adam Beck 1 | BK1 G4 Refurbishment | 86570 | 26 | Sustaining (Refurbishment) | 2022-05-20 | 2027-06-08 | 109.129 | 109.1 | 2027-06-08 | 96.7 | 0 | 96.7 | 0 | 0 | 0.99 | -2350.5246 | n/a | 1.04 | 1.5239 | 0.029 | n/a | n/a | n/a | n/a | n/a | n/a
36 | Niagara | Sir Adam Beck 2 | BK2 G18 G17 Refurbishment | 87356 | 37 | Sustaining (Refurbishment) | 2025-05-22 | 2030-11-30 | 361.1 | n/a | n/a | 344.2 | 0 | 344.2 | 0 | 0 | 1.02 | 1006.1685 | n/a | 1.19 | 0.58 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
37 | Niagara | Sir Adam Beck 2 | BK2 G14 G13 Refurbishment | 87357 | 38 | Sustaining (Refurbishment) | 2025-05-25 | 2032-07-08 | 375.5516 | n/a | n/a | 360.8 | 0 | 0 | 0 | 0 | 0.69 | -13954.1555 | n/a | 1.07 | 0.185 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
38 | Eastern | R.H. Saunders | SAU - G16 Capital Refurbishment | 86937 | 32 | Sustaining (Refurbishment) | 2024-11-29 | 2028-02-08 | 49.3 | n/a | n/a | 38.7 | 0 | 38.7 | 0 | 0 | 1.1 | n/a | 0.173 | 1.02 | 0.044 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
39 | Niagara | Sir Adam Beck 2 | BK2 230kV Conductor Replacement | 87362 | 39 | Sustaining | 2025-03-25 | 2039-08-12 | 35.9234 | n/a | n/a | 29.8 | 0 | 9.6 | 0 | 0 | 0.93 | -87.3918 | n/a | 0.92 | -0.016 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
40 | Eastern | R.H. Saunders | SAU - Long Sault Dam Downstream Concrete (JW) (NYPA) | 87575 | 40 | Regulatory | 2024-06-11 | 2038-12-31 | 38.38 | n/a | n/a | 32.623 | 0 | 20.2 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  |  | Total Regulated Hydroelectric | [5 empty] | 4200.3947 |  |  | 3954.8 | 655.516 | 2408.3 | 153.745 | 236.6