## Table 2a-2g
D2-AMPCO-34 |  |  |  | Filed: 2026-04-22
EB-2025-0297
Ref: D2-1-3 Tables 2a-2g |  |  |  | Exhibit L
D2-AMPCO-034
Capital Project Listing - OPG Nuclear Facilities Projects |  |  |  | Attachment 1
Projects $10M - $30M Total Project Cost (Allocated)
Cost Driver Variance
Line No. | Facility | Project Name | Project Number | Category | Start Date | Final In-Service Date | Total Project Cost ($M) | Final In-Service Date at time of EB-2020-0290 | Project Cost at time of EB-2020-0290 ($M) | Cost at Execution BCS($M) | Final In-Service Date at Execution BCS | Total In-Service ($M) | Total In-Service LTD ($M) | In-Service 2025 ($M) | In-Service 2026 ($M) | In-Service Term ($M) | SPI = EV/PV | Schedule Variance (SV) = PV-EV (hours) | Schedule Variance (SV) = PV-EV ($M) | CPI = EV/AC | Cost Variance = EV-AC ($M) | Cost Variance ($M) | Variance to Approved Project Cost at D2-1-3 Attachment #1 ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Commissioning ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
ONGOING PROJECTS FROM EB-2020-0290
1 | DN | DN Active Liquid Waste System Upgrade | 31403 | Regulatory | 2009-11-01 | 2026-05-01 | 17.86 | Dec-22 | 12.1 | 12.076 | 2014-01-30 | 15.205 | 4.203 | 0 | 10.923 | 0.079 | 1.0034 | 277.411 | n/a | 0.99 | -0.107 | 5.784 | n/a | 1.2432 | 1.4402 | 1.0816 | -0.26044 | 0 | 0 | 2.2801 | Procurement included
2 | DN | DN Dryer Programmable Logic Controller Replacement | 31420 | Sustaining | 2014-02-01 | 2026-06-01 | 15.1271 | Aug-24 | 12.2 | 12.15 | 2022-04-30 | 14.9094 | 10.5486 | 1.4999 | 2.045 | 0.816 | 1.0053 | 473.6321 | n/a | 0.95 | -0.691 | 2.9771 | n/a | 3.987 | 4.0164 | 4.8166 | 0 | 0 | 0 | -9.8428 | Procurement included
3 | DN | DN Replacement Of Obsolete Online Chemistry Analyzers | 31520 | Sustaining | 2012-10-01 | 2024-08-01 | 16.2069 | Jan-21 | 16.7 | 10.585 | 2017-11-18 | 13.9652 | 13.8532 | 0.112 | 0 | 0 | 0.99935 | -78.072 | n/a | 0.98 | -0.295 | 5.6219 | n/a | 4.7348 | 4.4307 | -1.843 | 0.95556 | -1.81 | -0.351 | -0.49539 | Procurement included
4 | DN | DN Feeder Scanner Replacement | 31526 | Sustaining | 2012-12-01 | 2022-12-01 | 15.3489 | Aug-22 | 18.9 | 10.8 | 2019-03-31 | 15.0668 | 14.5128 | 0.554 | 0 | 0 | 0.99995 | -4.7887 | n/a | 1.01 | 0.158 | 8.6729 | n/a | 3.7741 | 1.9601 | 4.1197 | 0 | -0.994 | -0.262 | 0.075014 | Procurement included
5 | DN | DN Fuel Handling Obsolete Control Relay Re-Engineer/Replacement | 31704 | Sustaining | 2013-10-01 | 2026-06-01 | 17.1699 | Jul-24 | 5.8 | 5.78 | 2019-10-30 | 14.7715 | 5.0568 | 2.9797 | 6.735 | 0 | 0.93057 | -6125.1511 | n/a | 0.94 | -0.782 | 11.3899 | n/a | 0.94564 | 2.4803 | 6.125 | 0.1409 | 0 | 0 | 1.6981 | Procurement included
6 | DN | DN Vapour Recovery Button-Up Valve Replacements | 31706 | Sustaining | 2013-12-01 | 2026-01-01 | 23.7005 | Feb-24 | 16.2 | 23.7 | 2026-12-30 | 15.151 | 0 | 9.033 | 6.118 | 0 | 0.90279 | -8056.7811 | n/a | 0.95 | -0.697 | 0.00046 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
7 | DN | DN Neutron Over-Power Ion Chamber & In-Core Flux Detector Amplifier Replacement (Reactor Regulating System, Shutdown System 1 & Shutdown System 2) | 31716 | Sustaining | 2013-07-01 | 2028-11-01 | 23.8465 | Apr-27 | 23.8 | 23.846 | 2024-04-30 | 18.3166 | 4.8772 | 3.0705 | 3.51 | 6.859 | 1.0021 | 190.7894 | n/a | 0.9 | -1.265 | 0.000514 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
8 | DN | DN Replacement Of Emergency Power Supply Uninterruptible Power Supply | 33258 | Sustaining | 2010-02-01 | 2024-11-01 | 27.2949 | Feb-22 | 24.6 | 15.2 | 2016-07-31 | 26.3218 | 26.0768 | 0.245 | 0 | 0 | 1 | -0.001625 | n/a | 0.98 | -0.385 | 12.0949 | n/a | 8.418 | 0.52393 | 6.5741 | 0.59341 | -1.436 | -1.166 | -1.4345 | Procurement included
9 | DN | Fuel Handling Computer Replacement | 33815 | Sustaining | 2005-08-01 | 2024-08-01 | 16.7372 | Nov-21 | 15.6 | 12.47 | 2012-02-28 | 16.7274 | 16.3034 | 0 | 0.424 | 0 | 0.99 | -396 | n/a | 0.97 | -0.453 | 4.2672 | n/a | 0.86946 | 0.044699 | 0.59993 | 0 | -2.048 | -1.107 | 5.9084 | Procurement included
10 | DN | DN Digital Control Computer Replacement/ Refurbishment/ Upgrades | 33977 | Sustaining | 2003-09-01 | 2025-05-01 | 29.9 | Dec-21 | 26.5 | 22.058 | 2010-12-30 | 29.932 | 28.678 | 1.254 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 7.842 | n/a | 2.7882 | 13.8131 | -7.472 | 0 | -2.876 | -1.712 | 3.3223 | Procurement included
11 | DN | DN Standby Generators Protective Relay Replacement | 80063 | Sustaining | 2015-12-01 | 2026-11-01 | 22.0005 | Feb-23 | 20 | 22 | 2024-06-12 | 19.2642 | 7.4912 | 5.312 | 3.979 | 2.482 | 1.0309 | 1990.5097 | n/a | 0.94 | -0.942 | 0.000468 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
12 | DN | DN Irradiated Fuel Discharge Mechanism Major Component Repla | 82841 | Sustaining | 2015-11-01 | 2028-12-01 | 10.6982 | Feb-24 | 5.9 | 5.945 | 2022-06-30 | 8.1902 | 4.5238 | 1.99 | 0.899 | 0.77735 | 1.0157 | 309.9553 | n/a | 1.24 | 1.399 | 4.7532 | n/a | 0.86434 | 1.4766 | 0.65192 | 0.1351 | 0 | 0 | 1.6253 | Procurement included
13 | DN | DN Fuel Handling Trolley Major Auxiliary Component Replacement | 82842 | Sustaining | 2017-01-01 | 2028-01-01 | 19.1021 | Feb-24 | 18.3 | 18.304 | 2024-10-30 | 16.2252 | 5.3267 | 1.6625 | 2.998 | 6.238 | 1.0664 | 1536.7194 | n/a | 0.97 | -0.184 | 0.79809 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
14 | DN | DN Class 1 Rectifier Replacement | 82883 | Sustaining | 2018-05-01 | 2028-01-01 | 24.6639 | Dec-32 | 42.3 | 24.664 | 2027-12-28 | 21.657 | 11.986 | 2.104 | 3.606 | 3.961 | 0.97758 | -2301.6623 | n/a | 0.97 | -0.584 | -0.000126 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
15 | DN | DN Fuel Handling Motor Replacement | 82886 | Sustaining | 2017-01-01 | 2030-12-01 | 14.6003 | Apr-23 | 16.9 | 16.865 | 2023-08-30 | 12.9224 | 2.9478 | 0.33763 | 0.69 | 8.947 | 0.79199 | -9166.5175 | n/a | 0.9 | -0.405 | -2.2647 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
16 | SEC | Security Project C | 82930 | Sustaining | 2016-06-01 | 2025-06-01 | 29.6738 | Mar-21 | 22.9 | 22.894 | 2021-02-26 | 28.541 | 27.228 | 1.313 | 0 | 0 | 1.0051 | 566.4392 | n/a | 0.94 | -1.716 | 6.7798 | n/a | 2.8231 | -3.3626 | 3.2161 | 0.53152 | -3.442 | -1.074 | 8.0877 | Procurement included
17 | DN | DN Fuel Handling Power & Signal Cable Catenary Replacement | 83052 | Sustaining | 2019-04-01 | 2027-12-01 | 18.3658 | Jan-27 | 24.6 | 18.366 | 2026-11-17 | 3.2629 | 2.7729 | 0 | 0 | 0.49 | 0.99889 | -20.3037 | n/a | 1.16 | 0.448 | -0.000162 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
18 | DN | DN Phase 2 Station Battery Replacement | 83076 | Sustaining | 2016-08-01 | 2027-11-01 | 27.7356 | Dec-28 | 34.5 | 18.9 | 2028-11-30 | 24.3201 | 13.4983 | 3.6688 | 3.859 | 3.294 | 1.0181 | 947.5741 | n/a | 1.06 | 1.054 | 9.0696 | n/a | 2.5174 | 0.44099 | 4.4843 | 0.60163 | -4.196 | -0.472 | 5.6933 | Procurement included
19 | DN | DN Heavy Water Management System Computer Distributed Control Units Replacement | 83288 | Sustaining | 2018-01-01 | 2027-09-01 | 16.5449 | Sep-24 | 18.8 | n/a | n/a | 14.035 | 2.168 | 0 | 0 | 11.867 | 0.74811 | -14174.2802 | n/a | 0.78 | -2.283 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
20 | DN | DN Irradiated Fuel Bay Cooling and Purification Pump Replacement | 83483 | Sustaining | 2017-12-01 | 2029-01-01 | 29 | Sep-21 | 6.9 | 6.858 | 2022-08-15 | 24.7345 | 2.3964 | 2.6281 | 0.919 | 18.791 | 0.66043 | -26262.2182 | n/a | 0.84 | -1.09 | 22.142 | n/a | 2.7428 | 2.7027 | 3.9867 | 0.10644 | 0 | 0 | 12.645 | Procurement included
21 | DN | DN Fuel Handling Service Area Bridge F5 Ball Screw Assembly Replacement | 83558 | Sustaining | 2018-03-01 | 2024-11-01 | 16.6924 | Jun-25 | 28.2 | 22.441 | 2024-12-20 | 16.1381 | 15.6271 | 0.511 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -5.7486 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
22 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 83560 | Sustaining | 2018-05-01 | 2025-12-01 | 12.6906 | Dec-19 | 10 | 6.792 | 2022-03-25 | 10.3217 | 6.8827 | 2.3 | 1.139 | 0 | 0.97346 | -927.0845 | n/a | 0.97 | -0.291 | 5.8986 | n/a | 1.5556 | 1.4151 | 0.83918 | 0.013432 | 0 | 0 | 2.0759 | Procurement included
23 | DN | Fleet Monitoring Initiative (Monitoring & Diagnostic Centre) | 83828 | Sustaining | 2018-03-01 | 2026-09-01 | 29.9 | Jul-23 | 29.3 | 29.998 | 2024-10-31 | 28.4701 | 20.2006 | 3.4875 | 4.782 | 0 | 0.94327 | -7634.5786 | n/a | 0.95 | -1.294 | -0.098 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
24 | DN | DN Fuel Handling Replacement of Fuelling Machine Calibration Facility | 83916 | Sustaining | 2019-02-01 | 2027-11-01 | 18.7648 | Jul-25 | 22.4 | n/a | n/a | 14.465 | 0 | 4.141 | 3.554 | 6.77 | 0.96238 | -834.1633 | n/a | 1.02 | 0.091 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
25 | DN | DN Shutdown System 1 and Reactor Regulating System Ion Chamber Replacements | 83937 | Sustaining | 2018-12-01 | 2033-07-01 | 11.336 | Dec-28 | 11.3 | 11.337 | 2033-12-30 | 8.778 | 2.031 | 0 | 1.37 | 4.388 | 0.97041 | -2168.1324 | n/a | 1.09 | 0.222 | -0.001002 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
26 | DN | DN Fuelling Machine Duct & Central Service Area Air Conditioning Unit Replacement | 84006 | Sustaining | 2019-08-01 | 2029-07-01 | 25.1 | Aug-21 | 18.3 | n/a | n/a | 19.382 | 0 | 0 | 0 | 19.382 | 0.63654 | -6724.8509 | n/a | 0.99 | -0.013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
27 | DN | DN Air Operated Valve Replacements | 84009 | Sustaining | 2020-03-01 | 2025-12-01 | 18.9512 | Dec-28 | 85.7 | 18.951 | 2025-12-19 | 16.9793 | 6.9515 | 8.1637 | 1.864 | 0 | 0.99613 | -359.1657 | n/a | 1.05 | 0.753 | 0.000164 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
28 | AIM | PN Circumferential Wet Scrape Tool Enhancements | 84140 | Sustaining | 2019-11-01 | 2023-12-01 | 18.6 | Dec-22 | 18.6 | 18.584 | 2022-12-01 | 8.3706 | 8.3706 | 0 | 0 | 0 | 0.99905 | -144.0994 | n/a | 1.02 | 0.196 | 0.016 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
29 | DN | DN Radiation Detection Equipment Obsolescence - Moderator Cover Gas Monitors & Fixed Area Alarming Gamma Monitors | 84399 | Sustaining | 2019-11-01 | 2025-05-01 | 19.2856 | Dec-23 | 18 | 19.595 | 2026-07-31 | 19.2856 | 15.0289 | 4.0131 | 0.32 | 0 | 0.99429 | -694.3097 | n/a | 1.02 | 0.303 | -0.30938 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
30 | DN | DN Radiation Detection Obsolescence- Active Liquid Waste and Liquid Effluent Monitor | 84400 | Sustaining | 2019-11-01 | 2026-04-01 | 19.2084 | Sep-23 | 15 | 19.208 | 2026-03-15 | 16.476 | 3.3 | 0 | 13 | 0.176 | 0.88094 | -10139.4348 | n/a | 1.01 | 0.071 | 0.00043 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
31 | DN | DN Primary Heat Transport Pump Rotor Inspection and Replacement | 84799 | Sustaining | 2020-05-01 | 2024-07-01 | 28.3722 | Oct-26 | 89.2 | 89.21 | 2026-01-15 | 28.3722 | 28.3722 | 0 | 0 | 0 | 0.95 | -1868 | n/a | 1.43 | 10.449 | -60.8378 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
32 | DN | DN Main Power Output Transformer Fire Containment System Upgrade | 86055 | Sustaining | 2020-07-01 | 2026-09-01 | 29.8634 | Aug-21 | 20 | 21.932 | 2025-10-31 | 27.448 | 14.198 | 9.286 | 2.334 | 1.63 | 0.9894 | -1247.3636 | n/a | 0.96 | -0.835 | 7.9314 | n/a | -1.0983 | 0.25887 | 4.7244 | 1.5399 | 0 | 0 | 2.5062 | Procurement included
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
33 | DN | DN Pressurizer Heaters and Controllers Replacement | 31422 | Sustaining | 2011-04-01 | 2022-10-01 | 12.1027 | Dec-21 | 13.9 | 14.511 | 2016-08-08 | 11.2996 | 11.2996 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -2.0973 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
34 | DN | DN Fuel Handling Inverter Replacement | 31426 | Sustaining | 2011-11-01 | 2022-03-01 | 25.1315 | Apr-21 | 26.2 | 13.855 | 2019-09-03 | 25.0815 | 25.0815 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 11.2765 | n/a | 1.729 | 14.2558 | -2.2034 | 1.2292 | -2.347 | -1.137 | -0.25093 | Procurement included
35 | DN | DN Station Fluorescent Lighting Fixtures Retrofit | 31516 | Sustaining | 2012-12-01 | 2023-11-01 | 20.1652 | Jan-23 | 20.7 | 16.895 | 2020-12-21 | 19.747 | 19.747 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 3.2702 | n/a | 0.47188 | -0.28196 | 6.3804 | 0 | -5.148 | -0.277 | 2.1241 | Procurement included
36 | DN | DN Restore Emergency Service Water and Firewater Margins | 31518 | Regulatory | 2012-12-01 | 2021-01-01 | 22.1833 | Aug-19 | 28.5 | 28.461 | 2018-11-30 | 10.5098 | 10.5098 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -6.2777 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
37 | DN | DN Tritium Removal Facility Deuterium Make-up System Electrolyzer Replacement | 31522 | Sustaining | 2012-11-01 | 2021-11-01 | 13.9382 | Oct-19 | 14.5 | 7.024 | 2015-04-21 | 13.7383 | 13.7382 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 6.9142 | n/a | 2.8458 | 5.0394 | -0.030702 | 0 | -1.15 | -0.237 | 0.44678 | Procurement included
38 | DN | DN Transformer Multi-Gas Analyzer Installation | 31542 | Sustaining | 2012-10-01 | 2020-09-01 | 22.4604 | Dec-20 | 23.8 | 15.157 | 2017-12-31 | 22.461 | 22.461 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 7.3034 | n/a | 2.744 | 2.8052 | 2.9631 | 0 | -2.527 | -0.862 | 2.1884 | Procurement included
39 | DN | DN Feedwater Chemistry Control Improvements | 31548 | Sustaining | 2013-11-01 | 2020-11-01 | 11.625 | Feb-20 | 14 | 10.329 | 2022-11-02 | 11.625 | 11.625 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 1.296 | n/a | 1.0339 | 1.7472 | -0.027326 | 0.15134 | -2.177 | -0.938 | 1.5059 | Procurement included
40 | DN | DN Hydrogen Cooling Temperature Control Valve TCV20 Redesign | 33228 | Sustaining | 2012-11-01 | 2021-11-01 | 12.4373 | Jun-21 | 16.2 | 8.562 | 2019-06-15 | 12.3573 | 12.3573 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 3.8753 | n/a | 3.4862 | 1.8168 | 0.01318 | 0.21369 | -1.782 | -0.41 | 0.53745 | Procurement included
41 | DN | DN Chiller Replacement to Reduce Chlorofluorocarbon Emissions | 33631 | Regulatory | 2004-01-01 | 2021-12-01 | 24.0491 | Dec-17 | 30 | 14.9 | 2011-05-31 | 22.3301 | 22.3301 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 9.1491 | n/a | 12.6132 | -2.0809 | -0.13781 | 0.043496 | -1.6 | -0.713 | 1.0241 | Procurement included
42 | PN | PB Emergency Power Generator and Main Output Power Protective Relay Replace | 40691 | Sustaining | 2012-02-01 | 2021-03-01 | 25.6822 | Oct-19 | 29.7 | 7.45 | 2016-12-30 | 25.6822 | 25.6822 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 18.2322 | n/a | 5.4577 | 7.2598 | 4.8933 | 0.088601 | -0.637 | -0.334 | 1.5037 | Procurement included
43 | PN | PA Standby Generator Reliability Upgrades | 40972 | Sustaining | 2012-04-01 | 2024-12-01 | 19.6613 | Dec-21 | 19 | 4.65 | 2015-03-01 | 19.617 | 19.617 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 15.0113 | n/a | 2.8543 | 7.8849 | 2.4909 | 0.38216 | -0.975 | -0.2 | 2.5739 | Procurement included
44 | PN | PN Obsolete Online Chemistry Analyzer Replacement | 40985 | Sustaining | 2013-03-01 | 2021-07-01 | 16.3507 | Aug-19 | 18.5 | 5.556 | 2016-12-01 | 15.9496 | 15.9496 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 10.7947 | n/a | 4.5765 | 3.7628 | 1.8937 | -0.01007 | -1.141 | -0.214 | 1.9168 | Procurement included
45 | DN | DN Feeder Scanner Replacement | 80070 | Sustaining | 2014-05-01 | 2025-02-01 | 15.1128 | Aug-22 | 18.9 | 7.96 | 2019-03-31 | 15.1128 | 14.9058 | 0.20692 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 7.1528 | n/a | 1.357 | 3.6832 | -1.8526 | 0 | -1.107 | -0.326 | 5.3981 | Procurement included
46 | DN | DN Fire Hazard Assessment and Fire Safe Shutdown Analysis Modifications | 80151 | Regulatory | 2015-11-01 | 2022-10-01 | 17.9666 | Sep-21 | 20 | 16.129 | 2020-04-09 | 17.9666 | 17.9666 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 1.8376 | n/a | -1.7503 | 0.96649 | 0.18156 | 0.38455 | 0 | 0 | 2.0549 | Procurement included
47 | DN | DN Vault Cooling Coil Replacement | 82816 | Regulatory | n/a | 2020-10-01 | 16.2044 | Jul-19 | 17.8 | 26.322 | 2020-07-30 | 15.3915 | 15.3915 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -10.1176 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
48 | DN | DN Main Power Output and Class IV Transformer Control Cabinet Wiring Replacement | 82890 | Sustaining | 2019-01-01 | Deferred | 26.8 | Deferred | 26.8 | n/a | n/a | 23.0353 | 0 | 0 | 0 | 11.7036 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
49 | PN | PN P58 Buried Blowdown Piping Replacement | 83072 | Sustaining | 2016-11-01 | 2021-09-01 | 21.3103 | Dec-20 | 20.9 | 20.948 | 2020-11-30 | 18.6322 | 18.6322 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0.36234 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
50 | PN | PN U14 Low Pressure Feedheater Heat Exchanger Replacement | 83088 | Sustaining | 2016-05-01 | 2021-02-01 | 22.007 | May-18 | 22 | 19.389 | 2018-09-30 | 20.0377 | 20.0377 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 2.618 | n/a | 1.7815 | -0.55325 | 8.0707 | 0 | -6.463 | -0.85 | 0.63205 | Procurement included
51 | DN | DN Condenser Steam Discharge Valve Control System Replacement | 83299 | Sustaining | 2019-01-01 | Cancelled | 11.5099 | Dec-27 | 29.7 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
52 | DN | DN Turbine Hall Crane Controls Upgrade | 83556 | Sustaining | 2017-12-01 | 2020-04-01 | 24.2299 | Dec-20 | 23.6 | 19.736 | 2020-01-30 | 23.4053 | 23.4053 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 4.4939 | n/a | 1.1459 | -1.9715 | 4.6177 | 0.32097 | 0 | 0 | 0.38083 | Procurement included
53 | DN | DN Irradiated Fuel Bay Permanent Fuel Inspection Equipment | 83559 | Regulatory | 2018-03-01 | 2023-05-01 | 23.9047 | May-22 | 25 | 24.997 | 2021-02-04 | 23.3278 | 22.9567 | 0.37113 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -1.0923 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
54 | PN | PN High Pressure Turbine Spindle Capital Spares | 83668 | Sustaining | 2017-11-01 | 2020-06-01 | 21.3356 | Aug-19 | 21.3 | 23.375 | 2020-02-15 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -2.0394 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
55 | AIM | Steam Generator Manipulator & Automated Tube Plug | 84888 | Sustaining | 2020-03-01 | Deferred | 12.5 | May-20 | 8.2 | 8.236 | 2022-12-15 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 4.264 | n/a | 1.4281 | 4.0143 | 0 | 0.049348 | -1.901 | -0.07 | 0.70424 | Procurement included
PROJECTS NOT IN EB-2020-0290
56 | DN | DN Frazil Ice and Discharge Gate Replacement | 31554 | Sustaining | 2024-08-01 | 2027-08-01 | 27.0141 | n/a | n/a | n/a | n/a | 20.532 | 0 | 0 | 0 | 20.532 | 0.49747 | -11034.9551 | n/a | 0.64 | -0.531 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
57 | DN | DN Glycol Chiller Single Point Vulnerability Removal | 80152 | Sustaining | 2024-06-01 | 2027-06-01 | 17.7959 | n/a | n/a | n/a | n/a | 7.069 | 0 | 0 | 0 | 7.069 | 0.95235 | -674.0755 | n/a | 1.1 | 0.125 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
58 | DN | DN Lake Current Monitoring System Replacement | 83289 | Sustaining | 2021-12-01 | 2026-06-01 | 10.9961 | n/a | n/a | n/a | n/a | 7.64 | 0 | 0 | 7.423 | 0.217 | 0.9918 | -82.0057 | n/a | 1.04 | 0.036 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
59 | DN | DN Turbine Lubricating Oil Cooler Replacement | 83300 | Sustaining | 2025-03-01 | 2029-05-01 | 29.1 | n/a | n/a | n/a | n/a | 19.027 | 0 | 0 | 4.899 | 14.128 | 0.63054 | -4423.5481 | n/a | 1.01 | 0.035 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
60 | DN | DN Emergency Service Water & Low Pressure Service Water Expansion Joints Replacement | 83665 | Sustaining | 2021-07-01 | 2028-08-01 | 13.9 | n/a | n/a | n/a | n/a | 10.538 | 0 | 0 | 0 | 10.538 | 0.87413 | -2726.8423 | n/a | 1.4 | 0.742 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
61 | DN | DN Tritium Removal Facility/ Heavy Water Management Interim Lifecycle Plan Implementation | 83669 | Sustaining | 2021-01-01 | 2026-05-01 | 29.8886 | n/a | n/a | 19.419 | 2024-09-09 | 29.682 | 1.53 | 18.108 | 10.044 | 0 | 1.0094 | 1496.2453 | n/a | 0.93 | -2 | 10.4696 | n/a | 3.3203 | 1.5913 | 2.944 | 0.3622 | 0 | 0 | 2.2517 | Procurement included
62 | DN | DN Active Liquid Waste Tank Liner Replacement | 83918 | Sustaining | 2025-04-01 | 2029-05-01 | 16.9694 | n/a | n/a | n/a | n/a | 11.226 | 0 | 0 | 0 | 11.226 | 1.008 | 27.0111 | n/a | 1.1 | 0.035 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
63 | DN | DN Condenser Water Box Isolation From Discharge Duct | 84134 | Sustaining | 2020-10-01 | Aug-24 (Complete) | 14.7605 | n/a | n/a | 18.535 | 2023-07-31 | 14.7614 | 14.7614 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -3.7745 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
64 | DN | DN Vault Vapour Recovery System Component Replacement | 84138 | Sustaining | 2021-02-01 | 2025-03-25 | 21.7567 | n/a | n/a | 8.6 | 2022-06-30 | 21.7559 | 20.25 | 1.5059 | 0 | 0 | 1.0012 | 181.9033 | n/a | 0.88 | -2.385 | 13.1567 | n/a | 3.3985 | 4.4529 | 4.1455 | -0.077758 | -3.011 | -0.098 | 4.3408 | Procurement included
65 | DN | DN Inactive Drainage Sump Pump Replacement | 84300 | Sustaining | 2024-12-01 | 2029-08-01 | 19.2422 | n/a | n/a | n/a | n/a | 16.405 | 0 | 1.563 | 5.4 | 9.442 | 0.8846 | -5151.1389 | n/a | 0.98 | -0.073 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
66 | DN | DN Low Pressure Service Water Heat Exchanger Coil Replacement | 84301 | Sustaining | 2022-05-01 | 2028-02-01 | 11.7911 | n/a | n/a | n/a | n/a | 9.4348 | 0 | 1.3268 | 2.873 | 5.235 | 1.11 | -663 | n/a | 0.94 | -0.155 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
67 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 84308 | Sustaining | 2024-12-01 | 2027-01-01 | 14.8856 | n/a | n/a | n/a | n/a | 11.423 | 0 | 0 | 0 | 11.423 | 0.63887 | -3743.6032 | n/a | 0.99 | -0.003 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
68 | DN | DN Emergency Service Water Travelling Screen, Motor and Bubbler Replacement | 84312 | Sustaining | 2025-04-01 | 2028-03-01 | 10.1924 | n/a | n/a | n/a | n/a | 8.291 | 0 | 0 | 1 | 7.291 | 0.86979 | -801.281 | n/a | 0.98 | -0.012 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
69 | AIM | AIM Advanced Non-Destructive Examination MK3 Inspection Tool | 86043 | Sustaining | 2023-08-01 | 2027-12-01 | 19.0092 | n/a | n/a | n/a | n/a | 16.085 | 0 | 0 | 0 | 16.085 | 0.85588 | -8255.1067 | n/a | 1 | -0.024 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
70 | DN | DN Steam Generator Waterlancing Optimization | 86086 | Sustaining | 2022-08-01 | 2026-01-01 | 12.9299 | n/a | n/a | 12.93 | 2025-12-10 | 9.247 | 0 | 1.293 | 7.954 | 0 | 1.3879 | 13625.5131 | n/a | 1.23 | 1.017 | -7.1e-05 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
71 | DN | DN Fuelling Machine Head Gap Air Sensing Package | 86302 | Sustaining | 2021-03-01 | 2029-12-01 | 14.8804 | n/a | n/a | 9.849 | 2028-02-29 | 7.851 | 0 | 0 | 1.803 | 6.048 | 1 | -29 | n/a | 1.03 | 0.089 | 5.0314 | n/a | 2.0893 | -0.63563 | 1.2675 | -0.23858 | 0 | 0 | 2.549 | Procurement included
72 | AIM | AIM Connectorized Umbilical Cable | 86520 | Sustaining | 2024-06-01 | 2028-09-01 | 11.9518 | n/a | n/a | n/a | n/a | 8.235 | 0 | 0 | 0 | 8.235 | 0.40861 | -24497.9485 | n/a | 1.59 | 0.419 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
73 | DN | DN Fuelling Machine Trolley Air Compressor Replacement | 86553 | Sustaining | 2024-03-01 | 2027-09-01 | 17.1379 | n/a | n/a | n/a | n/a | 10.102 | 0 | 0 | 0 | 10.102 | 1.0167 | 490.3178 | n/a | 1.25 | 0.434 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
74 | PN | PN Irradiated Fuel Bay Heat Exchanger Replacement | 86831 | Sustaining | 2022-06-01 | Dec-23 (Complete) | 12.1286 | n/a | n/a | 7.933 | 2022-12-15 | 11.5156 | 11.5157 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 4.1956 | n/a | 0.77029 | -0.03 | -0.36341 | -0.2 | 0 | 0 | 4.0187 | Procurement included
75 | DN | DN Electrical Signature Analysis Monitoring 13.2KV And 4KV Motors | 87342 | Value Enhancing | 2024-05-01 | 2030-05-01 | 13.7175 | n/a | n/a | n/a | n/a | 8.796 | 0 | 0 | 1.495 | 7.301 | 0.81 | n/a | -0.292 | 0.76 | -0.394 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
76 | DN | DN Sensor Development | 87698 | Sustaining | 2024-04-01 | 2026-06-01 | 13.4269 | n/a | n/a | 13.427 | 2026-06-01 | 13.1159 | 0 | 5.9129 | 7.203 | 0 | 0.8 | n/a | -2.334 | 0.98 | -0.188 | -0.000128 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
77 | DN | DN Main Control Room and Simulators Renovation | 87806 | Value Enhancing | 2024-12-01 | 2030-06-01 | 16.4868 | n/a | n/a | n/a | n/a | 12.807 | 0 | 0 | 0 | 12.807 | 0.7118 | -4411.2703 | n/a | 0.84 | -0.205 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
78 | PN | PN Emergency Response Team Garage | 87809 | Sustaining | 2024-05-01 | 2025-06-01 | 17.5845 | n/a | n/a | 17.584 | 2025-06-01 | 9.711 | 0 | 9.711 | 0 | 0 | 0.99 | -120 | n/a | 1.06 | 0.911 | 0.000478 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
79 | PN | PN Polychlorinated Biphenyl Lighting 5-8 | 87845 | Regulatory | 2023-12-01 | 2025-12-01 | 25 | n/a | n/a | 25 | 2025-12-01 | 19.0815 | 11.6455 | 7.436 | 0 | 0 | 0.99576 | -472.2501 | n/a | 1.03 | 0.608 | 8e-06 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
80 | DN | DN Turbine Protection Reliability Improvement | 87920 | Sustaining | 2023-12-01 | 2027-08-01 | 19.3065 | n/a | n/a | 19.307 | 2027-12-31 | 8.855 | 2.74 | 1.674 | 2.619 | 1.822 | 0.76552 | n/a | -2.7289 | 1.73 | 3.751 | -0.000454 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
81 | DN | Darlington Site Shoreline Protection | 87998 | Sustaining | 2025-03-01 | 2026-08-01 | 12.8335 | n/a | n/a | 12.834 | 2026-08-12 | 9.949 | 0 | 0 | 9.949 | 0 | 0.89936 | -2523.7537 | n/a | 1.02 | 0.136 | -0.00048 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
82 | DN | DN Generator Rotor Refurbishment | 89305 | Sustaining | 2025-03-01 | 2029-08-01 | 25.4 | n/a | n/a | n/a | n/a | 18.259 | 0 | 0 | 0 | 18.259 | 0.96286 | -379.5026 | n/a | 1.01 | 0.043 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
83 | DN | DN Atmospheric Steam Discharge Valve Silencers Replacement | 89591 | Sustaining | 2025-03-01 | 2025-08-27 | 12.674 | n/a | n/a | 12.674 | 2027-08-30 | 10.598 | 0 | 1.4 | 3.1 | 6.098 | 1.54 | n/a | 1.351 | 1.06 | 0.213 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
84 | PN | PN Class 1 & 2 Battery Bank Replacement | 89865 | Sustaining | 2025-05-01 | 2033-06-01 | 29.7574 | n/a | n/a | n/a | n/a | 23.7 | 0 | 0 | 2.5 | 18.4 | 0.9966 | -13.1307 | n/a | 1.01 | 0.037 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Total |  |  |  |  | 1615.5273 | [6 empty] | 120.175 | 143.33 | 310.9089

## Sheet1
31403 | 31403;31420;31520;31526;31704;31706;31716;33258;33815;33977;80063;82841;82842;82883;82886;82930;83052;83076;83288;83483;83558;83560;83828;83916;83937;84006;84009;84140;84399;84400;84799;86055;31422;31426;31516;31518;31522;31542;31548;33228;33631;40691;40972;40985;80070;80151;82816;82890;83072;83088;83299;83556;83559;83668;84888;31554;80152;83289;83300;83665;83669;83918;84134;84138;84300;84301;84308;84312;86043;86086;86302;86520;86553;86831;87342;87698;87806;87809;87845;87920;87998;89305;89591;89865
31420
31520
31526
31704
31706
31716
33258
33815
33977
80063
82841
82842
82883
82886
82930
83052
83076
83288
83483
83558
83560
83828
83916
83937
84006
84009
84140
84399
84400
84799
86055
31422
31426
31516
31518
31522
31542
31548
33228
33631
40691
40972
40985
80070
80151
82816
82890
83072
83088
83299
83556
83559
83668
84888
31554
80152
83289
83300
83665
83669
83918
84134
84138
84300
84301
84308
84312
86043
86086
86302
86520
86553
86831
87342
87698
87806
87809
87845
87920
87998
89305
89591
89865