## D1-1-2_Table1
Numbers may not add due to rounding. | [9 empty] | Filed: 2026-04-22
EB-2025-0297
Exhibit L
D1-SEC-45
Attachment 1
L-D1-SEC-45 - Attachment 1
Capital Project Listing - Regulated Hydroelectric
Projects ≥ $30M Annual Capital Expenditures (Allocated)
[6 empty] | Expenditures | Expenditures | Expenditures | Expenditures | Expenditures
Line |  |  |  | Project | CRVA | 2027 | 2028 | 2029 | 2030 | 2031
No. | Region | Facility | Project Name | Number | Eligible1 | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j)
1 | Portfolio Projects (Allocated)
2 | Niagara | Sir Adam Beck Pump Generating Station | Sir Adam Beck Pump GS - Reservoir Refurbishment | 80583 | Yes | 0 | 0 | 0 | 0 | 0
3 | Niagara | Sir Adam Beck 1 | SAB1 Station Service Upgrade | 86364 | No | 0.79 | 3.81 | 7.69 | 10.78 | 0
4 | Niagara | Sir Adam Beck 2 | BK2 230kV Conductor Replacement | 87362 | No | 0.74 | 4.66 | 0.79 | 4.81 | 4.89
5 | Subtotal Portfolio Projects (Allocated) - Niagara Region |  |  |  |  | 1.53 | 8.47 | 8.48 | 15.59 | 4.89
6 | Eastern | Frederick House | Frederick House Lake Dam Upgrades | 83194 | Yes | 0 | 0 | 0 | 0 | 0
7 | Eastern | Chenaux | CHE - Limerick Isl. Spr Structure Sluice Gate Hoist | 84494 | Yes | 0 | 0 | 0 | 0 | 0
8 | Eastern | R.H. Saunders | SAU - Long Sault Dam Capital Program (JW)(NYPA) | 86595 | No | 2.15 | 8.23 | 9.63 | 10.26 | 10.13
9 | Eastern | R.H. Saunders | SAU - Massena Canal Dam (JW)(NYPA)(CAP) | 87142 | No | 10.53 | 6.71 | 3.88 | 0 | 0
10 | Eastern | R.H. Saunders | SAU - Long Sault Dam Downstream Concrete (JW) (NYPA) | 87575 | No | 3.08 | 3.72 | 3.81 | 3.9 | 3.99
11 | Eastern | Otto Holden | OTO - Refurbish Stop Log Sluice Piers | 89354 | No | 1.58 | 10.67 | 16.21 | 16.42 | 16.63
12 | Subtotal Portfolio Projects (Allocated) - Eastern Region |  |  |  |  | 17.34 | 29.33 | 33.53 | 30.58 | 30.75
13 | Western | Silver Falls | Surge Tank Replacement | 83833 | Yes | 9.84 | 28.01 | 0.07 | 0 | 0
14 | Western | Northwest Operations | NWO Work Centre Building | 84901 | No | 4.6 | 0 | 0 | 0 | 0
15 | Western | Aguasabon | Aguasabon Dam Rehab. Hayes Lake Main Dam | 87217 | Yes* | 3.3 | 3.78 | 14.27 | 26.94 | 31.65
16 | Subtotal Portfolio Projects (Allocated) - Western Region |  |  |  |  | 17.74 | 31.79 | 14.34 | 26.94 | 31.65
17 | Subtotal Portfolio Projects (Allocated) |  |  |  |  | 36.61 | 69.59 | 56.35 | 73.11 | 67.29
18 | Refurbishments (Allocated)
19 | Niagara | DeCew Falls 2 | G2 Overhaul & Upgrade | 80851 | Yes | 0 | 0 | 0 | 0 | 0
20 | Niagara | Sir Adam Beck 1 | Sir Adam Beck I GS - G10 Major Overhaul & Upgrade | 80649 | Yes | 0 | 0 | 0 | 0 | 0
21 | Niagara | Sir Adam Beck 1 | Sir Adam Beck 1 GS - Unit G5 Upgrade | 82777 | Yes | 0 | 0 | 0 | 0 | 0
22 | Eastern | Abitibi Canyon | Abitibi - G2 Capital Upgrades/HG | 83155 | Yes | 0 | 0 | 0 | 0 | 0
23 | Eastern | Otter Rapids | Otter Project Camp | 84907 | No | 0 | 0 | 0 | 0 | 0
24 | Eastern | R.H. Saunders | SAU - G9 Capital Refurbishment | 83495 | Yes | 0 | 0 | 0 | 0 | 0
25 | Eastern | Otter Rapids | Otter G2 Capital Upgrade | 82543 | Yes | 0 | 0 | 0 | 0 | 0
26 | Niagara | Sir Adam Beck 2 | BK2 G20/G19 Refurbishment | 87768 | Yes* | 121.81 | 88.81 | 12.08 | 0 | 0
27 | Eastern | R.H. Saunders | SAU - G12 Capital Refurbishment | 86587 | Yes | 0.05 | 0 | 0 | 0 | 0
28 | Eastern | Otter Rapids | Otter G1 Capital Upgrade | 82542 | Yes | 0.06 | 0 | 0 | 0 | 0
29 | Eastern | Abitibi Canyon | ABI - G1 Capital Upgrades | 83148 | Yes* | 0.52 | 1.6 | 21.26 | 16.03 | 14.75
30 | Western | Alexander | G1 Capital Refurb | 82391 | Yes* | 1.84 | 4.34 | 26.81 | 10.82 | 0.59
31 | Western | Alexander | G2 Capital Refurb | 86792 | Yes* | 8.78 | 21.2 | 8.32 | 0.56 | 0.56
32 | Western | Alexander | G3 Capital Refurb | 86793 | Yes* | 0.35 | 3.05 | 5.25 | 22.81 | 10.96
33 | Western | Manitou Falls | MAN G3 Capital Refurb | 86860 | Yes* | 12.47 | 21.48 | 10.37 | 0.46 | 0.46
34 | Niagara | Sir Adam Beck 1 | BK1 G6 G8 Refurbishment | 86372 | Yes* | 66.08 | 73.14 | 37.92 | 2.29 | 0
35 | Niagara | Sir Adam Beck 1 | BK1 G4 Refurbishment | 86570 | Yes* | 3.46 | 0.29 | 0 | 0 | 0
36 | Niagara | Sir Adam Beck 2 | BK2 G18 G17 Refurbishment | 87356 | Yes* | 50.79 | 73.08 | 127.89 | 99.1 | 0
37 | Niagara | Sir Adam Beck 2 | BK2 G14 G13 Refurbishment | 87357 | Yes* | 2.98 | 18.79 | 37.58 | 114.61 | 93.95
38 | Eastern | R.H. Saunders | SAU - G16 Capital Refurbishment | 86937 | Yes* | 19.69 | 1.58 | 0.22 | 0 | 0
39 | Subtotal Refurbishments (Allocated) |  |  |  |  | 288.88 | 307.36 | 287.7 | 266.68 | 121.27
40 | Redevelopments (Allocated)
41 | Eastern | Calabogie | Calabogie GS - Redevelopment | 82089 | Yes* | 0 | 0 | 0 | 0 | 0
42 | Western | Kakabeka Falls | Kakabeka Falls GS Redevelopment | 86386 | Yes* | 96.27 | 4.95 | 0.8 | 0 | 0
43 | Eastern | Coniston/Stinson | Coniston/Stinson GS Redevelopment | 82087 | Yes* | 8.39 | 0 | 0 | 0 | 0
44 | Eastern | Matabitchuan | Matabitchuan GS Redevelopment | 86387 | Yes* | 52.04 | 13.19 | 0.2 | 0 | 0
45 | Subtotal Redevelopments (Allocated) |  |  |  |  | 156.7 | 18.14 | 1 | 0 | 0
46 | Sir Adam Beck 1 GS Canal Rehabilitation
47 | Niagara | Sir Adam Beck 1 | SAB1 Canal Isolation Preparedness Phase 1 (SAB1 CIP1) | 89252 | Yes* | 18.32 | 20.83 | 12.74 | 0 | 0
48 | Expansion Projects
49 | Niagara | Sir Adam Beck 1 | BK1 G1/G2 Replacement | 84185 | Yes | 0 | 0 | 0 | 0 | 0
50 | Western | Ranney Falls | Ranney Falls Expansion Project | 80581 | Yes | 0 | 0 | 0 | 0 | 0
51 | Subtotal Expansion Projects |  |  |  |  | 0 | 0 | 0 | 0 | 0
52 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program
53 | Eastern | Abitibi Canyon | Abitibi Canyon Concrete Repair Zone 7 | 89505 | Yes | 0 | 0 | 0 | 0 | 0
54 |  |  | Total Regulated Hydroelectric |  |  | 500.51 | 415.92 | 357.79 | 339.79 | 188.56
Notes:
1 | Col.(e): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2016-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 5). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D1-1-2_Table 2a&b
Numbers may not add due to rounding. | [9 empty] | Filed: 2026-04-22
EB-2025-0297
Exhibit L
D1-SEC-045
Attachment 1
L-D1-SEC-045 - Attachment 1
Capital Project Listing - Regulated Hydroelectric and Hydro Common
Projects $10M - $30M Annual Capital Expenditures (Allocated)
[6 empty] | Expenditures | Expenditures | Expenditures | Expenditures | Expenditures
Line |  |  |  | Project | CRVA | 2027 | 2028 | 2029 | 2030 | 2031
No. | Region | Facility | Project Name | Number | Eligible1 | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j)
1 | Portfolio Projects (Allocated)
2 | Niagara | Sir Adam Beck 2 | Sir Adam Beck II GS - Station Service Upgrades | 80666 | No | 0 | 0 | 0 | 0 | 0
3 | Niagara | Sir Adam Beck 2 | Battery Banks and DC System Upgrade | 80812 | No | 0 | 0 | 0 | 0 | 0
4 | Niagara | Sir Adam Beck Pump GS | Hatchcover and Drive System | 82210 | No | 0 | 0 | 0 | 0 | 0
5 | Niagara | Sir Adam Beck 2 | BK2 Hoist Refurbishment G11-18 | 84568 | No | 0 | 0 | 0 | 0 | 0
6 | Niagara | Sir Adam Beck 1 | BK1 Tailrace Deck | 86053 | No | 0 | 0 | 0 | 0 | 0
7 | Niagara | Sir Adam Beck 2 | SAB2 Headgate Replt. | 86376 | No | 0 | 0 | 0 | 0 | 0
8 | Niagara | Sir Adam Beck 2 | SAB OH Site Prep and Facility Rehab | 86379 | No | 0 | 0 | 0 | 0 | 0
9 | Niagara | Sir Adam Beck 2 | SAB2 N and S Phse Cranes | 86438 | No | 0 | 0 | 0 | 0 | 0
10 | Niagara | Sir Adam Beck 2 | SAB2 Rock Cliff Conc. Rehab | 86491 | No | 0 | 0 | 0 | 0 | 0
11 | Niagara | Sir Adam Beck Pump GS | BKP Headworks Crane Replacement | 86920 | No | 2.89 | 0.33 | 0 | 0 | 0
12 | Niagara | Sir Adam Beck 2 | BK2 Penstock Concrete Restoration | 87951 | No | 0 | 0 | 0 | 0 | 0
13 | Niagara | Sir Adam Beck 2 | BK2 Phse. Cranes Replacement | 89025 | No | 6.31 | 4.79 | 0 | 0 | 0
14 | Subtotal Portfolio Projects (Allocated) - Niagara Region |  |  |  |  | 9.2 | 5.12 | 0 | 0 | 0
15 | Eastern | Chenaux | Chenaux GS - Replace Protections and Controls | 80596 | No | 0 | 0 | 0 | 0 | 0
16 | Eastern | Des Joachims | Replace Generator Breakers and Station Service Brks. | 80602 | No | 0 | 0 | 0 | 0 | 0
17 | Eastern | R.H. Saunders | R.H Saunders GS - Replace Powerhouse Crane | 80635 | No | 0 | 0 | 0 | 0 | 0
18 | Eastern | R.H. Saunders | R.H. Saunders GS - Replace Station Service Breakers | 80637 | No | 0 | 0 | 0 | 0 | 0
19 | Eastern | Matabitchuan | Replace Penstocks & Saddles | 80703 | No | 0 | 0 | 0 | 0 | 0
20 | Eastern | Otto Holden | Otto Holden GS - Replace Sluicegates & Rehabilitate Sluicegates System | 80717 | Yes | 0 | 0 | 0 | 0 | 0
21 | Eastern | Arnprior | ARN - Repl. AC Stn. Serv. Switchgear & Brkrs. | 80951 | No | 0 | 0 | 0 | 0 | 0
22 | Eastern | Otter Rapids | Otter Sluice Gate Upgrades | 82246 | Yes | 0 | 0 | 0 | 0 | 0
23 | Eastern | Otter Rapids | OTR -T2/T1 Transformer Replacement | 82255 | Yes | 0 | 0 | 0 | 0 | 0
24 | Eastern | Abitibi Canyon | Abitibi - Transformer Deck Roof Replacement | 82257 | No | 0 | 0 | 0 | 0 | 0
25 | Eastern | Crystal Falls | Crystal Falls Elect./Controls Upgrade | 82261 | No | 0 | 0 | 0 | 0 | 0
26 | Eastern | R.H. Saunders | Replacement of Excitation System All 16 Units | 82986 | Yes | 0 | 0 | 0 | 0 | 0
27 | Eastern | Mountain Chute | MTN - Repl. AC Sta. Serv. Trnsfrmrs Switch | 82987 | No | 2.71 | 0.3 | 0 | 0 | 0
28 | Eastern | R.H. Saunders | SAU - Headwork Crane Replacement | 83111 | No | 0 | 0 | 0 | 0 | 0
29 | Eastern | Abitibi Canyon | Abitibi - Breaker Roof Replt. | 83153 | No | 0 | 0 | 0 | 0 | 0
30 | Eastern | Des Joachims | DEJ - Controls - Repl. Generator Controls | 83353 | No | 0 | 0 | 0 | 0 | 0
31 | Eastern | Stewartville | Replace AC Station Service Transformers, Switchgear and Distribution Panels | 83763 | No | 0 | 0 | 0 | 0 | 0
32 | Eastern | R.H. Saunders | Install Concrete Plug in Ice Sluice Drum Gate Openings | 84202 | No | 0 | 0 | 0 | 0 | 0
33 | Eastern | Elliott Chute | Elliott - Service Gate and Gains Upgrade | 84534 | No | 0 | 0 | 0 | 0 | 0
34 | Eastern | Chenaux | CHE - PH Cranes 2 - Cntrls & Cndctr Upgrade | 86200 | No | 0 | 0 | 0 | 0 | 0
35 | Eastern | Des Joachims | DEJ - Headpond and Tailrace Booms | 86204 | No | 0.08 | 0 | 0 | 0 | 0
36 | Eastern | R.H. Saunders | SAU - Headgate Control Replacement | 86220 | No | 2.6 | 3.93 | 3.98 | 3.08 | 0
37 | Eastern | Coniston | Wanapitei Civil Upgrades | 86310 | No | 0.1 | 0 | 0 | 0 | 0
38 | Eastern | R.H. Saunders | SAU - Repl. Iroquois Dam 2 Cranes (JW) (OPG) | 86586 | No | 10 | 0 | 0 | 0 | 0
39 | Eastern | R.H. Saunders | SAU - Long Sault Dam Superstructure Automation (JW) (NYPA) | 87140 | No | 1.35 | 8.13 | 6.75 | 0.34 | 0
40 | Eastern | R.H. Saunders | SAU - 13.8KV Underground Feeder Eval. (JW) (NYPA) | 87141 | No | 2.03 | 8.13 | 10.13 | 0.34 | 0
41 | Eastern | Arnprior | ARN - Replace T1 Main Output Transformer | 87513 | No | 1.67 | 6.04 | 1.68 | 0 | 0
42 | Eastern | Abitibi Canyon | ABI - Powerhouse Crane Refurb / Replace | 89078 | No | 7.96 | 11.8 | 0.26 | 0 | 0
43 | Eastern | Abitibi Canyon | ABI - Unloading Crane Refurb/Replacement | 89079 | No | 11.48 | 0.26 | 0 | 0 | 0
44 | Eastern | R.H. Saunders | SAU - Concrete Rehabilitation | 89543 | No | 0 | 0 | 0 | 0 | 0
45 | Eastern | Stewartville | STW - Access Rd and Bank Stabilization | 89572 | No | 0 | 0 | 0 | 0 | 0
46 | Subtotal Portfolio Projects (Allocated) - Eastern Region |  |  |  |  | 39.98 | 38.59 | 22.8 | 3.76 | 0
47 | Western | Silver Falls | SLV Electrical Infrastructure Replacement | 82005 | No | 2.2 | 9.59 | 0 | 0 | 0
48 | Western | Alexander | Stn. Switchgear, Protections & Ctrls. Repl. | 82378 | No | 0 | 0 | 0 | 0 | 0
49 | Western | Cameron Falls | T1 & T2 Replacement | 82390 | No | 0 | 0 | 0 | 0 | 0
50 | Western | Caribou Falls | Sluicegate Replacement | 82799 | Yes | 0 | 0 | 0 | 0 | 0
51 | Western | Pine Portage | PIN Sluicegate Replacement | 82802 | Yes | 0 | 0 | 0 | 0 | 0
52 | Western | Manitou Falls | Sluicegate Replacement | 82940 | Yes | 0 | 0 | 0 | 0 | 0
53 | Western | Caribou Falls | Caribou Block Dam #2 Rehab | 83029 | No | 0 | 0 | 0 | 0 | 0
54 | Western | Whitedog Falls | WHD Sluicegate Replacement | 83031 | Yes | 0 | 0 | 0 | 0 | 0
55 | Western | Aguasabon | Surge Tank Replacement | 83610 | Yes | 0 | 0 | 0 | 0 | 0
56 | Western | Caribou Falls | CAF Electrical Infrastructure Replacement | 84430 | No | 10.69 | 0.09 | 0 | 0 | 0
57 | Western | Caribou Falls | CAF 120/208V & Lighting Upgrade | 84432 | No | 0 | 0 | 0 | 0 | 0
58 | Western | Manitou Falls | MOT T1 Replacement | 84436 | No | 0.04 | 0 | 0 | 0 | 0
59 | Western | Whitedog Falls | WHD Sluicegate Repl. - Dogged #1-#4- #5-#6 | 84446 | Yes | 0 | 0 | 0 | 0 | 0
60 | Western | Whitedog Falls | WHD Electrical Infrastructure Replacement | 84448 | No | 3.6 | 10.63 | 0.11 | 0 | 0
61 | Western | Pine Portage | Black Sturgeon Dam | 86369 | No | 0 | 0.03 | 0.25 | 0.26 | 16.59
62 | Western | Caribou Falls | CAF Block Dam 4 Rehabilitation | 86602 | No | 0 | 0 | 0 | 0 | 0
63 | Western | Cameron Falls | CAM - Block Dam 3-4 Life Extension | 89000 | No | 0.41 | 0 | 0 | 0 | 0
64 | Subtotal Portfolio Projects (Allocated) - Western Region |  |  |  |  | 16.94 | 20.34 | 0.36 | 0.26 | 16.59
65 | Subtotal Portfolio Projects (Allocated) |  |  |  |  | 66.12 | 64.05 | 23.16 | 4.02 | 16.59
66 | Refurbishments (Allocated)
67 | Eastern | Lower Notch | Lower Notch GS - Unit G2 Capital Upgrades | 80694 | No | 0 | 0 | 0 | 0 | 0
68 | Eastern | Lower Notch | Lower Notch GS - G1 Capital Upgrade | 80692 | No | 0 | 0 | 0 | 0 | 0
69 | Eastern | Des Joachims | Des Joachims GS - Rewind Generators G1, G3, G5 | 80604 | No | 0 | 0 | 0 | 0 | 0
70 | Western | Silver Falls | SLV G1 Rewind and New Core | 82385 | Yes | 0 | 0 | 0 | 0 | 0
71 | Eastern | Otto Holden | OTO - Capital Project Scope G7 1st Unit | 84385 | Yes | 0 | 0 | 0 | 0 | 0
72 | Eastern | Barrett Chute | Rewind Generators & Reinsulate Field Poles (G1-4) First Unit (G3) | 80980 | Yes | 0 | 0 | 0 | 0 | 0
73 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1-4) Second Unit (G4) | 84587 | Yes | 0 | 0 | 0 | 0 | 0
74 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1) | 86082 | Yes | 0 | 0 | 0 | 0 | 0
75 | Eastern | Otter Rapids | Otter Runner Purchase | 80684 | Yes* | 0 | 0 | 0 | 0 | 0
76 | Niagara | DeCew Falls 2 | G1 Runner Shaft Replacement | 84558 | Yes | 0 | 0 | 0 | 0 | 0
77 | Eastern | Stewartville | STW - G5 Cap. Refurb. - Rwnd Gen. & Reinsul. | 82351 | Yes* | 5.31 | 0 | 0 | 0 | 0
78 | Eastern | Otto Holden | OTO - New Turbine Runners | 83356 | Yes* | 2.92 | 2.84 | 2.87 | 0.42 | 0
79 | Eastern | Otto Holden | OTO - G1 Refurb - Turbine & Generator | 87545 | Yes* | 3 | 0 | 0 | 0 | 0
80 | Western | Aguasabon | G2 Rewind & Core Replacement | 86383 | Yes | 0 | 0 | 0 | 0 | 0
81 | Western | Cameron Falls | CAM G7 Capital Refurb | 83257 | Yes | 0.64 | 0 | 0 | 0 | 0
82 | Eastern | Barrett Chute | BAR - G2 Cap. Rfrb; Rwnd Gen. Reins. Fld. Pls. | 86077 | Yes | 0 | 0 | 0 | 0 | 0
83 | Eastern | Otto Holden | OTO - G8 Refurb - Turbine & Generator | 86477 | Yes | 0 | 0 | 0 | 0 | 0
84 | Eastern | Otto Holden | OTO - G6 Refurb - Turbine & Generator | 86478 | Yes | 0 | 0 | 0 | 0 | 0
85 | Eastern | R.H. Saunders | Runner Replacement | 83104 | Yes | 1.79 | 0.81 | 0 | 0 | 0
86 | Subtotal Refurbishments (Allocated) |  |  |  |  | 13.66 | 3.65 | 2.87 | 0.42 | 0
87 | Redevelopments (Allocated)
88 | Eastern | Bingham Chute | Bingham Chute GS Redevelopment | 86385 | Yes* | 0.2 | 0 | 0 | 0 | 0
89 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program
90 | Eastern | Abitibi Canyon | Canyon Dam Downstream Concrete Rehab | 87192 | Yes | 0 | 0 | 0 | 0 | 0
91 |  |  | Total Regulated Hydroelectric |  |  | 79.98 | 67.7 | 26.03 | 4.44 | 16.59
92 |  |  | Hydro Common
93 | Western | Kenora Common | NWK Work Centre Buidling | 87139 | No | 7.3 | 0.1 | 0 | 0 | 0
94 |  |  | Total Hydro Common |  |  | 7.3 | 0.1 | 0 | 0 | 0
Notes:
1 | Col.(e): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2016-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 5). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.