## E-2-1-A1
Filed: April 22, 2026, EB-2025-0302, Exhibit E-2-1 Attachment 1, Page 1 of 1
Capital Projects - Appendix 2-AA
Note: 1. All the dollar figures listed below are in millions 2. Life to Date Capital Budget is the sum of prior year Capital actuals and current year Capital budget to account for the progressive elaboration of the budget. Life to Date Capital Actual is the sum of prior year Capital actuals and current year Capital actuals.
Change Initiatives/ Projects | 2023 Capital Budget | 2023 Capital Actual | 2024 Capital Budget | 2024 Capital Actual | 2025 Capital Budget | 2025 Capital Actual | Life to Date Capital Budget | Life to Date Capital Actuals | Life to Date Capital Variance | Variance Reason | 2026 Capital Budget | 2027 Capital Budget | 2028 Capital Budget | Status
Capacity Auction Enhancement | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | -0.2 | Underspend due to deferral of project to 2026 due to higher prioirity projects. | 1.2348 | 0.7392 | 0.7392 | Not Initiated - Plan to start in 2026
Other Initiatives/Projects (Less than $1 million) | [10 empty] | 0.92229 | 0.294 | 0.294
Commercial Reconciliation System Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.945 | 0.924 | 0.924 | In-flight - Initiation
Contract Settlement Solution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.42 | 1.26 | 0 | In-flight - Execution
DLRT- Dynamic Limit in Real Time Program - Project 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5586 | 0.5586 | 0.5628 | Not Initiated - Plan to start in 2026
Online IESO Enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.26 | 0 | 0
Enabling Resources Program (ERP) | 0.3 | 0 | 0.6 | 0.0026298 | 3.3 | 4.1268 | 4.2 | 4.1294 | -0.070556 | Underspend due to cashflow shift to future years. | 9.7098 | 8.5775 | 11.3541 | In-flight - Initiation
A. Storage and Hybrid Integration - Hitachi Energy | 0 | 0 | 0 | 0 | 0 | 0.0051839 | 0 | 0.0051839 | 0.0051839 | Project budget is drawn from the total Program budget
B. DER Integration | 0 | 0 | 0 | 0 | 0 | 0.049319 | 0 | 0.049319 | 0.049319 | Project budget is drawn from the total Program budget
Other Initiatives/Projects (Less than $1 million) | [10 empty] | 2.0802 | 0.70296 | 0.00040682
ADCS and MFT Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.428 | 0 | 0 | Not Initiated - Plan to start in 2026
Adopt Buy Model For User Computers | 0 | 0 | 0 | 0 | 0 | 2.1247 | 0 | 2.1247 | 2.1247 | Off-cycle project initiated. | 0.5778 | 0.58403 | 0.47951 | In-flight - Execution
Backup System Refresh | 0 | 0 | 0.25 | 0 | 0.6 | 3.2658 | 0.85 | 3.2658 | 2.4158 | Additional expense due to a combination of market and scope changes, including Commvault’s shift from a perpetual licensing model to a subscription-based model, updated vendor pricing and increased storage capacity requirements driven by data growth at the IESO. Additionally, the project scope has expanded beyond a standard hardware refresh to include enhanced capabilities such as ransomware protection and cloud backup functionality, aligning the solution with current cybersecurity and operational requirements. | 1.2693 | 0 | 0 | In-flight - Execution
Customer Interaction Center (CIC) Replacement | 0.2 | 0 | 0.15 | 0.13888 | 0 | 1.8017 | 0.35 | 1.9406 | 1.5906 | Additional expense due to change in approach from upgrade of the existing Genesys CIC platform to full replacement. However, due to the current (Genesys CIC) vendor’s transition to a cloud-only model that did not meet IESO’s compliance requirements, a competitive RFP was required, resulting in the selection of a more complex on-premises solution (Enghouse CIC) with expanded scope and higher associated costs. | 1.1384 | 0 | 0 | In-flight - Execution
Data Center Capacity Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.672 | 1.092 | 0.672 | Not Initiated - Plan to start in 2026
Data Governance Program Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.63 | 0.63 | Not Initiated - Plan to start in 2026
Data Warehouse Optimization | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | -0.5 | Underspend due to deferral of project to 2026 due to higher priority projects. | 0 | 1.05 | 0 | Not Initiated - Plan to start in 2026
DDMS and MPIS Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.68 | 5.04 | 0 | Not Initiated - Plan to start in 2026
DSO and SMDP Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.52 | 4.62 | Not Initiated - Plan to start in 2026
Facilities Maintenance Program 2026-2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5.46 | 8.4 | 3.78 | Not Initiated - Plan to start in 2026
Market Analysis and Simulation Toolset (MAST) | 0.5 | 0.2 | 2.4 | 0.4 | 1 | 0.6 | 3.9 | 1.2 | -2.7 | Underspend due to deferral of project to 2026 due to higher priority projects. | 0 | 0 | 0 | In-flight - Execution
MIM Replacement Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.42 | 1.176 | 0.672 | Not Initiated - Plan to start in 2026
Network Security Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.441 | 0.94616 | 2.8019 | Not Initiated - Plan to start in 2026
Network Upgrade Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.344 | 1.344 | 5.88 | Not Initiated - Plan to start in 2026
Network WAN Infrastructure | 0 | 0 | 1.6e-06 | 0 | 1e-07 | 0 | 1.7e-06 | 0 | -1.7e-06 |  | 1.05 | 0 | 0 | Not Initiated - Plan to start in 2026
SCADA/EMS AND PSS Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.924 | 5.46 | Not Initiated - Plan to start in 2026
Space Needs Program Phase 3 - Future @ Work | 7 | 0.24993 | 10 | 2.2588 | 13 | 14.2593 | 30 | 16.768 | 13.232 | Underspend due to delays in finalizing builiding design and permit reviews resulting in delays to start of construction. | 20.2029 | 15.6201 | 9.5015 | In-flight - Planning
Wallboard Video Wall Display Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5544 | 2.268 | 0 | Not Initiated - Plan to start in 2026
Subtotal: Capital Projects ($1 million and above) | 1.2 | 0.24993 | 1 | 2.4029 | 3.9 | 29.921 | 6.1 | 32.5739 | 26.4738 |  | 0 | 0 | 0
Other Initiatives/Projects (Less than $1 million) | 3.914 |  | 5.983 |  | 5.1285 |  | 21.2 | 20.9 | -0.3 |  | 7.1 | 3.7 | 2.8
Total Core IESO Capital Portfolio | 5.114 | 0.24993 | 6.983 | 2.4029 | 9.0285 | 29.921 | 103.9 | 102.1 | -1.8 |  | 60.4685 | 58.3506 | 51.1715
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update project list based on Appendix 3 2026-2028