## Sheet1
Project Name Plan | Planned In-Service Year | Actual In-Service Year | Status part a) iii) | Initiating Party part a) iv)
W2019-5546, Brock (Rossland x Manning) Ph B | 2020 | 2021 | Delayed | Joint
W2019-0512, Thickson (Wentworth - C.N. Rail) | 2020 | 2021 | Delayed | Elexicon
2020-6609, W Smith Dr x Wentworth OH relocation | 2020 | 2021 | Delayed | Joint
2020-0527, Thickson Rd S x Burns St E RR | 2020 | 2021 | Delayed | Joint
2020-6618, ROD MUP Rossland Rd W-Cntre St N x Sato St | 2020 | 2022 | Delayed | Joint
2020-0518, 200 Garden St - Anchor Relocation | 2020 | 2021 | Delayed | Joint
2020-0510, 794 McKay Rd Anchor Relocation | 2020 | 2023 | Delayed | Joint
2020-6607, U/G Service - 1615 Muskoka Rd N | 2020 | 2021 | Delayed | Joint
2020-0525, Fuller Rd Pole Removal | 2020 | 2021 | Delayed | Third-Party
2019-6609, Whites Rd (Taunton x Whitevale) - UG Streetlight Supply | 2020 | 2021 | Delayed | Joint
2019-6609B, Whites Rd (Taunton x Whitevale) - UG Streetlight Supply Phase 1 B | 2020 | 2021 | Delayed | Joint
2019-6610, Whites Rd (Whitvalex407) OH Temp Poleline | 2020 | 2021 | Delayed | Joint
2020-0207, Harwood & Salem feeder to 40-M47 | 2020 | 2021 | Delayed | Elexicon
2020-0513, Winchester Rd (Baldwin x Thickson) RR | 2020 | 2020 | - | -
W2019-5546A, Rossland (Brock St x Centre) Ph A | 2020 | 2020 | - | -
2019-0505, Region Rd 57 (Linden x CPR) Road Relocation | 2020 | 2020 | - | -
2020-6601, 3rd Party Damages | 2020 | 2020 | - | -
2017-0512, NE Industrial Park Rd | 2020 | 2020 | - | -
2017-0507B, Church St (Rossland Rd x ROW) Phase 2 | 2020 | 2020 | - | -
2018-0508, Paxton St (RosaxOld Simcoe)-Helipad Relocation | 2020 | 2020 | - | -
2020-0507, Bayly & Salem Anchor Relocation RR | 2020 | 2020 | - | -
2019-6607, Rossland Road Pole Supporting | 2020 | 2020 | - | -
2019-6623, 119 Franklin St Uxbridge-Pole relocation | 2020 | 2020 | - | -
2020-0301, Croft Street - 27.6kV Line Expansion | 2020 | 2020 | - | -
2020-6602, Third Party Make Ready Work | 2020 | 2020 | - | -
2020-6608, New Street Light Service Region of York | 2020 | 2020 | - | -
2019-6601, 3rd Party Damages | 2020 | 2020 | - | -
2020-0516, Bell Boulevard (West of Sidney St) RR | 2020 | 2020 | - | -
2020-0520, 9 Miller Island Pole Relocation Project | 2020 | 2020 | - | -
2020-0514, Sideline 24 RR | 2020 | 2020 | - | -
2016-0511, Toronto St Pole relocations | 2020 | 2020 | - | -
2016-0502, Sidney St at (Bell x Maple) | 2020 | 2020 | - | -
2018-0605, Temporary Services with and w/o TX's | 2020 | 2020 | - | -
2018-6625, Gordon Food Service Site Work - 200 Salem Rd (pole removals) | 2020 | 2020 | - | -
2019-6614, Squires Beach & Bayly – DL Intersection improvements | 2020 | 2020 | - | -
2019-6629, Taunton Rd (SL22XBurkholder Dr) | 2020 | 2020 | - | -
2020-6600, Customer Station Isolations | 2020 | 2020 | - | -
2020-6606, Ann and Cameron Intersection OH to UG | 2020 | 2020 | - | -
2020-6610, 41 Garden St Anchor Relocation | 2020 | 2020 | - | -
2020-6612, Generation Connection | 2020 | 2020 | - | -
W2019-1108, Coronation Road from Taunton Road to Rossland Road Line Removal | 2020 | 2020 | - | -
2020-6611, Anderson x Dundas Pole Relocation | 2020 | 2020 | - | -
2019-6617, Kellino & Church – DL Intersection improvements | 2020 | 2020 | - | -
2017-0303A, Metrolinx-Rodd Ave | 2020 | 2020 | - | -
2020-5542, Giffard St Pole Line upgrade (1300 Giffard St subdivision) | 2020 | 2020 | - | -
2019-6616, Westney & Bayly – DL Intersection improvements | 2020 | 2020 | - | -
2019-6631, 1460 Whites Rd Anchor Reconfiguration | 2020 | 2020 | - | -
2019-6621B, PTC Loop Restoration 2020 | 2020 | 2020 | - | -
2018-0205, Whites Rd Expansion (Hwy 7 x 407) | 2020 | 2020 | - | -
2018-0602, Transformers-General Services | 2020 | 2020 | - | -
W2019-0518, Rossland Rd. W (McQuay - DGN) | 2020 | 2020 | - | -
2017-0525, closed job - scugog x wellington | 2020 | 2020 | - | -
W2019-0525, Pole removals on Brock (Rossland - Taunton) | 2020 | 2020 | - | -
W2019-0520, Centre st. - (Miller x Dunlop) | 2020 | 2020 | - | -
2019-6615, Church & Bayly - DL Intersection improvements | 2020 | 2020 | - | -
W2019-0505, MTO Project (Brock st. - 401 bridge reconstruction) | 2020 | 2020 | - | -
2019-6605, Lot 14A Rankin Island (14LM) Relocation | 2020 | 2020 | - | -
W2019-0504, 407 Baldwin St | 2020 | 2020 | - | -
2017-0507, Church St (Rossland Rd x ROW) | 2020 | 2020 | - | -
2016-0205H, DL Kellino St Relocation (Squires X Bayly)- 2019 | 2020 | 2020 | - | -
W2019-0527, Electrification Project - Brock St. Rail crossing | 2020 | 2020 | - | -
2020-0515, 39 Mill Street North Stub Pole Relocation | 2020 | 2020 | - | -
2020-0519, U/G Service Repair - 5176 Main Street Orono | 2020 | 2020 | - | -
2020-6603, U/G Capital Cable Locates | 2020 | 2020 | - | -
2020-6604, P112954 - Pole Removal | 2020 | 2020 | - | -
2020-6605, 6700 Coronation Rd Whitby 1Ph Service | 2020 | 2020 | - | -
2020-6613, Port Hope CP Rail Bridge Repair | 2020 | 2020 | - | -
2020-6615, Dunlop St Pole Line Upgrade | 2020 | 2020 | - | -
W2019-0525B, Brock Street Pole Support (Pole #19635) | 2020 | 2020 | - | -
2015-0507B, Westney Rd (Magill Dr x Rossland Rd) Phase B | 2020 | 2020 | - | -
W2019-0501, Metrolinx Electrification Project - South Blair | 2021 | 2025 | Deferred | Joint
W2019-0502, Electrification Project - Thickson CN crossing (West Side) | 2021 | 2024 | Delayed | Joint
2019-6613, Brock & Bayly – DL Intersection improvements | 2021 | Projected 2028 | Deferred | Third-Party
2020-0208, Temp Pole Line at DNB Relocation | 2021 | Projected 2031 | Deferred | Third-Party
2020-0521, Coronation (Taunton x Des Newman) RR | 2021 | Projected 2026 | Deferred | Elexicon
2020-0523, Whitevale (Altona x Golf Club) | 2021 | Projected 2026 | Delayed | Third-Party
2020-0524, Victoria (Thickson x Oshawa Border) | 2021 | 2023 | Delayed | Elexicon
2017-0303H, Metrolinx-Salem Rd | 2021 | 2025 | Delayed | Third-Party
2017-0303B, Metrolinx-Brock Rd west of Trans Tower | 2021 | 2022 | Delayed | Third-Party
2017-0303G, Metrolinx-Harwood Ave (Windsor Ave) | 2021 | 2022 | Delayed | Third-Party
2020-6614, 1160 Narrows Rd New Service | 2021 | 2022 | Delayed | Joint
2020-6619, 1018 Sutherland Point New Service | 2021 | 2022 | Delayed | Joint
2017-0303C, Metrolinx-Brock Rd East of Trans Tower | 2021 | 2022 | Delayed | Third-Party
2017-0303F, Metrolinx-Westney Rd (Knapton Ave) | 2021 | 2022 | Delayed | Third-Party
2020-0512, Rossland (Church x Westney) RR | 2021 | 2021 | - | -
2017-0526E, BRT Highway 2 (Salem x Galea) | 2021 | 2021 | - | -
2017-0520, Westney Rd N (Williamson x Taunton) | 2021 | 2021 | - | -
2021-6612, 95 Taunton Rd E Pole 6911 relocation | 2021 | 2021 | - | -
2021-6618, Dufferin St Poles Relocation | 2021 | 2021 | - | -
2021-6601, 3rd Party Damages | 2021 | 2021 | - | -
2021-6608, 218 Park Street Service Conductor Relocation | 2021 | 2021 | - | -
2019-6618, Marquis Towns. Relocation of existing plant | 2021 | 2021 | - | -
2021-0509, Orchard & Pringle Relocations | 2021 | 2021 | - | -
2020-6616, Lakeridge LTC Pole Relocation | 2021 | 2021 | - | -
2020-0526, Planks x Franklin Uxbridge RR | 2021 | 2021 | - | -
W2019-1109, DNB - Rossland road from Lakeridge Road to Des Newman Blvd | 2021 | 2021 | - | -
2021-6607, Station St Anchor Reconfig | 2021 | 2021 | - | -
2021-6615, Annes St Strut Install (Pole 413, 426) | 2021 | 2021 | - | -
2021-6616, 505 Victoria St E (pole 1210) | 2021 | 2021 | - | -
2021-0516, TOW MUP 505 Victoria St. - Whitby Anchor Relocation | 2021 | 2021 | - | -
2021-6622, Pole Removal - Park Cres | 2021 | 2021 | - | -
2019-6620, Whites & Whitevale Loop Connection | 2021 | 2021 | - | -
2021-6617-1, 3rd Party Damage Oil Spill | 2021 | 2021 | - | -
2020-0210, 360 Frankcom St Poleline relocation | 2021 | 2021 | - | -
2021-6600, Customer Station Isolations | 2021 | 2021 | - | -
2021-6611, 333 Rossland Rd E - Relocations | 2021 | 2021 | - | -
2021-6621, 5185 Garrard - Pole relocation | 2021 | 2021 | - | -
2020-0511, 1475 Whites Road Relocation | 2021 | 2021 | - | -
W2019-0529, MTO - Hwy 12 Relocation | 2021 | 2021 | - | -
2016-0518, Westney Rd (Rossland x Williamson) | 2021 | 2021 | - | -
2019-6619, Given Rd (King Ave x Rudell Rd) - Pole relocation | 2021 | 2021 | - | -
2019-6622, Bayly W of Squires Beach DL Intersection improvements | 2021 | 2021 | - | -
2021-6603, U/G Capital Cable Locates | 2021 | 2021 | - | -
2021-6604, Generation Connection | 2021 | 2021 | - | -
W2019-0507A, Victoria St W (South Blair to Thickson) - Relocation (Service to Metrolinx) ph 1 of 2 | 2021 | 2021 | - | -
W2019-0507B, Victoria St W (South Blair to Thickson) - Relocation (Service to Metrolinx) ph 2 of 2 | 2021 | 2021 | - | -
W2019-0509, Winchester Rd. (Baldwin - Gerrard) (actual scope Baldwin to Thickson) | 2021 | 2021 | - | -
W2019-5501, Metrolinx Jack and bore for CN crossing at Thickson (West side) | 2021 | 2021 | - | -
2018-0510, Sandy Beach (Montgomery x Bayly) RR | 2022 | Projected 2027 | Deferred | Third-Party
2020-0211, Dunlop St Pole Line Expansion | 2022 | 2025 | Delayed | Joint
2020-0214, Burkholder (Hwy 7 x Kubota) | 2022 | Project is cancelled | Cancelled | Third-Party
2016-0516A, Peter Matthews (Brock x Toronto Landfill) – Road Relocation | 2022 | 2023 | Delayed | Joint
2017-0526C, BRT Hwy 2 (Liverpool x Dixie) (ICM) | 2022 | 2023 | Delayed | Third-Party
2023-6610, Customer Requested Work | 2022 | 2023 | Delayed | Joint
2017-0303E, Metrolinx-Squires Beach Rd-LSE 139 (wood pole crossing) | 2022 | 2023 | Delayed | Third-Party
2022-6604, Generation connection | 2022 | 2021 | Delayed | Joint
W2019-0507AB, Victoria St W (South Blair to Thickson) PhAB | 2022 | 2022 | - | -
2017-0526B, BRT Hwy 2 (Glenanna x Brock) (ICM) | 2022 | 2022 | - | -
2015-0501, Brock Rd (Taunton x 5th Conc) | 2022 | 2022 | - | -
2022-1000, Misc Jobs | 2022 | 2022 | - | -
2022-0000, TEMP NUMBER | 2022 | 2022 | - | -
2022-6610, Customer Requested Work | 2022 | 2022 | - | -
2021-0515, Lakeridge (Myrtle x CP Rail) RR | 2022 | 2022 | - | -
2022-6601, 3rd Party Damages | 2022 | 2022 | - | -
2022-0523, Brown St Road Relocation | 2022 | 2022 | - | -
2020-0512A, Rossland (Church x Westney) RR | 2022 | 2022 | - | -
W2019-0512B, Thickson (Wentworth - C.N. Rail) | 2022 | 2022 | - | -
2022-6605, Pole Removal - 143 New St, Uxb | 2022 | 2022 | - | -
2017-0520A, Westney (TauntonxTelfod) Removals | 2022 | 2022 | - | -
2021-0517, Pole 392 Dundas St Whitby | 2022 | 2022 | - | -
2022-6602, Third Party Make Ready Work | 2022 | 2022 | - | -
2020-0511A, Pine Ridge Tower Ltd-Removals | 2022 | 2022 | - | -
2020-6620, Pole 779 Anchor Relocation | 2022 | 2022 | - | -
2021-0513, Sidney St (Bridge St W x Wilkins St) RR | 2022 | 2022 | - | -
2021-6609, Thompson St Pole Line Relocation | 2022 | 2022 | - | -
2022-0502, Garrard Rd - North of Conlin | 2022 | 2022 | - | -
2021-6621A, 5185 Garrard - Pole relocation | 2022 | 2022 | - | -
2017-0517, Henry Street Relocations - Moira x Cedar | 2022 | 2022 | - | -
2019-6621A, PTC - UG Re-Connection | 2022 | 2022 | - | -
W2019-5546B, Rossland (Brock St x Centre) Ph B | 2022 | 2022 | - | -
2021-6617, 3rd Party Damage Trouble Call 11161532 | 2022 | 2022 | - | -
2022-6603, U/G Capital Cable Locates | 2022 | 2022 | - | -
2019-0502, Liberty St (Longworth Ave x Conc Rd 3) ($300K estimate with $90K contribution) | 2023 | 2024 | Delayed | Joint
2017-0526d, BRT Hwy 2 (Delta x Merritton) | 2023 | 2023 | - | -
2017-0526BA, BRT Hwy 2 (Glennana X Brock) | 2023 | 2023 | - | -
2022-0512, Thickson & Rossland RR | 2023 | 2023 | - | -
2022-0509, Taunton & Anderson RR | 2023 | 2023 | - | -
2013-0503, Rossland Road (Clearside x Southcott) | 2023 | 2023 | - | -
2023-6601, 3rd Party Damages | 2023 | 2023 | - | -
2022-0515, Orchard Dr (N Park Gardens x N Park Gardens) | 2023 | 2023 | - | -
2022-0517, Murney Street (Moira x Catharine) | 2023 | 2023 | - | -
2020-0517A, Bowmanville Ave (Baseline x Hwy 2) | 2023 | 2023 | - | -
W2019-0512BA, Thickson (Wentworkth - C.N. Rail) | 2023 | 2023 | - | -
2020-0512B, Rossland (Church X Westney) Rem | 2023 | 2023 | - | -
2020-0210A, Poleline Reloc - 360 Frankcom | 2023 | 2023 | - | -
W2019-5546C, Rossland x Brock Pole Removals | 2023 | 2023 | - | -
2023-0502, Whites Rd (North of Kingston Rd x Finch Ave) | 2023 | 2023 | - | -
2023-6602, Third Party Make Ready Work | 2023 | 2023 | - | -
2022-0508, Kerrison (E of Salem) | 2023 | 2023 | - | -
2022-0208, Project Toro 44kV Expansion | 2023 | 2023 | - | -
2023-0501, Road Relocation bucket | 2023 | 2023 | - | -
2023-6611, Columbus x White Bridge - Temp Pole Reloc | 2023 | 2023 | - | -
2021-0211B, 1652 Tricont Ave- 44KV Expansion -LEAR | 2023 | 2023 | - | -
2023-1000, Misc Jobs | 2023 | 2023 | - | -
2015-0501A, Brock (Taunton x Alex Knox) Ph2 | 2023 | 2023 | - | -
2016-0516A2, Peter Matthews (Brock x Toronto Landfill) – Road Relocation Ph2 | 2023 | 2023 | - | -
2022-0521, Sidney (CPR x College) | 2023 | 2023 | - | -
2023-6603, U/G Capital Cable Locates | 2023 | 2023 | - | -
2017-0526G, BRT Highway 2 (Lakeridge x Des Newman) | 2024 | 2024 | - | -
2017-0526M, BRT Hwy 2 at Salem | 2024 | 2024 | - | -
2022-0514, Rossland & Garden Intersection | 2024 | 2024 | - | -
2022-0525, Baldwin at MBAR | 2024 | 2024 | - | -
2017-0526BA2, BRT Hwy 2 (Glennana X Brock) ICM | 2024 | 2024 | - | -
2015-0501B, Brock Rd(Taunton x 5th Conc) Ph3 | 2024 | 2024 | - | -
2017-0526CA, BRT Hwy 2 (Liverpool x Dixie)-ICM | 2024 | 2024 | - | -
2020-0513A, Winchester Rd (Baldwin x Thickson) Cleanup | 2024 | 2024 | - | -
2024-6610, Customer Requested Work | 2024 | 2024 | - | -
W2019-0507AB2, Victoria St W (South Blair to Thickson) PhAB | 2024 | 2024 | - | -
2022-0524, 401 W of Sleeman Dr | 2024 | 2024 | - | -
2024-6601, 3rd Party Damages | 2024 | 2024 | - | -
2024-6602, Third Party Make Ready Work | 2024 | 2024 | - | -
2017-0303A2, Metrolinx-Rodd Ave (Remaining work) | 2024 | 2024 | - | -
2022-0508A, Kerrison (E of Salem) | 2024 | 2024 | - | -
2024-0501, Road Relocation bucket | 2024 | 2024 | - | -
2024-6603, U/G Capital Cable Locates | 2024 | 2024 | - | -