## 2-CCC-19 Attachment 1
Completion Year | Project | NET ISA Plan | NET ISA Actual ($) | Net Variance Actual (%) | Variance Exceed +/- 10% (Yes/No) | Description of Project | Description of Variance | Variance Theme
2020 | Ajax Renewal-Reactive | 618000 | 922080.04 | 49.2% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2020 | Ashburn Rd (Townline Rd x Brawley) OH Rebuild Ph1 & 2 | 1250000 | 1346266.54 | 7.701% | No | Overhead rebuild along Townline Rd and Ashburn Rd from Townline Rd to Brawley Rd, including CP rail crossing | Not applicable. | -
2020 | Brock (Rossland x Manning) Ph B | 852000 | 921010.6 | 8.1% | No | Request from road authority to relocate pole line on Brock Street from Rossland Road to Manning Road. | Not applicable. | -
2020 | New Res Development-Non Seaton | 1771000 | 1193190.03 | -32.63% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions. Excludes Seaton area of Pickering. | Actual customer‑driven work volumes below the levels forecasted in the original plan. | Customer Demand-Driven Project
2020 | New Res Development-Seaton | 1270000 | 2433641.98 | 91.63% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in Seaton Area of Pickering | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2020 | Toronto Substation Rebuild | 1950000 | 1765634.94 | -9.455% | No | Planned Capital Project to rebuild Toronto substation, located in Newcastle, Ontario. | Not applicable. | -
2020 | U/G New Residential Services | 847769 | 1002215.98 | 18.22% | Yes | Customer driven low voltage residential connections from customer lot to meter for underground servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2020 | Winchester Rd (Baldwin x Thickson) RR | 863400 | 703472.85 | -18.52% | Yes | Customer driven project which involved relocation of Overhead System to accommodate road authority road widening | Labour cost variance relative to amounts forecast in the annual plan. | Customer Demand-Driven Project
2020 | Wood Poles Renewal-Planned | 1413000 | 1517761.75 | 7.414% | No | Planned replacement of Poles based on Asset Condition | Not applicable. | -
2021 | Cavan South Ph 2 Voltage Conv (4.16kV x 27.6kV) | 500000 | 954758.94 | 90.95% | Yes | Planned capital project to convert the voltage from 4.16kV to 27.6kV in Port Hope. | Variance due to labour requirements under-estimated in preliminary stages of project planning. | Planned Distribution Project
2021 | Ajax Renewal-Reactive | 500000.01 | 843584.51 | 68.72% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2021 | CIS Merge Project | 962000 | 909671.27 | -5.44% | No | Customer Information System (CIS) project to merge the Whitby and Veridian NorthStar CIS Instances. | Not applicable. | -
2021 | Firon In-Line Switch Replacements | 317000 | 870361.35 | 174.6% | Yes | Planned replacement of In-Line Switches based on Asset Condition. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2021 | MS11 T2 44kV reliability W. Lawler SS | 2660445 | 2954956 | 11.07% | Yes | Project to improve reliability and capacity for W. Lawler Substation in Whitby- adding new protective devices and upgraded transformer. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project
2021 | New Res Development-Non Seaton | 1450000 | 5437669.22 | 275% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in all Elexicon Service territory. Excludes Seaton Area of Pickering | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2021 | Overhead Line Switches (LIS) - Renewal Planned (VW) | 300000 | 726782.04 | 142.3% | Yes | Planned replacement of Load Interrupter Switches based on Asset Condition. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2021 | Padmount Switchgear-Renewal Planned | 700000 | 841337.32 | 20.19% | Yes | Planned replacement of Padmount Switchgear based on Asset Condition. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2021 | Primary Cable - UG Rehabilitation | 2399000 | 2524987.05 | 5.252% | No | Underground cable rehabilitation project to replace underground primary, secondary cables and trasformers. Area experienced multiple cable faults, project initiated to address the deficiencies | Not applicable. | -
2021 | Primary Cable - UG Rejuvenation | 1800000 | 1936890.76 | 7.605% | No | Cable injection rejuvenation project for underground direct buried cables to extend the useful life. | Not applicable. | -
2021 | Residential Type Meters | 1059240 | 716640.48 | -32.34% | Yes | Supply and install meters for new residential connections and address meter failures | Variance attributable to supply chain delays (60–80 weeks) and fluctuations in housing market demand. | Customer Demand-Driven Project
2021 | Rossland (Church x Westney) RR | 753250 | 922320.65 | 22.45% | Yes | Relocation request from road authority involving removal and installation of new poles, removal and installation of transformers, removal and installation of 44 kV LIS. | Variance attributable to actual material and labour costs exceeding project estimates. | Customer Demand-Driven Project
2021 | Rossland W (MS8) Substation TX & Relay replacement | 1200000 | 1010581.87 | -15.78% | Yes | Substation growth and expansion project to upgrade the transformer capacity due to load growth in area and to upgrade protection relay at station | Variance attributable to actual costs being lower than the preliminary scope-based estimate. | Planned Distribution Project
2021 | U/G New Residential Services | 726000 | 1254666.95 | 72.82% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for underground servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2021 | Wood Poles Renewal-Planned | 1200000 | 2924375.61 | 143.7% | Yes | Planned replacement of Poles based on Asset Condition. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2022 | Ajax Renewal-Reactive | 500000 | 1214122.26 | 142.8% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2022 | Belleville Relocation building | 5200000 | 4523212.95 | -13.02% | Yes | Construction of new Belleville Building as the previous lease arrangement was not extended by City of Belleville. | Variance attributable to a scope deferral of the communications tower in 2023 due to permitting issues. | General Plant Project
2022 | Brock Rd (Taunton x Alex Knox) | 868614.74 | 977815.79 | 12.57% | Yes | Relocation request from road authority to relocate/adjust poles in conflict with new road design. (1.8 Kms of Overhead Pole Line) | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2022 | Data Centre infrastructure - Upgrades and enhancements | 1024000 | 1608638.72 | 57.09% | Yes | Replacement of aging network devices, including network redesign, implementation and integration. Existing infrastructure was end of life and end of support. | Accelerated replacement of end-of-life network infrastructure was required to mitigate cyber security risks and maintain vendor support for critical systems. Costs include network switch replacements and consulting for design and implementation support. | General Plant Project
2022 | New Res Development-Non Seaton | 2221588 | 2978585.16 | 34.07% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in all Elexicon Service territory except for Seaton Area of Pickering | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2022 | New Res Development-Seaton | 506050 | 878764.02 | 73.65% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in Seaton Area of Pickering | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2022 | Overhead Line Switches-Sustainment Planned | 300000 | 749787.56 | 149.9% | Yes | Planned replacement of Load Interrupter Switches based on Asset Condition as highlighted by Asset Condition Assessment. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2022 | Pickering Beach Station upgrade | 1086000 | 1007482.2 | -7.23% | No | Replacement of existing assets due to poor condition. Installation of new switchgear, transformer protection relay, current transformer, riser poles and associated civil work. | Not applicable. | -
2022 | Primary Cable - UG Rejuvenation-V | 500000 | 1205359.54 | 141.1% | Yes | Injection of the cables based Asset Condition Assessment study and Non Destructive Testing results. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2022 | Substation Deficiency Corrections-V | 400000 | 753217.51 | 88.3% | Yes | Reactive correction of issues in Substations found during trouble calls and monthly inspections for the Veridian Service Territory. | Incremental expenditures required to reactively address deficiencies in substations which were identified during the calendar year. | Reactive Project
2022 | U/G New Residential Services | 699125 | 1201971 | 71.93% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for underground servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2022 | Victoria St W (South Blair to Thickson) PhAB | 1863587 | 2340820.57 | 25.61% | Yes | Road Relocation request from road authority to relocate the pole line. | Labour cost variance relative to amounts forecast in the annual plan. | Customer Demand-Driven Project
2022 | Whitby Renewal-Reactive | 500000 | 798974.81 | 59.79% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2022 | Windstorm VRZ | 0 | 3443612.38 |  | No | Reactive capital work in response to Derecho Windstorm in May 2022 in Veridian Service Territory | Reactive Derecho storm response, unplanned work | Reactive Project
2022 | Windstorm WRZ | 0 | 822412.04 |  | No | Reactive capital work in response to Derecho Windstorm in May 2022 in Whitby Service Territory | Reactive Derecho storm response, unplanned work | Reactive Project
2022 | Wood Poles Renewal Program | 671000 | 2077822.32 | 209.7% | Yes | Planned replacement of Wood Poles based on Asset Condition as highlighted by Asset Condition Assessment. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2023 | Ajax Renewal-Reactive | 500000.36 | 1768225.15 | 253.6% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2023 | Brock Renewal-Reactive | 84481 | 896613.67 | 961.3% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2023 | BRT Hwy 2 (Delta x Merritton) | 960687 | 953440.6 | -0.7543% | No | Ongoing Metrolinx Bus Rapid Transit (BRT) Project through Pickering requiring Elexicon infrastructure relocations for additional bus lanes. | Not applicable. | -
2023 | BRT Hwy 2 (Glennana X Brock) | 1950000 | 734637.28 | -62.33% | Yes | Ongoing Metrolinx Bus Rapid Transit (BRT) Project through Pickering requiring Elexicon infrastructure relocations for additional bus lanes. | Variance attributable to actual in‑service timing differing from that assumed in the capital plan. | Customer Demand-Driven Project
2023 | Church SS Cable Replacement | 265000 | 1131658.12 | 327% | Yes | Replacement of F1 and F2 feeder egress cables from Church Substation in Belleville due to poor condition. | The variance is primarily attributable to higher‑than‑estimated material costs, particularly underground cable, relative to the estimate prepared in 2019 and construction executed in 2023. | Planned Distribution Project
2023 | CN crossing at Thickson (West side) (NOT Metrolinx) | 1144000 | 1645816.68 | 43.87% | Yes | System reliability improvement project to complete the 44KV and 13.8KV distribution system along the Metrolinx - CN Tracks via underground. | The variance is primarily attributable to higher‑than‑estimated material costs, particularly underground cable, relative to the estimate prepared in 2020 and construction executed in 2023. | Planned Distribution Project
2023 | Cyber Security | 150000 | 869245.69 | 479.5% | Yes | Annual cyber security project to address identified cyber security risks through targeted investments in security related infrastructure and systems. Focus on maintaining the reliability, security, and supportability of Elexicon’s IT and operational technology environments. | The 2023 cyber security capital variance was primarily attributable to an unplanned, urgent firewall replacement initiative that was identified after the original capital budget was approved. | General Plant Project
2023 | Data Centre infrastructure - Upgrades and enhancements | 150000 | 728303.04 | 385.5% | Yes | Replacement of aging network devices, including network redesign, implementation and integration | Accelerated replacement of end-of-life network infrastructure was required to mitigate cyber security risks and maintain vendor support for critical systems. Costs include network switch replacements and consulting for design and implementation support. | General Plant Project
2023 | Des Newman (MS16) Upgrade | 1000000 | 1111367.41 | 11.14% | Yes | Substation Growth & Expansion project which involves installation of power transfomers and new feeders. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project
2023 | Main St E (Nancy x Madill) Beaverton Ph2 | 633438 | 863302 | 36.29% | Yes | Planned Capital work related to replacement and removal of pole, installation of conductors, switches and transformers. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project
2023 | Montgomery Park (Sandy Beach x Brock) | 538000 | 1007667.31 | 87.3% | Yes | System service, system reliability improvement project involving building of 13.8kV crcuit | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project
2023 | New Res Development-Non Seaton | 1220900 | 3194271.36 | 161.6% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in all Elexicon Service territory except for Seaton Area of Pickering | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2023 | New Res Development-Seaton | 2839100 | 1239261 | -56.35% | Yes | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in Seaton Area of Pickering | Actual customer‑driven work volumes below the levels forecasted in the original plan. | Customer Demand-Driven Project
2023 | P&C- James Collins SS- Control Hut/Recloser Controls Repl | 420000 | 964717.53 | 129.7% | Yes | Replacement of Control shed for James Collins substation in Port Hope and associated obsolete recloser controls. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project
2023 | Peter Matthews (Brock x Toronto Landfill) | 2260000 | 3416046.37 | 51.15% | Yes | Road relocation request from road authority with region planning a road widening and Elexicon assets had to be replaced to accommodate. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2023 | Residential Type Meters | 519960 | 841536.15 | 61.85% | Yes | Purchase and Supply meters for new residential connections and address meter failures | Variance attributable to supply chain delays leading to an increase of meter installations in 2023 along with fluctuations in housing market demand. | Customer Demand-Driven Project
2023 | U/G New Residential Services | 624500 | 1071121.65 | 71.52% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for underground servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2023 | Whitby Renewal-Reactive | 500000 | 1005802.78 | 101.2% | Yes | Reactive corrective actions undertaken by Line Operations in response to issues identified during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2023 | Wood Poles Renewal-Planned-V | 640000 | 1032919.45 | 61.39% | Yes | Planned replacement of Poles based on Asset Condition Assessment. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2024 | Ajax Renewal-Reactive | 500000 | 3042578.69 | 508.5% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2024 | Belleville Renewal-Reactive | 400000 | 1008585.67 | 152.1% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2024 | Brock Renewal-Reactive | 84480 | 1023679.69 | 1112% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2024 | BRT Highway 2 (Lakeridge x Des Newman) | 1576193 | 1435902.2 | -8.901% | No | Ongoing Metrolinx Bus Rapid Transit (BRT) Project through Pickering requiring Elexicon infrastructure relocations for additional bus lanes. Not part of ICM EB-2021-0015 | Not applicable. | -
2024 | Clarington Renewal-Reactive | 219320 | 719994.29 | 228.3% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2024 | Gravenhurst Renewal-Reactive | 116186 | 1661138.08 | 1330% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2024 | Integrated Operations Centre | 1681526 | 1346447.42 | -19.93% | Yes | Project to move the Elexicon Control room to Ajax from Clarington and make necessary building/communications/networking adjustments in Ajax to accommodate it. Move to Ajax driven by ongoing communications and networking issues with Clarington site. | Variance primarily attributable to database and middleware enhancements that were pushed to the following year due to the complexity of the program and sequencing of projects required. Additionally, a fire supression project was delayed to the following year given the complexity of the permitting process. | General Plant Project
2024 | Liberty St (Longworth x Conc Rd 3) | 925000 | 817812.82 | -11.59% | Yes | Road relocation request from the region to relocate/adjust poles in conflict with new design. | Actual estimated customer‑driven work volume less than the levels forecasted in the original plan. | Customer Demand-Driven Project
2024 | Monarch SS- Swgr Replacement | 3125910 | 4498238.39 | 44% | Yes | Substation renewal project involving replacement of Switchgear, Transformer, Relays, Reclosers and additional equipment. | Variance attributable to an increase in the scope of work based on the inclusion of additional station assets which were found to be in poor and deteriorating condition, as well as higher than estimated material and labour costs. | Planned Distribution Project
2024 | O/H New Residential Services | 622212 | 865174.94 | 39.05% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for overhead servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2024 | Residential Type Meters | 519960 | 866648.77 | 66.68% | Yes | Purchase and Supply meters for new residential connections and address meter failures | Variance attributable to supply chain delays leading to an increase of meter installations in 2024 along with fluctuations in housing market demand. | Customer Demand-Driven Project
2024 | U/G New Residential Services | 626212 | 1538542.81 | 145.7% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for underground servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2024 | Vehicles, (Small) | 250000 | 777883.4 | 211.2% | Yes | Spend on purchase of small vehicles including pickup trucks/Van/SUV | Updated plan was $590K (for 7 small vehicles) in 2024. Total of 10 vehicles purchased. Replacement of end of life vehicles based on the mileage and/or age threshold. | General Plant Project
2024 | Whitby Renewal-Reactive | 500000 | 2559771.67 | 412% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2025 | 1900 Boundary Road 44 KV Expansion 2024-0211 | 967004.85 | 849432.31 | -12.16% | Yes | Customer driven feeder expansion work where an industrial warehouse requested for service. Existing 44kV line extended to frontage of customer address. To mitigate power disruptions within the industrial zone, most of feeder extension installed underground. | The planned replacement of one Load Break Switch (~$100K) was removed from the scope of work and dealt with as a separate project due to age and safety concerns. | Customer Demand-Driven Project
2025 | 2025 L4L Pole Repl- Whitby 1 | 603275 | 799351.95 | 32.5% | Yes | Planned replacement of Wood Poles based on Asset Condition as highlighted by Asset Condition Assessment. | Variance attributable to an increase in the scope of work and the inclusion of additional units to address deteriorating asset condition and reliability. | Planned Distribution Project
2025 | 2025 Storm Restoration Costs | 3300000 | 3178953.85 | -3.668% | No | Reactive capital work in response to March 2025 Icestorm impacting Elexicon service territories | Not applicable. | -
2025 | 27.6kV Whites (407 x Hwy 7) Caplink FGF - EE EXP | 1543000 | 1385895.35 | -10.18% | Yes | Customer driven feeder expansion project with a request of additional load. As existing feeder does not have capacity for this request, an expansion of additional circuit was required. | Variance primarily attributable to labour and material costs below the original estimate. | Customer Demand-Driven Project
2025 | 44KV Garrard-Taunton to Conlin | 750000 | 780043.98 | 4.006% | No | Customer Driven project to service new industrial development- included expanding 44 kV feeder,and loop 44 kV from Taunton Rd to Conlin Rd (west of Garrard Rd). | Not applicable. | -
2025 | BAYLY (SANDY BEACH X BROCK) | 2143484 | 2288013.01 | 7.083% | No | Feeder Expansion Project. Existing 13.8 kV system in this area does not have sufficient capacity so 27.6kV expansion is required. This project is just for Bayly St portion. | Not applicable. | -
2025 | Bayly St (Sandy BeachxBrock) | 2143484 | 2288013.01 | 6.743% | No | Project to convert the 13.8kV System to 27.6kV to enable servicing the South Pickering area the existing 13.8kV system is at capacity. | Not applicable. | -
2025 | Bowmanville Ave (Baseline x Hw | 1298686 | 1704701.39 | 31.26% | Yes | Road Relocation project driven request from City of Pickering to relocate/adjust poles in conflict with the culvert an watermain installation. | Variance attributable to labour and material costs exceeding the original estimate. | Customer Demand-Driven Project
2025 | Brock Rd (Hwy 2 X Bayly)-27.6kV | 4866336.5 | 3845872.74 | -20.97% | Yes | Customer driven project, existing 13.8kV nearing full capacity. New 27.6kV circuit to serve the customer. | Project was redesigned due to regional work and soil contamination along Bayly and Brock. The scope of work was over-estimated, with less remediation work required than projected. | Customer Demand-Driven Project
2025 | Brock Rd (Hwy 401 Crossing) | 2040501 | 2632756.46 | 29.03% | Yes | Feeder Expansion Project. Existing 13.8 kV system in this area does not have sufficient capacity so 27.6kV expansion is required. This project is just for Hwy 401 crossing. | The variance is primarily attributable to higher‑than‑estimated material costs, particularly underground cable, relative to the estimate prepared in 2022 and construction executed in 2025. | Customer Demand-Driven Project
2025 | Customer 44kV Poleline 2021-0210 | 3826782.73 | 4761326.26 | 24.42% | Yes | Customer driven feeder expansion project with customer requiring additional amount of load to their service. As the existing feeder did not have capacity for required service upgrade, service upgrade was installed on the 8M-10 feeder. | Hydro One Connection Cost ($2.2M) was initially paid by Customer but not included in the initial Economic Evaluation. Repayment of Hydro One connection cost to customer was not included in the plan resulting in higher spend than planned. Plan line was based on Forecasted Project Cost from 2022, Actual Design was completed in 2024 with differences seen in labour and material costs. | Customer Demand-Driven Project
2025 | O/H New Residential Services | 862036.592 | 1195109.37 | 38.64% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for overhead servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2025 | Renewal-Reactive - Ajax | 1925000 | 4074913.74 | 111.7% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2025 | Renewal-Reactive - Belleville | 700000 | 1092645.09 | 56.09% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2025 | Renewal-Reactive - Clarington | 614951.9855 | 878370.98 | 42.84% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Incremental expenditures required to reactively address distribution system deficiencies identified during the calendar year. | Reactive Project
2025 | Renewal-Reactive - Whitby | 1700000 | 1280967.2 | -24.65% | Yes | Reactive correction by Line Operations of issues found during trouble calls and inspections. | Variance attributed to lower expenditures required to reactively address deficiencies identified during the calendar year. | Reactive Project
2025 | Residential Development | 4000000 | 3991245.58 | -0.2189% | No | Customer driven work related to installation of primary electrical infrastructure to energize new subdivisions in Ajax. | Not applicable. | -
2025 | Residential Type Meters | 836400 | 894664.59 | 6.966% | No | Purchase and Supply meters for new residential connections and address meter failures | Not applicable. | -
2025 | U/G New Residential Services | 1406811.5784 | 1912023.57 | 35.91% | Yes | Customer Driven Low Voltage Residential Connections from customer lot line to meter for underground servicing. | Actual customer‑driven work volumes exceeded the levels forecasted in the original plan. | Customer Demand-Driven Project
2025 | Whitby, Bucket V614&615 | 1464720 | 1436374.05 | -1.935% | No | Spend related to fleet purchase. | Not applicable. | -