## 2-Staff-73 a) 2025
Project Name | Project Description | DSP Program | Project Category | In-Service Addition Planned Completion Milestone | Net $ Planned ISA in ERA plan | Actual ISA
Metrolinx-Squires Beach Rd-LSE 139 (wood pole crossing) | Third Party - Metrolinx Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-01-20 | 0 | 0
Bowmanville Ave (Baseline x Hwy 2) RR (Regional Rd 57) | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-12-02 | 0 | 1704701.39
Krosno Creek Culvert RR | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-12-01 | 119600 | 232074.21
Sidney (CPRxCollege) | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | To Be Determined | 253170.1 | 0
ROD Trunk Sewer Relocns-Bowm | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-08-17 | 45000 | 0
Westney Rd S Relocation (Bayly x Westney) Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-10-01 | 30844.05 | 26138.74
SC2127 & SC2128 Relocn - Pick | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-10-23 | 6656.64 | 0
Dowty Rd x Hunt St Sidewalk Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-10-15 | 15000 | 20594.7
Rossland (Garden x Civic) Road Relocation – Deficiency Correction | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-03-23 | 14260 | 0
Damages - 3rd Party | Damages - 3rd Party | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-12-19 | 369895 | 100208.33
Customer Requested Work | Customer Requested Work | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-12-19 | 369381.81 | 4568.37
Scugog x Church Pole Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-01-08 | 5764 | 24.76
Metrolinx-South Blair Electrification Project | Third Party - Metrolinx Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-03-22 | 0 | 30976
Residential Development - Ajax | Residential Development | A2 Customer & Generation Connections | Customer Driven | 2025-12-10 | 4000000 | 3194666.64
Residential Development - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 305577.41
Residential Development - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 8344.45
Residential Development - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 0
Residential Development - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 0
Residential Development - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 482657.08
O/H New Residential Services | O/H New Residential Services | A2 Customer & Generation Connections | Customer Driven | 2025-11-05 | 862036.592 | 1195109.37
U/G New Residential Services | U/G New Residential Services | A2 Customer & Generation Connections | Customer Driven | 2025-11-05 | 1406811.5784 | 1912023.57
Residential Development - New Duffins Village | Residential Development | A2 Customer & Generation Connections | Customer Driven | 2025-12-10 | 67140 | 0
Brock Rd (Hwy 2 X Bayly)-27.6kV | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-10-30 | 2116336.5 | 1922936.37
Brock Rd (Hwy 401 Crossing) | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-10-29 | 2040501 | 1316378.22
BAYLY (SANDY BEACH X BROCK)-UCC | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-11-07 | 2143484 | 1144006.5
Winchester (Ashburn x Baldwin)-Conlin/Broccolini | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-10-11 | 811585 | 0
44kV Poleline | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-12-13 | 3826782.73 | 4761326.26
27.6kV Whites (407 x Hwy 7) - Wonder Drive Phase 1B | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-12-22 | 3256368 | 0
27.6kV Whites (407 x Hwy 7) - Phase 1C | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-11-19 | 1543000 | 1385895.35
Kingston RD Expansion | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-06-07 04:48 | 2393085 | 0
Baldwin x Ashburn Rd | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-12-17 | 1207850 | 0
Winchester (Ashburn x Baldwin) 13.8kV Exp | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-02-21 | 72959.32 | 0
Boundary Road 44 KV Expansion | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-11-30 | 967004.85 | 849432.31
Champlain Ave 44 KV Expansion | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-12-16 | 661999 | 0
Rossland Rd (McQuay x MS8)-Removals | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-02-26 | 13106.34 | 0
Newcastle 44kV Primary Meter Installation | 44kV Primary Meter Installation | A4 Metering & AMI 2.0 | Metering | 2025-12-10 | 191928 | 0
Residential Type Meters | Residential Type Meters | A4 Metering & AMI 2.0 | Metering | 2025-11-19 | 836400 | 894664.59
Current and Voltage Transformers | Current and Voltage Transformers | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 91800 | 251800.19
Polyphase Meters SC | Polyphase Meters | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 86700 | 261163.33
Trans Type both interval and smart meter nodes | Interval and Smart Meter Nodes | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 91800 | 555079.55
Wholesale ION Main/Alternate Meters/upgrades of Metering cabinets | Wholesale ION Meters | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 85680 | 28199.97
Other, Modems, locks, metering wire, Key holders, test blocks etc | Other, Modems, locks, metering wire, Key holders, test blocks etc | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 56100 | 111369.45
Replacement of modems only for retail customers Replacement of gate keepers and modems for AMI | Replacement of Modems/Gate Keepers | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 153000 | 66416.98
Remote Disconnect Units | Remote Disconnect Units | A4 Metering & AMI 2.0 | Metering | 2025-12-19 | 111180 | 916.74

## 2-Staff-73 a) 2026
Project Name | Project Description | DSP Program | Project Category | In-Service Addition Planned Completion Milestone | Net $ Planned ISA in ERA plan | Planned ISA in EWP
Brock & Bayly – DL Intersection improvements | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | To be determined | 567490.6772
Brock x Water Whitby Harbor Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | To be determined | 60101.437
Avonlough SPS | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-08-06 12:00 | 1521343.53 | 902273.53
Baldwin (Garden x Midblock Arterial) Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-06-25 | 2520000 | 53178
Rossland Road (Westney x Salem) Relocation (Phase 5) | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-11-27 14:24 |  | 2114855.3
Henry (Octavia x Murney) Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-08-22 09:36 |  | 102200
Westney Rd N Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-11-27 21:36 |  | 94675.3
Damages - 3rd Party | Damages - 3rd Party | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-10-22 | 205539.7203 | 0
Customer Requested Work - 2026 Budget Placeholder | Customer Requested Work - Placeholder | A1 Externally-Initiated Plant Relocation | Customer Driven | To be determined | 539000
Pickering Parkway 44kV Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | To be determined | 40544.4149
Residential Development - Ajax | Residential Development | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 3629110.8802 | 1000000
Residential Development - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 144080.86
Residential Development - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 136951.96
Residential Development - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-31 |  | 11290.125
Residential Development - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 71005.695
Residential Development - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-30 |  | 1000000
Transformers - General Services - Ajax | Transformers - General Services | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 146847.0044 | 66080.9475
Transformers - General Services - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 97994.835
Transformers - General Services - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 2503.1005
Transformers - General Services - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-31 |  | 51770.535
Transformers - General Services - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 12655.375
Transformers - General Services - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 9805.3652
O/H New Residential Services - Ajax | O/H New Residential Services | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 366318.2255 | 153007.65
O/H New Residential Services - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 28788.54
O/H New Residential Services - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 25728.7
O/H New Residential Services - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-31 |  | 12215
O/H New Residential Services - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 16129.58
O/H New Residential Services - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 31238.4511
U/G New Residential Services - Ajax | U/G New Residential Services | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 368673.9697 | 153991.8
U/G New Residential Services - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 17998.09
U/G New Residential Services - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 13342.755
U/G New Residential Services - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-31 |  | 20697.165
U/G New Residential Services - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 13434.415
U/G New Residential Services - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 46113.3299
Temporary Services with w/o TX's | Temporary Services | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 64782.9659 | 0
Service Upgrades for Residential Customers - Ajax | Service Upgrades for Residential Customers | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 810410.8264 | 169451.325
Service Upgrades for Residential Customers - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 39716.68
Service Upgrades for Residential Customers - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 23794.725
Service Upgrades for Residential Customers - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-31 |  | 56231.45
Service Upgrades for Residential Customers - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 18827.925
Service Upgrades for Residential Customers - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 70463.9247
Burkholder (Zenith X Alex Knox) | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 18115.1193 | 0
Triovest Notion Rd New LIS & Feeder Expansion | Customer Expansion | A3 System Expansion | Customer Driven | 2026-04-30 | 699313 | 789038
Pickering Nuclear Generation (PNG) Feeder Expansion | Customer Expansion | A3 System Expansion | Customer Driven | 2027-05-30 | 1939415.4659 | 0
913 Brock Rd Feeder Expansion | Customer Expansion | A3 System Expansion | Customer Driven | Cancelled | 717070.2447 | 0
310 Kingston Rd E 27.6 KV EXP | Customer Expansion | A3 System Expansion | Customer Driven | 2027-12-20 | 756230.2385 | 0
Uxbridge Hospital 44kV Expansion | Customer Expansion | A3 System Expansion | Customer Driven | 2028-06-30 | 819249.4251 | 0
Ashburn (Brooklin SS x Columbus) Expansion - BLG | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 75479.6636 | 0
Ashburn (Columbus x Brawley) Expansion - BLG | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 75479.6636 | 0
Columbus (Country Lane x Ashburn) Expansion - BLG | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 75479.6636 | 0
Columbus (Ashburn x Cachet) Expansion -BLG | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 75479.6636 | 0
Baldwin (Columbus x Thickson) Expansion - BLG | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 75479.6636 | 0
Brock St S x Water St Whitby Harbour Exp | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 2128063.0997
South Ajax Expansion | Customer Expansion | A3 System Expansion | Customer Driven | To Be Determined | 3400000
Residential Type Meters | Residential Type Meters | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 878487.4604 | 536400
Current and Voltage Transformers | Current and Voltage Transformers | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 96419.3554 | 91800
Smart Suite Metering - 1 building | Smart Suite Metering - 1 building | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 21006.3955 | 0
Polyphase Meters SC | Polyphase Meters | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 91062.7246 | 486700
Trans Type both interval and smart meter nodes | Interval and Smart Meter Nodes | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 96419.3554 | 91800
Wholesale ION Main/ Alternate Meters /upgrades of Metering cabinets | Wholesale ION Main/Alternate Meters/Upgrades of Metering cabinets | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 89991.3984 | 85680
Other, Modems, locks, metering wire, Key holders, test blocks etc | Other, Modems, Locks, Metering Wire, Key Holders, Test Blocks, etc | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 58922.9394 | 56100
Replacement of modems only for retail customers Replacement of gate keepers and modems for AMI | Gatekeeper and Modem Replacement for AMI | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 160698.9257 | 153000
2025-6011 - Remote Disconnect Units | Remote Disconnect Units | A4 Metering & AMI 2.0 | Metering | 2026-10-22 | 116774.5527 | 111180

## 2-Staff-73 b) 2025
Project Name | Project Description | DSP Program | Project Category | In-Service Addition Planned Completion Milestone | Net $ Planned ISA in ERA plan | Actual ISA | Status
Bowmanville Ave (Baseline x Hwy 2) RR (Regional Rd 57) | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2025-12-02 | 0 | 1704701.39 | In-Service Addition Complete
Residential Development - Ajax | Residential Development | A2 Customer & Generation Connections | Customer Driven | 2025-12-10 | 4000000 | 3194666.64 | In-Service Addition Complete
Residential Development - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 305577.41
Residential Development - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 8344.45
Residential Development - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 0
Residential Development - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 0
Residential Development - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2025-12-19 |  | 482657.08
O/H New Residential Services | O/H New Residential Services | A2 Customer & Generation Connections | Customer Driven | 2025-11-05 | 862036.592 | 1195109.37 | In-Service Addition Complete
U/G New Residential Services | U/G New Residential Services | A2 Customer & Generation Connections | Customer Driven | 2025-11-05 | 1406811.5784 | 1912023.57 | In-Service Addition Complete
Brock Rd (Hwy 2 X Bayly)-27.6kV | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-10-30 | 2116336.5 | 1922936.37 | In-Service Addition Complete
Brock Rd (Hwy 401 Crossing) | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-10-29 | 2040501 | 1316378.22 | In-Service Addition Complete
BAYLY (SANDY BEACH X BROCK)-UCC | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-11-07 | 2143484 | 1144006.5 | In-Service Addition Complete
44kV Poleline | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-12-13 | 3826782.73 | 4761326.26 | In-Service Addition Complete
27.6kV Whites (407 x Hwy 7) Caplink FGF - Wonder Drive Phase 1B | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-12-22 | 3256368 | 0 | In progress, In-Service Addition December 2026
27.6kV Whites (407 x Hwy 7) Caplink FGF - Phase 1C | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2025-11-19 | 1543000 | 1385895.35 | In-Service Addition Complete
Kingston RD Expansion | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-06-07 04:48 | 2393085 | 0 | In Progress, In-Service Addition in June 2026
Baldwin x Ashburn Rd | Customer Feeder Expansion | A3 System Expansion | Customer Driven | 2026-12-17 | 1207850 | 0 | In progress, In-Service Addition December 2026

## 2-Staff-73 b) 2026
Project Name | Project Description (Excl. sensitive Information) | DSP Program | Project Category | In-Service Addition Planned Completion Milestone | Net $ Planned ISA in ERA plan | Planned ISA in EWP | Status
Baldwin (Garden x Midblock Arterial) Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-06-25 | 2520000 | 53178 | Project On Track
Rossland Road (Westney x Salem) Relocation (Phase 5) | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-11-27 14:24 |  | 2114855.3 | Project On Track
2025 - Henry (Octavia x Murney) Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-08-22 09:36 |  | 102200 | Project On Track
2026 - Westney Rd N Road Relocation | Road Authority Relocation | A1 Externally-Initiated Plant Relocation | Customer Driven | 2026-11-27 21:36 |  | 94675.3 | Project On Track
Residential Development - Ajax | Residential Development | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 | 3629110.8802 | 1000000 | Forecast - Placeholder
Residential Development - Belleville |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 144080.86
Residential Development - Clarington |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-20 |  | 136951.96
Residential Development - Gravenhurst |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-31 |  | 11290.125
Residential Development - Brock |  | A2 Customer & Generation Connections | Customer Driven | 2026-10-22 |  | 71005.695
Residential Development - Whitby |  | A2 Customer & Generation Connections | Customer Driven | 2026-12-30 |  | 1000000
Pickering Feeder Expansion | Customer Expansion | A3 System Expansion | Customer Driven | 2027-05-30 | 1939415.4659 | 0 | Design in Progress
Brock St S x Water St Whitby Harbour Exp | Customer Expansion | A3 System Expansion | Customer Driven | To be determined | 2128063.0997 | - | Customer Delayed
South Ajax Expansion | Customer Expansion | A3 System Expansion | Customer Driven | To be determined | 3400000 | - | Offer To Connect - In Progress