## D1-1-1_Table 1
Numbers may not add due to rounding. | [11 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 1
Table 1
Table 1
Capital Expenditures Summary - Regulated Hydroelectric and Hydro Common1 ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Category | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Budget | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
1 | Total Regulated Hydroelectric Capital | 127.5 | 147.15 | 168 | 205.11 | 288.95 | 388 | 314.78 | 371.04 | 433.01 | 835.4 | 984.2
2 | Total Hydro Common Capital1 | 3.48 | 0.2 | 1.12 | 2.3 | 3.18 | 4.5 | 5.09 | 10.31 | 8.6 | 21 | 34.1
Line |  | (a): 2027; (b): 2028; (c): 2029; (d): 2030; (e): 2031
No. | Category | (a): Plan; (b): Plan; (c): Plan; (d): Plan; (e): Plan
|  | (a) | (b) | (c) | (d) | (e)
3 | Total Regulated Hydroelectric Capital | (a): 880.9; (b): 920.4; (c): 1024.95; (d): 1001.2; (e): 946.6
4 | Total Hydro Common Capital1,2 | (a): 35.9; (b): n/a; (c): n/a; (d): n/a; (e): n/a
Notes:
1 | Hydro Common refers to projects for assets that support OPG's regulated and unregulated Renewable Generation assets (see Ex. D1-1-1, Section 6.0). Costs associated with these projects are total project costs, and are charged to the regulated business using the asset service fee methodology described in Ex. F3-2-1.
2 | As Hydro Common projects represent inputs into asset service fees (OM&A costs), rather than forming capital-related revenue requirement, any forecast in-service additions after 2027 will not impact the regulated hydroelectric payment amounts during the 2027-2031 IR under the proposed rate-setting methodology.

## D1-1-1_Table 2
Numbers may not add due to rounding. | [11 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 1
Table 2
Table 2
Capital Expenditures Summary - Regulated Hydroelectric and Hydro Common ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Prescribed Facility Category1 | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Budget | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
1 | Niagara Region | 47.58 | 20.1 | 21.7 | 19.98 | 18.1 | 31.9 | 38.5 | 69.8 | 53.33 | 83.95 | 50.2
2 | Eastern Region | 37.1 | 45.1 | 70.6 | 71.57 | 68.44 | 89.75 | 82.14 | 108.6 | 117.5 | 143.45 | 140.8
3 | Western Region | 10.9 | 17.7 | 20.15 | 51.29 | 66.18 | 79.4 | 56.27 | 64.74 | 74.9 | 70.9 | 101.5
4 | Subtotal Portfolio Projects (Allocated) | 95.58 | 82.9 | 112.45 | 142.84 | 152.72 | 201.05 | 176.91 | 243.14 | 245.73 | 298.3 | 292.5
Portfolio Projects (Unallocated)
5 | Niagara Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | -22.1
6 | Eastern Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 20.4
7 | Western Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | -10.8
8 | Subtotal Portfolio Projects (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3 | -12.5
9 | Subtotal Project Capital (Portfolio) | 95.58 | 82.9 | 112.45 | 142.84 | 152.72 | 201.05 | 176.91 | 243.14 | 245.73 | 305.6 | 280
10 | Refurbishments (Allocated) | 29.74 | 34.8 | 18.3 | 27 | 66.8 | 83.13 | 50.88 | 92.8 | 106.61 | 212.1 | 325.9
11 | Refurbishments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 13.5
12 | Redevelopments (Allocated) | 0 | 0.7 | 2.1 | 4.5 | 25.2 | 62.04 | 65.1 | 27.4 | 53.41 | 283.4 | 355.6
13 | Redevelopments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Sir Adam Beck 1 GS Canal Rehabilitation2 | 0 | 2.75 | 2.5 | 2.5 | 4.64 | 0.056 | -0.003 | -0.09 | 0.37 | 6.6 | 4.6
15 | Expansion Projects2,3 | 2 | 25.36 | 31.6 | 27.2 | 38.5 | 40.19 | 20.6 | 1.3 | 0 | 0 | 1.052
16 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 25.23 | 19.7 | 2.1
17 | Minor Fixed Assets | 0.17 | 0.673 | 1 | 1.1 | 1.1 | 1.49 | 1.3 | 1.37 | 1.64 | 3.2 | 1.48
18 | Total Regulated Hydroelectric Capital | 127.49 | 147.183 | 167.95 | 205.14 | 288.96 | 387.956 | 314.787 | 371.02 | 432.99 | 835.4 | 984.232
19 | Total Hydro Common Capital | 3.48 | 0.2 | 1.12 | 2.3 | 3.18 | 4.5 | 5.09 | 10.31 | 8.6 | 21 | 34.1
Line |  | (a): 2027; (b): 2028; (c): 2029; (d): 2030; (e): 2031
No. | Prescribed Facility Category1 | (a): Plan; (b): Plan; (c): Plan; (d): Plan; (e): Plan
|  | (a) | (b) | (c) | (d) | (e)
Portfolio Projects (Allocated)
20 | Niagara Region | (a): 30.4; (b): 18.76; (c): 17.69; (d): 22.25; (e): 6.03
21 | Eastern Region | (a): 106.3; (b): 89.6; (c): 64.5; (d): 37.87; (e): 34.08
22 | Western Region | (a): 52.55; (b): 59.79; (c): 20.2; (d): 30.61; (e): 46.3
23 | Subtotal Portfolio Projects (Allocated) | (a): 189.25; (b): 168.15; (c): 102.39; (d): 90.73; (e): 86.41
Portfolio Projects (Unallocated)
24 | Niagara Region | (a): 14.2; (b): 30.65; (c): 47.8; (d): 48.7; (e): 20
25 | Eastern Region | (a): 65.9; (b): 106.13; (c): 62.9; (d): 97.8; (e): 109.3
26 | Western Region | (a): 11.87; (b): 27.84; (c): 90.3; (d): 95.1; (e): 115.9
27 | Subtotal Portfolio Projects (Unallocated) | (a): 91.97; (b): 164.62; (c): 201; (d): 241.6; (e): 245.2
28 | Subtotal Project Capital (Portfolio) | (a): 281.22; (b): 332.77; (c): 303.39; (d): 332.33; (e): 331.61
29 | Refurbishments (Allocated) | (a): 289; (b): 299.9; (c): 278.2; (d): 263.62; (e): 117.77
30 | Refurbishments (Unallocated) | (a): 119.55; (b): 186.7; (c): 148.9; (d): 202; (e): 288
31 | Redevelopments (Allocated) | (a): 156.9; (b): 18.14; (c): 1.0027; (d): 0; (e): 0
32 | Redevelopments (Unallocated) | (a): 0; (b): 0; (c): 0; (d): 0; (e): 0
33 | Sir Adam Beck 1 GS Canal Rehabilitation2 | (a): 18.3; (b): 20.83; (c): 134.1; (d): 1.5; (e): 0
34 | Expansion Projects2,3 | (a): 3.9109; (b): 6.15; (c): 25.8946; (d): 34.4777; (e): 27.9919
35 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program2 | (a): 10.5; (b): 54.31; (c): 131.88; (d): 165.66; (e): 179.5
36 | Minor Fixed Assets | (a): 1.5; (b): 1.57; (c): 1.6; (d): 1.65; (e): 1.69
37 | Total Regulated Hydroelectric Capital | (a): 880.8809; (b): 920.37; (c): 1024.9673; (d): 1001.2377; (e): 946.5619
38 | Total Hydro Common Capital | (a): 35.9; (b): n/a; (c): n/a; (d): n/a; (e): n/a
Notes:
1 | Operating Region descriptions effective 2021 (see Ex. A1-4-2).
2 | Includes both allocated and unallocated projects.
3 | Expansion projects include the Sir Adam Beck 1 GS G1/G2 Replacement (#84185), Ranney Falls GS Expansion (#80581), and Chats Falls Expansion (#TBD).

## D1-1-1_Table 3
Numbers may not add due to rounding. | [11 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 1
Table 3
Table 3
Capital Expenditures Summary - Regulated Hydroelectric Projects and Hydro Common (Allocated) ($M)
By Project Category
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Project Category | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Budget | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Regulated Hydroelectric Projects (Allocated)
1 | Regulatory | 6.59 | 10.9 | 2.9 | 3.2 | 2.6 | 14.78 | 14.3 | 12.64 | 8.4 | 19.4 | 28.6
2 | Sustaining | 118.66 | 106.37 | 129 | 164.9 | 212.2 | 264.27 | 212.1 | 324.94 | 366.52 | 512.5 | 531.3
3 | Value Enhancing / Strategic | 2.07 | 29.27 | 35.1 | 35.9 | 73.1 | 107.49 | 87.1 | 32.1 | 56.45 | 287.8 | 361.8
4 | Total Regulated Hydroelectric Capital | 127.32 | 146.54 | 167 | 204 | 287.9 | 386.54 | 313.5 | 369.68 | 431.37 | 819.7 | 921.7
Hydro Common (Allocated)
5 | Regulatory | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 2.14 | 2.68 | 2.09 | 0
6 | Sustaining | 3.48 | 0.2 | 0.28 | 0.23 | 0.62 | 1.98 | 2.03 | 6.25 | 4.059 | 15.1 | 30.2
7 | Value Enhancing / Strategic | 0 | 0 | 0.84 | 2.06 | 2.56 | 2.52 | 2.45 | 1.91 | 1.9 | 1.5 | 1.5
8 | Total Hydro Common Capital | 3.48 | 0.2 | 1.12 | 2.29 | 3.18 | 4.5 | 5.08 | 10.3 | 8.639 | 18.69 | 31.7
|  | 2027 | 2028 | 2029 | 2030 | 2031
|  | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e)
Regulated Hydroelectric Projects (Allocated)
9 | Regulatory | (a): 19.98; (b): 34.9; (c): 34.2; (d): 14.8; (e): 14.1
10 | Sustaining | (a): 447.12; (b): 461.19; (c): 371.54; (d): 346.65; (e): 192.8
11 | Value Enhancing / Strategic | (a): 163.8; (b): 23.29; (c): 4.38; (d): 0.39; (e): 0
12 | Total Regulated Hydroelectric Capital | (a): 630.9; (b): 519.38; (c): 410.12; (d): 361.84; (e): 206.9
Hydro Common (Allocated)
13 | Regulatory | (a): 0; (b): n/a; (c): n/a; (d): n/a; (e): n/a
14 | Sustaining | (a): 33.7; (b): n/a; (c): n/a; (d): n/a; (e): n/a
15 | Value Enhancing / Strategic | (a): 0; (b): n/a; (c): n/a; (d): n/a; (e): n/a
16 | Total Hydro Common Capital1 | (a): 33.7; (b): n/a; (c): n/a; (d): n/a; (e): n/a

## D1-1-1_Table 4
Numbers may not add due to rounding. | [11 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 1
Table 4
Table 4
Comparison of Capital Expenditures - Regulated Hydroelectric and Hydro Common ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Prescribed Facility Category1 | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Budget | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
1 | Niagara Region | 47.58 | 20.1 | 21.7 | 19.98 | 18.1 | 31.9 | 38.5 | 69.8 | 53.33 | 83.95 | 50.2
2 | Eastern Region | 37.1 | 45.1 | 70.6 | 71.57 | 68.44 | 89.75 | 82.14 | 108.6 | 117.5 | 143.45 | 140.8
3 | Western Region | 10.9 | 17.7 | 20.15 | 51.29 | 66.18 | 79.4 | 56.27 | 64.74 | 74.9 | 70.9 | 101.5
4 | Subtotal Portfolio Projects (Allocated) | 95.58 | 82.9 | 112.45 | 142.84 | 152.72 | 201.05 | 176.91 | 243.14 | 245.73 | 298.3 | 292.5
Portfolio Projects (Unallocated)
5 | Niagara Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | -22.1
6 | Eastern Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 20.4
7 | Western Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | -10.8
8 | Subtotal Portfolio Projects (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3 | -12.5
9 | Subtotal Project Capital (Portfolio) | 95.58 | 82.9 | 112.45 | 142.84 | 152.72 | 201.05 | 176.91 | 243.14 | 245.73 | 305.6 | 280
10 | Refurbishments (Allocated) | 29.74 | 34.8 | 18.3 | 27 | 66.8 | 83.13 | 50.88 | 92.8 | 106.61 | 212.1 | 325.9
11 | Refurbishments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8 | 13.5
12 | Redevelopments (Allocated) |  | 0.7 | 2.1 | 4.5 | 25.2 | 62.04 | 65.1 | 27.4 | 53.41 | 283.4 | 355.6
13 | Redevelopments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Sir Adam Beck 1 GS Canal Rehabilitation2 |  | 2.75 | 2.5 | 2.5 | 4.64 | 0.056 | -0.003 | -0.09 | 0.37 | 6.6 | 4.6
15 | Expansion Projects2,3 | 2 | 25.36 | 31.6 | 27.2 | 38.5 | 40.19 | 20.6 | 1.3 | 0 | 0 | 1.052
16 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 25.23 | 19.7 | 2.1
17 | Minor Fixed Assets | 0.17 | 0.673 | 1 | 1.1 | 1.1 | 1.49 | 1.3 | 1.37 | 1.64 | 3.2 | 1.48
18 | Total Regulated Hydroelectric Capital | 127.49 | 147.183 | 167.95 | 205.14 | 288.96 | 387.956 | 314.787 | 371.02 | 432.99 | 835.4 | 984.232
19 | Total Hydro Common Capital1 | 3.48 | 0.2 | 1.12 | 2.3 | 3.18 | 4.5 | 5.09 | 10.31 | 8.6 | 21 | 34.1
Line |  | (a): 2017-2021 Actual; (b): (c)-(a); (c): 2022-2026 Actuals &; (d): (e)-(c); (e): 2027-2031 Plan4
No. | Prescribed Facility Category1 | (b): Change; (c): Budget4; (d): Change
|  | (a) | (b) | (c) | (d) | (e)
Portfolio Projects (Allocated)
20 | Niagara Region | (a): 111.78; (b): 184; (c): 295.78; (d): -200.65; (e): 95.13
21 | Eastern Region | (a): 345.46; (b): 247.03; (c): 592.49; (d): -260.14; (e): 332.35
22 | Western Region | (a): 234.72; (b): 133.59; (c): 368.31; (d): -158.86; (e): 209.45
23 | Subtotal Portfolio Projects (Allocated) | (a): 691.96; (b): 564.62; (c): 1256.58; (d): -619.65; (e): 636.93
Portfolio Projects (Unallocated)
24 | Niagara Region | (a): 0; (b): -18.6; (c): -18.6; (d): 179.95; (e): 161.35
25 | Eastern Region | (a): 0; (b): 22.5; (c): 22.5; (d): 419.53; (e): 442.03
26 | Western Region | (a): 0; (b): -9.1; (c): -9.1; (d): 350.11; (e): 341.01
27 | Subtotal Portfolio Projects (Unallocated) | (a): 0; (b): -5.2; (c): -5.2; (d): 949.59; (e): 944.39
28 | Subtotal Project Capital (Portfolio) | (a): 691.96; (b): 559.42; (c): 1251.38; (d): 329.94; (e): 1581.32
29 | Refurbishments (Allocated) | (a): 230.03; (b): 558.26; (c): 788.29; (d): 460.2; (e): 1248.49
30 | Refurbishments (Unallocated) | (a): 0; (b): 18.3; (c): 18.3; (d): 926.85; (e): 945.15
31 | Redevelopments (Allocated) | (a): 94.54; (b): 690.37; (c): 784.91; (d): -608.8673; (e): 176.0427
32 | Redevelopments (Unallocated) | (a): 0; (b): 0; (c): 0; (d): 0; (e): 0
33 | Sir Adam Beck 1 GS Canal Rehabilitation2 | (a): 12.446; (b): -0.969; (c): 11.477; (d): 163.253; (e): 174.73
34 | Expansion Projects2,3 | (a): 162.85; (b): -139.898; (c): 22.952; (d): 75.4731; (e): 98.4251
35 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program2 | (a): 0; (b): 52.13; (c): 52.13; (d): 489.72; (e): 541.85
36 | Minor Fixed Assets | (a): 5.363; (b): 3.627; (c): 8.99; (d): -0.98; (e): 8.01
37 | Total Regulated Hydroelectric Capital | (a): 1197.189; (b): 1741.24; (c): 2938.429; (d): 1835.5888; (e): 4774.0178
38 | Total Hydro Common Capital1 | (a): 11.3; (b): 67.8; (c): 79.1; (d): n/a; (e): n/a
38a | Total Hydro Common Capital1,4 | (a): n/a; (b): n/a; (c): 15.82; (d): 20.08; (e): 35.9
Notes: | Refer to Notes described in Table 2
4 | Term-over-term variance is provided for the annual average of 2022-2026 (2022-2024 actuals, 2025-2026 forecast) versus the 2027 test year forecast - refer to Ex. D1-1-1, Section 6.0

## D1-1-2_Table 1
Numbers may not add due to rounding. | [19 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 1
Table 1
Capital Project Listing - Regulated Hydroelectric and Hydro Common
Projects ≥ $30M Total Project Cost (Allocated)1
[9 empty] | Total | 1st Execution Business Case3
[8 empty] | Final | Project |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  |  | Project |  | CRVA | Start | In-Service | Cost2 |  | In-Service | LTD5 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Region | Facility | Project Name | Number | Category | Eligible8 | Date | Date4 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s) | (t)
1 | Eastern | Calabogie | Calabogie GS - Redevelopment | 82089 | Value Enhancing (Redevelopment) | Yes* | 2017-01-31 | 2023-10-25 | 167.204 | 136.5 | 165.552 | 165.682 | 0 | -0.13 | 0 | 0 | 0 | 0 | 0 | 0
2 | Niagara | DeCew Falls 2 | G2 Overhaul & Upgrade | 80851 | Sustaining (Refurbishment) | Yes | 2015-02-05 | 2019-07-01 | 35.5 | 38.1 | 34.944 | 34.944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Niagara | Sir Adam Beck 1 | BK1 G1/G2 Replacement | 84185 | Value Enhancing (Expansion) | Yes | 2019-02-25 | 2022-10-05 | 122.765 | 119.7 | 112.851 | 112.851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Niagara | Sir Adam Beck 1 | SAB1 Canal Isolation Preparedness Phase 1 (SAB1 CIP1) | 89252 | Sustaining (Canal Rehabilitation) | Yes* | 2025-07-11 | 2029-12-01 | 65 | n/a | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0
5 | Niagara | Sir Adam Beck Pump Generating Station | Sir Adam Beck Pump GS - Reservoir Refurbishment | 80583 | Sustaining | Yes | 2011-09-19 | 2017-04-01 | 48.689 | 58.2 | 48.689 | 48.689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Niagara | Sir Adam Beck 1 | Sir Adam Beck I GS - G10 Major Overhaul & Upgrade | 80649 | Sustaining (Refurbishment) | Yes | 2013-10-18 | 2017-06-09 | 30.81 | 27 | 30.165 | 30.165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Western | Ranney Falls | Ranney Falls Expansion Project | 80581 | Value Enhancing (Expansion) | Yes | 2011-09-19 | 2022-06-01 | 74.5 | 77.3 | 74.496 | 74.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Niagara | Sir Adam Beck 1 | Sir Adam Beck 1 GS - Unit G5 Upgrade | 82777 | Sustaining (Refurbishment) | Yes | 2018-05-03 | 2021-09-23 | 44.675 | 19.771 | 43.393 | 43.393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Eastern | Abitibi Canyon | Abitibi - G2 Capital Upgrades/HG | 83155 | Sustaining (Refurbishment) | Yes | 2019-02-01 | 2022-03-01 | 30.105 | 27.5 | 29.508 | 29.233 | 0 | 0.275 | 0 | 0 | 0 | 0 | 0 | 0
10 | Eastern | Otter Rapids | Otter Project Camp | 84907 | Sustaining | No | 2020-06-08 | 2024-07-16 | 39.47 | 39.472 | 38.954 | 38.554 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
11 | Eastern | Frederick House6 | Frederick House Lake Dam Upgrades | 83194 | Sustaining | Yes | 2021-10-29 | 2025-12-31 | 90 | 90 | 79.9 | 35.3 | 0 | 37.4 | 7.2 | 0 | 0 | 0 | 0 | 0
12 | Eastern | R.H. Saunders | SAU - G9 Capital Refurbishment | 83495 | Sustaining (Refurbishment) | Yes | 2020-12-16 | 2025-08-22 | 42.688 | 17.2 | 38.4 | 0 | 0 | 37 | 1.4 | 0 | 0 | 0 | 0 | 0
13 | Eastern | Chenaux | CHE - Limerick Isl. Spr Structure Sluice Gate Hoist | 84494 | Regulatory | Yes | 2019-05-27 | 2023-11-30 | 32.7 | 32.701 | 28.84 | 28.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Eastern | Otter Rapids | Otter G2 Capital Upgrade | 82543 | Sustaining (Refurbishment) | Yes | 2020-08-14 | 2025-12-15 | 78.05 | 43.11 | 70.069 | 7.769 | 0 | 61.9 | 0.4 | 0 | 0 | 0 | 0 | 0
15 | Eastern | Coniston/Stinson | Coniston/Stinson GS Redevelopment | 82087 | Value Enhancing (Redevelopment) | Yes* | 2019-03-28 | 2027-04-01 | 177.99 | 178 | 176.4 | 0 | 45.9 | 0 | 130.5 | 45.9 | 0 | 0 | 0 | 0
16 | Western | Kakabeka Falls | Kakabeka Falls GS Redevelopment | 86386 | Value Enhancing (Redevelopment) | Yes* | 2021-03-22 | 2028-05-05 | 519 | 519 | 511 | 0 | 487.1 | 12.7 | 11.2 | 300.6 | 171.9 | 14.6 | 0 | 0
17 | Niagara | Sir Adam Beck 2 | BK2 G20/G19 Refurbishment | 87768 | Sustaining (Refurbishment) | Yes* | 2019-10-31 | 2029-02-10 | 377.5 | n/a | 353 | 0 | 353 | 0 | 0 | 0 | 176.5 | 176.5 | 0 | 0
18 | Eastern | Matabitchuan | Matabitchuan GS Redevelopment | 86387 | Value Enhancing (Redevelopment) | Yes* | 2022-11-16 | 2028-08-07 | 190 | 190 | 187.55 | 0 | 183.35 | 4.2 | 0 | 3.1 | 179.95 | 0.3 | 0 | 0
19 | Eastern | R.H. Saunders | SAU - G12 Capital Refurbishment | 86587 | Sustaining (Refurbishment) | Yes | 2022-06-14 | 2026-06-09 | 30.38 | 30.38 | 26.9 | 0 | 0 | 0 | 26.9 | 0 | 0 | 0 | 0 | 0
20 | Eastern | Otter Rapids | Otter G1 Capital Upgrade | 82542 | Sustaining (Refurbishment) | Yes | 2019-02-21 | 2026-12-10 | 40.664 | 40.7 | 35.8 | 0 | 1.8 | 0 | 34 | 1.8 | 0 | 0 | 0 | 0
21 | Eastern | Abitibi Canyon | ABI - G1 Capital Upgrades | 83148 | Sustaining (Refurbishment) | Yes* | 2025-03-06 | 2031-01-30 | 54.67 | n/a | 46.8 | 0 | 46.8 | 0 | 0 | 0 | 0 | 0 | 0 | 46.8
22 | Eastern | R.H. Saunders | SAU - Long Sault Dam Capital Program (JW)(NYPA) | 86595 | Regulatory | No | 2023-03-01 | 2033-12-31 | 88.01 | n/a | 74.8085 | 0 | 45.3 | 0 | 0 | 0 | 0 | 25 | 9 | 11.3
23 | Eastern | R.H. Saunders | SAU - Massena Canal Dam (JW)(NYPA)(CAP) | 87142 | Regulatory | No | 2015-05-29 | 2029-12-31 | 47.31 | n/a | 39.1 | 0 | 39.1 | 0 | 0 | 0 | 0 | 39.1 | 0 | 0
24 | Eastern | Abitibi Canyon | Abitibi Canyon Concrete Repair Zone 7 | 89505 | Sustaining (Abitibi Concrete) | Yes | 2024-12-10 | 2026-04-30 | 35.6 | 35.6 | 26.4 | 1.4 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0
25 | Eastern | Otto Holden | OTO - Refurbish Stop Log Sluice Piers | 89354 | Sustaining | No | 2024-10-10 | 2036-09-30 | 107.95 | n/a | 91.7575 | 0 | 51.3 | 0 | 0 | 0 | 9.4 | 13.8 | 14 | 14.1
26 | Western | Alexander | G1 Capital Refurb | 82391 | Sustaining (Refurbishment) | Yes* | 2023-04-30 | 2030-09-23 | 45.8888 | n/a | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 41 | 1
27 | Western | Silver Falls | Surge Tank Replacement | 83833 | Sustaining | Yes | 2021-03-15 | 2028-12-15 | 40.6954 | n/a | 38.8 | 0 | 38.8 | 0 | 0 | 0 | 38.8 | 0 | 0 | 0
28 | Western | Northwest Operations7 | NWO Work Centre Building | 84901 | Sustaining | No | 2020-02-26 | 2027-08-27 | 44.4 | n/a | 39.9 | 0 | 39.9 | 0 | 0 | 39.9 | 0 | 0 | 0 | 0
29 | Western | Alexander | G2 Capital Refurb | 86792 | Sustaining (Refurbishment) | Yes* | 2023-04-30 | 2029-03-01 | 49.7319 | n/a | 43.5 | 0 | 43.5 | 0 | 0 | 0 | 0 | 42.5 | 0 | 1
30 | Western | Alexander | G3 Capital Refurb | 86793 | Sustaining (Refurbishment) | Yes* | 2023-06-13 | 2031-12-20 | 43.6394 | n/a | 41.5 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40
31 | Western | Manitou Falls | MAN G3 Capital Refurb | 86860 | Sustaining (Refurbishment) | Yes* | 2024-12-03 | 2029-05-29 | 53.2184 | n/a | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 47 | 0 | 1
32 | Western | Aguasabon | Aguasabon Dam Rehab. Hayes Lake Main Dam | 87217 | Sustaining | Yes* | 2023-08-14 | 2033-12-20 | 116.4634 | n/a | 110 | 0 | 70 | 0 | 0 | 0 | 0 | 10 | 30 | 30
33 | Niagara | Sir Adam Beck 1 | SAB1 Station Service Upgrade | 86364 | Sustaining | No | 2020-12-15 | 2030-01-24 | 33.4359 | n/a | 31.8 | 0 | 31.8 | 0 | 0 | 0 | 0 | 15.9 | 15.9 | 0
34 | Niagara | Sir Adam Beck 1 | BK1 G6 G8 Refurbishment | 86372 | Sustaining (Refurbishment) | Yes* | 2024-05-24 | 2030-04-10 | 232.3075 | n/a | 226.2 | 0 | 226.2 | 0 | 0 | 0 | 113.1 | 0 | 113.1 | 0
35 | Niagara | Sir Adam Beck 1 | BK1 G4 Refurbishment | 86570 | Sustaining (Refurbishment) | Yes* | 2022-05-20 | 2027-06-08 | 109.129 | 109.1 | 96.7 | 0 | 96.7 | 0 | 0 | 96.5 | 0.2 | 0 | 0 | 0
36 | Niagara | Sir Adam Beck 2 | BK2 G18 G17 Refurbishment | 87356 | Sustaining (Refurbishment) | Yes* | 2025-05-22 | 2030-11-30 | 361.1 | n/a | 344.2 | 0 | 344.2 | 0 | 0 | 0 | 0 | 0 | 344.2 | 0
37 | Niagara | Sir Adam Beck 2 | BK2 G14 G13 Refurbishment | 87357 | Sustaining (Refurbishment) | Yes* | 2025-05-25 | 2032-07-08 | 375.5516 | n/a | 360.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Eastern | R.H. Saunders | SAU - G16 Capital Refurbishment | 86937 | Sustaining (Refurbishment) | Yes* | 2024-11-29 | 2028-02-08 | 49.3 | n/a | 38.7 | 0 | 38.7 | 0 | 0 | 0 | 38.6 | 0.1 | 0 | 0
39 | Niagara | Sir Adam Beck 2 | BK2 230kV Conductor Replacement | 87362 | Sustaining | No | 2025-03-25 | 2039-08-12 | 35.9234 | n/a | 29.8 | 0 | 9.6 | 0 | 0 | 3.2 | 0 | 3.2 | 0 | 3.2
40 | Eastern | R.H. Saunders | SAU - Long Sault Dam Downstream Concrete (JW) (NYPA) | 87575 | Regulatory | No | 2024-06-11 | 2038-12-31 | 38.38 | n/a | 32.623 | 0 | 20.2 | 0 | 0 | 0 | 0 | 9.6 | 4.9 | 5.7
| (c): Total Regulated Hydroelectric; (i): 4200.3947 |  |  |  | 2408.25 | 153.745 | 236.6 | 491 | 728.45 | 462.6 | 572.1 | 154.1
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in the historical, bridge, or forecast period AND Completed/Deferred Projects in the historical period (2016-2024) at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): The designation of "n/a" means the project has not advanced to a First Execution BCS.
4 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
5 | (a): Life Time to Date (LTD) means in service amounts as of Dec 31, 2024.
6 | (a): Frederick House Lake Dam supports Abitibi Canyon and Otter Rapids generating stations.
7 | (a): Supports regulated generating stations in Thunder Bay and Kenora (refer to Ex. A1-4-2, Att. 1).
8 | (a): Col.(f): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2016-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 5). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D1-1-2_Table 2a
Numbers may not add due to rounding. | [17 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 2a
Table 2a
Capital Project Listing - Regulated Hydroelectric and Hydro Common
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[9 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Region | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r)
1 | Eastern | Matabitchuan | Replace Penstocks & Saddles | 80703 | Sustaining | Design and installation of new steel penstock and associated foundation saddles in place of 2 existing steel riveted penstocks. | No | 2009-12-11 | 2013-01-14 | 20.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Eastern | Otto Holden | Otto Holden GS - Replace Sluicegates & Rehabilitate Sluicegates System | 80717 | Sustaining | Replacement of 6 sluicegates and rehabilitation of sluicegate system to comply with dam safety requirements and address operational and reliability needs. | Yes | 2006-05-25 | 2015-11-04 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Niagara | Sir Adam Beck 2 | Sir Adam Beck II GS - Station Service Upgrades | 80666 | Sustaining | Purchase and installation of 2 new 600V switchgear lineups and 10 new 600V motor control centres. Includes removal of old equipment and cabling. | No | 2011-03-31 | 2019-04-29 | 14.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Eastern | R.H. Saunders | R.H. Saunders GS - Replace Station Service Breakers | 80637 | Sustaining | Station Service replacement of main, tie and feeder breakers. 600V lockable visi-break distribution panels to replace existing. | No | 2012-02-15 | 2018-12-03 | 16.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Eastern | R.H. Saunders | R.H Saunders GS - Replace Powerhouse Crane | 80635 | Sustaining | Replace original 300 ton station gantry crane, at end of life. | No | 2008-08-26 | 2015-06-12 | 15.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Eastern | Lower Notch | Lower Notch GS - Unit G2 Capital Upgrades | 80694 | Sustaining (Refurbishment) | Major unit refurbishment of all mechanical and electrical components, excluding replacement of the stator core. | No | 2012-09-13 | 2018-06-01 | 15.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Eastern | Lower Notch | Lower Notch GS - G1 Capital Upgrade | 80692 | Sustaining (Refurbishment) | Major unit refurbishment of all mechanical and electrical components, excluding replacement of the stator core. | No | 2011-11-22 | 2016-09-24 | 17.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Eastern | Des Joachims | Des Joachims GS - Rewind Generators G1, G3, G5 | 80604 | Sustaining (Refurbishment) | Stator rewind of G1, G3 and G5 units along with runner upgrade. Stator windings nearing 40 years old and risk of failure is increasing. | No | 2010-09-07 | 2015-05-08 | 10.738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Eastern | Chenaux | Chenaux GS - Replace Protections and Controls | 80596 | Sustaining | Replacement of DC distribution equipment including switchgear, distribution panels, battery chargers, batteries and inverters. Existing equipment is at end of life. | No | 2008-08-29 | 2019-11-25 | 14.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Western | Caribou Falls | Caribou Block Dam #2 Rehab | 83029 | Regulatory | Repair and remediate the slumped Caribou Block Dam #2 by constructing a new wall downstream of existing dam and stabilizing the existing dam structure. | No | 2016-03-14 | 2019-10-30 | 24.649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Western | Manitou Falls | Sluicegate Replacement | 82940 | Sustaining | Replacement of existing sluicegate system as it is no longer suitable for current operational requirements. Conversion of adjacent log sluice to an auto sluice. | Yes | 2018-04-23 | 2021-09-15 | 25.448 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0
12 | Western | Silver Falls | SLV G1 Rewind and New Core | 82385 | Sustaining (Refurbishment) | Replace various G1 components including generator stator winding, rotor/field winding and stator core. | Yes | 2018-01-22 | 2022-12-05 | 21.434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Western | Aguasabon | Surge Tank Replacement | 83610 | Sustaining | Replacement of surge tank, which is in poor condition with moderate loss of wall thickness due to corrosion. | Yes | 2018-01-22 | 2023-08-31 | 26.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Western | Whitedog Falls | WHD Sluicegate Replacement | 83031 | Sustaining | Replacement of existing auto sluice gates #8 and #9, which are at end of life. Conversion of pinned gate #7 to an auto sluice gate. | Yes | 2017-02-27 | 2021-12-03 | 16.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Eastern | Des Joachims | DEJ - Controls - Repl. Generator Controls | 83353 | Sustaining | Replacement and upgrade of protections and controls to address deficiencies noted with current systems and adhere to current standards and specifications. | No | 2016-11-04 | 2022-06-17 | 13.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Eastern | Otto Holden | OTO - Capital Project Scope G7 1st Unit | 84385 | Sustaining (Refurbishment) | Refurbishment of station unit, including turbine stay ring realignment, field pole refurbishment and auxiliary system upgrades. | Yes | 2019-09-18 | 2022-09-21 | 12.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Eastern | Otter Rapids | OTR -T2/T1 Transformer Replacement | 82255 | Sustaining | Replacement of T1 and T2 transformers with uprated transformers to allow for increase in capacity of planned runner upgrades. Procurement of additional spare transformer. | Yes | 2017-03-13 | 2020-08-28 | 12.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Western | Pine Portage | PIN Sluicegate Replacement | 82802 | Sustaining | Replacement of existing auto sluice gates, hoist, structure and gains; these assets were at end of life. Project expanded to include replacement of deteriorated dam deck surface. | Yes | 2016-03-14 | 2021-10-29 | 13.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Western | Whitedog Falls | WHD Sluicegate Repl. - Dogged #1-#4- #5-#6 | 84446 | Sustaining | Replacement of sluice gates #1, #4, #5 ad #6, including secondary concrete, embedded parts and associated electrical components, all at end of life. | Yes | 2019-08-12 | 2021-10-16 | 12.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Western | Caribou Falls | Sluicegate Replacement | 82799 | Sustaining | Replacement of existing auto sluice gates #8 and #9, which are at end of life. Conversion of pinned gate #7 to an auto sluice gate. | Yes | 2018-04-23 | 2023-10-20 | 17.25 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
21 | Eastern | R.H. Saunders | SAU - Headwork Crane Replacement | 83111 | Sustaining | Replacement of headworks gantry crane. Design and installation of new crane consisting of 100-ton hoist, 15-ton auxiliary hoist and 10-ton debris-removal hoist. | No | 2016-04-28 | 2022-12-03 | 10.85 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
22 | Eastern | Des Joachims | Replace Generator Breakers and Station Service Brks. | 80602 | Sustaining | Replacement of existing switchgears at all 8 units, which are approaching end of life, with arc-resistant switchgear. Includes bus work, generator and station service breakers. | No | 2011-11-30 | 2020-12-14 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dorian Mary
23 | Eastern | Barrett Chute | Rewind Generators & Reinsulate Field Poles (G1-4) First Unit (G3) | 80980 | Sustaining (Refurbishment) | Refurbishment of station unit G3, including stator rewind, field pole refurbishment and replacement of stator core, frame and key bars. | Yes | 2016-05-10 | 2023-11-30 | 13.682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1-4) Second Unit (G4) | 84587 | Sustaining (Refurbishment) | Refurbishment of station unit G4, including stator rewind, field pole refurbishment and replacement of stator core, frame and key bars. | Yes | 2019-07-12 | 2023-11-30 | 11.878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1) | 86082 | Sustaining (Refurbishment) | Refurbishment of station unit G1 including generator rewind and field pole reinsulation. Field poles are original to station and are at end of life. | Yes | 2022-05-18 | 2024-05-24 | 11.455 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0
26 | Eastern | Otter Rapids | Otter Runner Purchase | 80684 | Value Enhancing (Refurbishment) | Design and procurement of turbine runners for installation within the Otter Rapids G1, G2, G3 and G4 generating units. | Yes* | 2010-04-10 | 2029-11-28 | 17.9 | 13.2 | 4.4 | 0 | 4.4 | 4.4 | 4.4 | 0 | 0 | Dorian Mary
27 | Eastern | Otter Rapids | Otter Sluice Gate Upgrades | 82246 | Sustaining | Replacement of eight deteriorated sluice gates at station to allowfor improved operational reliablilty. | Yes | 2019-03-19 | 2024-12-18 | 23.9 | 0 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0
28 | Eastern | Abitibi Canyon | Abitibi - Transformer Deck Roof Replacement | 82257 | Sustaining | Replacement of degraded roof system and transformer foundations. Remedial work to ensure adequate structural integrity. | No | 2019-02-09 | 2024-12-09 | 26.685 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
29 | Eastern | Stewartville | Replace AC Station Service Transformers, Switchgear and Distribution Panels | 83763 | Sustaining | Replacement of AC station switchgear, transformers, panels, breakers and controls. Current AC station service equipment is original to station and is obsolete. | No | 2018-06-25 | 2023-12-01 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Eastern | Elliott Chute | Elliott - Service Gate and Gains Upgrade | 84534 | Sustaining | Replacement of deterioated service gate, gains, sill beam and lifting device. Widening existing powerhouse approach access ramp. | No | 2021-02-04 | 2024-11-13 | 13.187 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
31 | Eastern | R.H. Saunders | Replacement of Excitation System All 16 Units | 82986 | Sustaining | Replacement of outdated excitation systems in all 16 units. Systems built with now-obsolete technology, diminishing ability for maintenance. | Yes | 2016-07-06 | 2026-12-31 | 17.17 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0
32 | Eastern | R.H. Saunders | Install Concrete Plug in Ice Sluice Drum Gate Openings | 84202 | Sustaining | Decommissioning of existing ice sluice gates. Installation of concrete plug and rehabilitation of ice sluice structure to restore loading capacity on the headworks deck. | No | 2017-03-28 | 2026-12-19 | 22.6 | 0 | 0.8 | 3.6 | 0 | 0 | 0 | 0 | 0
33 | Niagara | DeCew Falls 2 | G1 Runner Shaft Replacement | 84558 | Sustaining (Refurbishment) | Replacement of unit G1 existing runner and shaft, repairing of draft tube and installation of new bottom ring. Project to reduce runner and shaft tube cavitation damage. | Yes | 2020-08-04 | 2024-11-29 | 19.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Niagara | Sir Adam Beck 1 | BK1 Tailrace Deck | 86053 | Sustaining | Replacement of existing tailrace deck, which has deteriorated and is not in alignment with current regulations and standards. | No | 2020-11-20 | 2025-05-14 | 18.93 | 0 | 0.314 | 0 | 0 | 0 | 0 | 0 | 0
35 | Niagara | Sir Adam Beck 2 | SAB2 Headgate Replt. | 86376 | Sustaining | Replacement of 31 (of 32) station headgates, which are advanced in age and have suffered from reduced operational performance. | No | 2021-03-18 | 2024-09-30 | 23.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Niagara | Sir Adam Beck 2 | SAB2 Rock Cliff Conc. Rehab | 86491 | Sustaining | Substantial rehabilitation of SAB2 rock cliff to prevent rock and concrete debris from falling to lower levels. | No | 2021-07-06 | 2024-12-09 | 22.84 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0
37 | Niagara | Sir Adam Beck 2 | Battery Banks and DC System Upgrade | 80812 | Sustaining | Replacement of 250 Vdc system battery banks, battery room upgrades and installation of new switchgears, panels and inverters. | No | 2018-07-27 | 2024-02-27 | 11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dorian Mary
38 | Western | Alexander | Stn. Switchgear, Protections & Ctrls. Repl. | 82378 | Sustaining | Replace station switchgear, plant/unit controls and unit/transformer protections to ensure reliability of switchgear and bus system. | No | 2018-11-23 | 2023-12-01 | 27.5 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0
39 | Western | Cameron Falls | T1 & T2 Replacement | 82390 | Sustaining | Replacement of T1 and T2 transformers, high-voltage insulators and bus work, high-voltage disconnects; repair of oil containment systems. | No | 2020-02-05 | 2025-02-24 | 25.05 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0
40 | Niagara | Sir Adam Beck 2 | BK2 Penstock Concrete Restoration | 87951 | Sustaining | Rehabilitatation of penstock concrete at Sir Adam Beck 2. Reduces safety risk to assets and personnel by preventing concrete debris from falling to lower levels. | No | 2024-06-14 | 2026-08-25 | 24.7 | 0 | 15.6 | 9 | 0 | 0 | 0 | 0 | 0
Table continues on EX. D1-1-2, Table 2b
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in the historical, bridge, or forecast period AND Completed/Deferred Projects in the historical period (2016-2024) at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): Col.(g): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2016-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 5). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D1-1-2_Table 2b
Numbers may not add due to rounding. | [17 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 2b
Table 2b
Capital Project Listing - Regulated Hydroelectric and Hydro Common
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[9 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Region | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r)
41 | Western | Caribou Falls | CAF 120/208V & Lighting Upgrade | 84432 | Sustaining | Replacement of the 120/208 VAC distribution system, 125 VDC infrastructure, unit headcover pump systems, HVAC system and lighting, as well as building renovations. | No | 2021-09-15 | 2024-01-23 | 10.225 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
42 | Eastern | R.H. Saunders | SAU - Concrete Rehabilitation | 89543 | Sustaining | Restoration of the integrity of powerhouse structural components adversely impacted by concrete expansion from Alkali-Aggregate Reaction. | No | 2024-12-17 | 2026-10-01 | 16.55 | 0 | 7 | 0.8 | 0 | 0 | 0 | 0 | 0
43 | Eastern | Bingham Chute | Bingham Chute GS Redevelopment | 86385 | Value Enhancing (Redevelopment) | Redevelopment of Bingham Chute GS to support continued operations. | Yes* | 2021-06-24 | 2027-04-15 | 24 | 0.5 | 0 | 23.5 | 0.5 | 0 | 0 | 0 | 0
44 | Eastern | Crystal Falls | Crystal Falls Elect./Controls Upgrade | 82261 | Sustaining | Replacement of electrical systems that are at end of life or obsolete in design. | No | 2020-11-10 | 2026-11-12 | 20.8 | 0 | 0 | 16.2 | 0 | 0 | 0 | 0 | 0
45 | Eastern | Stewartville | STW - G5 Cap. Refurb. - Rwnd Gen. & Reinsul. | 82351 | Sustaining (Refurbishment) | Refurbishment of station unit G5, including a generator rewind, field pole refurbishment, runner seal replacement and high pressure oil system replacement. | Yes* | 2024-10-10 | 2027-05-31 | 19.14 | 17.0956 | 0 | 0 | 17.0956 | 0 | 0 | 0 | 0
46 | Eastern | Otto Holden | OTO - New Turbine Runners | 83356 | Value Enhancing (Refurbishment) | Procurement and installation of new runners for units G1 to G4. | Yes* | 2017-01-30 | 2030-04-30 | 15.54 | 15.3591 | 0 | 0 | 6.9 | 3.9 | 3.1 | 1.4591 | 0
47 | Eastern | R.H. Saunders | SAU - Headgate Control Replacement | 86220 | Sustaining | Replacement of head gate controls for all 48 gates at RH Saunders GS. | No | 2023-11-27 | 2030-12-19 | 19.03 | 11.3988 | 0.82987 | 1.9 | 2.1 | 3.3 | 3.3797 | 2.6192 | 0
48 | Eastern | Coniston | Wanapitei Civil Upgrades | 86310 | Sustaining | Replacement or remediation of deteriorating elements of the control dam, which has been in operation since 1927 and has sustained damage to concrete structures. | No | 2021-12-21 | 2026-11-27 | 29.1 | 0 | 4.1 | 18.3 | 0 | 0 | 0 | 0 | 0
49 | Eastern | R.H. Saunders | SAU - Long Sault Dam Superstructure Automation (JW) (NYPA) | 87140 | Regulatory | NYPA-executed project to automate hoist operations at NYPA Long Sault Dam/Spillway. | No | 2023-03-01 | 2029-12-31 | 19.06 | 15.8 | 0 | 0 | 0 | 9 | 6.8 | 0 | 0
50 | Eastern | R.H. Saunders | SAU - 13.8KV Underground Feeder Eval. (JW) (NYPA) | 87141 | Regulatory | NYPA-executed project to replace Long Sault Spillway 13.8 kV underground feeder cables in order to correct operational inefficiencies. | No | 2023-03-01 | 2025-12-31 | 20.8 | 17.5 | 0 | 0 | 0 | 0 | 0 | 17.5 | 0
51 | Eastern | Otto Holden | OTO - G1 Refurb - Turbine & Generator | 87545 | Sustaining (Refurbishment) | Refurbishment of station unit G1, including turbine stay ring realignment, field pole refurbishment and installation of monitoring and diagnostic instrumentation. | Yes* | 2025-01-30 | 2027-04-30 | 13.3 | 12.0254 | 0 | 0 | 12.0254 | 0 | 0 | 0 | 0
52 | Eastern | Abitibi Canyon | ABI - Powerhouse Crane Refurb / Replace | 89078 | Sustaining | Refurbishment or replacement of two powerhouse cranes manufactured in 1931, both presenting mechanical and safety issues. | No | 2024-12-12 | 2028-05-15 | 20.5 | 17.2 | 0 | 0 | 0 | 17.2 | 0 | 0 | 0
53 | Eastern | Abitibi Canyon | ABI - Unloading Crane Refurb/Replacement | 89079 | Sustaining | Replacement of the station unloading crane components and support structure. | No | 2024-11-29 | 2028-01-30 | 15.26 | 12.8 | 0 | 0 | 0 | 12.8 | 0 | 0 | 0
54 | Western | Silver Falls | SLV Electrical Infrastructure Replacement | 82005 | Sustaining | Replacement of station service transformers near end of life in order to maintain station reliability. | No | 2021-03-18 | 2028-10-18 | 18.7631 | 18.6685 | 0 | 0 | 0 | 18.6685 | 0 | 0 | 0
55 | Western | Caribou Falls | CAF Electrical Infrastructure Replacement | 84430 | Sustaining | Replacement of existing medium voltage switchgear, high voltage disconnect switch, protections, and unit/station controls. Existing equipment is dated 1958 and is in poor condition. | No | 2021-03-18 | 2027-12-03 | 23.4821 | 22.8302 | 0 | 0 | 22.8302 | 0 | 0 | 0 | 0
56 | Western | Manitou Falls | MOT T1 Replacement | 84436 | Sustaining | Replacement of T1 main output transformers and associated equipment to reduce forced unit outages and support reliable operation for 25-30 years. | No | 2022-04-27 | 2027-02-24 | 12.6 | 10.7223 | 0 | 0 | 10.7223 | 0 | 0 | 0 | 0
57 | Western | Whitedog Falls | WHD Electrical Infrastructure Replacement | 84448 | Sustaining | Replacement of existing medium voltage switchgear, high voltage disconnect switch, protections, and unit/station controls. Existing equipment is dated 1958 and is in poor condition. | No | 2021-03-18 | 2028-10-13 | 23.6306 | 22.6834 | 0 | 0 | 0 | 22.6834 | 0 | 0 | 0
58 | Western | Pine Portage | Black Sturgeon Dam | 86369 | Sustaining | Rehabilitation of the Black Sturgeon Dam and access road. | No | 2021-02-15 | 2031-12-15 | 17.1353 | 16.2785 | 0 | 0 | 0 | 0 | 0 | 0 | 16.2785
59 | Western | Aguasabon | G2 Rewind & Core Replacement | 86383 | Sustaining (Refurbishment) | Replacement of existing stator frame, core and windings as well as the installation of a machine monitoring system to support a long, reliable service life. | Yes | 2021-08-09 | 2025-10-10 | 17.521 | 0 | 16.6 | 0 | 0 | 0 | 0 | 0 | 0
60 | Western | Cameron Falls | CAM - Block Dam 3-4 Life Extension | 89000 | Sustaining | Remediation of Cameron Falls GS block dams #3 and #4, 100-year-old earthfill embankments experiencing internal erosion within their timber pile cores. | No | 2025-06-12 | 2027-12-12 | 15.4239 | 9.6 | 5 | 0 | 9.6 | 0 | 0 | 0 | 0
61 | Niagara | Sir Adam Beck 2 | SAB OH Site Prep and Facility Rehab | 86379 | Sustaining | Rehabilitation and upgrade of Sir Adam Beck building infrastructure to address adverse conditions and optimize personnel occupancy in preparation for SAB Refurbishment Program. | No | 2021-08-31 | 2026-02-27 | 17.68 | 0 | 15.7 | 0 | 0 | 0 | 0 | 0 | 0
62 | Niagara | Sir Adam Beck 2 | BK2 Phse. Cranes Replacement | 89025 | Sustaining | Replacement of two powerhouse overhead cranes, repair crane runway and replace crane rails. | No | 2025-01-13 | 2031-01-07 | 14.712 | 14.4514 | 0 | 0 | 7.9483 | 6.5031 | 0 | 0 | 0
63 | Eastern | Arnprior | ARN - Repl. AC Stn. Serv. Switchgear & Brkrs. | 80951 | Sustaining | Upgrade of Arnprior GS AC station, including replacement of station service transformers,MV switchgear and PLC panels. | No | 2022-07-14 | 2025-09-25 | 14.32 | 0 | 5.4 | 0 | 0 | 0 | 0 | 0 | 0
64 | Niagara | Sir Adam Beck Pump GS | Hatchcover and Drive System | 82210 | Sustaining | Replacement of all eight hatchcovers with a new and improved design, removal of asbestos, and replacement of hydraulic drive system with an electric drive system to eliminate oil leaks. | No | 2024-04-11 | 2026-02-19 | 11.79 | 0 | 5 | 1.3 | 0 | 0 | 0 | 0 | 0
65 | Eastern | Mountain Chute | MTN - Repl. AC Sta. Serv. Trnsfrmrs Switch | 82987 | Sustaining | Replacement of AC station switchgear ad addition of a separate enclosure, transformers, PLC equipment and software, 600V panels, breakers and controls. | No | 2022-07-14 | 2028-03-30 | 11.7 | 3.3 | 0 | 7.3 | 3.3 | 0 | 0 | 0 | 0
66 | Eastern | Abitibi Canyon | Abitibi - Breaker Roof Replt. | 83153 | Sustaining | Rehabilitation of deteriorated concrete on breaker roof, application of new roof membrane and replacement of guardrails and access doors. | No | 2023-03-20 | 2026-11-07 | 10.8 | 0 | 0.5 | 8 | 0 | 0 | 0 | 0 | 0
67 | Western | Cameron Falls | CAM G7 Capital Refurb | 83257 | Sustaining (Refurbishment) | Refurbishment of station unit G7, including replacement of generator windings, field poles, bearings and instrumentation. | Yes | 2019-08-12 | 2026-12-08 | 29.4 | 0 | 0 | 25.3 | 0 | 0 | 0 | 0 | 0
68 | Eastern | R.H. Saunders | SAU - Repl. Iroquois Dam 2 Cranes (JW) (OPG) | 86586 | Sustaining | Replacement of original (1956) gantry cranes used to raise and lower dam gates. New cranes to have a minimum service life of 50 years. | No | 2024-05-07 | 2028-12-21 | 20.1 | 8.5 | 0 | 8.5 | 8.5 | 0 | 0 | 0 | 0
69 | Eastern | Barrett Chute | BAR - G2 Cap. Rfrb; Rwnd Gen. Reins. Fld. Pls. | 86077 | Sustaining (Refurbishment) | Refurbishment of station unit G2, including replacement of generator windings and thurst bearings as well as refurbishment of field poles. | Yes | 2020-07-17 | 2025-04-07 | 10.475 | 0 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0
70 | Eastern | Chenaux | CHE - PH Cranes 2 - Cntrls & Cndctr Upgrade | 86200 | Sustaining | Replacement of two powerhouse overhead cranes originally installed in 1948 with new powerhouse cranes. | No | 2021-12-20 | 2025-09-04 | 11.053 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0
71 | Niagara | Sir Adam Beck 2 | SAB2 N and S Phse Cranes | 86438 | Sustaining | Refurbishment of two 200-ton powerhouse cranes to ensure reliable operation in support of the Sir Adam Beck 2 maintenance and refurbishment program. | No | 2020-09-25 | 2025-08-29 | 10.544 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
72 | Eastern | Otto Holden | OTO - G8 Refurb - Turbine & Generator | 86477 | Sustaining (Refurbishment) | Refurbishment of station unit G8, including replacement of thurst bearings, refurbishment of field poles and turbine stay ring realignment. | Yes | 2023-02-22 | 2025-04-11 | 13.6 | 0 | 12.1 | 0 | 0 | 0 | 0 | 0 | 0
73 | Eastern | Otto Holden | OTO - G6 Refurb - Turbine & Generator | 86478 | Sustaining (Refurbishment) | Refurbishment of station unit G6, including replacement of thurst bearings, refurbishment of field poles and turbine stay ring realignment. | Yes | 2024-02-07 | 2026-05-29 | 10.742 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
74 | Western | Caribou Falls | CAF Block Dam 4 Rehabilitation | 86602 | Sustaining | Installation of downstream rockfill toe berm at Caribou Block Dam #4 to resolve dam safety risks and reduce likelihood of failure. | No | 2021-07-28 | 2024-10-23 | 10.4 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0
75 | Eastern | Stewartville | STW - Access Rd and Bank Stabilization | 89572 | Sustaining | Reconstruction of the single access road to Stewartville GS, including construction of a new turnaround area, stormwater drainage system and underground electrical duct bank. | No | 2025-03-26 | 2026-06-26 | 10.68 | 0 | 6.8 | 0.9 | 0 | 0 | 0 | 0 | 0
76 | Eastern | Arnprior | ARN - Replace T1 Main Output Transformer | 87513 | Sustaining | Replacement of main output transformer. | No | 2024-12-16 | 2029-10-16 | 11.95 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0
77 | Niagara | Sir Adam Beck Pump GS | BKP Headworks Crane Replacement | 86920 | Sustaining | Replacement of the headworks crane and rails as well as repair of the headworks deck. | No | 2023-12-19 | 2027-10-22 | 19.6 | 16.8 | 0 | 0 | 16.8 | 0 | 0 | 0 | 0
78 | Eastern | Des Joachims | DEJ - Headpond and Tailrace Booms | 86204 | Regulatory | Installation of new headpond and tailrace booms to restrict boat access to main dam hazardous area. | No | 2022-08-08 | 2028-09-30 | 10.8 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0
79 | Niagara | Sir Adam Beck 2 | BK2 Hoist Refurbishment G11-18 | 84568 | Sustaining | Replacement of headgates and refurbishment of headgate gains and hoist system. | No | 2020-09-23 | 2036-09-29 | 17.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Eastern | R.H. Saunders | Runner Replacement | 83104 | Value Enhancing (Refurbishment) | Design and procurement of turbine runners for installation within the R.H. Saunders Unit G9, G12 and G16 generating units. | Yes | 2016-08-22 | 2028-03-31 | 17.9 | 3.3 | 10 | 2.8 | 0 | 3 | 0 | 0.3 | 0
81 | Eastern | Abitibi Canyon | Canyon Dam Downstream Concrete Rehab | 87192 | Sustaining | Rehabilitation of downstream concrete walls to extend life of wall surfaces and eliminate health and safety risks of falling concrete. | Yes | 2023-05-04 | 2026-02-11 | 24.8 | 0 | 1.4 | 2.3 | 0 | 0 | 0 | 0 | 0
| (c): Total Regulated Hydroelectric; (j): 1396.653; (k): 295.0133 | 147.3439 | 140.5 | 127.7218 | 101.4551 | 27.6797 | 21.8783 | 16.2785
Hydro Common
82 | Western | Kenora Common | NWK Work Centre Buidling | 87139 | Sustaining | Design and construction of a permanent work centre for Kenora staff supporting nearby hydroelectric stations. | No | 2023-03-31 | 2027-12-31 | 16.5 | 16.5 | 0 | 0 | 16.5 | 0 | 0 | 0 | 0
| (c): Total Hydro Common; (j): 16.5; (k): 16.5 | 0 | 0 | 16.5 | 0 | 0 | 0 | 0
Notes:
Refer to Notes in Table 2a

## D1-1-2_Table 3
Numbers may not add due to rounding. | [11 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 3
Table 3
Capital Project Listing - Regulated Hydroelectric and Hydro Common
Projects < $10M Total Project Cost1
|  |  | Total | Average
|  | Number | Project | Cost of All | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | of | Cost | Projects | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Prescribed Facility Category | Projects | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | Niagara Region | 168 | 414.38 | 2.4665 | 80.86 | 22.7 | 34.92 | 50 | 10.04 | 11.86 | 7.82 | 1.14
2 | Eastern Region | 279 | 776.13 | 2.7818 | 113.94 | 43.24 | 47.08 | 62.66 | 25.85 | 11.09 | 7.19 | 7.15
3 | Western Region | 180 | 442.64 | 2.4591 | 69.78 | 37.25 | 52.05 | 20.58 | 17.4 | 16.34 | 12.71 | 2.75
4 | Total Regulated Hydroelectric | 627 | 1633.15 | 2.6047 | 264.58 | 103.19 | 134.05 | 133.24 | 53.29 | 39.29 | 27.72 | 11.04
5 | Total Hydro Common | 20 | 70.86 | 3.543 | 0 | 9.76 | 10.23 | 0 | n/a | n/a | n/a | n/a
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in the historical, bridge, or forecast period AND Completed/Deferred Projects in the historical period (2016-2024) at the time of preparing the 2025-2031 Business Plan.

## D1-1-2_Table 4
Numbers may not add due to rounding. | [11 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 4
Table 4
Comparison of In-Service Capital Additions - Regulated Hydroelectric and Hydro Common ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Prescribed Facility Category | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Budget | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
1 | Niagara Region | 10.7 | 49.7 | 34.4 | 21.6 | 19 | 17 | 35.7 | 44.9 | 69.6 | 55.3 | 45.2
2 | Eastern Region | 34.1 | 48.2 | 67.4 | 82 | 69.6 | 77.4 | 85.2 | 90.3 | 103.7 | 118.4 | 120.6
3 | Western Region | 4.3 | 13.8 | 24.2 | 46.45 | 40.8 | 98 | 55.4 | 61.4 | 67.9 | 52.5 | 52.05
4 | Subtotal Portfolio Projects (Allocated) | 49.1 | 111.7 | 126 | 150.05 | 129.4 | 192.4 | 176.3 | 196.6 | 241.2 | 226.2 | 217.85
Portfolio Projects (Unallocated)
5 | Niagara Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9 | 7.6
6 | Eastern Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
7 | Western Region | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.2
8 | Subtotal Supplemental In-Service Forecast1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 19.8
9 | Total Portfolio In-Service Forecast | 49.1 | 111.7 | 126 | 150.05 | 129.4 | 192.4 | 176.3 | 196.6 | 241.2 | 231.6 | 237.65
10 | Refurbishments (Allocated) | 14.7 | 40.6 | 19.9 | 42.1 | 3.4 | 55.4 | 95 | 34.8 | 80.6 | 165.1 | 100.7
11 | Refurbishments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.5 | 0
12 | Redevelopments (Allocated) | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 30.8 | 1.8 | 16.8 | 165.2
13 | Redevelopments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Sir Adam Beck 1 GS Canal Rehabilitation2 | 0 | 0 | 0 | 0 | 0.26 | 0 | 0 | 0 | 0 | 0 | 0
15 | Expansion Projects | 0 | 0 | 0 | 53.7 | 11.7 | 0 | 118.4 | 5.2 | 0 | 0 | 0
16 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.57 | 1.4 | 27.3
17 | Minor Fixed Assets | 0.17 | 0.67 | 1.012 | 1.086 | 1.127 | 1.493 | 1.292 | 1.371 | 1.649 | 3.2 | 1.5
18 | Total Regulated Hydroelectric In-Service Capital Additions | 63.97 | 152.97 | 146.912 | 246.936 | 145.887 | 249.293 | 523.992 | 268.771 | 347.819 | 418.6 | 532.35
19 | Hydro Common | 0 | 3.71 | 0 | 2.62 | 2.89 | 3.67 | 4.44 | 4.23 | 4.44 | 9.76 | 10.23
Line |  | 2027 | 2028 | 2029 | 2030 | 2031 | 2017-2021 | (h)-(f) | 2022-2026 | (j)-(h) | 2027-2031
No. | Prescribed Facility Category | Plan | Plan | Plan | Plan | Plan | Actuals | Change | Actuals & Budget3 | Change | Plan3
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j)
Portfolio Projects (Allocated)
20 | Niagara Region | 77.9 | 16.5 | 30.9 | 23.7 | 4.3 | 141.7 | 109 | 250.7 | -97.4 | 153.3
21 | Eastern Region | 81.6 | 77.6 | 118.8 | 55.1 | 38.2 | 344.6 | 173.6 | 518.2 | -146.9 | 371.3
22 | Western Region | 103.7 | 97.6 | 18.8 | 42.7 | 46.3 | 223.25 | 66 | 289.25 | 19.85 | 309.1
23 | Subtotal Portfolio Projects (Allocated) | 263.2 | 191.7 | 168.5 | 121.5 | 88.8 | 709.55 | 348.6 | 1058.15 | -224.45 | 833.7
Portfolio Projects (Unallocated)
24 | Niagara Region | -8.4 | 35.5 | 43.1 | 53.4 | 26.4 | 0 | 11.5 | 11.5 | 138.5 | 150
25 | Eastern Region | 87 | 87 | 69.8 | 67.6 | 56.3 | 0 | 12 | 12 | 355.7 | 367.7
26 | Western Region | -2.7 | 21.4 | 83.2 | 55.3 | 158 | 0 | 1.7 | 1.7 | 313.5 | 315.2
27 | Subtotal Supplemental In-Service Forecast1 | 75.9 | 143.9 | 196.1 | 176.3 | 240.7 | 0 | 25.2 | 25.2 | 807.7 | 832.9
28 | Total Portfolio In-Service Forecast | 339.1 | 335.6 | 364.6 | 297.8 | 329.5 | 709.55 | 373.8 | 1083.35 | 583.25 | 1666.6
29 | Refurbishments (Allocated) | 138.8 | 339.7 | 281.1 | 500.1 | 92.5 | 161.4 | 314.8 | 476.2 | 876 | 1352.2
30 | Refurbishments (Unallocated) | 12 | 76 | 243.2 | 93.9 | 137 | 0 | 0.5 | 0.5 | 561.6 | 562.1
31 | Redevelopments (Allocated) | 350.1 | 351.8 | 15 | 0 | 0 | 0 | 347.6 | 347.6 | 369.3 | 716.9
32 | Redevelopments (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Sir Adam Beck 1 GS Canal Rehabilitation2 | 0 | 0 | 190 | 0 | 0 | 0.26 | -0.26 | 0 | 190 | 190
34 | Expansion Projects | 0 | 0 | 0 | 0 | 0 | 65.4 | 58.2 | 123.6 | -123.6 | 0
35 | Abitibi Canyon Concrete and Sluiceway Rehabilitation Program2 | 0 | 0 | 20 | 45 | 66.4 | 0 | 51.27 | 51.27 | 80.13 | 131.4
36 | Minor Fixed Assets | 1.53 | 1.57 | 1.61 | 1.65 | 1.69 | 5.388 | 3.624 | 9.012 | -0.962 | 8.05
37 | Total Regulated Hydroelectric In-Service Capital Additions | 841.53 | 1104.67 | 1115.51 | 938.45 | 627.09 | 941.998 | 1149.534 | 2091.532 | 2535.718 | 4627.25
38 | Hydro Common | 16.5 | n/a | n/a | n/a | n/a | 12.89 | 20.21 | 33.1 | n/a | n/a
38a | Hydro Common3 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 6.62 | 9.88 | 16.5
Notes:
1 | In-service amounts for unallocated projects (see Ex. D1-1-1, Section 3.0); reflects the difference between total approved portfolio budget and amount allocated to portfolio projects.
2 | Includes forecast in-service amounts for both allocated and unallocated projects.
3 | Term-over-term variance is provided for the annual average of 2022-2026 (2022-2024 actuals, 2025-2026 forecast) versus the 2027 test year forecast - refer to Ex. D1-1-1, Section 6.0.

## D1-1-2_Table 5a
Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 5a
Table 5a
Capital Project Listing - Regulated Hydroelectric1
(Unallocated)2
Potential
Line |  |  |  | CRVA | Start
No. | Facility | Project Name | Category | Eligible3 | Date
|  | (a) | (b) | (c) | (d)
Projects With Potential Cost >$30M
1 | Abitibi Canyon | Abitibi - G3 Capital Upgrades | Sustaining (Refurbishment) | Yes* | 2028
2 | Abitibi Canyon | Abitibi - G4 Capital Upgrades | Sustaining (Refurbishment) | Yes* | 2030
3 | Abitibi Canyon | Abitibi - G5 Capital Upgrades | Sustaining (Refurbishment) | Yes* | 2031
4 | Aguasabon | AGU Upgrade Water Conveyance Capabilities | Value Enhancing | Yes* | 2027
5 | Alexander | ALX Spillwall Rehabilitation | Sustaining | No | 2028
6 | Sir Adam Beck 2 | BK2 G16 G15 Refurbishment | Sustaining (Refurbishment) | Yes* | 2027
7 | Sir Adam Beck 2 | BK2 G26 G25 Refurbishment | Sustaining (Refurbishment) | Yes* | 2028
8 | Sir Adam Beck Pump Generating Station | PGS Refurbishment | Sustaining (Refurbishment) | Yes* | 2029
9 | Chats Falls | CHF - Generator Rewinds (NET) | Sustaining (Refurbishment) | Yes* | 2026
10 | Des Joachims | DEJ - Capital Refurb Program Rewind Generators / Stators G2,4,6,7,8 | Sustaining (Refurbishment) | Yes* | 2030
11 | Manitou Falls | MAN G4 - Capital Refurb | Sustaining (Refurbishment) | Yes* | 2028
12 | Manitou Falls | MAN G1 - Capital Refurb | Sustaining (Refurbishment) | Yes* | 2026
13 | Manitou Falls | MAN G2 - Capital Refurb | Sustaining (Refurbishment) | Yes* | 2026
14 | Manitou Falls | MAN G5 - Capital Refurb | Sustaining (Refurbishment) | Yes* | 2030
15 | DeCew Falls | DeCew Earth Structures Rehab | Sustaining | No | 2026
16 | Pine Portage | NWN Waboose Dam Life Extension | Sustaining | Yes* | 2031
17 | Otter Rapids | Otter G3 Capital Upgrade | Sustaining (Refurbishment) | Yes* | 2026
18 | Otter Rapids | Otter G4 Capital Upgrade | Sustaining (Refurbishment) | Yes* | 2026
19 | Pine Portage | PIN G1 Capital Refurb | Sustaining (Refurbishment) | Yes* | 2028
20 | Pine Portage | PIN G2 Capital Refurb | Sustaining (Refurbishment) | Yes* | 2030
21 | Pine Portage | PIN Main Dam Life Extension | Sustaining | Yes* | 2030
22 | R.H. Saunders | SAU - Replace Generator Breakers and Switchgear | Sustaining | No | 2025
23 | R.H. Saunders | SAU - G10 Capital Refurbishment | Sustaining (Refurbishment) | Yes* | 2026
24 | R.H. Saunders | SAU - G11 Capital Refurb Project Fifth Unit | Sustaining (Refurbishment) | Yes* | 2027
25 | R.H. Saunders | SAU - Iroquois Dam Env Mgmt | Regulatory | No | 2027
26 | R.H. Saunders | SAU - G2 Capital Refurb Project Sixth Unit | Sustaining (Refurbishment) | Yes* | 2029
27 | R.H. Saunders | SAU - G3 Capital Refurb Project Seventh Unit | Sustaining (Refurbishment) | Yes* | 2031
28 | Abitibi Canyon | Abitibi Canyon Sluiceway Rehabilitation | Sustaining (Abitibi Concrete) | Yes* | 2025
29 | Abitibi Canyon | ABI - Upstream Concrete Liner | Sustaining (Abitibi Concrete) | Yes* | 2025
30 | Abitibi Canyon | Abitibi Canyon Concrete Zone 1 2 4B 5 6 | Sustaining (Abitibi Concrete) | Yes* | 2028
31 | Chats Falls | Chats Falls GS Expansion | Value Enhancing (Expansion) | Yes* | 2026
32 | Sir Adam Beck 1 | SAB1 Canal Isolation Preparedness Phase 2 | Sustaining (Canal Rehabilitation) | Yes* | 2029
33 | DeCew Falls | DeCew I GS Refurbishment | Sustaining (Refurbishment) | Yes* | 2025
Notes:
1 | There are no unallocated Hydro Common projects in this category.
2 | Unallocated includes projects with forecast expenditures during the 2027-2031 forecast period.
3 | Col.(c): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2016-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 5). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D1-1-2_Table 5b
Updated: 2026-03-10
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 5b
Table 5b
Capital Project Listing - Regulated Hydroelectric1
(Unallocated)2
Potential
Line |  |  |  | CRVA | Start
No. | Facility | Project Name | Category | Eligible3 | Date
|  | (a) | (b) | (c) | (d)
Projects With Potential Cost between $10M - $30M
1 | Abitibi Canyon | ABI - Intake Gantry Crane Refurb / Replacement | Sustaining | No | 2026
2 | Aguasabon | AGU Intake Plug | Sustaining | No | 2029
3 | Arnprior | ARN - Replace Sluice Gates | Sustaining | Yes* | 2031
4 | Arnprior | ARN - Replace Turbine Runners | Sustaining (Refurbishment) | Yes* | 2027
5 | Arnprior | ARN - Capital Refurb Project Re-insulate Rotor Field Poles First Unit | Sustaining (Refurbishment) | Yes* | 2029
6 | Sir Adam Beck 1 | BK1 Headworks Curtain Wall Restoration | Sustaining | No | 2025
7 | Cameron Falls | CAM Spillway Training Wall Repl | Sustaining | No | 2027
8 | Chenaux | CHE - 1st Unit Capital Refurb | Sustaining (Refurbishment) | Yes* | 2025
9 | Chenaux | CHE - 2nd Unit Capital Refurb | Sustaining (Refurbishment) | Yes* | 2029
10 | Chenaux | CHE - 3rd Unit Capital Refurb | Sustaining (Refurbishment) | Yes* | 2030
11 | Chenaux | CHE - 4th Unit Capital Refurb | Sustaining (Refurbishment) | Yes* | 2031
12 | Chats Falls | CHF - Replace Powerhouse Cranes, Supply Bus, & Disc SW (NET) | Sustaining | No | 2025
13 | Chats Falls | CHF - Replace Screw Hoists on Sluice Gates (NET) | Sustaining | No | 2026
14 | Des Joachims | DEJ - Replace Powerhouse Cranes (2) | Sustaining | No | 2029
15 | Des Joachims | DEJ - Sluicegate Structure & Hoist Wire Rope, Controls Replacement McConnell Lake | Sustaining | Yes* | 2030
16 | DeCew Falls 2 | DQ2 G2 Runner and Governor Upgrade | Value Enhancing (Refurbishment) | Yes* | 2029
17 | DeCew Falls 2 | DQ2 G1 Electrical Refurbishment | Sustaining (Refurbishment) | Yes* | 2029
18 | Eastern Operations | EOP - Renfrew Office | Sustaining | No | 2030
19 | Kakabeka Falls | KAK Headgate and Building Replacement | Sustaining | No | 2025
20 | McVittie | McVittie - Headworks Upgrades | Sustaining | No | 2026
21 | McVittie | McVittie Service Gates and Gains Upgrades | Sustaining | No | 2026
22 | Niagara Region | NIA Upgrade PLC Equip | Sustaining | No | 2026
23 | International Niagara Control Works | ICD Gate Rehabilitation (13-16) (JW) (OPG) | Sustaining | No | 2029
24 | Otto Holden | OTO - Replace trash racks | Sustaining | No | 2026
25 | Otto Holden | OTO - G2 Refurb - Turbine & Generator | Sustaining (Refurbishment) | Yes* | 2027
26 | Otto Holden | OTO - Powerhouse Crane Replacement | Sustaining | No | 2028
27 | Otto Holden | OTO - G3 Refurb - Turbine & Generator | Sustaining (Refurbishment) | Yes* | 2028
28 | Otto Holden | OTO - G4 Refurb - Turbine & Generator | Sustaining (Refurbishment) | Yes* | 2029
29 | Pine Portage | PIN G4 Headgate, Hoist & Controls Repl | Sustaining | No | 2026
30 | Pine Portage | PIN G3 Headgate, Hoist & Controls Repl | Sustaining | No | 2026
31 | Pine Portage | PIN G2 Headgate, Hoist & Controls Repl | Sustaining | No | 2031
32 | Pine Portage | PIN G1 Headgate, Hoist & Controls Repl | Sustaining | No | 2029
33 | Pine Portage | PIN Tailrace Pier Rehab | Sustaining | No | 2027
34 | R.H. Saunders | SAU - Re-Insulate Field Poles | Sustaining (Refurbishment) | Yes* | 2026
35 | R.H. Saunders | SAU - Iroquois Dam 32 Control Gates (JW)(OPG) NET | Sustaining | No | 2027
36 | R.H. Saunders | SAU - Protection & Controls Refresh | Sustaining | No | 2029
37 | R.H. Saunders | SAU - Replace Generator, Transformer, Line and Station Service Bus Protections | Sustaining | No | 2029
38 | Stewartville | STW - Capital Refurb - Rewind Generator and Reinsulate Field Poles (Second Unit) | Sustaining (Refurbishment) | Yes* | 2026
39 | Stewartville | STW - Capital Refurb - Rewind Generator and Reinsulate Field Poles (Third Unit) | Sustaining (Refurbishment) | Yes* | 2027
40 | Stewartville | STW - Capital Refurb - Rewind Generators and Reinsulate Field Poles (Fourth Unit) | Sustaining (Refurbishment) | Yes* | 2029
41 | Stewartville | STW - Capital Refurb - Rewind Generator and Reinsulate Field Poles (Fifth Unit) | Sustaining (Refurbishment) | Yes* | 2030
42 | R.H. Saunders | Fisheries Act Compliance - Saunders | Regulatory | No | 2031
43 | Chats Falls | Fisheries Act Compliance - Chats Falls | Regulatory | No | 2030
44 | Dymond Service Centre4 | Mistinikon Control Dam Upgrades | Regulatory | Yes* | 2026
45 | Eastern Operations | EOP - Correct IDF Flow Deficient MADA Syst. | Sustaining | No | 2026
Notes:
Refer to Table 5a for Notes 1-3
4 | Mistinikon Control Dam supports both the Chute GS and the Lower Notch GS.

## D1-1-2_Table 6
Updated: 2026-05-21
EB-2025-0297
Exhibit D1
Tab 1
Schedule 2
Table 6
Table 6
Capital Projects - Regulated Hydroelectric and Hydro Common
Listing of Business Case Summaries Filed
BCS
Line |  |  | Project | Approval |  | BCS
No. | Facility | Business Case Summary (BCS) Title | Number | Date | Project Stage | Status
| (a) | (b) | (c) | (d) | (e) | (f)
1 | Ranney Falls | Ranney Falls Expansion Project | 80581 | 2017-03-14 | Closed | Full Release Execution
2 | Sir Adam Beck Pump Generating Station | Sir Adam Beck Pump GS - Reservoir Refurbishment | 80583 | 2015-08-18 | Closed | Full Release Execution
3 | Sir Adam Beck 1 | Sir Adam Beck I GS - G10 Major Overhaul & Upgrade | 80649 | 2016-08-31 | Closed | Superseding Execution
4 | DeCew Falls 2 | G2 Overhaul & Upgrade | 80851 | 2016-04-20 | Closed | Full Release Execution
5 | Coniston/Stinson | Coniston/Stinson GS Redevelopment | 82087 | 2024-11-25 | Execution | Full Release Execution
6 | Calabogie | Calabogie GS - Redevelopment | 82089 | 2022-10-26 | Closed | Superseding Execution
7 | Alexander | G1 Capital Refurb | 82391 | 2023-04-19 | Development | Full Release Development
8 | Otter Rapids | Otter G1 Capital Upgrade | 82542 | 2024-11-21 | Execution | Full Release Execution
9 | Otter Rapids | Otter G2 Capital Upgrade | 82543 | 2025-07-02 | Execution | Superseding Execution
10 | Sir Adam Beck 1 | Sir Adam Beck 1 GS - Unit G5 Upgrade | 82777 | 2021-09-19 | Closed | Superseding Execution
11 | Abitibi Canyon | ABI - G1 Capital Upgrades | 83148 | 2025-03-06 | Development | Full Release Execution
12 | Abitibi Canyon | Abitibi - G2 Capital Upgrades/HG | 83155 | 2019-12-12 | Closed | Full Release Execution
13 | Abitibi Canyon | Abitibi - G2 Capital Upgrades/HG | 83155 | 2024-08-27 | Closed | Over-Variance Execution
14 | Frederick House6 | Frederick House Lake Dam Upgrades | 83194 | 2023-05-29 | Execution | Full Release Execution
15 | R.H. Saunders | SAU - G9 Capital Refurbishment | 83495 | 2024-08-27 | Execution | Superseding Execution
16 | Silver Falls | Surge Tank Replacement | 83833 | 2021-03-18 | Development | Full Release Development
17 | Sir Adam Beck 1 | BK1 G1/G2 Replacement | 84185 | 2020-10-07 | Closed | Full Release Execution
18 | Sir Adam Beck 1 | BK1 G1/G2 Replacement | 84185 | 2020-10-01 | Closed | Over-Variance Execution
19 | Chenaux | CHE - Limerick Isl. Spr Structure Sluice Gate Hoist | 84494 | 2020-12-10 | Execution | Full Release Execution
20 | Northwest Operations1 | NWO Work Centre Building | 84901 | 2023-07-15 | Execution | Full Release Execution
21 | Otter Rapids | Otter Project Camp | 84907 | 2023-04-06 | Execution | Full Release Execution
22 | Sir Adam Beck 1 | SAB1 Station Service Upgrade | 86364 | 2023-07-06 | Definition | Full Release Definition
23 | Sir Adam Beck 1 | BK1 G6 G8 Refurbishment | 86372 | 2025-05-29 | Definition | Full Release Definition
24 | Kakabeka Falls | Kakabeka Falls GS | 86386 | 2024-11-25 | Execution | Full Release Execution
25 | Matabitchuan | Matabitchuan GS | 86387 | 2025-03-20 | Execution | Full Release Execution
26 | Sir Adam Beck 1 | BK1 G4 Refurbishment | 86570 | 2024-12-10 | Execution | Full Release Execution
27 | R.H. Saunders | SAU - G12 Capital Refurbishment | 86587 | 2024-05-07 | Execution | Full Release Execution
28 | R.H. Saunders | SAU - LSD Capital Program (JW)(NYPA) | 86595 | 2023-03-01 | Development | Full Release Development
29 | Alexander | G2 Capital Refurb | 86792 | 2025-05-15 | Development | Superseding Development
30 | Alexander | G3 Capital Refurb | 86793 | 2023-06-13 | Development | Full Release Development
31 | Manitou Falls | MAN G3 Capital Refurb | 86860 | 2024-12-03 | Development | Full Release Development
32 | R.H. Saunders | SAU - G16 Capital Refurbishment | 86937 | 2024-11-29 | Definition | Full Release Definition
33 | R.H. Saunders | SAU - Massena Canal Dam (JW)(NYPA)(CAP) | 87142 | 2023-03-01 | Definition | Full Release Definition
34 | Timmins (Hydro Common) | Timmins Building Expansion | 87197 | 2024-09-20 | Development | Full Release Development
35 | Aguasabon | Aguasabon Dam Rehab. Hayes Lake Main Dam | 87217 | 2023-08-14 | Development | Full Release Development
36 | Dymond (Hydro Common) | Dymond Machine Shop Expansion | 87329 | 2025-04-17 | Development | Superseding Development
37 | Sir Adam Beck 2 | BK2 G18 G17 Refurbishment | 87356 | 2025-05-22 | Development | Full Release Development
38 | Sir Adam Beck 2 | BK2 G14 G13 Refurbishment | 87357 | 2025-05-26 | Development | Full Release Development
39 | Sir Adam Beck 2 | BK2 230kV Conductor Replacement | 87362 | 2025-03-25 | Development | Full Release Development
40 | R.H. Saunders | SAU - Long Sault Dam Downstream Concrete JW NYPA | 87575 | 2024-06-11 | Development | Full Release Development
41 | Sir Adam Beck 2 | BK2 G20/G19 Refurbishment | 87768 | 2024-12-10 | Definition | Full Release Definition
42 | Sir Adam Beck 1 | SAB1 Canal Isolation Preparedness Phase 1 (SAB1 CIP1) | 89252 | 2025-07-11 | Definition | Full Release Definition
43 | Otto Holden | OTO - Refurbish Stop Log Sluice Piers | 89354 | 2024-10-10 | Definition | Partial Release Definition
44 | Abitibi Canyon | Abitibi Canyon Concrete Repair Zone 7 | 89505 | 2025-04-25 | Execution | Full Release Execution
Notes:
1 | Supports generating stations in Thunder Bay and Kenora (refer to Ex. A1-4-2, Att. 1).

## D2-1-2_Table 1
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 2
Table 1
Table 1
Capital Expenditures Summary - OPG Nuclear Facilities ($M)
Line |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Category | Actual | Actual | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | Nuclear Operations Capital1 | 380.8082 | 366.8003 | 481.2651 | 566.8341 | 548.5837 | 579.7159 | 861.1671 | 1053.1322 | 1004.7848 | 1138.7466 | 1154.0585 | 836.6416
2 | Darlington Refurbishment Program2 | 781.5139 | 812.9589 | 970.2979 | 973.2176 | 988.2493 | 835.1583 | 392.005 | 0 | 0 | 0 | 0 | 0
3 | Pickering Refurbishment Program3 | 0 | 0 | 0 | 15.3667 | 371.6051 | 1500 | 3045.5782 | 3473.2055 | 3607.5781 | 3578.2596 | 2681.4355 | 1860.5442
4 | Total OPG Nuclear Facilities Capital | 1162.3221 | 1179.7592 | 1451.563 | 1555.4184 | 1908.4381 | 2914.8742 | 4298.7503 | 4526.3377 | 4612.3628 | 4717.0062 | 3835.494 | 2697.1858
5 | DNNP Capitalized Fuel4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.1167 | 25.0441
Notes:
1 | Refer to Ex. D2-1-2, Table 2, line 22.
2 | Refer to Ex. D2-2-3, Table 1b, line 5.
3 | Refer to Ex. D2-3-8, Table 1, line 4.
4 | Refer to Ex. D2-1-2, Table 2, line 23.

## D2-1-2_Table 2
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 2
Table 2
Table 2
Capital Expenditures Summary - Nuclear Operations ($M)
Line |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Category | Actual | Actual | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
OPG Nuclear Facilities Portfolio Projects (Allocated)
1 | Darlington NGS | 263.7759 | 252.8869 | 311.3845 | 358.8195 | 302.8011 | 317.5632 | 351.5421 | 286.4661 | 160.0669 | 110.3825 | 73.9284 | 43.6898
2 | Pickering NGS | 25.6068 | 12.0697 | 9.6292 | 19.1132 | 6.6991 | 6.7692 | 54.812 | 44.1228 | 22.5521 | 14.2101 | 0.224 | 3.386
3 | Operations and Project Support | 38.3015 | 54.5098 | 38.2765 | 37.2039 | 36.7199 | 33.4112 | 21.1603 | 8.5487 | 4.8485 | 2.0933 | 1.8 | 0.415
4 | Subtotal OPG Nuclear Facilities Portfolio Projects (Allocated) | 327.6842 | 319.4664 | 359.2901 | 415.1366 | 346.2201 | 357.7435 | 427.5144 | 339.1376 | 187.4675 | 126.6858 | 75.9524 | 47.4908
OPG Nuclear Facilities Portfolio Projects (Unallocated)
5 | Darlington NGS | 0 | 0 | 0 | 0 | 0 | -41.369 | -27.8394 | 62.2206 | 94.9236 | 119.7457 | 130.7657 | 160.6801
6 | Pickering NGS | 0 | 0 | 0 | 0 | 0 | 81.6279 | 76.2312 | 133.4171 | 188.3196 | 230.481 | 254.0448 | 257.7584
7 | Operations and Project Support | 0 | 0 | 0 | 0 | 0 | 3.3048 | 7.3954 | 15.031 | 21.5289 | 31.7392 | 20.3007 | 0.97284
8 | Subtotal OPG Nuclear Facilities Portfolio Projects (Unallocated) | 0 | 0 | 0 | 0 | 0 | 43.5637 | 55.7872 | 210.6687 | 304.7722 | 381.9659 | 405.1112 | 419.4114
9 | Subtotal OPG Nuclear Facilities Project Capital (Portfolio) | 327.6842 | 319.4664 | 359.2901 | 415.1366 | 346.2201 | 401.3072 | 483.3015 | 549.8063 | 492.2396 | 508.6517 | 481.0636 | 466.9022
10 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 68.3304 | -0.2 | 0 | 0 | 0 | 0 | 0 | 0
11 | Darlington Unit 2 Turbine Control and Auxiliary Systems Upgrade | 15.289 | 3.9193 | 18.0406 | 23.9417 | 4.1021 | 14.7 | 27.6929 | 65.6528 | 3.8752 | 0 | 0 | 0
12 | Tritium Removal Facility Major Component Replacement Program | 0 | 0.36183 | 3.5482 | 4.2709 | 6.2371 | 24.6258 | 36.2889 | 53.8473 | 32.8879 | 57.4855 | 29.768 | 18.3364
13 | Darlington Steam Generator Primary Moisture Separators Replacement Projects | 0 | 5.7444 | 70.0298 | 98.6287 | 83.91 | 42 | 81.4175 | 100.7045 | 12.8757 | 0 | 0 | 0
14 | Pickering Extended Operations | 19.7476 | 17.5303 | 0.7669 | 0.31629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Darlington Non-Routine Steam Generator Cleanings | 0 | 0 | 0 | 0 | 0.2075 | 12.3 | 14.3609 | 12.5616 | 11.5899 | 8.5501 | 0 | 0
16 | Darlington Unit 1 and 2 Generator Stator Rewind | 0 | 0 | 0 | 0 | 0 | 18.7 | 41.1175 | 16.003 | 112.499 | 30.216 | 93.046 | 0.764
17 | Darlington Turbine Rotors Replacement2 | 0 | 0 | 0 | 0 | 0 | 27.2 | 161.8092 | 241.339 | 321.813 | 519.491 | 407.751 | 308.425
18 | Pickering Water Treatment Plant Lease1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.225 | 0
19 | Darlington Refurbishment New Fuel | 0.22389 | 0 | 15.5716 | 0.32683 | 17.3765 | 20.0604 | 0.3 | 0 | 0 | 0 | 0 | 0
20 | Pickering Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.7385 | 24.8602
21 | OPG Nuclear Facilities Minor Fixed Assets | 17.8636 | 19.7781 | 14.0179 | 24.2131 | 22.2 | 19.0225 | 14.8787 | 13.2178 | 17.0044 | 14.3523 | 20.4663 | 17.3538
22 | Total Nuclear Operations Capital | 380.8082 | 366.8003 | 481.2651 | 566.8341 | 548.5837 | 579.7159 | 861.1671 | 1053.1322 | 1004.7848 | 1138.7466 | 1154.0585 | 836.6416
23 | DNNP Capitalized Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.1167 | 25.0441
Notes
1 | Amounts associated with Pickering Water Treatment Plant Lease are unallocated.
2 | Darlington Turbine Rotors Replacement consists of two projects (87807 - replacement & 87811 - capital spare). Project 87811 is not CRVA eligible.

## D2-1-2_Table 3
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 2
Table 3
Table 3
Capital Expenditures Summary - OPG Nuclear Facilities Portfolio Projects (Allocated) ($M) 1
By Project Category
Line |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Category | Actual | Actual | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
Portfolio Projects (Allocated)
1 | Regulatory | 83.8287 | 49.2189 | 70.9202 | 75.4425 | 52.8641 | 50.6085 | 43.4543 | 27.9953 | 19.9645 | 11.8974 | 11.1771 | 10.0836
2 | Sustaining | 243.8176 | 270.1039 | 288.3699 | 339.0456 | 360.7239 | 305.3401 | 378.4452 | 306.442 | 162.6282 | 110.8709 | 62.1453 | 37.4073
3 | Value Enhancing | 0.01034 | 0.14365 | 0 | 0.64854 | 0.96255 | 1.5949 | 5.6149 | 4.7004 | 4.8748 | 3.9176 | 2.63 | 0
4 | Total | 327.6566 | 319.4664 | 359.2901 | 415.1366 | 414.5506 | 357.5435 | 427.5144 | 339.1376 | 187.4675 | 126.6858 | 75.9524 | 47.4908
Notes
1 | Col. (e) and (f) include Darlington Water Treatment Plant Lease.

## D2-1-2_Table 4
Numbers may not add due to rounding. | [12 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 1
Schedule 2
Table 4
Table 4
Comparison of Capital Expenditures - Nuclear Operations ($M)
Line |  | 2020 | (c)-(a) | 2020 | 2021 | (f)-(d) | 2021 | 2022 | (i)-(g) | 2022 | 2023 | (l)-(j) | 2023
No. | Business Unit | OEB Approved1 | Change | Actual | OEB Approved1 | Change | Actual | OEB Approved1 | Change | Actual | OEB Approved1 | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
OPG Nuclear Facilities Portfolio Projects (Allocated)
1 | Darlington NGS2 | 37.381 | 226.3949 | 263.7759 | 30.231 | 222.6559 | 252.8869 | 352.943 | -41.5585 | 311.3845 | 285.037 | 73.7825 | 358.8195
2 | Pickering NGS | 0 | 25.6068 | 25.6068 | 0 | 12.0697 | 12.0697 | 0.375 | 9.2542 | 9.6292 | 0 | 19.1132 | 19.1132
3 | Operations and Project Support | 0 | 38.3015 | 38.3015 | 0 | 54.5098 | 54.5098 | 18.842 | 19.4345 | 38.2765 | 4.567 | 32.6369 | 37.2039
4 | Subtotal OPG Nuclear Facilities Portfolio Projects (Allocated) | 37.381 | 290.3032 | 327.6842 | 30.231 | 289.2354 | 319.4664 | 372.16 | -12.8699 | 359.2901 | 289.604 | 125.5326 | 415.1366
OPG Nuclear Facilities Portfolio Projects (Unallocated)
5 | Darlington NGS | 0 | 0 | 0 | 0 | 0 | 0 | 1.034 | -1.034 | 0 | 35.236 | -35.236 | 0
6 | Pickering NGS | 0 | 0 | 0 | 0 | 0 | 0 | 4 | -4 | 0 | 0 | 0 | 0
7 | Operations and Project Support | 221.619 | -221.619 | 0 | 149.769 | -149.769 | 0 | 7.95 | -7.95 | 0 | 13.253 | -13.253 | 0
8 | Subtotal OPG Nuclear Facilities Portfolio Projects (Unallocated) | 221.619 | -221.619 | 0 | 149.769 | -149.769 | 0 | 12.984 | -12.984 | 0 | 48.489 | -48.489 | 0
9 | Subtotal OPG Nuclear Facilities Project Capital (Portfolio) | 259 | 68.6842 | 327.6842 | 180 | 139.4664 | 319.4664 | 385.144 | -25.8539 | 359.2901 | 338.093 | 77.0436 | 415.1366
10 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Darlington Unit 2 Turbine Control and Auxiliary Upgrade | 0 | 15.289 | 15.289 | 0 | 3.9193 | 3.9193 | 8.203 | 9.8376 | 18.0406 | 6.728 | 17.2137 | 23.9417
12 | Tritium Removal Facility Major Component Replacements Projects | 0 | 0 | 0 | 0 | 0.36183 | 0.36183 | 0 | 3.5482 | 3.5482 | 0 | 4.2709 | 4.2709
13 | Darlington Steam Generator Primary Moisture Separators Replacement Projects | 0 | 0 | 0 | 0 | 5.7444 | 5.7444 | 0 | 70.0298 | 70.0298 | 0 | 98.6287 | 98.6287
14 | Pickering Extended Operations | 0 | 19.7476 | 19.7476 | 0 | 17.5303 | 17.5303 | 0 | 0.7669 | 0.7669 | 0 | 0.31629 | 0.31629
15 | Darlington Non-Routine Steam Generator Cleanings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Darlington Unit 1 and 2 Generator Stator Rewind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Darlington Turbine Rotors Replacement4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Pickering Water Treatment Plant Lease3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Darlington Refurbishment New Fuel | 0 | 0.22389 | 0.22389 | 0 | 0 | 0 | 0 | 15.5716 | 15.5716 | 16.458 | -16.1312 | 0.32683
20 | Pickering Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | OPG Nuclear Facilities Minor Fixed Assets | 19.467 | -1.6034 | 17.8636 | 19.32 | 0.45805 | 19.7781 | 19.6154 | -5.5975 | 14.0179 | 21.0441 | 3.169 | 24.2131
22 | Total OPG Nuclear Facilities Capital | 278.467 | 102.3412 | 380.8082 | 199.32 | 167.4803 | 366.8003 | 412.9624 | 68.3027 | 481.2651 | 382.3231 | 184.511 | 566.8341
23 | DNNP Capitalized Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line |  | 2024 | (c)-(a) | 2024 | 2025 | (f)-(d) | 2025 | 2026 | (i)-(g) | 2026 | 2022-2026 | (l)-(j) | 2027-2031
No. | Business Unit | OEB Approved1 | Change | Actual | OEB Approved1 | Change | Budget | OEB Approved1 | Change | Budget | Actuals & Budget | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
OPG Nuclear Facilities Portfolio Projects (Allocated)
24 | Darlington NGS2 | 248.04 | 54.7611 | 302.8011 | 166.668 | 150.8952 | 317.5632 | 134.907 | 216.6351 | 351.5421 | 1642.1104 | -967.5767 | 674.5337
25 | Pickering NGS | 0 | 6.6991 | 6.6991 | 0 | 6.7692 | 6.7692 | 0 | 54.812 | 54.812 | 97.0226 | -12.5276 | 84.495
26 | Operations and Project Support | 1.817 | 34.9029 | 36.7199 | 3.136 | 30.2752 | 33.4112 | 0 | 21.1603 | 21.1603 | 166.7717 | -149.0662 | 17.7055
27 | Subtotal OPG Nuclear Facilities Portfolio Projects (Allocated) | 249.857 | 96.3631 | 346.2201 | 169.804 | 187.9395 | 357.7435 | 134.907 | 292.6074 | 427.5144 | 1905.9047 | -1129.1705 | 776.7342
OPG Nuclear Facilities Portfolio Projects (Unallocated)
28 | Darlington NGS | 17.732 | -17.732 | 0 | 53.209 | -94.578 | -41.369 | 40.198 | -68.0374 | -27.8394 | -69.2084 | 637.5442 | 568.3358
29 | Pickering NGS | 0 | 0 | 0 | 0 | 81.6279 | 81.6279 | 0 | 76.2312 | 76.2312 | 157.8591 | 906.1618 | 1064.0209
30 | Operations and Project Support | 15.844 | -15.844 | 0 | 13.5 | -10.1952 | 3.3048 | 16.657 | -9.2616 | 7.3954 | 10.7002 | 78.8724 | 89.5726
31 | Subtotal OPG Nuclear Facilities Portfolio Projects (Unallocated) | 33.576 | -33.576 | 0 | 66.709 | -23.1453 | 43.5637 | 56.855 | -1.0678 | 55.7872 | 99.3509 | 1622.5784 | 1721.9293
32 | Subtotal OPG Nuclear Facilities Project Capital (Portfolio) | 283.433 | 62.7871 | 346.2201 | 236.513 | 164.7942 | 401.3072 | 191.762 | 291.5395 | 483.3015 | 2005.2556 | 493.4079 | 2498.6635
33 | Darlington Water Treatment Plant Lease | 138.6 | -70.2696 | 68.3304 | 0 | -0.2 | -0.2 | 0 | 0 | 0 | 68.1304 | -68.1304 | 0
34 | Darlington Unit 2 Turbine Control and Auxiliary Systems Upgrade | 13.3 | -9.198 | 4.1021 | 47.733 | -33.033 | 14.7 | 0 | 27.6929 | 27.6929 | 88.4772 | -18.9492 | 69.5279
35 | Tritium Removal Facility Major Component Replacement Program | 0 | 6.2371 | 6.2371 | 0 | 24.6258 | 24.6258 | 0 | 36.2889 | 36.2889 | 74.9709 | 117.3541 | 192.325
36 | Darlington Steam Generator Primary Moisture Separators Replacement Projects | 0 | 83.91 | 83.91 | 0 | 42 | 42 | 0 | 81.4175 | 81.4175 | 375.986 | -262.4058 | 113.5802
37 | Pickering Extended Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0832 | -1.0832 | 0
38 | Darlington Non-Routine Steam Generator Cleanings | 0 | 0.2075 | 0.2075 | 0 | 12.3 | 12.3 | 0 | 14.3609 | 14.3609 | 26.8684 | 5.8331 | 32.7016
39 | Darlington Unit 1 and 2 Generator Stator Rewind | 0 | 0 | 0 | 0 | 18.7 | 18.7 | 0 | 41.1175 | 41.1175 | 59.8175 | 192.7105 | 252.528
40 | Darlington Turbine Rotors Replacement4 | 0 | 0 | 0 | 0 | 27.2 | 27.2 | 0 | 161.8092 | 161.8092 | 189.0092 | 1609.8098 | 1798.819
41 | Pickering Water Treatment Plant Lease3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.225 | 98.225
42 | Darlington Refurbishment New Fuel | 16.86 | 0.5165 | 17.3765 | 0 | 20.0604 | 20.0604 | 18.064 | -17.764 | 0.3 | 53.6354 | -53.6354 | 0
43 | Pickering Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.5987 | 48.5987
44 | OPG Nuclear Facilities Minor Fixed Assets | 29.2277 | -7.0277 | 22.2 | 18.6771 | 0.34536 | 19.0225 | 11.3895 | 3.4891 | 14.8787 | 94.7379 | -12.3432 | 82.3947
45 | Total Nuclear Operations Capital | 481.4207 | 67.163 | 548.5837 | 302.9231 | 276.7928 | 579.7159 | 221.2155 | 639.9516 | 861.1671 | 3037.5659 | 2149.7977 | 5187.3637
46 | DNNP Capitalized Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.1608 | 103.1608
Notes
1 | Amounts per EB-2016-0152, Ex. D2-1-2, Table 4 for 2020 and 2021, with exception of 2021 Projects Portfolio (Allocated) that have been adjusted for reclassification of projects from Darlington to Operations and Project Support. Amounts per EB-2020-0290, Ex. D2-1-2, Table 4 for 2022-2026 with exception of 2022 Projects Portfolio (Allocated) that have been adjusted for reclassification of projects from Darlington to Operations and Project Support.
2 | Amounts per EB-2016-0152, Ex. D2-1-1, Table 4 for 2020 and 2021. Amounts per EB-2020-0290, Ex. D2-1-2, Table 4 for 2022-2026 with the exception of 2022, 2023, 2024, 2025 Projects Portfolio (Allocated) that have been adjusted for reclassification of projects from Darlington to Darlington Unit 2 Turbine Control and Auxiliary Upgrade.
3 | Amounts associated with Pickering Water Treatment Plant Lease are unallocated.
4 | Darlington Turbine Rotor Replacement consists of two projects (87807 - replacement & 87811 - capital spare). Project 87811 is not CRVA eligible.

## D2-1-3_Table 1a
Numbers may not add due to rounding. | [23 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 1a
Table 1a
Capital Project Listing - OPG Nuclear Facilities Projects
Projects ≥ $30M Total Project Cost (Allocated)1
[8 empty] | Total | Partial/ | Initial | Superceding | Total | 1st Execution Business Case3 | 1st Execution Business Case- EB-2020-0290
[7 empty] | Final | Project | Devmt. | Full | Full | Project |  |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | CRVA | Start | In-Service | Cost2 | Release | Release | Release | Cost - EB-2020-0290 |  |  | In-Service | LTD5 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Eligible8 | Date | Date4 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (h) | (i) | (j) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s) | (t) | (u)
ONGOING PROJECTS FROM EB-2020-0290
1 | DN | DN Class II Uninterruptable Power Supply Replacement | 31412 | Sustaining | No | 2011-01-01 | 2027-02-01 | 69.3972 | 56.282 |  |  | 63.634 | 38.442 | 38.442 | 66.927 | 57.444 | 2.354 | 0.5 | 6.629 | 2.354 | 0 | 0 | 0 | 0
2 | DN | DN Station Roofs Replacement | 31524 | Sustaining | No | 2012-11-01 | 2024-10-01 | 71.6698 |  | 26.244 |  | 116.938 | 72.2 | N/A | 71.6068 | 70.3768 | 0 | 1.23 | 0 | 0 | 0 | 0 | 0 | 0
3 | DN | DN Powerhouse Water Air Condition Units Replacement | 31532 | Sustaining | No | 2012-10-01 | 2025-07-01 | 38.2112 |  | 20.743 |  | 38.179 | 26.595 | 26.595 | 37.6759 | 35.9067 | 0 | 1.7692 | 0 | 0 | 0 | 0 | 0 | 0
4 | DN | DN Water Treatment Plant Interconnections | 31535 | Sustaining | No | 2011-09-01 | 2024-12-01 | 94.8918 |  | 28.461 |  | 53.155 | 58.262 | N/A | 94.9 | 94.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | DN | DN Radiation Detection Equipment Obsolescence | 31544 | Sustaining | No | 2014-01-01 | 2026-09-01 | 65.3028 | 34.198 |  |  | 45 | 58.19 | N/A | 63.7554 | 53.9384 | 0 | 6 | 3.817 | 0 | 0 | 0 | 0 | 0
6 | DN | DN Air Conditioning Unit Replacement For Secondary Control Area | 33621 | Sustaining | No | 2009-02-01 | 2026-01-01 | 47.5869 |  | 38.179 |  | 35.957 | 12.291 | 12.291 | 43.475 | 34.123 | 0 | 5.868 | 3.484 | 0 | 0 | 0 | 0 | 0
7 | DN | DN Major Pump-Sets Vibration Monitoring System Upgrades | 33819 | Sustaining | No | 2006-03-01 | 2027-04-01 | 60.5698 | 20.26 |  |  | 55.385 | 12.766 | 12.766 | 54.619 | 46.799 | 2.462 | 3.45 | 1.908 | 2.462 | 0 | 0 | 0 | 0
8 | DN | DN Standby Generator Controls Replacement | 33973 | Sustaining | No | 2006-12-01 | 2025-07-01 | 45.9475 |  | 22.719 | 23.823 | 46.254 | 21.768 | 21.768 | 45.935 | 45.866 | 0 | 0.069 | 0 | 0 | 0 | 0 | 0 | 0
9 | DN | DN OH180 Aging Management Hardware Installation | 80022 | Sustaining | No | 2014-12-01 | 2029-11-01 | 60.9 | 39.873 |  |  | 60.931 | 60.93 | 60.93 | 36.9042 | 27.8443 | 4.1908 | 2.55 | 2.319 | 2.6022 | 0.26093 | 1.3277 | 0 | 0
10 | DN | DN R22 Refrigerant Air Conditioning Unit Replacement | 80036 | Regulatory | No | 2015-12-01 | 2027-01-01 | 59.7431 |  | 111.4 |  | 50.7⁷ | 50.7 | 50.7 | 54.9975 | 29.5445 | 5.586 | 7.448 | 12.419 | 5.586 | 0 | 0 | 0 | 0
11 | DN | DN Digital Control, Common Process And Sequence Of Events Monitoring Computer Aging Management | 80078 | Regulatory | No | 2015-11-01 | 2035-03-01 | 156.4 | 18.465 |  |  | 77.498 | N/A | N/A | 124.3 | 3.7952 | 77.129 | 0 | 0.462 | 21.893 | 10.112 | 10.799 | 8.262 | 26.063
12 | DN | DN Main Power Output Protection System Replacement | 80122 | Sustaining | No | 2016-09-01 | 2028-01-01 | 124.9038 |  | 24.606 |  | 65 | 124.904 | N/A | 111.2703 | 18.6913 | 32.91 | 42.31 | 17.359 | 19.584 | 13 | 0.326 | 0 | 0
13 | DN | DN Group II Pressure Transmitter Replacement | 80123 | Sustaining | No | 2016-01-01 | 2028-12-01 | 43.6907 |  | 26.829 |  | 47.748 | 43.69 | N/A | 32.4267 | 11.7319 | 10.735 | 4.9598 | 5 | 5 | 4.9 | 0.835 | 0 | 0
14 | DN | DN Obsolete Controller Replacement | 80124 | Sustaining | No | 2017-06-01 | 2028-12-01 | 38.0231 |  | 29.975 |  | 38.023 | 38.023 | 38.023 | 28.466 | 19.592 | 4.164 | 1.75 | 2.96 | 1.73 | 2.434 | 0 | 0 | 0
15 | DN | DN Emergency Power Generator 1 And 2 Replacement | 80126 | Regulatory | No | 2017-02-01 | 2023-11-01 | 178.0382 |  | 0 |  | 203.8⁶ | 176.239 | 176.239 | 174.882 | 173.515 | 0 | 1.367 | 0 | 0 | 0 | 0 | 0 | 0
16 | DN | DN Fuel Handling Computer Input/ Output Subsystem Interprocessor Communication Replacement | 80148 | Sustaining | No | 2015-12-01 | 2027-12-01 | 40.2134 |  | 43.484 |  | 23.445 | N/A | N/A | 32.8523 | 6.7857 | 12.744 | 6.0776 | 7.245 | 10.773 | 1.971 | 0 | 0 | 0
17 | DN | DN Fire Resistant Fluid Pump Improvement | 80150 | Sustaining | No | 2016-01-01 | 2029-12-01 | 55 |  | 22.058 | 26.467 | 30 | N/A | N/A | 40.8928 | 16.1648 | 24.728 | 0 | 0 | 8.177 | 5.404 | 10.487 | 0.66 | 0
18 | SEC | Security Project B | 82929 | Sustaining | No | 2016-06-01 | 2025-10-01 | 44.3 |  | 99.497 | 107.149 | 32.747 | 32.747 | 32.747 | 43.1995 | 37.1012 | 0 | 5.0983 | 1 | 0 | 0 | 0 | 0 | 0
19 | DN | DN Fuel Handling Head Major Component Replacement | 82947 | Sustaining | No | 2018-10-01 | 2028-08-01 | 120.0908 |  | 21.481 | 36.634 | 98.041 | 120.091 | N/A | 90.3658 | 34.2831 | 29.66 | 11.5337 | 14.889 | 17.347 | 11.987 | 0.326 | 0 | 0
20 | AIM | DN Rapid Delivery Machine | 83039 | Sustaining | No | 2014-11-01 | 2029-07-01 | 206.7 |  | 84 |  | 162.2 | 162.2 | N/A | 181.0195 | 59.2955 | 7.851 | 9.419 | 104.454 | 1.835 | 0.583 | 5.433 | 0 | 0
21 | DN | DN Main Output Transformer & Unit Service Transformer Replacement | 83296 | Sustaining | No | 2018-07-01 | 2027-12-01 | 170 | 52.826 |  |  | 170.125 | 170.125 | 170.125 | 151.0993 | 101.5653 | 49.534 | 0 | 0 | 46.947 | 2.587 | 0 | 0 | 0
22 | DN | DN Large Moderator Temperature Control Valve Replacement | 83297 | Sustaining | No | 2018-11-01 | 2030-01-01 | 39.8583 | 24.64 |  |  | 36.928 | 39.858 | N/A | 36.678 | 18.507 | 14.005 | 2.351 | 1.815 | 0 | 6.587 | 0 | 7.418 | 0
23 | DN | DN Secondary System Obsolete Control Valve Replacement | 83298 | Sustaining | No | 2018-03-01 | 2027-10-01 | 38.3519 | 21.428 |  |  | 35.433 | 38.352 | N/A | 31.4643 | 12.725 | 7.804 | 4.7353 | 6.2 | 7.804 | 0 | 0 | 0 | 0
24 | DN | DN 4KV Motor Refurbishment And Replacement | 83480 | Sustaining | No | 2018-10-01 | 2036-06-01 | 146.7924 | 12.968 |  |  | 278.792 | 146.792 | N/A | 116.1437 | 6.887 | 48 | 3.9707 | 3.9 | 4 | 11 | 12 | 10 | 11
25 | DN | DN Isolated Phase Bus Refurbishment | 83484 | Sustaining | No | 2020-07-01 | 2028-07-01 | 43.966 |  |  |  | 62.408 | 43.966 | N/A | 30.0656 | 5.8186 | 12.099 | 0 | 12.148 | 2.58 | 8.241 | 1.278 | 0 | 0
26 | DN | DN Powerhouse Upper Level Service Water Piping Replacement | 83530 | Sustaining | No | 2019-05-01 | 2025-11-01 | 82.7 |  |  |  | 85.5⁷ | 55.698 | 55.698 | 79.133 | 60.199 | 0 | 15.769 | 3.165 | 0 | 0 | 0 | 0 | 0
27 | DN | DN Unit 2 Turbine Control & Auxiliary Systems Upgrade | 83664 | Sustaining | Yes* | 2019-12-01 | 2028-01-01 | 194.5632 |  |  |  | 112.681 | 194.563 | N/A | 177.162 | 0 | 177.162 | 0 | 0 | 0 | 177.162 | 0 | 0 | 0
28 | DN | DN Primary Heat Transport Liquid Relief Valve Modifications (Waterhammer) | 84235 | Regulatory | No | 2019-01-01 | 2026-01-01 | 86.8 |  |  |  | 86.754 | 85.941 | 85.941 | 72.3415 | 58.4963 | 0 | 11.0772 | 2.768 | 0 | 0 | 0 | 0 | 0
29 | DN | DN Motor Operated Valve Replacements | 84551 | Sustaining | No | 2020-03-01 | 2029-12-01 | 34.2514 |  |  |  | 44.536 | 34.25 | N/A | 26.9933 | 10.3353 | 8.477 | 2.41 | 5.771 | 0 | 0 | 7.885 | 0.592 | 0
30 | DN | DN Revenue Metering Transformer Replacement | 84939 | Regulatory | No | 2020-04-01 | 2028-07-01 | 56.6972 | 14.438 |  |  | 35.854 | 56.697 | N/A | 48.6983 | 8.7441 | 12.221 | 8.4882 | 19.245 | 5.991 | 5.999 | 0.231 | 0 | 0
|  | Subtotal | [5 empty] | 2515.5606 | (n): 543.8158 | 160.2011 | 238.957 | 166.6652 | 262.2279 | 50.9277 | 26.932 | 37.063
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | The designation of "n/a" means the project has not advanced to a First Execution BCS.
4 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
5 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2024.
6 | EB-2020-0260 L-D2-01-AMPCO-27.
7 | EB-2020-0260 L-D2-01-AMPCO-044.
8 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 1b
Numbers may not add due to rounding. | [20 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 1b
Table 1b
Capital Project Listing - OPG Nuclear Facilities Projects
Projects ≥ $30M Total Project Cost (Allocated)1
[8 empty] | Total | Total | 1st Execution Business Case3 | 1st Execution Business Case EB-2020-0290
[7 empty] | Final | Project | Project |  |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | CRVA | Start | In-Service | Cost2 | Cost - EB-2020-0290 |  |  | In-Service | LTD6 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Eligible7 | Date | Date5 | (M$) | (M$) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s) | (t) | (u)
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
31 | DN | DN Shutdown Cooling Heat Exchanger Replacement | 31710 | Sustaining | No | 2012-11-01 | 2021-11-01 | 85.518 | 111.4 | 56.085 | 56.085 | 73.8091 | 73.8091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | DN | DN Auxiliary Heating System | 34000 | Regulatory | No | 2006-03-01 | 2018-06-01 | 106.3597 | 107.149 | 45.607 | 45.607 | 102.6442 | 102.6442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | DN | DN Zebra Mussels Mitigation & Improvements | 38948 | Sustaining | No | 2012-11-01 | 2021-12-01 | 37.1392 | 36.634 | 21.481 | 21.481 | 37.1392 | 37.1392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | DN | DN RS Primary Heat Transport Pump Motor Replacement4 | 73566 | Sustaining | No | 2015-07-01 | 2022-10-01 | 77.8983 | 84 | 26.7 | 26.7 | 72.0935 | 72.0935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | DN | DN Steam Generator Level Control Valve Replacement | 80023 | Sustaining | No | 2015-01-01 | Cancelled | 9.3298 | 38.6 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | DN | DN Primary Heat Transport Pump Motor Overhaul | 80144 | Sustaining | No | 2015-07-01 | 2021-12-01 | 43.5744 | 53.3 | 102.8 | 102.8 | 42.6119 | 42.6119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | DN | DN Copper Piping Replacement | 83049 | Sustaining | No | 2016-08-01 | 2023-08-01 | 44.3056 | 45.072 | 29.334 | 29.334 | 42.8248 | 42.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (b): Subtotal; (h): 404.1248 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): The designation of "n/a" means the project has not advanced to a First Execution BCS.
4 | (a): As per EB-2020-0290, Projects 73566 ($84.0M), 36001 ($27.6M) and 80144 ($53.3M) are combined in a single Business Case Summary ($164.9M). First execution BCS amounts are derived from the combined amount.
5 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
6 | (a): Life Time to Date (LTD) means in service amounts as of Dec 31, 2024.
7 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 1c
Numbers may not add due to rounding. | [23 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 1c
Table 1c
Capital Project Listing - OPG Nuclear Facilities Projects
Projects ≥ $30M Total Project Cost (Allocated)1
[8 empty] | Total | Partial/ | Initial | Superceding | Total Project Cost EB-2020-0290 | 1st Execution Business Case | 1st Execution Business Case EB-2020-0290
[7 empty] | Final | Project | Devmt. | Full | Full |  |  |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | CRVA | Start | In-Service | Cost2 | Release | Release | Release |  |  |  | In-Service | LTD5 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Eligible7 | Date | Date4 | (M$) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (h) | (i) | (j) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s) | (t) | (u)
PROJECTS NOT IN EB-2020-0290
38 | DN | DN Public Address System Upgrade | 31708 | Sustaining | No | 2021-10-01 | 2027-03-01 | 51.6288 |  |  |  | n/a | n/a | n/a | 40.567 | 0 | 23.189 | 0 | 17.378 | 23.189 | 0 | 0 | 0 | 0
39 | DN | DN Breathing, Instrument and Service Air Compressor Replacement | 83933 | Sustaining | No | 2023-02-01 | 2030-02-01 | 64.1 |  |  |  | n/a | n/a | n/a | 49.479 | 0 | 49.479 | 0 | 0 | 15.556 | 15.328 | 14.742 | 3.853 | 0
40 | DN | DN Powerhouse Elevator Replacement | 84135 | Sustaining | No | 2021-08-01 | 2031-06-01 | 49 |  |  |  | n/a | n/a | n/a | 38.701 | 0 | 26.201 | 6.5 | 6 | 6 | 6 | 5 | 5 | 4.201
41 | DN | DN Powerhouse Cranes Refurbishment | 84139 | Sustaining | No | 2022-12-01 | 2032-12-01 | 93.1 |  |  |  | n/a | n/a | n/a | 72.1 | 0 | 59.2973 | 0 | 0 | 0 | 0 | 13.7518 | 22.3966 | 23.1488
42 | DN | DN Vacuum Building Outage Power Operated Valves Replacement | 84552 | Sustaining | No | 2023-12-01 | 2028-10-01 | 95.2537 |  |  |  | n/a | n/a | n/a | 76.934 | 0 | 76.934 | 0 | 0 | 50.753 | 21.181 | 5 | 0 | 0
43 | DN | Tritium Removal Facility Major Component Replacement Program | 84764 | Sustaining | Yes* | 2021-11-01 | 2038-02-01 | 540.9504 |  |  |  | n/a | n/a | n/a | 452 | 0 | 157.645 | 0 | 0 | 52.5 | 0 | 0 | 105.145 | 0
44 | DN | DN Low Pressure Service Water Strainer Backwash Motorized Valves Replacement | 86280 | Sustaining | No | 2025-06-01 | 2028-05-01 | 31.9801 |  |  |  | n/a | n/a | n/a | 22.204 | 0 | 22.204 | 0 | 0 | 11.516 | 10.091 | 0.597 | 0 | 0
45 | DN | Darlington Steam Generator Moisture Separator Replacement | 86693 | Sustaining | Yes* | 2021-10-01 | 2025-12-01 | 359.2 |  |  |  | n/a | 380.829 | n/a | 278.6123 | 170.1353 | 0 | 107.977 | 0.5 | 0 | 0 | 0 | 0 | 0
46 | DN | DN Motor Operated Valve Replacement Innage | 86795 | Sustaining | No | 2023-06-01 | 2029-09-01 | 32.8506 |  |  |  | n/a | n/a | n/a | 19.304 | 0 | 19.304 | 0 | 0 | 5.176 | 6.824 | 7.304 | 0 | 0
47 | DN | DN Lighting Fixtures Light Emitting Diode Replacement | 86910 | Sustaining | No | 2023-04-01 | 2029-02-01 | 39.8805 |  |  |  | n/a | 39.881 | n/a | 35.503 | 7.92 | 15.683 | 6.5 | 5.4 | 6.2 | 6.2 | 3.283 | 0 | 0
48 | DN | DN Copper Upgrades Phase III | 86915 | Sustaining | No | 2024-12-01 | 2031-04-01 | 38.3007 |  |  |  | n/a | n/a | n/a | 34.733 | 0 | 28.533 | 0 | 6.2 | 6 | 5.8 | 5.8 | 7.131 | 3.802
49 | DN | DN Unit 2 and 3 Steam Generator Moisture Separator Replacement | 87151 | Sustaining | Yes* | 2025-06-01 | 2027-12-01 | 275 |  |  |  | n/a | 275 | n/a | 216.6148 | 0 | 135.3058 | 0 | 81.309 | 122.1212 | 13.1846 | 0 | 0 | 0
50 | DN | DN Tritium Removal Facility Cryogenic Refrigeration System Turbine Replacement | 87191 | Sustaining | No | 2023-10-01 | 2027-10-01 | 50 |  |  |  | n/a | n/a | n/a | 37.122 | 0 | 37.122 | 0 | 0 | 35.584 | 1.538 | 0 | 0 | 0
51 | DN | DN Turbine Rotors Replacement6 | 87807 87811 | Sustaining | Yes* | 2025-03-01 | 2032-07-01 | 2589 |  |  |  | n/a | n/a | n/a | 2293.3 | 0 | 1692.711 | 0 | 0 | 0 | 0 | 625.0453 | 533.8566 | 533.8091
52 | DN | DN Smartops Sensor Integration | 87808 | Sustaining | No | 2024-05-01 | 2030-12-01 | 51.0184 |  |  |  | n/a | n/a | n/a | 37.818 | 0 | 35.318 | 0.856 | 1.644 | 1.739 | 10.943 | 10.938 | 11.161 | 0.537
53 | DN | DN Unit 1 and 2 Generator Stator Rewind | 89281 | Sustaining | Yes* | 2025-03-01 | 2030-12-01 | 350 |  |  |  | n/a | n/a | n/a | 312.3 | 0 | 312.3 | 0 | 0 | 0 | 159.273 | 3.123 | 146.781 | 3.123
54 | DN | DN Steam Generator Soft Chemical Clean | 89462 | Sustaining | Yes* | 2024-12-01 | 2029-02-01 | 77.9404 |  |  |  | n/a | n/a | n/a | 59.668 | 0 | 39.668 | 0 | 20 | 14.7 | 12.784 | 12.184 | 0 | 0
55 | PN | PN 058 Boiler Room and Turbine Hall Crane Upgrade | 89535 | Sustaining | No | 2025-01-01 | 2027-07-01 | 59.6669 |  |  |  | n/a | n/a | n/a | 47.338 | 0 | 32.869 | 0 | 14.469 | 32.569 | 0.3 | 0 | 0 | 0
56 | PN | PN 058 Turbine Auxiliary Building, Reactor Auxiliary Building Hoist & Cranes | 89536 | Sustaining | No | 2025-03-01 | 2029-12-01 | 47.7 |  |  |  | n/a | n/a | n/a | 36.1 | 0 | 27.0804 | 0 | 9.0196 | 18.0142 | 6.0286 | 3.0376 | 0 | 0
57 | PN | P58 Second Simulator and Pickering Learning Centre Extension | 89581 | Regulatory | No | 2025-05-01 | 2028-03-01 | 39.6924 |  |  |  | n/a | n/a | n/a | 28.8959 | 0 | 28.8959 | 0 | 0 | 11.4514 | 17.4445 | 0 | 0 | 0
|  | Subtotal | [5 empty] | 4936.2627 | (l): 4189.2941; (n): 2819.7395 | 121.833 | 161.9196 | 413.0688 | 292.9197 | 709.8058 | 835.3243 | 568.6209
Division Total
58 |  | Darlington NGS | [6 empty] | (n): 752.0671 | 159.5398 | 170.125 | 326.5432 | 168.3879 | 111.9105 | 76.4736 | 68.7518
59 |  | Pickering NGS | [6 empty] | (n): 59.9494 | 0 | 23.4886 | 50.5832 | 6.3286 | 3.0376 | 0 | 0
60 |  | Operations and Project Support | [6 empty] | (n): 36.7469 | 14.5173 | 105.454 | 13.2864 | 18.0275 | 5.433 | 0 | 0
61 |  | Darlington Unit 2 Turbine Control and Auxiliary Systems Upgrade | [6 empty] | (n): 177.162 | 0 | 0 | 0 | 177.162 | 0 | 0 | 0
62 |  | Tritium Removal Facility Major Component Replacement Program | [6 empty] | (n): 157.645 | 0 | 0 | 52.5 | 0 | 0 | 105.145 | 0
63 |  | Darlington Steam Generator Primary Moisture Separators Replacement Projects | [6 empty] | (n): 135.3058 | 107.977 | 81.809 | 122.1212 | 13.1846 | 0 | 0 | 0
64 |  | Darlington Non-Routine Steam Generator Cleanings | [6 empty] | (n): 39.668 | 0 | 20 | 14.7 | 12.784 | 12.184 | 0 | 0
65 |  | Darlington Unit 1 and 2 Generator Stator Rewind | [6 empty] | (n): 312.3 | 0 | 0 | 0 | 159.273 | 3.123 | 146.781 | 3.123
66 |  | Darlington Turbine Rotors Replacement | [6 empty] | (n): 1692.711 | 0 | 0 | 0 | 0 | 625.0453 | 533.8566 | 533.8091
|  | Total | [6 empty] | (n): 3363.5553 | 282.0341 | 400.8766 | 579.734 | 555.1477 | 760.7334 | 862.2563 | 605.6839
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | The designation of "n/a" means the project has not advanced to a First Execution BCS.
4 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
5 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2024.
6 | Darlington Turbine Rotor Replacement consists of two projects (87807 - replacement & 87811 - capital spare). Project 87811 is not CRVA eligible.
7 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2a
Numbers may not add due to rounding. | [16 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2a
Table 2a
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[8 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q)
ONGOING PROJECTS FROM EB-2020-0290
1 | DN | DN Active Liquid Waste System Upgrade | 31403 | Regulatory | Add aeration and chemical addition to the active liquid waste management system to ensure compliance with discharge criteria | No | 2009-11-01 | 2026-05-01 | 17.86 | 0.079 | 0 | 10.923 | 0.079 | 0 | 0 | 0 | 0
2 | DN | DN Dryer Programmable Logic Controller Replacement | 31420 | Sustaining | Replace obsolete programmable logic controllers. | No | 2014-02-01 | 2026-06-01 | 15.1271 | 0.816 | 1.4999 | 2.045 | 0.816 | 0 | 0 | 0 | 0
3 | DN | DN Replacement Of Obsolete Online Chemistry Analyzers | 31520 | Sustaining | Replace obsolete online chemistry analyzers. | No | 2012-10-01 | 2024-08-01 | 16.2069 | 0 | 0.112 | 0 | 0 | 0 | 0 | 0 | 0
4 | DN | DN Feeder Scanner Replacement | 31526 | Sustaining | Replace the equipment that scans the feeders to locate channels containing failed fuel bundles. | No | 2012-12-01 | 2022-12-01 | 15.3489 | 0 | 0.554 | 0 | 0 | 0 | 0 | 0 | 0
5 | DN | DN Fuel Handling Obsolete Control Relay Re-Engineer/Replacement | 31704 | Sustaining | Replace the obsolete Fuel Handling control relays with relays of equal quality and near identical installation to mitigate challenges to FH System reliability. | No | 2013-10-01 | 2026-06-01 | 17.1699 | 0 | 2.9797 | 6.735 | 0 | 0 | 0 | 0 | 0
6 | DN | DN Vapour Recovery Button-Up Valve Replacements | 31706 | Sustaining | Replace aging vapour recovery containment buttonup valves with new design less prone to passing. | No | 2013-12-01 | 2026-01-01 | 23.7005 | 0 | 9.033 | 6.118 | 0 | 0 | 0 | 0 | 0
7 | DN | DN Neutron Over-Power Ion Chamber & In-Core Flux Detector Amplifier Replacement (Reactor Regulating System, Shutdown System 1 & Shutdown System 2) | 31716 | Sustaining | Replace end-of-life Neutron Over-Power (NOP), In-Core Flux Detector (ICFD), and the Ion Chamber (IC) amplifiers that are used to convert very small current signals from neutron detectors in the nuclear reactor into voltage signals used by the Shutdown System #1 (SDS1), Shutdown System #2 (SDS2) and Reactor Regulation System (RRS) computers. | No | 2013-07-01 | 2028-11-01 | 23.8465 | 6.859 | 3.0705 | 3.51 | 2.79 | 2.294 | 1.775 | 0 | 0
8 | DN | DN Replacement Of Emergency Power Supply Uninterruptible Power Supply | 33258 | Sustaining | Replace EPS/UPS equipment throughout the station units (U1~U4, U0). | No | 2010-02-01 | 2024-11-01 | 27.2949 | 0 | 0.245 | 0 | 0 | 0 | 0 | 0 | 0
9 | DN | Fuel Handling Computer Replacement | 33815 | Sustaining | Replace obsolete components of the fuel handling system control computers. | No | 2005-08-01 | 2024-08-01 | 16.7372 | 0 | 0 | 0.424 | 0 | 0 | 0 | 0 | 0
10 | DN | DN Digital Control Computer Replacement/ Refurbishment/ Upgrades | 33977 | Sustaining | Replace unit Digital Control Computers, Common process computers and Sequence of Events Monitoring computers with emulator-based systems that will ensure reliable operation for the extended life of the station, prevent obsolescence and avoid shortage of spare parts. | No | 2003-09-01 | 2025-05-01 | 29.9 | 0 | 1.254 | 0 | 0 | 0 | 0 | 0 | 0
11 | DN | DN Standby Generators Protective Relay Replacement | 80063 | Sustaining | Replace electro-mechanical relays with digital relays for the protections of the Standby Generators in order to address relay obsolescence issues and to ensure that spare parts are available for the continued reliable operation of Darlington. | No | 2015-12-01 | 2026-11-01 | 22.0005 | 2.482 | 5.312 | 3.979 | 2.482 | 0 | 0 | 0 | 0
Table continues on Ex. D2-1-3 Table 2b
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2b
Numbers may not add due to rounding. | [16 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2b
Table 2b
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[8 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (m) | (o) | (p) | (q)
ONGOING PROJECTS FROM EB-2020-0290 (Continued from Ex. D2-1-3 Table 2a)
12 | DN | DN Irradiated Fuel Discharge Mechanism Major Component Repla | 82841 | Sustaining | Replace the shuttle cylinders and other major components of the Irradiated Fuel Discharge system which are approaching end of design life. | No | 2015-11-01 | 2028-12-01 | 10.6982 | 0.77735 | 1.99 | 0.899 | 0.62689 | 0.15046 | 0 | 0 | 0 | Nov-15 | 2015-11-01 | Jan-29 | 2029-01-01 | Jan | 1
13 | DN | DN Fuel Handling Trolley Major Auxiliary Component Replacement | 82842 | Sustaining | Replace various major auxiliary components on the Fuel Handling trolleys that are approaching the end of their design lives. Component failures impact on fuelling availability and nuclear safety. | No | 2017-01-01 | 2028-01-01 | 19.1021 | 6.238 | 1.6625 | 2.998 | 1.199 | 5.039 | 0 | 0 | 0 | Jan-17 | 2017-01-01 | Dec-26 | 2026-12-01 | Feb | 2
14 | DN | DN Class 1 Rectifier Replacement | 82883 | Sustaining | Replace Class 1 Rectifiers across DLC, Unit 0, 1,2,3 & 4. | No | 2018-05-01 | 2028-01-01 | 24.6639 | 3.961 | 2.104 | 3.606 | 1.1 | 2.861 | 0 | 0 | 0 | May-18 | 2018-05-01 | Dec-27 | 2027-12-01 | Mar | 3
15 | DN | DN Fuel Handling Motor Replacement | 82886 | Sustaining | Replace fuel handing system motors critical for the operation of various fuel handling systems that are nearing the end of their design lives. | No | 2017-01-01 | 2030-12-01 | 14.6003 | 8.947 | 0.33763 | 0.69 | 4.31 | 0.303 | 3.71 | 0.456 | 0.168 | Jan-17 | 2017-01-01 | Dec-30 | 2030-12-01 | Apr | 4
16 | SEC | Security Project C | 82930 | Sustaining | Proactively replace obsolete components within the security systems at Pickering. | No | 2016-06-01 | 2025-06-01 | 29.6738 | 0 | 1.313 | 0 | 0 | 0 | 0 | 0 | 0 | Jun-16 | 2016-06-01 | Jun-25 | 2025-06-01 | May | 5
17 | DN | DN Fuel Handling Power & Signal Cable Catenary Replacement | 83052 | Sustaining | Replacement of Trolley Power, Trolley Signal, Trolley Encoder, and Service Area Bridge catenary cables for life extension. | No | 2019-04-01 | 2027-12-01 | 18.3658 | 0.49 | 0 | 0 | 0.49 | 0 | 0 | 0 | 0 | Apr-19 | 2019-04-01 | Dec-27 | 2027-12-01 | Jun | 6
18 | DN | DN Phase 2 Station Battery Replacement | 83076 | Sustaining | Replacement of Class 1 station batteries in DNGS. | No | 2016-08-01 | 2027-11-01 | 27.7356 | 3.294 | 3.6688 | 3.859 | 2.757 | 0.537 | 0 | 0 | 0 | Aug-16 | 2016-08-01 | Nov-27 | 2027-11-01 | Jul | 7
19 | DN | DN Heavy Water Management System Computer Distributed Control Units Replacement | 83288 | Sustaining | Upgrade and/or replace the Distributed Control Units required for the monitoring and control of TRF, Upgrader and Heavy Water Management Building systems. | No | 2018-01-01 | 2027-09-01 | 16.5449 | 11.867 | 0 | 0 | 11.488 | 0.379 | 0 | 0 | 0 | Jan-18 | 2018-01-01 | Sep-27 | 2027-09-01 | Aug | 8
20 | DN | DN Irradiated Fuel Bay Cooling and Purification Pump Replacement | 83483 | Sustaining | Replace the pumps used to circulate Irradiated Fuel Bay water through the cooling circuits and thereby remove the decay heat generated by the irradiated fuel. | No | 2017-12-01 | 2029-01-01 | 29 | 18.791 | 2.6281 | 0.919 | 5.148 | 9.903 | 3.74 | 0 | 0 | Dec-17 | 2017-12-01 | Nov-28 | 2028-11-01 | Sep | 9
21 | DN | DN Fuel Handling Service Area Bridge F5 Ball Screw Assembly Replacement | 83558 | Sustaining | Replacement of F5 SAB ballscrews in the EFFAA. | No | 2018-03-01 | 2024-11-01 | 16.6924 | 0 | 0.511 | 0 | 0 | 0 | 0 | 0 | 0 | Mar-18 | 2018-03-01 | Nov-24 | 2024-11-01 | Oct | 10
22 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 83560 | Sustaining | Replace the air conditioning units used to provide cooling for the environment in the control room and equipment rooms. | No | 2018-05-01 | 2025-12-01 | 12.6906 | 0 | 2.3 | 1.139 | 0 | 0 | 0 | 0 | 0 | May-18 | 2018-05-01 | Aug-25 | 2025-08-01 | Nov | 11
23 | DN | Fleet Monitoring Initiative (Monitoring & Diagnostic Centre) | 83828 | Sustaining | Installation of sensors on station equipment, leveraging the existing network infrastructure, to provide diagnostic data to the Monitoring & Diagnostic Centre. | No | 2018-03-01 | 2026-09-01 | 29.9 | 0 | 3.4875 | 4.782 | 0 | 0 | 0 | 0 | 0 | Mar-18 | 2018-03-01 | Sep-26 | 2026-09-01 | Dec | 12
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2c
Numbers may not add due to rounding. | [16 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2c
Table 2c
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[8 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q)
ONGOING PROJECTS FROM EB-2020-0290 (Continued from Ex. D2-1-3 Table 2a)
24 | DN | DN Fuel Handling Replacement of Fuelling Machine Calibration Facility | 83916 | Sustaining | Replacement of each calibration facility (8 in the Fueling Facility Auxiliary Areas (FFAAs) and 1 in the Pressure Testing Facility (PTF)) followed by calibration and commissioning to ensure successful reliability and maintainability of the system. | No | 2019-02-01 | 2027-11-01 | 18.7648 | 6.77 | 4.141 | 3.554 | 4.578 | 2.192 | 0 | 0 | 0
25 | DN | DN Shutdown System 1 and Reactor Regulating System Ion Chamber Replacements | 83937 | Sustaining | Replace the aging Shutdown System 1 and Reactor Regulating System ion chambers that measure neutron flux in the reactor for trip parameter and reactor regulation purposes. | No | 2018-12-01 | 2033-07-01 | 11.336 | 4.388 | 0 | 1.37 | 0.673 | 0.91 | 0.7 | 1.16 | 0.945
26 | DN | DN Fuelling Machine Duct & Central Service Area Air Conditioning Unit Replacement | 84006 | Sustaining | Replace aging and degraded fan motors and cooling coils for the Fuelling Machine Duct and Central Service Area Air Conditioning Units (ACUs) to ensure reliable operation. | No | 2019-08-01 | 2029-07-01 | 25.1 | 19.382 | 0 | 0 | 4.466 | 7.59 | 7.326 | 0 | 0
27 | DN | DN Air Operated Valve Replacements | 84009 | Sustaining | Design, procure, install, commission, AFS and close-out 15 critical Air Operated Valve replacements (one of each equipment tag), and to complete the design for the 3 remaining units such that the station can procure and install them. | No | 2020-03-01 | 2025-12-01 | 18.9512 | 0 | 8.1637 | 1.864 | 0 | 0 | 0 | 0 | 0
28 | AIM | PN Circumferential Wet Scrape Tool Enhancements | 84140 | Sustaining | Implement Circumferential Wet Scrape Tool (CWEST) enhancements, to address high priority areas for improvement and address CWEST Project #66600 open issues. | No | 2019-11-01 | 2023-12-01 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | DN | DN Radiation Detection Equipment Obsolescence - Moderator Cover Gas Monitors & Fixed Area Alarming Gamma Monitors | 84399 | Sustaining | Replace both systems with new and modern equipment, since the existing equipment is obsolete and approaching the end of their useful design life. | No | 2019-11-01 | 2025-05-01 | 19.2856 | 0 | 4.0131 | 0.32 | 0 | 0 | 0 | 0 | 0
30 | DN | DN Radiation Detection Obsolescence- Active Liquid Waste and Liquid Effluent Monitor | 84400 | Sustaining | Replace the Active Liquid Waste (ALW) and Liquid Effluent Monitor (LEM) systems with new and modern equipment, since the existing equipment is obsolete and approaching the end of their useful design life. | No | 2019-11-01 | 2026-04-01 | 19.2084 | 0.176 | 0 | 13 | 0.176 | 0 | 0 | 0 | 0
31 | DN | DN Primary Heat Transport Pump Rotor Inspection and Replacement | 84799 | Sustaining | Inspect and assess condition of one PHT pump rotor components in each unit across the station, and replace the PHT pump components as required to maintain nuclear safety, and ensure long term reliability of Darlington. | No | 2020-05-01 | 2024-07-01 | 28.3722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | DN | DN Main Power Output Transformer Fire Containment System Upgrade | 86055 | Sustaining | Install upgraded Darlington Main Power Output Transformers Fire Containment System to improve deluge functionality and comply with Fire Codes. | No | 2020-07-01 | 2026-09-01 | 29.8634 | 1.63 | 9.286 | 2.334 | 1.63 | 0 | 0 | 0 | 0
| (b): Subtotal; (i): 664.3416; (j): 96.9473 | 69.6663 | 75.068 | 44.8089 | 32.1585 | 17.251 | 1.616 | 1.113
Table continues on Ex. D2-1-3 Table 2d
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2d
Numbers may not add due to rounding. | [16 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2d
Table 2d
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[8 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q)
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
33 | DN | DN Pressurizer Heaters and Controllers Replacement | 31422 | Sustaining | Replace electrical heaters in pressurizers that are at the end of their expected life. | No | 2011-04-01 | 2022-10-01 | 12.1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | DN | DN Fuel Handling Inverter Replacement | 31426 | Sustaining | Replacement of all 14 Fuel Handling Inverters in order to gain efficiencies from new technologies, ensure a continued supply of spares, increase equipment reliability and reduce the demands on maintenance resources. | No | 2011-11-01 | 2022-03-01 | 25.1315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | DN | DN Station Fluorescent Lighting Fixtures Retrofit | 31516 | Sustaining | Replace obsolete fluorescent lighting in powerhouse with new efficient LED lights. | No | 2012-12-01 | 2023-11-01 | 20.1652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | DN | DN Restore Emergency Service Water and Firewater Margins | 31518 | Regulatory | Restore Emergency Service Water (ESW) system margin following a Main Steam Line Break (MSLB) or a Beyond Design Basis Accident (BDBA). | No | 2012-12-01 | 2021-01-01 | 22.1833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | DN | DN Tritium Removal Facility Deuterium Make-up System Electrolyzer Replacement | 31522 | Sustaining | Replace aged and obsolete TRF DMS Electrolyzer, to ensure reliability to the end of facility operation. | No | 2012-11-01 | 2021-11-01 | 13.9382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | DN | DN Transformer Multi-Gas Analyzer Installation | 31542 | Sustaining | Install continuous multi-gas analyzers on the large transformers to detect incipient failure of winding insulation | No | 2012-10-01 | 2020-09-01 | 22.4604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | DN | DN Feedwater Chemistry Control Improvements | 31548 | Sustaining | Install improved feedwater chemistry monitoring and connections for portable filtration. | No | 2013-11-01 | 2020-11-01 | 11.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | DN | DN Hydrogen Cooling Temperature Control Valve TCV20 Redesign | 33228 | Sustaining | Replace Hydrogen Cooling temperature control system butterfly valve with a new type of control valve and controller, to address the reliability of the system during seasonal lake water temperature fluctuations | No | 2012-11-01 | 2021-11-01 | 12.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | DN | DN Chiller Replacement to Reduce Chlorofluorocarbon Emissions | 33631 | Regulatory | Chiller Replacement to Reduce CFC Emissions | No | 2004-01-01 | 2021-12-01 | 24.0491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | PN | PB Emergency Power Generator and Main Output Power Protective Relay Replace | 40691 | Sustaining | Replace obsolete Emergency Power Generator protective relays with new digital relays to improve availability | No | 2012-02-01 | 2021-03-01 | 25.6822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | PN | PA Standby Generator Reliability Upgrades | 40972 | Sustaining | Improve reliability and availability of the unit 012/034 Standby Generators (SG) by addressing obsolescence, lack of spare parts, maintenance and performance issues. | No | 2012-04-01 | 2024-12-01 | 19.6613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | PN | PN Obsolete Online Chemistry Analyzer Replacement | 40985 | Sustaining | Replace obsolete online chemistry analyzers. | No | 2013-03-01 | 2021-07-01 | 16.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | DN | DN Feeder Scanner Replacement | 80070 | Sustaining | Replace permanent feeder scanner equipment with portable system that can be setup outside of containment prior to use. | No | 2014-05-01 | 2025-02-01 | 15.1128 | 0 | 0.20692 | 0 | 0 | 0 | 0 | 0 | 0
46 | DN | DN Fire Hazard Assessment and Fire Safe Shutdown Analysis Modifications | 80151 | Regulatory | Implement modifications required for compliance to Canadian Standards Association N293-07 Fire Protection for Nuclear Power Plants identified in the updated Fire Hazard Assessment and Fire Safe Shutdown Analysis prepared during the Integrated Safety Review and committed in the Integrated Implementation Plan. | No | 2015-11-01 | 2022-10-01 | 17.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | DN | DN Vault Cooling Coil Replacement | 82816 | Regulatory | Replacement of the reactor vault cooling coils in all units as they are nearing end of life and developing leaks | No | n/a | 2020-10-01 | 16.2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table continues on Ex. D2-1-3 Table 2e
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2e
Numbers may not add due to rounding. | [25 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2e
Table 2e
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[8 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (d) | (e) | (f) | (g) | (j) | (k) | (l) | (m) | (n) | (k) | (l) | (m) | (n) | (o) | (p) | (q)
COMPLETED/CANCELLED PROJECTS FROM EB-2020-0290
48 | DN | DN Main Power Output and Class IV Transformer Control Cabinet Wiring Replacement | 82890 | Sustaining | Replace the Transformer Control Cabinets on the Station Service Transformer (SST) and the 10MVA transformer (junction box). | No | 2019-01-01 | Deferred | 26.8 | 11.7036 | 0.8 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 5.6035 | 6.1
49 | PN | PN P58 Buried Blowdown Piping Replacement | 83072 | Sustaining | The Buried Boiler Blowdown (BBD) carbon steel piping at Pickering Nuclear Generating Station (PNGS) requires replacement due to known degradation detected during inspections. The desired outcome is to maintain unit operation and address potential steam safety hazards. | No | 2016-11-01 | 2021-09-01 | 21.3103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | PN | PN U14 Low Pressure Feedheater Heat Exchanger Replacement | 83088 | Sustaining | Pickering Units 1 and 4 Low Pressure Feedwater Heat Exchanger tube bundles Replacement | No | 2016-05-01 | 2021-02-01 | 22.007 | 0 | 3.7 | 2.6 | 0.2 | 0 | -0.053864 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | DN | DN Condenser Steam Discharge Valve Control System Replacement | 83299 | Sustaining | Replace Condenser Steam Discharge Valves (CSDVs) actuators, including the actuator body and the auxiliaries and local instrumentation. | No | 2019-01-01 | Cancelled | 11.5099 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | DN | DN Turbine Hall Crane Controls Upgrade | 83556 | Sustaining | Upgrade the controls systems on the two Turbine Hall Cranes, which are currently obsolete and approaching end of life. | No | 2017-12-01 | 2020-04-01 | 24.2299 | 0 | 1.1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | DN | DN Irradiated Fuel Bay Permanent Fuel Inspection Equipment | 83559 | Regulatory | Installation of permanent fuel inspection equipment in the East Irradiated Fuel Bay and replacement of outdated equipment in the West Irradiated Fuel Bay. | No | 2018-03-01 | 2023-05-01 | 23.9047 | 0 | 14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.37113 | 0 | 0 | 0 | 0 | 0 | 0
54 | PN | PN High Pressure Turbine Spindle Capital Spares | 83668 | Sustaining | Purchase High Pressure Turbine Spindle spares to minimize operating risk to Pickering. | No | 2017-11-01 | 2020-06-01 | 21.3356 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | AIM | Steam Generator Manipulator & Automated Tube Plug | 84888 | Sustaining | Procure manipulators and automated tube plugging equipment, to address all obsolescence issues, reduce outage delays, improve productivity and allow for future equipment advancements. | No | 2020-03-01 | Deferred | 12.5 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotal | [6 empty] | 438.6683 | 11.7036 | 30.1 | 21.1 | 3.6 | 0 | -0.25383 | 0 | 0 | 0 | 0 | 0.57805 | 0 | 0 | 0 | 0 | 5.6035 | 6.1
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2f
Numbers may not add due to rounding. | [16 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2f
Table 2f
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[8 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | CRVA | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Eligible4 | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q)
PROJECTS NOT IN EB-2020-0290
56 | DN | DN Frazil Ice and Discharge Gate Replacement | 31554 | Sustaining | Replace both the Frazil Ice and Discharge Gates to continue to operate as originally intended. | No | 2024-08-01 | 2027-08-01 | 27.0141 | 20.532 | 0 | 0 | 19.462 | 1.07 | 0 | 0 | 0
57 | DN | DN Glycol Chiller Single Point Vulnerability Removal | 80152 | Sustaining | Remove Unit 01234 Chilled Glycol System SPVs. Currently installed pressure reduction equipment is prone to fouling and does not allow for proper control of chiller cooling at all chillers loads and intake water conditions. | No | 2024-06-01 | 2027-06-01 | 17.7959 | 7.069 | 0 | 0 | 6.331 | 0.738 | 0 | 0 | 0
58 | DN | DN Lake Current Monitoring System Replacement | 83289 | Sustaining | Replacement of the Darlington LCMS based on system needs and ensure sufficient spares to operate until Darlington end of life. | No | 2021-12-01 | 2026-06-01 | 10.9961 | 0.217 | 0 | 7.423 | 0.217 | 0 | 0 | 0 | 0
59 | DN | DN Turbine Lubricating Oil Cooler Replacement | 83300 | Sustaining | Replace the lube oil cooler tube bundles for all Units at DNGS. For U3, like-for-like tube bundles and for future units alternate material tube bundles. | No | 2025-03-01 | 2029-05-01 | 29.1 | 14.128 | 0 | 4.899 | 4.899 | 4.899 | 4.167 | 0.163 | 0
60 | DN | DN Emergency Service Water & Low Pressure Service Water Expansion Joints Replacement | 83665 | Sustaining | Replacement of expansion joints in the Darlington Emergency Service Water (ESW) and Low Pressure Service Water (LPSW) systems and procurement of lifetime spares. | No | 2021-07-01 | 2028-08-01 | 13.9 | 10.538 | 0 | 0 | 6.163 | 4.375 | 0 | 0 | 0
61 | DN | DN Tritium Removal Facility/ Heavy Water Management Interim Lifecycle Plan Implementation | 83669 | Sustaining | Replace the ITCAS oven, vacuum pumping and controls used to activate ITCs in the TRF and Increase the ITC vault storage capacity to meet the operational requirements of the TRF by providing more ITC Storage spaces. | No | 2021-01-01 | 2026-05-01 | 29.8886 | 0 | 18.108 | 10.044 | 0 | 0 | 0 | 0 | 0
62 | DN | DN Active Liquid Waste Tank Liner Replacement | 83918 | Sustaining | Replace 11 Active Liquid Waste Tank Liners at Darlington as they have reached the end of their life with new liners. | No | 2025-04-01 | 2029-05-01 | 16.9694 | 11.226 | 0 | 0 | 7.569 | 2.719 | 0.915 | 0.023 | 0
63 | DN | DN Condenser Water Box Isolation From Discharge Duct | 84134 | Sustaining | Development of tooling to provide independent isolation of a Condenser Water Box outlet isolation valve, condenser water box and/or condenser water box ball cleaning screen/collector(s) from the Condenser Cooling Water Discharge duct. | No | 2020-10-01 | Aug-24 (Complete) | 14.7605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | DN | DN Vault Vapour Recovery System Component Replacement | 84138 | Sustaining | Install an additional exhaust dryer and supporting equipment in Unit 2 of the Vault Vapour Recovery System (VVRS) to add necessary redundancy, in particular during refurbishment outages. | No | 2021-02-01 | 2025-03-25 | 21.7567 | 0 | 1.5059 | 0 | 0 | 0 | 0 | 0 | 0
65 | DN | DN Inactive Drainage Sump Pump Replacement | 84300 | Sustaining | Replacement of 23 Sumps across all 4 units in Darlington station. The replacement for each sump includes 2 pumps, 2 frames, 4 valves, and all associated piping. | No | 2024-12-01 | 2029-08-01 | 19.2422 | 9.442 | 1.563 | 5.4 | 5.377 | 3.9 | 0.165 | 0 | 0
66 | DN | DN Low Pressure Service Water Heat Exchanger Coil Replacement | 84301 | Sustaining | Replace the coils of thirty-four (34) Low Pressure Service Water (LPSW) Heat Exchangers (HXs) which are facing degradation, aging management, and performance issues. | No | 2022-05-01 | 2028-02-01 | 11.7911 | 5.235 | 1.3268 | 2.873 | 2.603 | 2.632 | 0 | 0 | 0
67 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 84308 | Sustaining | This project scope is for the replacement of two traveling screens and their auxiliary equipment, which have far surpassed the manufacturer’s recommended service life and have become difficult to maintain. | No | 2024-12-01 | 2027-01-01 | 14.8856 | 11.423 | 0 | 0 | 11.423 | 0 | 0 | 0 | 0
68 | DN | DN Emergency Service Water Travelling Screen, Motor and Bubbler Replacement | 84312 | Sustaining | Replacement of two Emergency Service Water (ESW) strainers and their auxiliary equipment, which have far surpassed the manufacturer’s recommended service life and have become difficult to maintain. | No | 2025-04-01 | 2028-03-01 | 10.1924 | 7.291 | 0 | 1 | 3.525 | 3.766 | 0 | 0 | 0
Table continues on Ex. D2-1-3 Table 2g
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 2g
Numbers may not add due to rounding. | [16 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 2g
Table 2g
Capital Project Listing - OPG Nuclear Facilities Projects
Projects $10M - $30M Total Project Cost (Allocated)1
Total
[6 empty] | CRVA |  | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Eligible4 | Start | In-Service | Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description |  | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q)
PROJECTS NOT IN EB-2020-0290
69 | AIM | AIM Advanced Non-Destructive Examination MK3 Inspection Tool | 86043 | Sustaining | Next generation fuel channel non-destructive examination (NDE) inspection tooling system component design, build, and deployment. Tooling to support full compliance for OPGN facility license condition for inspection requirements per CSA N285.4-19. | No | 2023-08-01 | 2027-12-01 | 19.0092 | 16.085 | 0 | 0 | 13.692 | 2.393 | 0 | 0 | 0
70 | DN | DN Steam Generator Waterlancing Optimization | 86086 | Sustaining | Optimization of Darlington SG Waterlancing system to reduce project critical path by building the capability to Waterlance 2 SGs in parallel, instead of 1 SG at a time. | No | 2022-08-01 | 2026-01-01 | 12.9299 | 0 | 1.293 | 7.954 | 0 | 0 | 0 | 0 | 0
71 | DN | DN Fuelling Machine Head Gap Air Sensing Package | 86302 | Sustaining | Replace obsolete Gap Air Sensing Package fluidic modules to resolve station obsolescence issue | No | 2021-03-01 | 2029-12-01 | 14.8804 | 6.048 | 0 | 1.803 | 3.563 | 1.248 | 1.128 | 0.109 | 0
72 | AIM | AIM Connectorized Umbilical Cable | 86520 | Sustaining | Rapid Delivery Machine (RDM) Connectorized Umbilical (CU) cable for commissioning and production use | No | 2024-06-01 | 2028-09-01 | 11.9518 | 8.235 | 0 | 0 | 3.806 | 4.429 | 0 | 0 | 0
73 | DN | DN Fuelling Machine Trolley Air Compressor Replacement | 86553 | Sustaining | Replacement of each Trolley Compressor Assembly for successful reliability and maintainability | No | 2024-03-01 | 2027-09-01 | 17.1379 | 10.102 | 0 | 0 | 9.994 | 0.108 | 0 | 0 | 0
74 | PN | PN Irradiated Fuel Bay Heat Exchanger Replacement | 86831 | Sustaining | Replace four heat exchangers in the Irradiated Fuel Bay as part of strategy to return to full designed cooling capacity of the system. | No | 2022-06-01 | Dec-23 (Complete) | 12.1286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | DN | DN Electrical Signature Analysis Monitoring 13.2KV And 4KV Motors | 87342 | Value Enhancing | Installation of Electrical Signature Analysis (ESA) Monitoring systems on 17 supply buses for DNGS 13.2kV and 4kV Motors. | No | 2024-05-01 | 2030-05-01 | 13.7175 | 7.301 | 0 | 1.495 | 2 | 2 | 2 | 1.301 | 0
76 | DN | DN Sensor Development | 87698 | Sustaining | Design and prototype wireless sensors to support expansion of the wireless sensor platform for equipment reliability improvement, condition-based monitoring, rounds and routines optimization and support enterprise operations excellence plan targets. | No | 2024-04-01 | 2026-06-01 | 13.4269 | 0 | 5.9129 | 7.203 | 0 | 0 | 0 | 0 | 0
77 | DN | DN Main Control Room and Simulators Renovation | 87806 | Value Enhancing | Renovation of the Darlington Main Control Room non-systems scope, including furniture, flooring, ceiling tiles, and lighting. The Darlington Simulators at both the DLC and PLC are also in scope. | No | 2024-12-01 | 2030-06-01 | 16.4868 | 12.807 | 0 | 0 | 2 | 3 | 3 | 4.807 | 0
78 | PN | PN Emergency Response Team Garage | 87809 | Sustaining | Build a new ERT Fire Hall Garage PNGS to comply with the CSA N293 (2012) standard for fire protection in nuclear power plants. This includes having an industrial fire brigade with sufficient personnel and equipment, and performing effective intervention within 15 minutes of a fire incident | No | 2024-05-01 | 2025-06-01 | 17.5845 | 0 | 9.711 | 0 | 0 | 0 | 0 | 0 | 0
79 | PN | PN Polychlorinated Biphenyl Lighting 5-8 | 87845 | Regulatory | Replacement and disposal of station equipment, such as lighting, capacitors, and bushings, that contain Polychlorinated Biphenyl (PCBs) greater than 50 ppm to disposition an environmental regulatory requirement. | No | 2023-12-01 | 2025-12-01 | 25 | 0 | 7.436 | 0 | 0 | 0 | 0 | 0 | 0
80 | DN | DN Turbine Protection Reliability Improvement | 87920 | Sustaining | Alter the Turbine Generator trip parameters from an Automatic trip to an alarm and manual trip. | No | 2023-12-01 | 2027-08-01 | 19.3065 | 1.822 | 1.674 | 2.619 | 1.822 | 0 | 0 | 0 | 0
81 | DN | Darlington Site Shoreline Protection | 87998 | Sustaining | Address the impacts of bluff erosion located southeast of the DNGS site to ensure compliance with Central Lake Ontario Conservation Authority (CLOCA) permit. | No | 2025-03-01 | 2026-08-01 | 12.8335 | 0 | 0 | 9.949 | 0 | 0 | 0 | 0 | 0
82 | DN | DN Generator Rotor Refurbishment | 89305 | Sustaining | Shipment, inspection and refurbishment of the current D7 Spare generator rotor to make it a viable station spare. | No | 2025-03-01 | 2029-08-01 | 25.4 | 18.259 | 0 | 0 | 0 | 0 | 18.259 | 0 | 0
83 | DN | DN Atmospheric Steam Discharge Valve Silencers Replacement | 89591 | Sustaining | Replace all degraded Atmospheric Steam Discharge Valve (ASDV) silencers, associated orifice plates with new models, and install permanent debris deflectors over the ASDVs on all units to protect plant personnel from potential debris ejection in the future. | No | 2025-03-01 | 2025-08-27 | 12.674 | 6.098 | 1.4 | 3.1 | 6.098 | 0 | 0 | 0 | 0
84 | PN | PN Class 1 & 2 Battery Bank Replacement | 89865 | Sustaining | P058 Class I/II battery banks like-for-like replacement during P2561 and Pickering Refurbishment. | No | 2025-05-01 | 2033-06-01 | 29.7574 | 18.4 | 0 | 2.5 | 7 | 4.4 | 7 | 0 | 0
| (b): Subtotal; (i): 512.5173; (j): 202.258 | 49.9306 | 68.262 | 117.544 | 41.677 | 36.634 | 6.403 | 0
| (b): Total; (i): 1615.5273; (j): 310.9089 | 120.175 | 143.33 | 162.3529 | 73.8355 | 53.885 | 13.6225 | 7.213
DIVISION TOTALS:
| (b): Darlington NGS; (j): 268.1889 | 101.715 | 140.83 | 137.8549 | 62.6135 | 46.885 | 13.6225 | 7.213
| (b): Pickering NGS; (j): 18.4 | 17.147 | 2.5 | 7 | 4.4 | 7 | 0 | 0
| (b): Operations and Project Support; (j): 24.32 | 1.313 | 0 | 17.498 | 6.822 | 0 | 0 | 0
| (b): Total; (j): 310.9089 | 120.175 | 143.33 | 162.3529 | 73.8355 | 53.885 | 13.6225 | 7.213
Notes:
1 | (a): Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | (a): Total Project Cost reflects BCS amounts at the time of preparing the 2025-2031 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown).
BCS amounts include minor removal costs and reflect point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost.
3 | (a): Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
4 | (a): "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 3
Numbers may not add due to rounding. | [11 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 3
Table 3
Capital Project Listing - OPG Nuclear Facilities Projects (Allocated)
Projects < $10M Total Project Cost1
|  |  | Total | Average | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | Number of | Project | Cost of All | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Sponsoring Division | Projects | Cost ($M) | Projects ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
1 | Darlington NGS | 92 | 305.2453 | 3.3179 | 35.075 | 17.9586 | 23.3179 | 15.3011 | 11.4212 | 5.1173 | 2.4633 | 0.77213
2 | Pickering NGS | 52 | 101.2729 | 1.9476 | 1.2995 | 0 | 3.62 | 0 | 0 | 0 | 0.69972 | 0.59976
3 | Operations and Project Support2 | 22 | 79.2424 | 3.6019 | 6.425 | 2.679 | 8.046 | 0.11 | 0 | 0 | 0 | 6.315
4 | Total | 166 | 485.7606 | 2.9263 | 42.7995 | 20.6376 | 34.9839 | 15.4111 | 11.4212 | 5.1173 | 3.163 | 7.6869
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.
2 | Operations and Project Support with capital projects includes Engineering, Advanced Inspection Maintenance Services, and Security & Emergency Services.

## D2-1-3_Table 4a
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 4a
Table 4a
Comparison of In-Service Capital Additions - Nuclear Operations ($M)
Line |  | 2020 | (c)-(a) | 2020 | 2021 | (f)-(d) | 2021 | 2022 | (i)-(g) | 2022 | 2023 | (l)-(j) | 2023
No. | Business Unit | OEB Approved1 | Change | Actual | OEB Approved | Change | Actual | OEB Approved | Change | Actual | OEB Approved | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
OPG Nuclear Facilities Portfolio Projects (Allocated)
1 | Darlington NGS | 101.271 | 84.5792 | 185.8502 | 61.442 | 161.3703 | 222.8123 | 409.748 | -148.8647 | 260.8833 | 317.555 | -5.3518 | 312.2032
2 | Pickering NGS | 0 | 35.6527 | 35.6527 | 0 | 15.7131 | 15.7131 | 0 | 17.1029 | 17.1029 | 0 | 8.9743 | 8.9743
3 | Operations and Project Support1 | 29.74 | -16.9118 | 12.8282 | 0.627 | 49.9918 | 50.6188 | 13.386 | 14.3049 | 27.6909 | 93.787 | -74.8407 | 18.9463
4 | Subtotal Portfolio Projects (Allocated) | 131.011 | 103.3201 | 234.3311 | 62.069 | 227.0752 | 289.1442 | 423.134 | -117.4569 | 305.6771 | 411.342 | -71.2182 | 340.1238
OPG Nuclear Facilities Portfolio Projects (Unallocated)
5 | Darlington NGS | 45.072 | -45.072 | 0 | 72.856 | -72.856 | 0 | -8.476 | 8.476 | 0 | 27.997 | -27.997 | 0
6 | Pickering NGS | 33.765 | -33.765 | 0 | 27.375 | -27.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Operations and Project Support1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.192 | -1.192 | 0
8 | Subtotal OPG Nuclear Facilities Portfolio Projects (Supplemental In-Service Forecast)2 | 78.837 | -78.837 | 0 | 100.231 | -100.231 | 0 | -8.476 | 8.476 | 0 | 29.189 | -29.189 | 0
9 | Total OPG Nuclear Facilities Portfolio In-Service Forecast | 209.848 | 24.4831 | 234.3311 | 162.3 | 126.8442 | 289.1442 | 414.658 | -108.9809 | 305.6771 | 440.531 | -100.4072 | 340.1238
10 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Darlington Unit 2 Turbine Control and Auxiliary Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Tritium Removal Facility Major Component Replacements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Darlington Steam Generator Primary Moisture Separators Replacement Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.2332 | 82.2332
14 | Pickering Extended Operations | 0 | 24.4186 | 24.4186 | 0 | 23.9177 | 23.9177 | 0 | 0.72279 | 0.72279 | 0 | 0.64524 | 0.64524
15 | Darlington Non-Routine Steam Generator Cleanings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Darlington Unit 1 and 2 Generator Stator Rewind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Darlington Turbine Rotors Replacement5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Pickering Water Treatment Plant Lease4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Darlington Refurbishment New Fuel | 15.345 | 1.7098 | 17.0548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.85 | 15.85
20 | Pickering Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Minor Fixed Assets | 19.5 | -1.6364 | 17.8636 | 19.3 | 0.47805 | 19.7781 | 19.6154 | -5.5975 | 14.0179 | 21.04 | 3.1731 | 24.2131
22 | Nuclear Operations Total In-Service Capital Additions Before Adjustments | 244.693 | 48.9751 | 293.6681 | 181.6 | 151.24 | 332.84 | 434.2734 | -113.8556 | 320.4178 | 461.571 | 1.4944 | 463.0654
23 | OEB/Settlement Adjustments3 | (a): -24.47; (d): -18.162; (g): -56.5; (h): 56.5; (j): -60; (k): 60
24 | Nuclear Operations Total In-Service Capital Additions Including Adjustments | 220.223 | 73.4451 | 293.6681 | 163.538 | 169.302 | 332.84 | 377.7734 | -57.3556 | 320.4178 | 401.571 | 61.4944 | 463.0654
25 | DNNP Capitalized Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line |  | 2024 | (c)-(a) | 2024 | 2025 | (f)-(d) | 2025 | 2026 | (i)-(g) | 2026 | 2027 | (l)-(j) | 2028
No. | Business Unit | OEB Approved | Change | Actual | OEB Approved | Change | Budget | OEB Approved | Change | Budget | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
OPG Nuclear Facilities Portfolio Projects (Allocated)
26 | Darlington NGS | 291.597 | 73.1206 | 364.7176 | 272.206 | 7.0074 | 279.2134 | 168.924 | 165.3489 | 334.2729 | 479.6991 | -237.2765 | 242.4226
27 | Pickering NGS | 0 | 11.8371 | 11.8371 | 0 | 17.147 | 17.147 | 0 | 29.6086 | 29.6086 | 69.0346 | -40.8615 | 28.1731
28 | Operations and Project Support1 | 0 | 43.7322 | 43.7322 | 29.533 | -11.0237 | 18.5093 | 0 | 113.5 | 113.5 | 19.443 | -12.038 | 7.405
29 | Subtotal OPG Nuclear Facilities Portfolio Projects (Allocated) | 291.597 | 128.6898 | 420.2868 | 301.739 | 13.1307 | 314.8697 | 168.924 | 308.4575 | 477.3815 | 568.1767 | -290.176 | 278.0007
OPG Nuclear Facilities Portfolio Projects (Unallocated)
30 | Darlington NGS | 1.363 | -1.363 | 0 | 30.326 | -54.7557 | -24.4297 | 138.43 | -171.5662 | -33.1362 | 60.4646 | 33.1573 | 93.622
31 | Pickering NGS | 0 | 0 | 0 | 0 | 4.781 | 4.781 | 0 | 0 | 0 | 13.5261 | 29.9146 | 43.4407
32 | Operations and Project Support1 | 11.743 | -11.743 | 0 | 7.605 | -7.605 | 0 | 11.472 | -11.472 | 0 | 3.2983 | 2.0397 | 5.338
33 | Subtotal OPG Nuclear Facilities Portfolio Projects (Supplemental In-Service Forecast)2 | 13.106 | -13.106 | 0 | 37.931 | -57.5797 | -19.6487 | 149.902 | -183.0382 | -33.1362 | 77.2891 | 65.1116 | 142.4007
34 | Total OPG Nuclear Facilities Portfolio In-Service Forecast | 304.703 | 115.5838 | 420.2868 | 339.67 | -44.449 | 295.221 | 318.826 | 125.4193 | 444.2453 | 645.4658 | -225.0644 | 396.1004
35 | Darlington Water Treatment Plant Lease | 138.6 | -70.4976 | 68.1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Darlington Unit 2 Turbine Control and Auxiliary Systems Upgrade | 0 | 0 | 0 | 102.127 | -102.127 | 0 | 0 | 0 | 0 | 0 | 177.162 | 177.162
37 | Tritium Removal Facility Major Component Replacement Program | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.5 | -52.5 | 0
38 | Darlington Steam Generator Primary Moisture Separators Replacement Projects | 0 | 87.9021 | 87.9021 | 0 | 107.977 | 107.977 | 0 | 81.809 | 81.809 | 122.1212 | -108.9366 | 13.1846
39 | Pickering Extended Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Darlington Non-Routine Steam Generator Cleanings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 14.7 | -1.916 | 12.784
42 | Darlington Unit 1 and 2 Generator Stator Rewind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159.273 | 159.273
43 | Darlington Turbine Rotors Replacement5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Pickering Water Treatment Plant Lease4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Darlington Refurbishment New Fuel | 16.458 | 0.90902 | 17.367 | 16.853 | -16.853 | 0 | 18.064 | 1.805 | 19.869 | 0 | 0 | 0
46 | Pickering Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | OPG Nuclear Facilities Minor Fixed Assets | 29.2277 | -7.0277 | 22.2 | 18.6771 | 0.34536 | 19.0225 | 11.3895 | 3.4891 | 14.8787 | 13.2178 | 3.7866 | 17.0044
48 | Nuclear Operations Total In-Service Capital Additions Before Adjustments | 488.9887 | 126.8695 | 615.8583 | 477.3271 | -55.1066 | 422.2205 | 348.2795 | 232.5224 | 580.802 | 848.0048 | -48.1954 | 799.8095
49 | OEB/Settlement Adjustments3 | -63.6 | 63.6 | 0 | -62.1 | 62.1 | 0 | -45.3 | 45.3 | 0 | 0 | 0 | 0
50 | Nuclear Operations Total In-Service Capital Additions Including Adjustments | 425.3887 | 190.4695 | 615.8583 | 415.2271 | 6.9934 | 422.2205 | 302.9795 | 277.8224 | 580.802 | 848.0048 | -48.1954 | 799.8095
51 | DNNP Capitalized Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
1 | Includes Engineering, Advanced Inspection and Maintenance, and Security & Emergency Services.
2 | Supplemental forecast to reconcile BCS in-service estimates to final business plan (see Ex. D2-1-3, Section 4.0).
3 | See EB-2020-0290, Ex. O, Tab 1, Sch. 1, Pg. 22 of 51, Table 14.
4 | Amounts associated with Pickering Water Treatment Plant Lease are unallocated.
5 | Darlington Turbine Rotors Replacement consists of two projects (87807 - replacement & 87811 - capital spare). Project 87811 is not CRVA eligible.
Waiting for 2027 - 2031 Plan Numbers
Trang is confirming with Jon Lucas.
April 28 2025

## D2-1-3_Table 4b
Numbers may not add due to rounding. | [10 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 4b
Table 4b
Comparison of In-Service Capital Additions - Nuclear Operations ($M)
Line |  | 2028 | (c)-(a) | 2029 | (e)-(c) | 2030 | (g)- (e) | 2031 | 2022-2026 Actuals & Budget | (j)-(h) | 2027-2031 Plan
No. | Business Unit | Plan | Change | Plan | Change | Plan | Change | Plan |  | Change | EB-2025-0297
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j)
OPG Nuclear Facilities Portfolio Projects (Allocated)
52 | Darlington NGS | 242.4226 | -78.5098 | 163.9128 | -71.3533 | 92.5595 | -15.8225 | 76.737 | 1551.2904 | -495.9594 | 1055.331
53 | Pickering NGS | 28.1731 | -18.1355 | 10.0376 | -9.3379 | 0.69972 | -0.09996 | 0.59976 | 84.6699 | 23.875 | 108.5448
54 | Operations and Project Support1 | 7.405 | -1.972 | 5.433 | -5.433 | 0 | 6.315 | 6.315 | 222.3786 | -183.7826 | 38.596
55 | Subtotal OPG Nuclear Facilities Portfolio Projects (Allocated) | 278.0007 | -98.6173 | 179.3834 | -86.1242 | 93.2592 | -9.6075 | 83.6517 | 1858.3389 | -655.867 | 1202.4719
OPG Nuclear Facilities Portfolio Projects (Unallocated)
56 | Darlington NGS | 93.622 | 0.005675 | 93.6276 | 67.8352 | 161.4628 | -25.0865 | 136.3763 | -57.5658 | 603.1192 | 545.5534
57 | Pickering NGS | 43.4407 | 20.3394 | 63.7801 | 134.1565 | 197.9366 | -65.5629 | 132.3737 | 4.781 | 446.2762 | 451.0572
58 | Operations and Project Support1 | 5.338 | 7.7758 | 13.1138 | 37.7792 | 50.8931 | -23.0474 | 27.8457 | 0 | 100.4888 | 100.4888
59 | Subtotal OPG Nuclear Facilities Portfolio Projects (Supplemental In-Service Forecast)2 | 142.4007 | 28.1209 | 170.5216 | 239.7709 | 410.2924 | -113.6967 | 296.5957 | -52.7848 | 1149.8842 | 1097.0994
60 | Total OPG Nuclear Facilities Portfolio In-Service Forecast | 420.4014 | -70.4964 | 349.905 | 153.6466 | 503.5516 | -123.3042 | 380.2474 | 1805.5541 | 494.0172 | 2299.5712
61 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.1024 | -68.1024 | 0
62 | Darlington Unit 2 Turbine Control and Auxiliary Systems Upgrade | 177.162 | -177.162 | 0 | 0 | 0 | 0 | 0 | 0 | 177.162 | 177.162
63 | Tritium Removal Facility Major Component Replacement Program | 0 | 0 | 0 | 105.145 | 105.145 | -105.145 | 0 | 0 | 157.645 | 157.645
64 | Darlington Steam Generator Primary Moisture Separators Replacement Projects | 13.1846 | -13.1846 | 0 | 0 | 0 | 0 | 0 | 359.9213 | -224.6155 | 135.3058
65 | Pickering Extended Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.368 | -1.368 | 0
67 | Darlington Non-Routine Steam Generator Cleanings | 12.8 | -0.616 | 12.184 | -12.184 | 0 | 0 | 0 | 20 | 19.668 | 39.668
68 | Darlington Unit 1 and 2 Generator Stator Rewind | 159.273 | -156.15 | 3.123 | 143.658 | 146.781 | -143.658 | 3.123 | 0 | 312.3 | 312.3
69 | Darlington Turbine Rotors Replacement5 | 0 | 625.0453 | 625.0453 | -91.1887 | 533.8566 | -0.047576 | 533.8091 | 0 | 1692.711 | 1692.711
70 | Pickering Water Treatment Plant Lease4 | 0 | 0 | 0 | 98.225 | 98.225 | -98.225 | 0 | 0 | 98.225 | 98.225
71 | Darlington Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.0861 | -53.0861 | 0
72 | Pickering Refurbishment New Fuel | 0 | 0 | 0 | 0 | 0 | 24.0917 | 24.0917 | 0 | 24.0917 | 24.0917
73 | OPG Nuclear Facilities Minor Fixed Assets | 17.0044 | -2.6521 | 14.3523 | 6.114 | 20.4663 | -3.1125 | 17.3538 | 94.3322 | -11.9375 | 82.3947
74 | Nuclear Operations Total In-Service Capital Additions Before Adjustments | 799.8255 | 204.7842 | 1004.6096 | 403.416 | 1408.0256 | -449.4007 | 958.6249 | 2402.364 | 2616.7104 | 5019.0745
75 | OEB/Settlement Adjustments3 | (a): 0; (f): 0; (i): 0; (j): 0
76 | Nuclear Operations Total In-Service Capital Additions Including Adjustments | 799.8255 | 204.7842 | 1004.6096 | 403.416 | 1408.0256 | -449.4007 | 958.6249 | 2402.364 | 2616.7104 | 5019.0745
77 | DNNP Capitalized Fuel | 0 | 0 | 0 | 78.1167 | 78.1167 | -53.0725 | 25.0441 | 0 | 103.1608 | 103.1608
Notes:
1 | Includes Engineering, Advanced Inspection and Maintenance, and Security & Emergency Services.
2 | Supplemental forecast to reconcile BCS in-service estimates to final business plan (see Ex. D2-1-3, Section 4.0).
3 | See EB-2020-0290, Ex. O, Tab 1, Sch. 1, Pg. 22 of 51, Table 14.
4 | Amounts associated with Pickering Water Treatment Plant Lease are unallocated.
5 | Darlington Turbine Rotor Replacement consists of two projects (87807 - replacement & 87811 - capital spare). Project 87811 is not CRVA eligible.
Waiting for 2027 - 2031 Plan Numbers
Trang is confirming with Jon Lucas.
April 28 2025

## D2-1-3_Table 5a
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 5a
Table 5a
Capital Project Listing - OPG Nuclear Facilities
Portfolio Projects (Unallocated)1
Potential
Line |  |  | CRVA | Start
No. | Project Name | Category | Eligible2 | Date
| (a) | (b) | (c) | (d)
Darlington NGS - Projects With Potential Cost >$10M and < $30M
1 | 84187 - DN Pressurizer Heaters Replacement Gasket Redesign | Sustaining | No | 2027
2 | 84299 - DN Fire Detection Panel Upgrade | Sustaining | No | 2025
3 | 84414 - DN Condenser Sampling Pumps & Analyzer | Sustaining | No | 2027
4 | 84592 - DN Low Pressure Service Water Pump Replacement | Sustaining | No | 2027
5 | 84890 - DN Condenser Cooling Water Pump Replacement | Sustaining | No | 2027
6 | 84891 - DN Main Condensate Extraction Pump Replacement | Sustaining | No | 2027
7 | 84970 - DN Ventilation & Air Conditioning Fans Replacement | Sustaining | No | 2025
8 | 86060 - DN Environmentally Qualified Cables Replacement | Sustaining | No | 2025
9 | 86323 - DN Start-Up Instrumentation | Sustaining | No | 2025
10 | 89027 - DN Vehicle Barrier System And Sally Port Upgrades | Sustaining | No | 2025
11 | 89225 - DN Emergency Acting System | Sustaining | No | 2028
12 | 89285 - DN Physical Barrier System Replacement | Sustaining | No | 2027
13 | 89299 - DN Security Access Doors | Sustaining | No | 2028
14 | 89300 - DN Containment Leak Rate Test Equipment | Sustaining | No | 2026
15 | 89301 - DN Plant Information Display System | Sustaining | No | 2028
16 | 89371 - DN Condensers Shell Modifications | Sustaining | No | 2025
17 | 89374 - DN Pipe Coating On Condenser Cooling Water | Sustaining | No | 2027
18 | 89463 - DN Generator Spare Rotor & H2 Fans | Sustaining | No | 2030
Darlington NGS - Projects With Potential Cost ≥ $30M
19 | 84309 - DN Boiler Level Control Valve Isolator Actuator Replace | Sustaining | No | 2030
20 | 87339 - DN Service Water Relief Valves | Sustaining | No | 2025
21 | 87805 - DN Retube Waste Process Building Permanent Modification | Sustaining | No | 2025
22 | 89220 - Project Design Standby Generators | Sustaining | No | 2029
23 | 89251 - DN D2O In H2O Equipment Replacement | Sustaining | No | 2025
24 | 89284 - DN Drain Valve Installation (MV4-15) Part 2 | Sustaining | No | 2025
25 | 89302 - DN Refrigeration Unit (RFU) Replacement | Value Enhancing | No | 2030
26 | 89304 - DN Class I Rectifier Replacement Phase 2 | Sustaining | No | 2025
27 | 89306 - DN 218 Cranes And Hoists | Sustaining | No | 2027
28 | 89370 - DN Condensers Tube Replacement | Sustaining | No | 2027
29 | 89372 - DN Condenser Tube Cleaning System Full Replacement | Sustaining | No | 2030
30 | 89464 - DN U1 Steam Generator Primary Side Clean | Sustaining | Yes* | 2027
31 | 89490 - Darlington Containment Vault Cranes Refurbishment | Sustaining | No | 2026
32 | 89491 - DN Fuel Handling Cranes Refurbishment | Sustaining | No | 2026
33 | 89544 - DN Condenser Cooling Water Expansion Joints Replacement | Sustaining | No | 2026
Table continues on Ex. D2-1-3 Table 5b
Notes:
1 | Projects with potential expenditures during IR term.
2 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 5b
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 5b
Table 5b
Capital Project Listing - OPG Nuclear Facilities
Portfolio Projects (Unallocated)1
Potential
Line |  |  | CRVA | Start
No. | Project Name | Category | Eligible2 | Date
| (a) | (b) | (c) | (d)
Pickering NGS - Projects With Potential Cost >$10M and < $30M
34 | 89454 - PN Physical Barrier System | Sustaining | No | 2027
35 | 89455 - PN Security Lighting Including Physical Barrier System Lighting | Sustaining | No | 2026
36 | 89691 - PN Class I & II Battery Rooms HVAC | Sustaining | No | 2031
37 | 89693 - PN Vacuum Duct Insulation Replacement | Sustaining | No | 2028
38 | 89695 - PN Isolating Valve Install Low Pressure Service Water/High Pressure Service Water Header | Sustaining | No | 2026
39 | 89697 - PN Primary Heat Transport Liquid Relief Valves Modification | Sustaining | No | 2025
40 | 89698 - PN Environmentally Qualified Temperature & Radiation Monitoring | Sustaining | No | 2025
41 | 89703 - PN Temperature Control Valve Replacement | Sustaining | No | 2025
42 | 89704 - PN Moderator Cover Gas Compressors Replacement | Sustaining | No | 2025
43 | 89718 - PN Auxiliary Boiler Feed Pump Motors ESA Installation | Sustaining | No | 2026
44 | 89730 - PN U5 Plant Computers | Sustaining | No | 2028
45 | 89735 - PN Tritium 3-Way Dampers Modification | Sustaining | No | 2026
46 | 89737 - PN Condenser Cooling Water Inlet Isolation Valve Seats Replacement | Sustaining | No | 2026
47 | 89738 - PN Service Air Compressors Replacement | Sustaining | No | 2026
48 | 89740 - PN Instrument Air Take-Off & Isolation Valves Replacement | Sustaining | No | 2025
49 | 89741 - Pickering B Bulkhead Panel Enhancements | Sustaining | No | 2027
50 | 89744 - PN Boiler Mock-Up & Inspection Robotic Arms | Sustaining | No | 2025
51 | 89747 - PN CIGAR Life Extension Upgrades | Sustaining | No | 2025
52 | 89761 - PN Moderator Heat Exchanger Isolation Valves Replacement | Sustaining | No | 2025
53 | 89763 - PN Moderator Pump Header Valves Replacement | Sustaining | No | 2025
54 | 89769 - PN Reactor Building Dome Concrete Coating | Sustaining | No | 2026
55 | 89787 - PN Class 2 Uninterruptible Power Supply Replacement | Sustaining | No | 2025
56 | 89790 - Unit 5 & 6 Buried Boiler Blowdown Abandoned Piping Replacement | Sustaining | No | 2026
57 | 89924 - PN Public Address System | Sustaining | No | 2025
58 | 89926 - PN U5 Reactor Regulating System Adjuster Rod Replacement | Sustaining | No | 2029
59 | 89936 - PN Fuel Handling Critical Component Obsolescence | Sustaining | No | 2026
60 | 90106 - PN Civil Structural Support Modification | Sustaining | No | 2027
61 | 90107 - PN Gaseous Fission Product Detection System | Sustaining | No | 2027
62 | 90108 - PN Vacuum Building Remote Monitoring Equipment | Sustaining | No | 2027
63 | 90111 - PN Sewage Piping Replacements | Sustaining | No | 2025
Table continues on Ex. D2-1-3 Table 5c
Notes:
1 | Projects with potential expenditures during IR term.
2 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.
Notes:
1 | Projects with potential expenditures during IR term

## D2-1-3_Table 5c
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 5c
Table 5c
Capital Project Listing - OPG Nuclear Facilities
Portfolio Projects (Unallocated)1
Potential
Line |  |  | CRVA | Start
No. | Project Name | Category | Eligible2 | Date
| (a) | (b) | (c) | (d)
Pickering NGS - Projects With Potential Cost ≥ $30M
64 | 89690 - PN Breathing Air Station Valves Replacement | Sustaining | No | 2025
65 | 89700 - PN Ajax Pump Replacement | Sustaining | No | 2025
66 | 89733 - PN Boiler Feed and Condensate Extraction Steam Joint Replacement | Sustaining | No | 2026
67 | 89736 - PN Fuelling Machine Modifications | Sustaining | No | 2025
68 | 89745 - PN Rapid Delivery Machine | Sustaining | No | 2026
69 | 89757 - PN Instrument Air Compressor Dryers/filters Replacement | Sustaining | No | 2025
70 | 89758 - PN U7/8 Buried Boiler Blowdown Line Replacement | Sustaining | No | 2027
71 | 89759 - PN Continuous Boiler Blowdown System Redesign | Sustaining | No | 2025
72 | 89762 - PN Standby Generators Replacement | Sustaining | No | 2025
73 | 89793 - PN New Waste Handling Buildings | Sustaining | No | 2025
74 | 89922 - PN Unit 5 Digital Control Computers Replacement | Sustaining | Yes | 2025
75 | 89927 - PN U5/7 Modify High Pressure Turbine Diagonal Stage | Sustaining | Yes | 2029
76 | 89930 - PN Vacuum Building Main Heating Supplies Relocation | Sustaining | No | 2029
77 | 89933 - PN Electrical Separation of 40 Loads | Sustaining | No | 2029
78 | 90105 - PN Pressure Relief Duct Component Replacement | Sustaining | No | 2027
Table continues on Ex. D2-1-3 Table 5d
Notes:
1 | Projects with potential expenditures during IR term.
2 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 5d
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 5d
Table 5d
Capital Project Listing - OPG Nuclear Facilities
Portfolio Projects (Unallocated)1
Potential
Line |  |  | CRVA | Start
No. | Project Name | Category | Eligible2 | Date
| (a) | (b) | (c) | (d)
Advanced Inspection & Maintenance - Projects With Potential Cost >$10M and < $30M
79 | 86175 - AIM Laser Induced Breakdown Spectroscopy Hydride Characterization Tool | Sustaining | No | 2027
80 | 89621 - Steam Generator Manipulator System | Sustaining | No | 2026
Advanced Inspection & Maintenance - Projects With Potential Cost ≥ $30M
81 | 84141 - AIM Next Generation Fuel Channel Inspection Tool | Sustaining | No | 2027
82 | 86147 - Next Generation Fuel Channel Scrape Tool | Sustaining | No | 2025
Notes:
1 | Projects with potential expenditures during IR term.
2 | "Yes" indicates identified CRVA-eligible projects with in-service amounts in the 2020-2024 period that do not also have in-service amounts in the 2025-2031 period, and therefore do not form part of the proposed 2027-2031 capital related revenue requirement for the CRVA. "Yes*" indicates identified CRVA-eligible projects with expected in-service amounts in the 2025-2031 period and forming part of the proposed 2027-2031 capital related revenue requirement for the CRVA (Ex. H1-1-1, Att. 8). Additionally, this includes a preliminary assessment of CRVA eligibility, amongst unallocated projects, without expected in-service amounts in the 2025-2031 period.

## D2-1-3_Table 6a
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 6a
Table 6a
Capital Projects - OPG Nuclear Facilities
Listing of Business Case Summaries Filed
|  |  |  | BCS |  |  | BCS
Line |  |  | Project | Approval |  | BCS | Status in
No. | Facility | Business Case Summary (BCS) Title | Number | Date | Project Stage | Status | EB-2020-0290
| (a) | (b) | (c) | (d) | (e) | (f) | (g)
ONGOING PROJECTS FROM EB-2020-0290
1 | DN | DN Class II Uninterruptable Power Supply Replacement | 31412 | Dec-21 | Execution | Full | Partial Execution
2 | DN | DN Station Roofs Replacement | 31524 | Jun-21 | Close out | Full | Superseding Definition
3 | DN | DN Powerhouse Water Air Condition Units Replacement | 31532 | May-19 | Execution | Full | Full Release Execution
4 | DN | DN Water Treatment Plant Interconnections | 31535 | Jul-23 | Execution | Superseding | Superseding Definition
5 | DN | DN Radiation Detection Equipment Obsolescence | 31544 | Sep-22 | Execution | Full | Superseding Definition
6 | DN | DN Air Conditioning Unit Replacement For Secondary Control Area | 33621 | Jun-25 | Execution | Superseding | Superseding Execution
7 | DN | DN Major Pump-Sets Vibration Monitoring System Upgrades | 33819 | Jan-22 | Execution | Full | Superseding Execution
8 | DN | DN Standby Generator Controls Replacement | 33973 | May-16 | Execution | Full | Over-Variance Execution
9 | DN | DN OH180 Aging Management Hardware Installation | 80022 | Sep-19 | Execution | Partial | Partial Execution
10 | DN | DN R22 Refrigerant Air Conditioning Unit Replacement | 80036 | Feb-24 | Execution | Full | Partial Execution
11 | DN | DN Digital Control, Common Process And Sequence Of Events Monitoring Computer Aging Management | 80078 | Oct-21 | Definition | Partial | Partial Definition
12 | DN | DN Main Power Output Protection System Replacement | 80122 | Jul-23 | Execution | Full | Superseding Definition
13 | DN | DN Group II Pressure Transmitter Replacement | 80123 | Aug-23 | Execution | Full | Full Release Definition
14 | DN | DN Obsolete Controller Replacement | 80124 | Oct-18 | Execution | Partial | Partial Execution
15 | DN | DN Emergency Power Generator 1 And 2 Replacement | 80126 | Jul-21 | Execution | Full | Superceding Execution
16 | DN | DN Fuel Handling Computer Input/ Output Subsystem Interprocessor Communication Replacement | 80148 | Mar-25 | Definition | Superseding | Partial Definition
17 | DN | DN Fire Resistant Fluid Pump Improvement | 80150 | Aug-23 | Definition | Superseding | Full Release Definition
18 | DN | DN Fuel Handling Head Major Component Replacement | 82947 | Nov-23 | Execution | Full | Partial Definition
19 | IRI | DN Rapid Delivery Machine | 83039 | Jun-24 | Execution | Superseding | Superseding Definition
20 | DN | DN Main Output Transformer & Unit Service Transformer Replacement | 83296 | Apr-19 | Execution | Full | Partial Execution
21 | DN | DN Large Moderator Temperature Control Valve Replacement | 83297 | Jan-23 | Execution | Full | Full Release Definition
22 | DN | DN Secondary System Obsolete Control Valve Replacement | 83298 | Mar-24 | Execution | Full | Full Release Definition
23 | DN | DN 4KV Motor Refurbishment And Replacement | 83480 | Aug-25 | Execution | Partial | Full Release Definition
24 | DN | DN Isolated Phase Bus Refurbishment | 83484 | Jun-23 | Execution | Partial | Full Release Development
25 | DN | DN Powerhouse Upper Level Service Water Piping Replacement | 83530 | May-22 | Execution | Full | Partial Execution
26 | DN | DN Unit 2 Turbine Control and Auxiliary Systems Upgrade | 83664 | Jun-25 | Execution | Full | Full Release Definition
27 | DN | DN Primary Heat Transport Liquid Relief Valve Modifications (Waterhammer) | 84235 | Mar-21 | Execution | Full | Partial Execution
28 | DN | DN Motor Operated Valve Replacements | 84551 | Nov-23 | Execution | Full | Full Release Development
29 | DN | DN Revenue Metering Transformer Replacement | 84939 | Aug-24 | Execution | Full | Full Release Development

## D2-1-3_Table 6b
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 6b
Table 6b
Capital Projects - OPG Nuclear Facilities
Listing of Business Case Summaries Filed
|  |  |  | BCS |  |  | BCS
Line |  |  | Project | Approval |  | BCS | Status in
No. | Facility | Business Case Summary (BCS) Title | Number | Date | Project Stage | Status | EB-2020-0290
| (a) | (b) | (c) | (d) | (e) | (f) | (g)
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
30 | DN | DN Shutdown Cooling Heat Exchanger Replacement | 31710 | Feb-18 | Complete | Full | Full Release Close-out
31 | DN | DN Auxiliary Heating System | 34000 | Jul-15 | Complete | Full | Over-Variance Close-out
32 | DN | DN Zebra Mussels Mitigation & Improvements | 38948 | Mar-18 | Complete | Superseding | Superseding Close-out
33 | DN | DN RS Primary Heat Transport Pump Motor Replacement & Overhaul | 73566 80144 | Jul-17 | Complete | Full | Full Release Execution
34 | DN | DN Steam Generator Level Control Valve Replacement | 80023 | Nov-19 | Cancelled | Superseding | Superseding Definition
35 | DN | DN Primary Heat Transport Pump Motor Overhaul | 83049 | Aug-19 | Complete | Superseding | Superseding Execution
PROJECTS NOT IN EB-2020-0290
36 | DN | DN Public Address System Upgrade | 31708 | Dec-24 | Definition | Full
37 | DN | DN Breathing, Instrument and Service Air Compressor Replacement | 83933 | Jul-25 | Definition | Partial
38 | DN | DN Powerhouse Elevator Replacement | 84135 | Sep-23 | Definition | Full
39 | DN | DN Powerhouse Cranes Refurbishment | 84139 | Nov-22 | Development | Full
40 | DN | DN Vacuum Building Outage Power Operated Valves Replacement | 84552 | Nov-24 | Definition | Partial
41 | DN | Tritium Removal Facility Major Component Replacement Program | 84764 | Feb-25 | Definition | Partial
42 | DN | DN Low Pressure Service Water Strainer Backwash Motorized Valves Replacement | 86280 | Jun-25 | Definition | Partial
43 | DN | Darlington Steam Generator Moisture Separator Replacement | 86693 | Mar-23 | Execution | Full
44 | DN | DN Motor Operated Valve Replacement Innage | 86795 | Dec-24 | Definition | Full
45 | DN | DN Lighting Fixtures Light Emitting Diode Replacement | 86910 | Apr-23 | Execution | Partial
46 | DN | DN Copper Upgrades Phase III | 86915 | Dec-24 | Definition | Full
47 | DN | DN Unit 2 and 3 Steam Generator Moisture Separator Replacement | 87151 | Jun-25 | Execution | Full
48 | DN | DN Tritium Removal Facility Cryogenic Refrigeration System Turbine Replacement | 87191 | 45953 | Definition | Superseding
49 | DN | DN Turbine Rotors Replacements & Capital Spare1 | 87807 87811 | Aug-25 | Definition | Full
50 | DN | DN Smartops Sensor Integration | 87808 | May-25 | Definition | Partial
51 | DN | DN Unit 1 and 2 Generator Stator Rewind | 89281 | Aug-25 | Definition | Full
52 | DN | DN Steam Generator Soft Chemical Clean | 89462 | Mar-25 | Definition | Full
53 | PN | PN 058 Boiler Room and Turbine Hall Crane Upgrade | 89535 | Jan-25 | Execution | Full
54 | PN | PN 058 Turbine Auxiliary Building, Reactor Auxiliary Building Hoist & Cranes | 89536 | Mar-25 | Definition | Full
55 | PN | P58 Second Simulator and Pickering Learning Centre Extension | 89581 | May-25 | Development | Full
1 | Darlington Turbine Rotor Replacement consists of two projects (87807 - replacement & 87811 - capital spare). Project 87811 is not CRVA eligible.

## D2-1-3_Table 7a
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 7a
Table 7a
Capital Projects - OPG Nuclear Facilities
Status of Projects > $10M with 2020 to 2026 Final In-Service Dates in EB-2020-0290
|  |  | In-Service Date | Project Stage
|  |  | at Time of | at Time of | Current Project Status
Line | Project |  | EB-2020-0290 | EB-2020-0290 | Project | Projected/Actual
No. | Number | Project Name | Application | Application | Status | In-Service Date
| (a) | (b) | (c) | (d) | (e) | (f)
1 | 31403 | DN Active Liquid Waste System Upgrade | Dec-22 | Execution | Execution | 2025-05-26
2 | 31412 | DN Class II Uninterruptable Power Supply Replacement | Mar-25 | Execution | Execution | Feb-27
3 | 31420 | DN Dryer Programmable Logic Controller Replacement | Aug-24 | Execution | Execution | 2025-06-26
4 | 31422 | DN Pressurizer Heaters and Controllers Replacement | Dec-21 | Execution | Complete | Oct-22
5 | 31426 | DN Fuel Handling Inverter Replacement | Apr-21 | Execution | Complete | Mar-22
6 | 31516 | DN Station Fluorescent Lighting Fixtures Retrofit | Jan-23 | Execution | Complete | Nov-23
7 | 31518 | DN Restore Emergency Service Water and Firewater Margins | Aug-19 | Close-out | Complete | Jan-21
8 | 31520 | DN Replacement Of Obsolete Online Chemistry Analyzers | Jan-21 | Execution | Execution | Aug-24
9 | 31522 | DN Tritium Removal Facility Deuterium Make-up System Electrolyzer Replacement | Oct-19 | Close-out | Complete | Nov-21
10 | 31524 | DN Station Roofs Replacement | Nov-27 | Definition | Close out | Oct-24
11 | 31526 | DN Feeder Scanner Replacement | Aug-22 | Execution | Execution | Dec-22
12 | 31532 | DN Powerhouse Water Air Condition Units Replacement | Jan-23 | Execution | Execution | Jul-25
13 | 31535 | DN Water Treatment Plant Replacement | Sep-24 | Definition | Execution | Dec-24
14 | 31542 | DN Transformer Multi-Gas Analyzer Installation | Dec-20 | Close-out | Complete | Sep-20
15 | 31544 | DN Radiation Detection Equipment Obsolescence | Sep-23 | Definition | Execution | Sep-26
16 | 31548 | DN Feedwater Chemistry Control Improvements | Feb-20 | Close-out | Complete | Nov-20
17 | 31704 | DN Fuel Handling Obsolete Control Relay Re-Engineer/Replacement | Jul-24 | Execution | Execution | Jun-26
18 | 31706 | DN Vapour Recovery Button-Up Valve Replacements | Feb-24 | Definition | Execution | Jan-26
19 | 31710 | DN Shutdown Cooling Heat Exchanger Replacement | Dec-21 | Close-out | Complete | Nov-21
20 | 31716 | DN Neutron Over-Power Ion Chamber & In-Core Flux Detector Amplifier Replacement (Reactor Regulating System, Shutdown System 1 & Shutdown System 2) | Apr-27 | Execution | Execution | Nov-28
21 | 33228 | DN Hydrogen Cooling Temperature Control Valve TCV20 Redesign | Jun-21 | Execution | Complete | Nov-21
22 | 33258 | DN Replacement Of Emergency Power Supply Uninterruptible Power Supply | Feb-22 | Execution | Execution | Nov-24
23 | 33621 | DN Air Conditioning Unit Replacement For Secondary Control Area | Aug-25 | Execution | Execution | Jan-26
24 | 33631 | DN Chiller Replacement to Reduce Chloroflurocarbon Emissions | Dec-17 | Execution | Complete | Dec-21
25 | 33815 | Fuel Handling Computer Replacement | Nov-21 | Execution | Execution | Aug-24
26 | 33819 | DN Major Pump-Sets Vibration Monitoring System Upgrades | Nov-26 | Execution | Execution | Apr-27
27 | 33973 | DN Standby Generator Controls Replacement | Mar-21 | Execution | Execution | Jul-25
28 | 33977 | DN Digital Control Computer Replacement/ Refurbishment/ Upgrades | Dec-21 | Execution | Execution | May-25
29 | 34000 | DN Auxiliary Heating System | Jun-18 | Close-out | Complete | Jun-18
30 | 38948 | DN Zebra Mussels Mitigation & Improvements | Dec-21 | Close-out | Complete | Dec-21
31 | 40691 | PB Emergency Power Generator and Main Output Power Protective Relay Replace | Oct-19 | Close-out | Complete | Mar-21
32 | 40972 | PA Standby Generator Reliability Upgrades | Dec-21 | Execution | Complete | Dec-24
33 | 40985 | PN Obsolete Online Chemistry Analyzer Replacement | Aug-19 | Execution | Complete | Jul-21
34 | 73566 | DN RS Primary Heat Transport Pump Motor Replacement | May-21 | Execution | Complete | Oct-22
35 | 80022 | DN OH180 Aging Management Hardware Installation | Jun-28 | Execution | Execution | Nov-29
36 | 80023 | DN Steam Generator Level Control Valve Replacement | Jun-26 | Definition | Cancelled | Cancelled
37 | 80036 | DN R22 Refrigerant Air Conditioning Unit Replacement | Jan-26 | Execution | Execution | Jan-27
38 | 80063 | DN Standby Generators Protective Relay Replacement | Feb-23 | Definition | Execution | 45987
39 | 80070 | DN Feeder Scanner Replacement | Aug-22 | Execution | Complete | Feb-25
40 | 80078 | DN Digital Control, Common Process And Sequence Of Events Monitoring Computer Aging Management | Feb-28 | Definition | Definition | Mar-35
41 | 80122 | DN Main Power Output Protection System Replacement | Aug-27 | Definition | Execution | Jan-28
42 | 80123 | DN Group II Pressure Transmitter Replacement | Jan-28 | Definition | Execution | Dec-28
43 | 80124 | DN Obsolete Controller Replacement | Dec-26 | Execution | Execution | Dec-28
44 | 80126 | DN Emergency Power Generator 1 And 2 Replacement | May-22 | Execution | Execution | Nov-23
45 | 80144 | DN Primary Heat Transport Pump Motor Overhaul | Oct-21 | Execution | Complete | Dec-21
46 | 80148 | DN Fuel Handling Computer Input/ Output Subsystem Interprocessor Communication Replacement | Apr-27 | Definition | Definition | Dec-27
47 | 80150 | DN Fire Resistant Fluid Pump Improvement | Nov-25 | Definition | Definition | Dec-29
48 | 80151 | DN Fire Hazard Assessment and Fire Safe Shutdown Analysis Modifications | Sep-21 | Execution | Complete | Oct-22
49 | 82816 | DN Vault Cooling Coil Replacement | Jul-19 | Close-out | Complete | Oct-20
50 | 82841 | DN Irradiated Fuel Discharge Mechanism Major Component Replacement | Feb-24 | Execution | Execution | Dec-28

## D2-1-3_Table 7b
Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 1
Schedule 3
Table 7b
Table 7b
Capital Projects - OPG Nuclear Facilities
Status of Projects > $10M with 2020 to 2026 Final In-Service Dates in EB-2020-0290
|  |  | In-Service Date | Project Stage
|  |  | at Time of | at Time of | Current Project Status
Line | Project |  | EB-2020-0290 | EB-2020-0290 | Project | Projected/Actual
No. | Number | Project Name | Application | Application | Status | In-Service Date
| (a) | (b) | (c) | (d) | (e) | (f)
51 | 82842 | DN Fuel Handling Trolley Major Auxiliary Component Replacement | Feb-24 | Execution | Execution | Jan-28
52 | 82883 | DN Class 1 Rectifier Replacement | Dec-32 | Development | Execution | Jan-28
53 | 82886 | DN Fuel Handling Motor Replacement | Apr-23 | Execution | Execution | Dec-30
54 | 82890 | DN Main Power Output and Class IV Transformer Control Cabinet Wiring Replacement | Jan-24 | Deferred | Deferred | Deferred
55 | 82929 | Security Project B | Sep-21 | Execution | Execution | Oct-25
56 | 82930 | Security Project C | Mar-21 | Execution | Execution | Jun-25
57 | 82947 | DN Fuel Handling Head Major Component Replacement | May-27 | Definition | Execution | Aug-28
58 | 83039 | DN Rapid Delivery Machine | May-25 | Definition | Execution | Jul-29
59 | 83049 | DN Copper Piping Replacement | Dec-22 | Execution | Complete | Aug-23
60 | 83052 | DN Fuel Handling Power & Signal Cable Catenary Replacement | Jan-27 | Definition | Execution | Dec-27
61 | 83072 | PN P58 Buried Blowdown Piping Replacement | Dec-20 | Execution | Complete | Sep-21
62 | 83076 | DN Phase 2 Station Battery Replacement | Dec-28 | Execution | Execution | Nov-27
63 | 83088 | PN U14 Low Pressure Feedheater Heat Exchanger Replacement | May-18 | Close-out | Complete | Feb-21
64 | 83288 | DN Heavy Water Management System Computer Distributed Control Units Replacement | Sep-24 | Development | Definition | Sep-27
65 | 83296 | DN Main Output Transformer & Unit Service Transformer Replacement | Jun-24 | Execution | Execution | Dec-27
66 | 83297 | DN Large Moderator Temperature Control Valve Replacement | Jun-26 | Definition | Execution | Jan-30
67 | 83298 | DN Secondary System Obsolete Control Valve Replacement | Dec-27 | Definition | Execution | Oct-27
68 | 83299 | DN Condenser Steam Discharge Valve Control System Replacement | Dec-27 | Definition | Cancelled | Cancelled
69 | 83480 | DN 4KV Motor Refurbishment And Replacement | Jun-28 | Definition | Execution | Jun-36
70 | 83483 | DN Irradiated Fuel Bay Cooling and Purification Pump Replacement | Sep-21 | Execution | Execution | Jan-29
71 | 83484 | DN Isolated Phase Bus Refurbishment | Jun-28 | Development | Execution | Jul-28
72 | 83530 | DN Powerhouse Upper Level Service Water Piping Replacement | Nov-25 | N/A | Execution | Nov-25
73 | 83556 | DN Turbine Hall Crane Controls Upgrade | Dec-20 | Execution | Complete | Apr-20
74 | 83558 | DN Fuel Handling Service Area Bridge F5 Ball Screw Assembly Replacement | Jun-25 | Definition | Execution | Nov-24
75 | 83559 | DN Irradiated Fuel Bay Permanent Fuel Inspection Equipment | May-22 | Execution | Complete | May-23
76 | 83560 | DN Tritium Removal Facility Water Air Conditioning Units Replacement | Dec-19 | Definition | Execution | Dec-25
77 | 83664 | DN Unit 2 Turbine Control and Auxiliary Systems Upgrade | Jul-25 | Definition | Execution | Jan-28
78 | 83668 | PN High Pressure Turbine Spindle Capital Spares | Aug-19 | Close-out | Complete | Jun-20
79 | 83828 | Fleet Monitoring Initiative (Monitoring & Diagnostic Centre) | Jul-23 | Definition | Execution | Aug-26
80 | 83916 | DN Fuel Handling Replacement of Fuelling Machine Calibration Facility | Jul-25 | Development | Definition | Nov-27
81 | 83937 | DN Shutdown System 1 and Reactor Regulating System Ion Chamber Replacements | Dec-28 | Execution | Execution | Jul-33
82 | 84006 | DN Fuelling Machine Duct & Central Service Area Air Conditioning Unit Replacement | Aug-21 | Definition | Definition | Jul-29
83 | 84009 | DN Air Operated Valve Replacements | Dec-28 | Development | Execution | Dec-25
84 | 84140 | PN Circumferential Wet Scrape Tool Enhancements | Dec-22 | Execution | Execution | Dec-23
85 | 84235 | DN Primary Heat Transport Liquid Relief Valve Modifications (Waterhammer) | Jul-26 | Execution | Execution | Jan-26
86 | 84399 | DN Radiation Detection Equipment Obsolence- Moderator Cover Gas Monitors & Fixed Area Alarming Gamma Monitors | Dec-23 | Definition | Execution | May-25
87 | 84400 | DN Radiation Detection Obsolescence- Active Liquid Waste and Liquid Effluent Monitor | Sep-23 | Definition | Execution | Apr-26
88 | 84551 | DN Motor Operated Valve Replacements | Dec-28 | Development | Execution | Dec-29
89 | 84799 | DN Primary Heat Transport Pump Rotor Inspection and Replacement | Oct-26 | Execution | Execution | Jul-24
90 | 84888 | Steam Generator Manipulator & Automated Tube Plug | May-20 | Execution | Deferred | Deferred
91 | 84939 | DN Revenue Metering Transformer Replacement | Oct-26 | Development | Execution | Jul-28
92 | 86055 | DN Main Power Output Transformer Fire Containment System Upgrade | Aug-21 | Definition | Execution | Sep-26

## D2-2-3 Table 1a
Numbers may not add due to rounding. | [12 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 1a
Table 1a
Program Expenditures Summary - Darlington Refurbishment Program ($M)
Line |  | 2010 | 2011 | 2012 | 2013+ | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
No. | Description | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | OM&A1,2,3,4 | 3.2 | 2.6 | 2.8324 | 6.3282 | 6.2547 | 1.5551 | 3.0997 | 36.1119 | 31.3358 | 1.7135 | 18.9689 | 35.5689
2 | Capital Expenditures1,2,3,4,5 | 32.6 | 91 | 232.5 | 409.3064 | 694.2656 | 705.8297 | 1019.189 | 1249.252 | 1079.205 | 1150.4642 | 781.5139 | 812.9589
3 | Total Darlington Refurbishment Program | 35.8 | 93.6 | 235.3324 | 415.6346 | 700.5203 | 707.3849 | 1022.2887 | 1285.3639 | 1110.5407 | 1152.1777 | 800.4827 | 848.5278
Line |  | (a): 2022; (b): 2023; (c): 2024; (d): 2025; (e): 2026; (f): 2010-2026
No. | Description | (a): Actual; (b): Actual; (c): Actual; (d): Budget; (e): Budget; (f): Total
|  | (a) | (b) | (c) | (d) | (e) | (f)
4 | OM&A | (a): 22.3; (b): 39; (c): 59.7; (d): 10.4931; (e): 1.7823; (f): 282.8446
5 | Capital Expenditures | (a): 970.2979; (b): 973.2174; (c): 988.2394; (d): 835.2; (e): 392; (f): 12417
6 | Total Darlington Refurbishment Program | (a): 992.5979; (b): 1012.2174; (c): 1047.9394; (d): 845.6931; (e): 393.7823; (f): 12699.8
Notes:
1 | Line 1 cols. (a) through (c) per EB-2013-0321, Ex. F2-7-1, Table 1, line 3, cols. (a) through (c) and Line 2 cols. (a) through (c) per EB-2013-0321, Ex. D2-1-2, Table 1, line 2, cols. (a) through (c).
2 | Line 1 cols. (d) through (f) per EB-2016-0152 Ex. F2-7-1, Table 1, line 3, cols. (a) through (c) and Line 2 cols. (d) through (f) per EB-2016-0152 Ex. D2-1-2, Table 1, line 2, cols. (a) through (c).
3 | Line 1 cols. (g) through (j) per EB-2020-0290 Ex. F2-7-1, Table 1, line 4, cols. (a) through (d) and Line 2 cols. (g) through (j) per EB-2020-0290 Ex. D2-1-2, Table 1, line 2, cols. (a) through (d).
4 | Line 1, cols. (k) through (l) and Line 4, cols. (a) through (e) per Ex. F2-7-1, Table 1, line 4, cols. (a) through (g) and Line 2, cols. (k) through (l) and Line 5, cols. (a) through (e) per Ex. D2-1-2, Table 1, line 2, cols. (a) through (g).
5 | + Line 2, col. (d) has been revised from amounts shown in EB-2016-0152 Ex. D2-1-2, Table 1, line 2, col. (a) as projects 73706, 25619 and 34000 were reclassified as noted in EB-2016-0152 Ex. D-2-10 pp. 10 and pp. 11.

## D2-2-3_Table 1b
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 1b
Table 1b
Capital Expenditures Summary - Darlington Refurbishment Program ($M)
Line |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Description | Actual | Actual | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (I) | (j) | (k) | (l)
1 | Darlington Refurbishment Program - Unit Refurbishment1 | 771.4079 | 813.9113 | 970.2487 | 971.3548 | 987.8958 | 835.1583 | 392.005 | 0 | 0 | 0 | 0 | 0
2 | Facilities and Infrastructure Projects | 0.40756 | -1.3939 | -0.90346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Heavy Water Storage Facility (D2O Storage) Project 2 | 7.0218 | -0.31499 | 0.014136 | 0.088839 | 0.42591 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Safety Improvement Opportunities | 2.6767 | 0.75651 | 0.93845 | 1.7739 | -0.072364 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Total Darlington Refurbishment | 781.5139 | 812.9589 | 970.2979 | 973.2176 | 988.2493 | 835.1583 | 392.005 | 0 | 0 | 0 | 0 | 0
Notes:
1 | The DRP Unit Refurbishment includes the Unit 2, Unit 3, Unit 1, Unit 4, and Early In-Service projects.
2 | Heavy Water Storage Facility (D2O Storage) project costs in rate base are limited to amounts approved by the OEB in EB-2020-0290.

## D2-2-3_Table 2
Numbers may not add due to rounding. | [14 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 2
Table 2
Capital Project Listing - Darlington Refurbishment Program
Projects ≥ $30M Total Project Cost 1
Total
[6 empty] | Final | Project | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Start | In-Service | Cost | In-Service | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o)
ONGOING PROJECTS FROM EB-2020-0290
1 | DN | Darlington Refurbishment - Unit Refurbishment - Unit 3 | Various | Unit Refurb -Unit 3 | 2020-09-02 | 2023-07-18 | 2295.0925 | 2295.0925 | 2.9534 | 0 | 0 | 0 | 0 | 0 | 0
2 | DN | Darlington Refurbishment - Unit Refurbishment - Unit 1 | Various | Unit Refurb -Unit 1 | 2022-02-15 | 2024-11-27 | 1731.7233 | 1731.7233 | 35.6561 | 6.2035 | 0 | 0 | 0 | 0 | 0
3 | DN | Darlington Refurbishment - Unit Refurbishment - Unit 4 | Various | Unit Refurb -Unit 4 | 2023-07-15 | 2026-04-15 | 2291.5296 | 2291.5296 | 0 | 2291.5296 | 0 | 0 | 0 | 0 | 0
4 |  | Subtotal |  |  |  |  | 6318.3454 | 6318.3454 | 38.6095 | 2297.7331 | 0 | 0 | 0 | 0 | 0
5 |  | Total - Projects ≥ $30M Total Project Cost |  |  |  |  | 6318.3454 | 6318.3454 | 38.6095 | 2297.7331 | 0 | 0 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.

## D2-2-3_Table 3
Numbers may not add due to rounding. | [15 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 3
Table 3
Capital Project Listing - Darlington Refurbishment Program
Projects $10M - $30M Total Project Cost
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
No projects in this category
Total - Projects $10M - $30M Total Project Cost

## D2-2-3_Table 4
Numbers may not add due to rounding. | [11 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 4
Table 4
Capital Project Listing - Darlington Refurbishment Program
Projects <$10M Total Project Cost1
|  |  | Total | Average Cost | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | Number of | Project | Of All | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Projects | Cost ($M) | Projects ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
1 | Unit Refurbishment - Early In-service | 3 | 7.385 | 2.4617 | 0 | 0 | 1.6889 | 0 | 0 | 0 | 0 | 0
2 | Facilities & Infrastructure Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Safety Improvement Opportunities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Total - Projects <$10M Total Project Cost | 3 | 7.385 | 2.4617 | 0 | 0 | 1.6889 | 0 | 0 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during forecast period OR In-Service Amounts in Bridge or forecast period AND Completed/Deferred Projects at the time of preparing the 2025-2031 Business Plan.

## D2-2-3_Table 5a
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 5a
Table 5a
Comparison of In-Service Capital Additions - Darlington Refurbishment Program ($M) 2020-2028
Line |  | 2020 | (c)-(a) | 2020 | 2021 | (f)-(d) | 2021 | 2022 | (i)-(g) | 2022 | 2023 | (l)-(j) | 2023
No. | Business Unit | OEB Approved | Change | Actual | OEB Approved | Change | Actual | OEB Approved | Change | Actual | OEB Approved | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | Darlington Refurbishment - Unit Refurbishment - Unit 2 | 4799.8 | -34.7824 | 4765.0176 | 0.4 | 5.7827 | 6.1827 | 0 | -2.5271 | -2.5271 | 0 | -2.355 | -2.355
2 | Darlington Refurbishment - Unit 2 Refurbishment - Early I/S | 0 | 2.1562 | 2.1562 | 0 | 1.508 | 1.508 | 0 | 0 | 0 | 0 | 0 | 0
3 | Subtotal | 4799.8 | -32.6262 | 4767.1738 | 0.4 | 7.2907 | 7.6907 | 0 | -2.5271 | -2.5271 | 0 | -2.355 | -2.355
4 | Facilities & Infrastructure Projects | 9.4 | 0.58153 | 9.9815 | 0 | -1.3937 | -1.3937 | 0 | -0.90346 | -0.90346 | 0 | 0 | 0
5 | D20 Storage Project 1 | 0 | 381 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Safety Improvement Opportunities | 0 | -3.0115 | -3.0115 | 0 | 1.5302 | 1.5302 | 0 | 4.2362 | 4.2362 | 0 | 0 | 0
7 | Darlington Refurbishment - Unit Refurbishment - Unit 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2242.4345 | 2242.4345
8 | Darlington Refurbishment - Unit 3 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8594 | 2.8594 | 0 | 0 | 0
9 | Darlington Refurbishment - Unit Refurbishment - Unit 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Darlington Refurbishment - Unit 1 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4434 | -1.4434 | 0
11 | Darlington Refurbishment - Unit Refurbishment - Unit 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Darlington Refurbishment - Unit 4 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Total In-Service Capital Additions | 4809.2 | 345.9438 | 5155.1438 | 0.4 | 7.4272 | 7.8272 | 0 | 3.6651 | 3.6651 | 1.4434 | 2238.6361 | 2240.0795
Line |  | 2024 | (c)-(a) | 2024 | 2025 | (f)-(d) | 2025 | 2026 | (i)-(g) | 2026 | 2027 | (l)-(j) | 2028
No. | Business Unit | OEB Approved | Change | Actual | OEB Approved | Change | Budget | OEB Approved | Change | Budget | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
14 | Darlington Refurbishment - Unit Refurbishment - Unit 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Darlington Refurbishment - Unit 2 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Facilities & Infrastructure Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | D20 Storage Project 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Safety Improvement Opportunities | 0 | 2.2923 | 2.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Darlington Refurbishment - Unit Refurbishment - Unit 3 | 2503.9636 | -2454.2591 | 49.7045 | 0 | 2.9534 | 2.9534 | 0 | 0 | 0 | 0 | 0 | 0
21 | Darlington Refurbishment - Unit 3 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Darlington Refurbishment - Unit Refurbishment - Unit 1 | 0 | 1689.8637 | 1689.8637 | 1907.3336 | -1871.6775 | 35.6561 | 0 | 6.2035 | 6.2035 | 0 | 0 | 0
23 | Darlington Refurbishment - Unit 1 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Darlington Refurbishment - Unit Refurbishment - Unit 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2028.3 | 263.2296 | 2291.5296 | 0 | 0 | 0
25 | Darlington Refurbishment - Unit 4 Refurbishment - Early I/S | 1.5679 | -1.5679 | 0 | 0 | 0 | 0 | 0 | 1.6889 | 1.6889 | 0 | 0 | 0
26 | Total In-Service Capital Additions | 2505.5315 | -763.671 | 1741.8605 | 1907.3336 | -1868.7241 | 38.6095 | 2028.3 | 271.1221 | 2299.4221 | 0 | 0 | 0
Notes:
1 | In its EB-2020-0290 Decision and Order, the OEB approved in-service additions of $381M, which factors in a permanent rate base disallowance of $113.7M to the total cost that OPG proposed to add to rate base for the D2O Storage Project.

## D2-2-3_Table 5b
Numbers may not add due to rounding. | [10 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 2
Schedule 3
Table 5b
Table 5b
Comparison of In-Service Capital Additions - Darlington Refurbishment Program ($M) 2028-2031
Line |  | 2028 | (c)-(a) | 2029 | (e)-(c) | 2030 | (g)-(e) | 2031 | 2022-2026 | (j)-(h) | 2027-2031
No. | Business Unit | Plan | Change | Plan | Change | Plan | Change | Plan | Actual & Budget | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j)
1 | Darlington Refurbishment - Unit Refurbishment - Unit 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.8821 | 4.8821 | 0
2 | Darlington Refurbishment - Unit 2 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.8821 | 4.8821 | 0
4 | Facilities & Infrastructure Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.90346 | 0.90346 | 0
5 | D2O Storage Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Safety Improvement Opportunities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5285 | -6.5285 | 0
7 | Darlington Refurbishment - Unit Refurbishment - Unit 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295.0925 | -2295.0925 | 0
8 | Darlington Refurbishment - Unit 3 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8594 | -2.8594 | 0
9 | Darlington Refurbishment - Unit Refurbishment - Unit 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731.7233 | -1731.7233 | 0
10 | Darlington Refurbishment - Unit 1 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Darlington Refurbishment - Unit Refurbishment - Unit 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2291.5296 | -2291.5296 | 0
12 | Darlington Refurbishment - Unit 4 Refurbishment - Early I/S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6889 | -1.6889 | 0
13 | Total In-Service Capital Additions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6323.6367 | -6323.6367 | 0

## D2-3-8_Table 1
Numbers may not add due to rounding. | [9 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 3
Schedule 8
Table 1
Table 1
Capital Expenditures Summary - Pickering Refurbishment Program ($M)
Line |  | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Description | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i)
1 | Pickering Refurbishment Program - Unit Refurbishment1 | 15.1112 | 354.6343 | 1363.6755 | 2778.4346 | 3117.7494 | 3289.9381 | 3396.7804 | 2562.9585 | 1860.5442
2 | Facilities and Infrastructure Projects | 0 | 1.0168 | 79.047 | 97.0596 | 2.7336 | 0 | 0 | 0 | 0
3 | Deep Water Intake | 0.25552 | 15.954 | 57.2774 | 170.084 | 352.7225 | 317.6399 | 181.4792 | 118.4771 | 0
4 | Total Pickering Refurbishment Program2 | 15.3667 | 371.6051 | 1500 | 3045.5782 | 3473.2055 | 3607.5781 | 3578.2596 | 2681.4355 | 1860.5442
Notes:
1 | The Pickering Unit Refurbishment includes Unit 5, Unit 6, Unit 7, and Unit 8.
2 | OM&A costs (L&ILW variable expenses and Removal costs) are excluded from Total Pickering Refurbishment Program.

## D2-3-8_Table 2
Numbers may not add due to rounding. | [14 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 3
Schedule 8
Table 2
Table 2
Capital Project Listing - Pickering Refurbishment Program
Projects ≥ $30M Total Project Cost 1
[7 empty] | Total | Total | In-Service
[6 empty] | Final | Project |  |  | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Start | In-Service | Cost | In-Service | IR Term | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o)
ONGOING PROJECTS FROM EB-2020-0290
1 |  | No projects in this category
2 |  | Subtotal
COMPLETED PROJECTS FROM EB-2020-0290
3 |  | No projects in this category
4 |  | Subtotal
PROJECTS NOT IN EB-2020-0290
5 | PN | Common Services Building (CSB) | 88537 | F&IP | 2025-04-30 | 2026-09-15 | 57.4204 | 57.4204 | 57.4204 | 57.4204 | 0 | 0 | 0 | 0 | 0
6 | PN | Pickering Maintenance Facility (PMF) | 88531 | F&IP | 2025-10-30 | 2026-09-15 | 30.7085 | 30.7085 | 30.7085 | 30.7085 | 0 | 0 | 0 | 0 | 0
7 | PN | Deep Water Intake (DWI) | Various | DWI | 2023-11-30 | 2031-05-15 | 1213.8897 | 1213.8897 | 1213.8897 | 0 | 0 | 0 | 0 | 0 | 1213.8897
8 | PN | Pickering Refurbishment - Unit Refurbishment - Unit 51 | Various | Unit Refurb -Unit 5 | 2023-10-30 | 2031-05-15 | 8474.1224 | 8474.1224 | 8474.1224 | 0 | 0 | 0 | 0 | 0 | 8474.1224
9 | PN | Pickering Refurbishment - Unit Refurbishment - Unit 61 | Various | Unit Refurb -Unit 6 | 2024-09-30 | 2032-07-02 | 4315.6601 | 4315.6601 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | PN | Pickering Refurbishment - Unit Refurbishment - Unit 71 | Various | Unit Refurb -Unit 7 | 2024-09-30 | 2033-04-16 | 4107.9258 | 4107.9258 | 0 | 0 |  | 0 | 0 | 0 | 0
11 | PN | Pickering Refurbishment - Unit Refurbishment - Unit 81 | Various | Unit Refurb -Unit 8 | 2024-09-30 | 2034-08-01 | 4112.5089 | 4112.5089 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Subtotal |  |  |  |  | 22312.2359 | 22312.2359 | 9776.141 | 88.1289 | 0 | 0 | 0 | 0 | 9688.0121
13 |  | Total - Projects ≥ $30M Total Project Cost |  |  |  |  | 22312.2359 | 22312.2359 | 9776.141 | 88.1289 | 0 | 0 | 0 | 0 | 9688.0121
Notes:
1 | OM&A costs (L&ILW variable expenses and Removal costs) are excluded from Total Project Cost

## D2-3-8_Table 3
Numbers may not add due to rounding. | [14 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 3
Schedule 8
Table 3
Table 3
Capital Project Listing - Pickering Refurbishment Program
Projects $10M - $30M Total Project Cost 1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost | IR Term | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o)
ONGOING PROJECTS FROM EB-2020-0290
1 | (b): No projects in this category
2 | (b): Subtotal; (i): 0 | 0 | 0 | 0 | 0 | 0 | 0
COMPLETED PROJECTS FROM EB-2020-0290
3 | (b): No projects in this category
4 | (b): Subtotal; (i): 0 |  | 0 | 0 | 0 | 0 | 0
PROJECTS NOT IN EB-2020-0290
5 | PN | F&IP - ESB1 & ESB2 WPO | 88532 | F&IP | Renovate the existing facilities that have deteriorated and no longer meet the functional, technological, or ergonomic needs of a modern workplace, while accommodating increased staffing and coordination required for the PRP. | 2025-04-30 | 2026-09-15 | 21.8453 | 21.8453 | 21.8453 | 0 | 0 | 0 | 0 | 0
6 | PN | F&IP - PN Campus Electrical Upgrades | 88536 | F&IP | Aging electrical and piping systems will be replaced to enhance reliability, safety, and efficiency, while also supporting future needs with new EV chargers. | 2025-08-30 | 2026-09-15 | 19.5189 | 19.5189 | 19.5189
7 | PN | F&IP - PN Campus Parking Lots/Roads (outside PA) | 88535 | F&IP | Parking areas and roadways will be expanded and upgraded to support increased personnel and vehicle traffic, with new lots, improved access, and enhanced lighting. | 2025-09-30 | 2026-12-15 | 17.1355 | 17.1355 | 17.1355
8 | PN | F&IP - Montgomery Park and Sandy Beach Roads Upgrades | 88548 | F&IP | Montgomery Park Road and Sandy Beach Road will be upgraded to handle increased traffic and load demands, improving capacity, durability, and safety. | 2026-03-30 | 2027-06-15 | 20.5691 | 20.5691 |  | 20.5691
9 | (b): Subtotal; (h): 79.0688; (i): 79.0688 | 58.4997 | 20.5691 | 0 | 0 | 0 | 0
10 | (b): Total - Projects $10M - $30M Total Project Cost; (h): 79.0688; (i): 79.0688 | 58.4997 | 20.5691 | 0 | 0 | 0 | 0
Notes:
1 | (a): OM&A costs (L&ILW variable expenses and Removal costs) are excluded from Total Project Cost

## D2-3-8_Table 4
Numbers may not add due to rounding. | [11 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 3
Schedule 8
Table 4
Table 4
Capital Project Listing - Pickering Refurbishment Program
Projects <$10M Total Project Cost
|  |  | Total | Average Cost | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | Number of | Project | Of All | IR Term | 2026 | 2027 | 2028 | 2029 | 2028 | 2030 | 2031
No. | Project Name | Projects | Cost ($M) | Projects ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
|  | (a) | (b) | (c) | (d) | (e) | (f) | (h) | (i) | (j) | (k) | (l)
1 | Unit Refurbishment
2 | Facilities & Infrastructure Projects | 2 | 12.6593 | 6.3297 | 12.6593 | 12.6593 | 0 | 0 | 0 | 0 | 0 | 0
3 | Total - Projects <$10M Total Project Cost | 2 | 12.6593 | 6.3297 | 12.6593 | 12.6593 | 0 | 0 | 0 | 0 | 0 | 0

## D2-3-8_Table 5
Numbers may not add due to rounding. | [14 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 3
Schedule 8
Table 5
Table 5
Comparison of In-Service Capital Additions - Pickering Refurbishment Program ($M) 2026-2031
Line |  | 2026 | (c)-(a) | 2027 | (e)-(c) | 2028 | (g)-(e) | 2029 | (i)-(g) | 2030 | (k)-(i) | 2031 | 2026 | (n)-(l) | 2027-2031
No. | Business Unit | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan | Change | Plan | Budget | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n)
1 | Unit Refurbishment - Unit 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8474.1224 | 8474.1224 | 0 | 8474.1224 | 8474.1224
2 | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8474.1224 | 8474.1224 | 0 | 8474.1224 | 8474.1224
3 | Deep Water Intake (DWI) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213.8897 | 1213.8897 | 0 | 1213.8897 | 1213.8897
4 | F&IP - Common Services Building (CSB) | 57.4204 | -57.4204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.4204 | -57.4204 | 0
5 | F&IP - Pickering Maintenance Facility (PMF) | 30.7085 | -30.7085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.7085 | -30.7085 | 0
6 | F&IP - ESB1 & ESB2 WPO | 21.8453 | -21.8453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.8453 | -21.8453 | 0
7 | F&IP - PN Campus Electrical Upgrades | 19.5189 | -19.5189 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.5189 | -19.5189 | 0
8 | F&IP - PN Campus Parking Lots/Roads (outside PA) | 17.1355 | -17.1355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1355 | -17.1355 | 0
9 | F&IP - Montgomery Park and Sandy Beach Roads Upgrades | 0 | 20.5691 | 20.5691 | -20.5691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5691 | 20.5691
10 | F&IP - under $10M projects | 12.6593 | -12.6593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6593 | -12.6593 | 0
11 | Total In-Service Capital Additions | 159.2879 | -138.7189 | 20.5691 | -20.5691 | 0 | 0 | 0 | 0 | 0 | 9688.0121 | 9688.0121 | 159.2879 | 9549.2932 | 9708.5812

## D2-4-8_Table 1
Numbers may not add due to rounding. | [12 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 4
Schedule 8
Table 1
Table 1
Capital Expenditures Summary - Darlington New Nuclear Program ($M)
Line |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Category | Actual | Actual | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
DNNP Capital
1 | Unit 1 & Common Scope Facilities | 0 | 0 | 163.3548 | 236.2134 | 528.9334 | 1215.9233 | 1455.5 | 1410.4 | 896.7 | 304.7 | 373.2 | 0
2 | Unit 2 - 4 | 0 | 0 | 0 | 0 | 39.3506 | 66.6757 | 178 | 210.3 | 0 | 0 | 0 | 0
3 | Total DNNP Released Capital | 0 | 0 | 163.3548 | 236.2134 | 568.284 | 1282.5991 | 1633.5 | 1620.7 | 896.7 | 304.7 | 373.2 | 0

## D2-4-8_Table 2
Numbers may not add due to rounding. | [13 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 4
Schedule 8
Table 2
Table 2
Comparison of Capital Expenditures - Darlington New Nuclear Program ($M)
Line |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2022-2026 | (m)-(k) | 2027-2031
No. | Business Unit | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan | Actuals & Budget | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m)
DNNP
1 | Unit 1 & Common Scope Facilities | 163.3548 | 236.2134 | 528.9334 | 1215.9233 | 1455.5 | 1410.4 | 896.7 | 304.7 | 373.2 | 0 | 3599.9249 | -614.9249 | 2985
2 | Unit 2 - 4 | 0 | 0 | 39.3506 | 66.6757 | 178 | 210.3 | 0 | 0 | 0 | 0 | 284.0264 | -73.7264 | 210.3
3 | Capital - Released DNNP Total | 163.3548 | 236.2134 | 568.284 | 1282.5991 | 1633.5 | 1620.7 | 896.7 | 304.7 | 373.2 | 0 | 3883.9513 | -688.6513 | 3195.3

## D2-4-8_Table 3
Numbers may not add due to rounding. | [18 empty] | Updated: 2026-03-10
EB-2025-0297
Exhibit D2
Tab 4
Schedule 8
Table 3
Table 3
Capital Project Listing - Darlington New Nuclear Program Facility Projects
Projects ≥ $30M Total Project Cost
|  |  |  | Description of Asset Being Placed in Service |  |  |  | Total | 1st Execution Business Case
[7 empty] | Final | Asset |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  |  | Start | In-Service | Cost |  | In-Service | LTD | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number |  | Category | Date | Date | (M$) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) |  | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (q) | (r) | (s) | (t) | (u) | (v) | (w)
1 | DNNP | DNNP Unit 1 & Common Scope Facilities | Various | Unit 1 In-Service | DNNP Unit 1 and Common Scope Facilities | 2022-01-01 | 2030-10-17 | 6584.9249 | 6584.9249 | 6584.9249 | 0 | 6584.9249 | 0 | 0 | 0 | 0 | 0 | 6584.9249 | 0

## D2-4-8_Table 4
Numbers may not add due to rounding. | [15 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 4
Schedule 8
Table 4
Table 4
Capital Project Listing - Darlington New Nuclear Program Facility Projects
Projects $10M - $30M Total Project Cost
|  |  |  | Description of Asset Being Placed in Service |  |  |  | Total
[7 empty] | Final | Asset | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  |  | Start | In-Service | Cost | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Facility | Project Name | Number |  | Category | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
No projects in this category

## D2-4-8_Table 5
Numbers may not add due to rounding. | [11 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 4
Schedule 8
Table 5
Table 5
Capital Project Listing - Darlington New Nuclear Program Facility Projects
Projects < $10M Total Project Cost1
|  |  | Total | Average | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | Number of | Project | Cost of All | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Sponsoring Division | Projects | Cost ($M) | Projects ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
1 | No projects in this category

## D2-4-8_Table 6
Numbers may not add due to rounding. | [13 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D2
Tab 4
Schedule 8
Table 6
Table 6
Comparison of In-Service Capital Additions - Darlington New Nuclear Program ($M)
Line |  | 2025 | (c)-(a) | 2026 | (e)-(c) | 2027 | (g)-(e) | 2028 | (i)-(g) | 2029 | (k)-(i) | 2030 | (m)-(k) | 2031
No. | Business Unit | Budget | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m)
1 | Unit 1 and Common Scope Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6584.9249 | 6584.9249 | -6584.9249 | 0
2 | Total Unit 1 & Common Scope Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6584.9249 | 6584.9249 | -6584.9249 | 0
3 | Minor Fixed Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Total In-Service Capital Additions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6584.9249 | 6584.9249 | -6584.9249 | 0

## D3-1-1_Table 1
Numbers may not add due to rounding. | [12 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D3
Tab 1
Schedule 1
Table 1
Table 1
Capital Expenditures Summary - Support Services3 ($M)
(Capital Expenditures Impacting OPG Rate Base or Asset Service Fees)
Line |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Support Services | Actual | Actual | Actual | Actual | Actual | Budget | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | IT Portfolio1 | 100.959 | 104.637 | 96.941 | 116.38 | 92.7065 | 103.003 | 96.566 | 77.096 | 84.116 | 88.7822 | 85.53 | 76.188
2 | Real Estate | 20.0054 | 24.264 | 27.934 | 37.373 | 34.711 | 36.1281 | 76.633 | 102.3718 | 39.5845 | 40.7149 | 45.4679 | 29.005
3 | Subtotal | 120.9644 | 128.901 | 124.875 | 153.753 | 127.4175 | 139.1311 | 173.199 | 179.4678 | 123.7005 | 129.497 | 130.9979 | 105.193
4 | Microsoft Enterprise Agreement | 23.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Corporate Headquarters2 | 0 | 0 | 0 | 61.378 | 44.131 | 85.315 | 0 | 0 | 0 | 0 | 0 | 0
6 | Enterprise System Modernization Projects | 0 | 0 | 0 | 0 | 0 | 12.197 | 58.452 | 104.799 | 60.155 | 43.681 | 44.278 | 39.751
7 | Subtotal | 23.07 | 0 | 0 | 61.378 | 44.131 | 97.512 | 58.452 | 104.799 | 60.155 | 43.681 | 44.278 | 39.751
8 | DNNP Operational Readiness Technology Projects (DNNP Asset Service Fee) | 0 | 0 | 0 | 0 | 0 | 25.4141 | 45.328 | 28.7494 | 22.444 | 16.56 | 7.508 | 5.78
9 | Total | 144.0344 | 128.901 | 124.875 | 215.131 | 171.5485 | 262.0572 | 276.979 | 313.0162 | 206.2995 | 189.738 | 182.7839 | 150.724
Notes:
1 | Expenditures include a project with a cloud computing arrangements (Ex. D3-1-2, p. 3, footnote 1) .
2 | Corporate Headquarters includes the cost to acquire the building and associated renovation. The acquisition cost excludes costs associated with undeveloped land.
3 | Clarington Corporate Campus (EB-2020-0290) is not shown as the project was cancelled for a preferrable alternative and written off to Project OM&A. The cancelled project is discussed further in Ex. D3-1-1 Section 3.2.

## D3-1-1_Table 2
Numbers may not add due to rounding. | [12 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D3
Tab 1
Schedule 1
Table 2
Table 2
Comparison of Capital Expenditures - Support Services ($M) 2020-2031
(Capital Expenditures Impacting OPG Rate Base or Asset Service Fees)
Line | Business Unit | 2020 | (c)-(a) | 2020 | 2021 | (f)-(d) | 2021 | 2022 | (i)-(g) | 2022 | 2023 | (l)-(j) | 2023
No. |  | OEB Approved | Change | Actual | OEB Approved | Change | Actual | OEB Approved5 | Change | Actual | OEB Approved5 | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
Capital Projects (Allocated)
1 | IT Portfolio1 | 6.2 | 94.759 | 100.959 | 7.4 | 97.237 | 104.637 | 76.5995 | 20.3415 | 96.941 | 70.999 | 45.381 | 116.38
2 | Real Estate | 8 | 12.0054 | 20.0054 | 8 | 16.264 | 24.264 | 29.465 | -1.531 | 27.934 | 4.18 | 33.193 | 37.373
3 | Subtotal Capital Projects (Allocated) | 14.2 | 106.7644 | 120.9644 | 15.4 | 113.501 | 128.901 | 106.0645 | 18.8105 | 124.875 | 75.179 | 78.574 | 153.753
4 | IT Portfolio (Unallocated) | 0 | 0 | 0 | 0 | 0 | 0 | 14.6 | -14.6 | 0 | 7.5 | -7.5 | 0
5 | Subtotal Capital Projects | 14.2 | 106.7644 | 120.9644 | 15.4 | 113.501 | 128.901 | 120.6645 | 4.2105 | 124.875 | 82.679 | 71.074 | 153.753
6 | Microsoft Enterprise Agreement2 | 0 | 23.07 | 23.07 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | -23 | 0
7 | Clarington Corporate Campus3 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | -93 | 0 | 80 | -80 | 0
8 | Corporate Headquarters4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.378 | 61.378
9 | Subtotal | 0 | 23.07 | 23.07 | 0 | 0 | 0 | 93 | -93 | 0 | 103 | -41.622 | 61.378
10 | Enterprise System Modernization Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Enterprise System Modernization Projects- Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | DNNP Operational Readiness Technology Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | DNNP Operational Readiness Technology Projects- Unallocated Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Total (line 5 + line 9 + line 12 + line 15) | 14.2 | 129.8344 | 144.0344 | 15.4 | 113.501 | 128.901 | 213.6645 | -88.7895 | 124.875 | 185.679 | 29.452 | 215.131
Line | Business Unit | 2024 | (c)-(a) | 2024 | 2025 | (f)-(d) | 2025 | 2026 | (i)-(g) | 2026 | 2022-2026 | (l)-(j) | 2027-2031
No. |  | OEB Approved5 | Change | Actual | OEB Approved5 | Change | Budget | OEB Approved5 | Change | Budget | Actuals & Budget | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
Capital Projects (Allocated)
17 | IT Portfolio1 | 41.7 | 51.0065 | 92.7065 | 66 | 37.003 | 103.003 | 14.5 | 18.895 | 33.395 | 442.4255 | -384.8403 | 57.5852
18 | Real Estate | 12.279 | 22.432 | 34.711 | 11.614 | 24.5141 | 36.1281 | 8.4 | 68.233 | 76.633 | 212.7791 | 44.365 | 257.1441
19 | Subtotal Capital Projects (Allocated) | 53.979 | 73.4385 | 127.4175 | 77.614 | 61.5171 | 139.1311 | 22.9 | 87.128 | 110.028 | 655.2046 | -340.4754 | 314.7292
20 | IT Portfolio (Unallocated) | 39.5 | -39.5 | 0 | 17.2 | -17.2 | 0 | 68.7 | -5.529 | 63.171 | 63.171 | 290.956 | 354.127
21 | Subtotal Capital Projects | 93.479 | 33.9385 | 127.4175 | 94.814 | 44.3171 | 139.1311 | 91.6 | 81.599 | 173.199 | 718.3756 | -49.5194 | 668.8562
22 | Microsoft Enterprise Agreement2 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | -23 | 0 | 0 | 0 | 0
23 | Clarington Corporate Campus3 | 18 | -18 | 0 | 2 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Corporate Headquarters4 | 0 | 44.131 | 44.131 | 0 | 85.315 | 85.315 | 0 | 0 | 0 | 190.824 | -190.824 | 0
25 | Subtotal | 18 | 26.131 | 44.131 | 2 | 83.315 | 85.315 | 23 | -23 | 0 | 190.824 | -190.824 | 0
26 | Enterprise System Modernization Projects | 0 | 0 | 0 | 0 | 12.197 | 12.197 | 0 | 48.122 | 48.122 | 60.319 | -2.042 | 58.277
27 | Enterprise System Modernization Projects- Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.33 | 10.33 | 10.33 | 224.057 | 234.387
28 | Subtotal | 0 | 0 | 0 | 0 | 12.197 | 12.197 | 0 | 58.452 | 58.452 | 70.649 | 222.015 | 292.664
29 | DNNP Operational Readiness Technology Projects | 0 | 0 | 0 | 0 | 15.116 | 15.116 | 0 | 15.262 | 15.262 | 30.378 | 7.895 | 38.273
30 | DNNP Operational Readiness Technology Projects- Unallocated Projects | 0 | 0 | 0 | 0 | 10.2981 | 10.2981 | 0 | 30.066 | 30.066 | 40.3641 | 2.4044 | 42.7684
31 | Subtotal | 0 | 0 | 0 | 0 | 25.4141 | 25.4141 | 0 | 45.328 | 45.328 | 70.7421 | 10.2994 | 81.0414
32 | Total (line 21 + line 25 + line 28 + line 31) | 111.479 | 60.0695 | 171.5485 | 96.814 | 165.2432 | 262.0572 | 114.6 | 162.379 | 276.979 | 1050.5907 | -8.029 | 1042.5617
Notes:
1 | Expenditures include a project with a cloud computing arrangements (Ex. D3-1-2, p. 3, footnote 1) .
2 | Variance in 2023 and 2026 due to updated accounting treatment of these costs as OM&A (Ex. D3-1-1, s. 3.1.4).
3 | Clarington Corporate Campus (EB-2020-0290) is not shown as the project was cancelled for a preferrable alternative and written off to Project OM&A. The cancelled project is discussed further in Ex. D3-1-1 Section 3.2.
4 | Corporate Headquarters includes the cost to acquire the building and associated renovation. The acquisition cost excludes costs associated with undeveloped land.
5 | For comparison with the Corporate Headquarters project, the "OEB Approved" column includes the Clarington Corporate Campus project capital expenditures planned EB-2020-0290, including the years 2022 ($93.0M), 2023 ($80.0M), 2024 ($18.0M) and 2025 ($2.0M). A deferral account for the Clarington Corporate Campus project was established in EB-2020-0290 and associated impacts were excluded from the EB-2020-0290 final payment amounts order.

## D3-1-2_Table 1
Numbers may not add due to rounding. | [18 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 1
Table 1
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects ≥ $30M Total Project Cost (Allocated)1
|  | Project |  | Project | Final | Total | Total Project | 1st Execution | 1st Execution |  |  | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | Summary |  | Start | In-Service | Project Cost2 | Cost EB-2020-0290 | Business Case | Business Case- EB-2020-02903 | Total In-Service | In-Service LTD4 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Ref. No. | Category | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s)
COMPLETED/DEFERRED PROJECTS FROM EB-2020-0290
IT - Asset Service Fee
1 | Asset Suite 9 Upgrade | 84975 | Sustaining | 2020-07-01 | 2023-12-01 | 37.8 | 15 | 37.5 | n/a | 37.8 | 37.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Subtotal |  |  |  |  | 37.8 | 15 | 37.5 | 0 | 37.8 | 37.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ONGOING PROJECTS FROM EB-2020-0290
IT - Nuclear Rate Base
3 | Cyber Security – CSA N290.7 Compliance5 | 82924 83690 83692 83800 86251 87895 87888 87893 87052 | Regulatory | 2017-07-01 | 2026-12-01 | 35.8 | 40.7 | 44.84 | n/a | 35.8 | 30.202 | 0 | 2.653 | 2.945 | 0 | 0 | 0 | 0 | 0
4 | Subtotal |  |  |  |  | 35.8 | 40.7 | 44.84 | 0 | 35.8 | 30.202 | 0 | 2.653 | 2.945 | 0 | 0 | 0 | 0 | 0
NEW PROJECTS NOT LISTED IN EB-2020-0290
IT - DNNP Asset Service Fee
5 | DNNP Enterprise Asset Management | 87188 | Sustaining- DNNP Operational Readiness Technology Projects | 2025-01-01 | 2032-12-01 | 68.7 | n/a | 68.7 | n/a | 68.7 | 0 | 56.035 | 0 | 0 | 0 | 0 | 0 | 50.767 | 5.268
6 | Subtotal |  |  |  |  | 68.7 | 0 | 68.7 | 0 | 68.7 | 0 | 56.035 | 0 | 0 | 0 | 0 | 0 | 50.767 | 5.268
IT - Asset Service Fee
7 | Integrated HR Service Delivery6 | 83746 | Sustaining | 2024-01-01 | 2026-04-30 | 52.726 | 40 | 52.726 | n/a | 52.7 | 0 | 0 | 50.065 | 2.635 | 0 | 0 | 0 | 0 | 0
8 | Finance ERP Solution | 89273 | Sustaining- Enterprise System Modernization Projects | 2025-06-01 | 2031-12-01 | 118.6017 | n/a | n/a | n/a | 118.6017 | 0 | 114.6017 | 0 | 4 | 0 | 89.104 | 18.7197 | 2.751 | 4.027
9 | Subtotal |  |  |  |  | 171.3277 | 40 | 52.726 | 0 | 171.3017 | 0 | 114.6017 | 50.065 | 6.635 | 0 | 89.104 | 18.7197 | 2.751 | 4.027
Real Estate - Asset Service Fee
10 | Corporate Headquarters7 | 87413 87414 | Value Enhancing | 2023-02-01 | 2025-12-01 | 190.824 | n/a | 205.172 | n/a | 190.824 | 7.7 | 0 | 183.1226 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal |  |  |  |  | 190.824 | 0 | 205.172 | 0 | 190.824 | 7.7 | 0 | 183.1226 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate - Rate Base
11 | Security Project D8 | 90092 | Sustaining | 2025-10-01 | 2027-12-01 | 34.273 | n/a | n/a | n/a | 34.274 | 0 | 26.1979 | 3.0761 | 5 | 26.1979 | 0 | 0 | 0 | 0
| Subtotal |  |  |  |  | 34.273 | 0 | 0 | 0 | 34.274 | 0 | 26.1979 | 3.0761 | 5 | 26.1979 | 0 | 0 | 0 | 0
CANCELLED PROJECTS FROM EB-2020-0290
12 | SAP Payroll Upgrade9 | n/a | Sustaining | n/a | n/a | 0 | 27 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Clarington Corporate Campus | 84640 | Value Enhancing | n/a | n/a | 0 | 200 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Subtotal | [5 empty] | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Total Projects |  |  |  |  | 538.7247 | 322.7 | 408.938 | 0 | 538.6997 | 75.702 | 196.8346 | 238.9167 | 14.58 | 26.1979 | 89.104 | 18.7197 | 53.518 | 9.295
Notes:
1 | Projects with expenditures during IR term OR In-Service amounts in Bridge or IR term and Completed/Deferred projects (from EB-2020-0290 or subsequent).
2 | Total Project Costs reflect BCS capital amounts (balance to be released) or the actual costs for completed projects, unless otherwise indicated.
3 | The designation of "n/a" means the project has not advanced to a First Execution BCS or the information is not applicable due to project timing.
4 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2024.
5 | Satisfaction of the CSA N290.7 cyber security standards is an ongoing compliance program comprised of nine distinct projects to address discrete requirements. The amount shown are the totals for all projects listed in this program. BCSs for these projects have not been provided as the total cost for each project is less than $30M.
6 | This project includes the SAP Payroll Upgrade project and the HR System Replacement project, which were listed as two separate projects in EB-2020-0290. Expenditures include cloud computing arrangements (Ex. D3-1-2, p. 3, footnote 1).
7 | Corporate Headquarters includes the cost to acquire the building and associated renovation. The acquisition cost excludes costs associated with undeveloped land.
8 | Total Project Costs represent the current estimated amount to undertake the upgrade; the final cost will be reflected in a BCS upon commencement of detailed work.
9 | SAP Payroll System project identified in EB-2020-0290 is now included in the Integrated HR Service Delivery project (line 7)

## D3-1-2_Table 2a
Numbers may not add due to rounding. | [13 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 2a
Table 2a
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects $10M - $30M Total Project Cost (Allocated)1
[5 empty] | Final | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project | Start | In-Service | Project Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n)
COMPLETED/DEFERRED PROJECTS FROM EB-2020-0290
IT - Asset Service Fee
1 | Tempus Lifecycle Upgrade | Sustaining | The business objective for this project was to upgrade the Tempus time reporting system at the end of its lifecycle. | 2017-12-01 | 2020-12-01 | 15.059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Network Segmentation - Campus Switch Replacement Project | Sustaining | This project replaced obsolete Network Hardware. Its objective was to improve performance while meeting mobile workforce requirements, and meet wireless needs. | 2017-02-01 | 2023-12-01 | 15.219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Reimagine Program | Value Enhancing | This project uses an automation first approach to identifying opportunities that drive process efficiencies, effectiveness, and enhanced controls, with opportunities for savings to achieve the 2020 Business Plan in the short to mid-range timeframe across Shared Services, Finance and Supply Chain. | 2019-03-01 | 2021-04-01 | 17.479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Reimagine Program 2.0 | Value Enhancing | This Program aims to optimize cost and quality across corporate functions, establish an end state that requires fewer staff delivering and improved services. | 2020-06-01 | 2023-06-01 | 16.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Microsoft Enterprise Agreement (EA) | Sustaining | This EA includes a robust Software Assurance program, and a comprehensive maintenance program that ensures OPG maximizes the benefits of the licensed products to help users save time and money while increasing productivity. These benefits support OPG’s ability to plan, deploy, use, maintain, train and transition software solutions. | 2020-09-01 | 2021-03-01 | 23.0758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CANCELLED PROJECTS FROM EB-2020-0290
6 | HR System Replacement3 | Sustaining | Human Resources System Replacement project deploys an integrated suite of human capital management web-based applications supporting OPG's HR system of record including Talent Management, Workforce Analytics and Succession planning. This project will enable digitization of records and enable better management of OPG's human capital. The scope of this project was included in the new Integrated HR Service Delivery project. | 2022-01-01 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Subtotal |  |  |  |  | 87.3428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT - Nuclear Rate Base
8 | Pickering Communication System Improvement Wi-Fi | Sustaining | This project replaces an existing aging and end of life network in order to mitigate operational risk. The establishment of wireless network infrastructure will enable the latest technology to improve quality and timely completion of work flows for the work control process by field staff. Wi Fi will facilitate the ability for field staff to directly access data and applications required to perform work. | 2020-06-01 | 2024-12-01 | 29.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CANCELLED PROJECTS FROM EB-2020-0290
9 | Nuclear Fleet Management Initiative - Pickering Wi-Fi - Power House Unit 1-84 | Sustaining | Establishment of wireless network infrastructures will provide up to date technology to improve efficiency, quality and timeliness completion of work flows for the work control process by field staff. Wi Fi will facilitate the ability for field staff, direct access to data and applications required to perform work in the field. | 2018-01-01 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Subtotal |  |  |  |  | 29.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during IR term OR In-Service amounts in Bridge or IR term AND Completed/Deferred projects (from EB-2020-0290 or subsequent).
2 | Total Project Costs reflect BCS capital amounts (balance to be released) or the actual costs for completed projects, unless otherwise indicated.
3 | This project and the SAP Payroll Upgrade project were combined into the Integrated HR Service Delivery project (Ex. D3-1-2, Table 1, line 7).
4 | This project was replaced by the Pickering Communication System Improvement Wi-Fi (line 8).

## D3-1-2_Table 2b
Numbers may not add due to rounding. | [13 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 2b
Table 2b
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects $10M - $30M Total Project Cost (Allocated)1
[5 empty] | Final | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project | Start | In-Service | Project Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n)
ONGOING PROJECTS FROM EB-2020-0290
IT - Asset Service Fee
11 | Energy Market Application Refresh Program | Regulatory | This project updates OPG’s Energy Markets systems to be compliant with the changes being implemented under the IESO’s Market Renewal Program. This project addresses updating OPG’s current Energy Trading and Risk Management (ETRM) system, identifying impacted business processes and related IT systems in detail, and documenting business/technical requirements, completing the technical upgrade of the Settlements system. | 2020-01-01 | 2025-12-01 | 21.153 | 0 | 10.732 | 0 | 0 | 0 | 0 | 0 | 0
12 | Subtotal |  |  |  |  | 21.153 | 0 | 10.732 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate - Nuclear Rate Base
13 | Workplace Transformation of Darlington Energy Complex 2nd Floor3 | Sustaining | Reconfigure the floor to construct agile workspaces and remove obsolete equipment to increase accessibility and usage, while aligning with the new office standard. | 2025-01-01 | 2027-12-01 | 11.072 | 4.374 | 0 | 6.698 | 4.374 | 0 | 0 | 0 | 0
14 | Subtotal |  |  |  |  | 11.072 | 4.374 | 0 | 6.698 | 4.374 | 0 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during IR term OR In-Service amounts in Bridge or IR term AND Completed/Deferred projects (from EB-2020-0290 or subsequent).
2 | Total Project Costs reflect BCS capital amounts (balance to be released) or the actual costs for completed projects, unless otherwise indicated.
3 | This project's name changed from Overhaul of the Darlington Energy Complex 2nd Floor as shown in EB-2020-0290.

## D3-1-2_Table 2c
Numbers may not add due to rounding. | [13 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 2c
Table 2c
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects $10M - $30M Total Project Cost (Allocated)1
[5 empty] | Final | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project | Start | In-Service | Project Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n)
NEW PROJECTS NOT IN EB-2020-0290
IT - Asset Service Fee
15 | Equipment Status Monitoring II Lifecycle | Sustaining | This project is a lifecycle upgrade for obsolete operations and maintenance system that manages Work Protection, Plant Status and Flowsheet changes for the Nuclear and Renewable Generation fleet. | 2021-01-01 | 2025-09-01 | 11.314 | 0 | 0.214 | 0 | 0 | 0 | 0 | 0 | 0
16 | Data Center Migration | Sustaining | This project will enable migration of data centres to OPG owned facilities, aligned with the cloud computing strategy to migrate to Azure and minimize the on-premise footprint. | 2020-10-01 | 2025-12-01 | 17.5846 | 0.00865 | 0.5 | 0 | 0 | 0.00865 | 0 | 0 | 0
17 | Enterprise Data Lake Deployment | Sustaining | This project establishes a central repository for storing data of various systems like AS9 and SAP. It will enable business units across OPG to run data analytics including dashboards, big data processing, on-demand analytics, and machine learning to support decision making. | 2021-09-01 | 2025-09-01 | 13.772 | 0 | 0.128 | 0 | 0 | 0 | 0 | 0 | 0
18 | Enterprise Service Management | Sustaining | This project replaces an end of life legacy service management system. The new platform is ServiceNow software which consolidates and integrates user experience by eliminating the need to go into individual systems for OPG's business needs. | 2023-06-30 | 2025-12-31 | 17.63 | 0 | 7.614 | 0 | 0 | 0 | 0 | 0 | 0
19 |  |  | Subtotal |  |  | 60.3006 | 0.00865 | 8.456 | 0 | 0 | 0.00865 | 0 | 0 | 0
IT - Nuclear Rate Base
20 | Intelligent Search Tool | Sustaining | This project enables staff to efficiently access information relevant to their role across various repositories and data sources that are currently not included in existing organizational search tools. The proposed solution will leverage enhanced search and employ Artificial Intelligence, Machine Learning and Natural Language Processing technologies. | 2020-11-01 | 2025-12-01 | 14.633 | 0 | 0.424 | 0 | 0 | 0 | 0 | 0 | 0
21 | Pickering Network Upgrade | Sustaining | This project is intended to deliver a reliable, secure, high-speed network that will support ongoing campus operations. The network design will include campus cores and edge switches and feature enhanced resiliency and redundancy, minimizing downtime and disruptions. The upgraded infrastructure (including wired and wireless) will be scalable, capable of accommodating future growth and the adoption of emerging technologies. | 2025-08-01 | 2028-12-01 | 11.984 | 11.984 | 0 | 0 | 2.614 | 9.37 | 0 | 0 | 0
22 | Subtotal |  |  |  |  | 26.617 | 11.984 | 0.424 | 0 | 2.614 | 9.37 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during IR term OR In-Service amounts in Bridge or IR term AND Completed/Deferred projects (from EB-2020-0290 or subsequent).
2 | Total Project Costs reflect BCS capital amounts (balance to be released) or the actual costs for completed projects, unless otherwise indicated.

## D3-1-2_Table 2d
Numbers may not add due to rounding. | [13 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 2d
Table 2d
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects $10M - $30M Total Project Cost (Allocated)1
[5 empty] | Final | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project | Start | In-Service | Project Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n)
NEW PROJECTS NOT IN EB-2020-0290 continued
Real Estate - Nuclear Rate Base
23 | Electric Service Distribution Analysis | Sustaining | Engineering, procurement and construction of electrical infrastructure at the East Complex Electrical System at Pickering, which includes Emergency Mitigation Buildings. | 2019-08-14 | 2025-12-01 | 10.442 | 0 | 4.535 | 0 | 0 | 0 | 0 | 0 | 0
24 | Upgrade Darlington Holt Road access to Auxiliary Security Building | Sustaining | Carry out road widening, relocation of parts of Holt road along with shifting existing storm water drainage and construct a new outfall to Lake Ontario. | 2022-02-08 | 2024-03-01 | 14.7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Workplace Transformation of Pickering Learning Center 1st Floor | Sustaining | Reconfigure the floor to construct agile workspaces and remove obsolete equipment to increase accessibility and usage, while aligning with the new office standard. | 2029-01-01 | 2030-12-01 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 13 | 0
26 | Workplace Transformation of Pickering Learning Center 2nd Floor | Sustaining | Reconfigure the floor to construct agile workspaces and remove obsolete equipment to increase accessibility and usage, while aligning with the new office standard. | 2029-01-01 | 2030-12-01 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 13 | 0
27 | Central Warehouse | Sustaining | Increasing capacity of warehouse to accommodate increased inventory needs for the Nuclear Fleet | 2026-03-01 | 2027-12-01 | 29.44 | 29.44 | 0 | 0 | 29.44 | 0 | 0 | 0 | 0
28 | Workplace Transformation of Darlington Energy Complex 3rd Floor | Sustaining | Reconfigure the floor to construct agile workspaces and remove obsolete equipment to increase accessibility and usage, while aligning with the new office standard. | 2026-01-01 | 2027-12-01 | 10.127 | 10.127 | 0 | 0 | 10.127 | 0 | 0 | 0 | 0
29 | Subtotal |  |  |  |  | 90.7462 | 65.567 | 4.535 | 0 | 39.567 | 0 | 0 | 26 | 0
Real Estate - Asset Service Fee
30 | Corporate Headquarters Parking | Sustaining | Create additional parking space at new Corporate Headquarters to accommodate the expected combined full occupancy and visitor spaces required for the building. Construction is currently on hold pending the completion of soil screening activities, which are included in the cost estimates. | 2024-09-01 | 2027-12-01 | 27.2 | 27.2 | 0 | 0 | 27.2 | 0 | 0 | 0 | 0
31 | Subtotal |  |  |  |  | 27.2 | 27.2 | 0 | 0 | 27.2 | 0 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during IR term OR In-Service amounts in Bridge or IR term AND Completed/Deferred projects (from EB-2020-0190 or subsequent).
2 | Total Project Costs reflect BCS capital amounts (balance to be released) or the actual costs for completed projects, unless otherwise indicated.

## D3-1-2_Table 2e
Numbers may not add due to rounding. | [13 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 2e
Table 2e
Capital Project Listing - Support Services - Regulated Hydroelectric
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects $10M - $30M Total Project Cost (Allocated)1
[5 empty] | Final | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project | Start | In-Service | Project Cost2 | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Name | Category | Description | Date | Date | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n)
NEW PROJECTS NOT IN EB-2020-0290
Real Estate - Hydroelectric Joint Use Assets
31 | Renewable Generation Training Center | Sustaining | Costs associated with setting up a new training facility subsequent to move from 800 Kipling Avenue. | 2026-03-01 | 2027-12-01 | 27.871 | 27.871 | 0 | 0 | 27.871 | 0 | 0 | 0 | 0
32 | EV Chargers | Sustaining | Install Electric vehicle charging infrastructure across Renewable Generation sites | 2027-01-01 | 2031-12-01 | 11 | 2.2 | 0 | 0 | 2.2 | 0 | 0 | 0 | 0
33 | Subtotal |  |  |  |  | 38.871 | 30.071 | 0 | 0 | 30.071 | 0 | 0 | 0 | 0
| Total Projects |  |  |  |  | 392.3146 | 139.2047 | 24.147 | 6.698 | 103.826 | 9.3786 | 0 | 26 | 0
Notes:
1 | Projects with expenditures during IR term OR In-Service amounts in Bridge or IR term AND Completed/Deferred projects (from EB-2020-0290 or subsequent).
2 | Total Project Costs reflect BCS capital amounts (balance to be released) or the actual costs for completed projects, unless otherwise indicated.

## D3-1-2_Table 3a
Numbers may not add due to rounding. | [11 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 3a
Table 3a
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Projects < $10M Total Project Cost1
|  |  | Total | Average Cost | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  | Number of | Project | Of All | IR Term | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Project Description | Projects | Cost ($M) | Projects ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | IT - Nuclear Rate Base | 105 | 98.3709 | 0.93687 | 1.0589 | 16.2 | 1.105 | 1.05 | 0.008881 | 0 | 0 | 0
2 | IT - Regulated Hydroelectric Rate Base | 2 | 2.144 | 1.072 | 0 | 2.025 | 0 | 0 | 0 | 0 | 0 | 0
3 | IT - Renewable Generation Joint Use Assets | 30 | 26.945 | 0.89817 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
4 | IT - Asset Service Fee | 271 | 213.369 | 0.78734 | 17.4799 | 15.7 | 15.0181 | 2.2 | 4.114 | 7.1659 | 2 | 2
5 | Real Estate - Nuclear Rate Base | 138 | 262.2212 | 1.9002 | 153.876 | 4.03 | 3.3512 | 37.371 | 35.963 | 32.7435 | 24.0925 | 23.706
6 | Real Estate - Asset Service Fee | 43 | 21.639 | 0.50323 | 7 | 4.735 | 0.2 | 0.4 | 1.4 | 4.4 | 0.4 | 0.4
7 | Total | 589 | 624.6891 | 1.0606 | 179.4148 | 45.69 | 19.6743 | 41.021 | 41.4859 | 44.3094 | 26.4925 | 26.106
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term.
Refer to Table 3b for further notes

## D3-1-2_Table 3b
Numbers may not add due to rounding. | [8 empty] | Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 3b
Table 3b
Notes to Table 3a
Capital Project Listing - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Notes:
2 | Capital Project Listing - Support Services for 2016 - 2019 period
|  | Capital | Capital | Capital | Capital | In-Service | In-Service | In-Service | In-Service
Line |  | 2016 | 2017 | 2018 | 2019 | 2016 | 2017 | 2018 | 2019
No. | Project Description | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h)
1 | IT - Regulated Hydroelectric Rate Base | 0.717 | 0.989 | 0.214 | 0 | 3.212 | 0 | 1.478 | 0
2 | IT - Renewable Generation Joint Use Assets | 3.242 | 4.983 | 5.246 | 6.966 | 3.714 | 0.605 | 0.599 | 5.356
3 | Total | 3.959 | 5.972 | 5.46 | 6.966 | 6.926 | 0.605 | 2.077 | 5.356

## D3-1-2_Table 4
Numbers may not add due to rounding. | [13 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 4
Table 4
Capital In-Service Additions - Support Services
(Capital In-Service Impacting Rate Base or Asset Service Fees)
In-Service Summary - All Capital
|  |  | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
No. | Capital In-Service Description | Reference | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
|  |  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
In-Service
Projects ≥ $30 M - Rate Base
1 | IT- Nuclear | D3-1-2_Table 1 | 2.055 | 3.094 | 3.807 | 4.073 | 4.873 | 2.653 | 2.945 | 0 | 0 | 0 | 0 | 0
2 | Real Estate- Nuclear | D3-1-2_Table 1 | 0 | 0 | 0 | 0 | 0 | 3.0761 | 5 | 26.1979 | 0 | 0 | 0 | 0
Projects ≥ $30 M - Asset Service Fee
3 | IT | D3-1-2_Table 1 | 0 | 9.655 | 21.837 | 6.334 | 0 | 50.065 | 2.635 | 0 | 0 | 0 | 0 | 0
4 | Enterprise System Modernization | D3-1-2_Table 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 89.104 | 18.7197 | 2.751 | 4.027
5 | Real Estate | D3-1-2_Table 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Corporate Headquarters | D3-1-2_Table 1 | 0 | 0 | 0 | 7.7014 | 0 | 183.1226 | 0 | 0 | 0 | 0 | 0 | 0
7 | IT DNNP | D3-1-2_Table 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.767 | 5.268
Projects $10M - $30M - Rate Base
8 | IT- Nuclear | D3-1-2 Table 2a/c | 9.292 | 7.928 | 13.088 | 5.876 | 7.037 | 0.424 | 0 | 2.614 | 9.37 | 0 | 0 | 0
9 | Real Estate | D3-1-2 Table 2b/d | 1.584 | 1.511 | 2.264 | 15.298 | 0.000176 | 4.535 | 6.698 | 43.941 | 0 | 0 | 26 | 0
Projects $10M - $30M - Asset Service Fee
10 | IT | D3-1-2 Table 2a/b/c | 35.401 | 30.248 | 20.198 | 9.7458 | 20.084 | 19.188 | 0 | 0 | 0.00865 | 0 | 0 | 0
11 | Real Estate | D3-1-2 Table 2d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 0 | 0 | 0 | 0
12 | Real Estate - Renewable Generation Joint Use Assets | D3-1-2 Table 2e | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.071 | 0 | 0 | 0 | 0
Projects < $10M - Rate Base
13 | IT- Nuclear | D3-1-2 Table 3a | 10.334 | 28.892 | 9.713 | 13.185 | 17.883 | 16.2 | 1.105 | 1.05 | 0.008881 | 0 | 0 | 0
14 | IT - Regulated Hydroelectric | D3-1-2 Table 3a | 0 | 0 | 0 | 0 | 0.119 | 2.025 | 0 | 0 | 0 | 0 | 0 | 0
15 | Real Estate | D3-1-2 Table 3a | 10.927 | 19.775 | 20.563 | 20.6 | 29.099 | 4.03 | 3.3512 | 37.371 | 35.963 | 32.7435 | 24.0925 | 23.706
Projects < $10M - Asset Service Fee
16 | IT | D3-1-2 Table 3a | 33.152 | 25.076 | 35.618 | 41.807 | 29.518 | 15.7 | 15.0181 | 2.2 | 4.114 | 7.1659 | 2 | 2
17 | IT - Renewable Generation Joint Use Assets | D3-1-2 Table 3a | 12.91 | 6.06 | 1.984 | 2.252 | 0.739 | 3 | 0 | 0 | 0 | 0 | 0 | 0
18 | Real Estate | D3-1-2 Table 3a | 3.48 | 2.355 | 1.063 | 2.326 | 0.48 | 4.735 | 0.2 | 0.4 | 1.4 | 4.4 | 0.4 | 0.4
Unallocated Projects
19 | IT - Nuclear Rate Base |  | 0 | 0 | 0 | 0 | 0 | 1.545 | 17.455 | 22.744 | 16.78 | 34.38 | 21.311 | 16
20 | IT - Asset Service Fee |  | 0 | 0 | 0 | 0 | 0 | 21.487 | 31.955 | 63.9 | 49.52 | 40.3 | 39.1 | 44.273
21 | IT - Regulated Hydroelectric Rate Base |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
22 | IT - Renewable Generation Joint Use Assets |  | 0 | 0 | 0 | 0 | 0 | 1 | 1.4 | 1.1 | 0 | 0 | 0 | 0
23 | Enterprise System Modernization Projects- Asset Service Fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.313 | 28.9384 | 116.488
25 | DNNP Operational Readiness Technology Projects- DNNP Asset Service Fee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.8614 | 1.259
Non-Project Related In-Service List
26 | Microsoft Enterprise Agreement1 - IT Asset Service Fee | D3-1-2 Table 2a | 22.926 | 0.144 | 0 | 0.0058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Minor Fixed Assets |  | 3.589 | 3.15 | 4.796 | 3.949 | 4.45 | 6 | 7 | 9 | 9 | 9 | 9 | 9
28 | Total In-Service Amounts |  | 145.65 | 137.888 | 134.931 | 133.153 | 114.2822 | 338.7857 | 99.2123 | 269.2889 | 216.7685 | 219.5221 | 287.7213 | 223.921

## D3-1-2_Table 5a
Numbers may not add due to rounding. | [12 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 5a
Table 5a
Comparison of In-Service Capital Additions - Support Services ($M) 2020-2028
Line |  | 2020 | (c)-(a) | 2020 | 2021 | (f)-(d) | 2021 | 2022 | (i)-(g) | 2022 | 2023 | (l)-(j) | 2023
No. | Business Unit | OEB Approved | Change | Actual | OEB Approved | Change | Actual | OEB Approved | Change | Actual | OEB Approved | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | IT - Nuclear Rate Base | 3.7 | 17.981 | 21.681 | 2.2 | 37.714 | 39.914 | 36.94 | -10.332 | 26.608 | 34.84 | -11.706 | 23.134
2 | IT - Regulated Hydroelectric Rate Base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | IT - Renewable Generation Joint Use Assets | 0 | 12.91 | 12.91 | 0 | 6.06 | 6.06 | 0 | 1.984 | 1.984 | 0 | 2.252 | 2.252
4 | IT - Asset Service Fee | 17 | 51.553 | 68.553 | 17 | 47.979 | 64.979 | 39.09 | 38.563 | 77.653 | 41.59 | 16.3026 | 57.8926
5 | Subtotal | 20.7 | 82.444 | 103.144 | 19.2 | 91.753 | 110.953 | 76.03 | 30.215 | 106.245 | 76.43 | 6.8486 | 83.2786
6 | Real Estate - Nuclear Rate Base | 1 | 11.511 | 12.511 | 1 | 20.286 | 21.286 | 31.3437 | -8.5167 | 22.827 | 3.15 | 32.748 | 35.898
7 | Real Estate - Asset Service Fee | 3 | 0.48 | 3.48 | 3 | -0.645 | 2.355 | 1 | 0.063 | 1.063 | 1 | 1.326 | 2.326
8 | Real Estate - Renewable Generation Joint Use Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Subtotal | 4 | 11.991 | 15.991 | 4 | 19.641 | 23.641 | 32.3437 | -8.4537 | 23.89 | 4.15 | 34.074 | 38.224
10 | Microsoft Enterprise Agreement1 | 0 | 22.926 | 22.926 | 0 | 0.144 | 0.144 | 0 | 0 | 0 | 23 | -22.9942 | 0.0058
11 | Clarington Corporate Campus2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Corporate Headquarters3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7014 | 7.7014
13 | Subtotal | 0 | 22.926 | 22.926 | 0 | 0.144 | 0.144 | 0 | 0 | 0 | 23 | -15.2928 | 7.7072
14 | Enterprise System Modernization Projects- ASF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | DNNP Operational Readiness Technology Projects- DNNP Asset Service Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Minor Fixed Assets | 1.2 | 2.389 | 3.589 | 1.2 | 1.95 | 3.15 | 3.2 | 1.596 | 4.796 | 3.2 | 0.749 | 3.949
19 | In-Service Capital Additions Before Adjustments | 25.9 | 119.75 | 145.65 | 24.4 | 113.488 | 137.888 | 111.5737 | 23.3573 | 134.931 | 106.78 | 26.3788 | 133.1588
20 | OEB/Settlement Adjustment4 | 0 | 0 | 0 | 0 | 0 | 0 | -3.4 | 3.4 | 0 | -1.9 | 1.9 | 0
21 | Total In-Service Capital Additions Including Adjustments | 25.9 | 119.75 | 145.65 | 24.4 | 113.488 | 137.888 | 108.1737 | 26.7573 | 134.931 | 104.88 | 28.2788 | 133.1588
Line |  | 2024 | (c)-(a) | 2024 | 2025 | (f)-(d) | 2025 | 2026 | (i)-(g) | 2026 | 2027 | (l)-(j) | 2028
No. | Business Unit | OEB Approved | Change | Actual | OEB Approved | Change | Budget | OEB Approved | Change | Budget | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
22 | IT - Nuclear Rate Base | 31.94 | -2.147 | 29.793 | 27.94 | -7.118 | 20.822 | 26.94 | -5.435 | 21.505 | 26.408 | -0.24912 | 26.1589
23 | IT - Regulated Hydroelectric Rate Base | 0 | 0.119 | 0.119 | 0 | 2.025 | 2.025 | 0 | 0.45 | 0.45 | 1.5 | 0 | 1.5
24 | IT - Renewable Generation Joint Use Assets | 0 | 0.739 | 0.739 | 0 | 4 | 4 | 0 | 1.4 | 1.4 | 1.1 | -1.1 | 0
25 | IT - Asset Service Fee | 39.89 | 9.712 | 49.602 | 45.89 | 60.55 | 106.44 | 46.89 | 2.7181 | 49.6081 | 66.1 | -12.4573 | 53.6427
26 | Subtotal | 71.83 | 8.423 | 80.253 | 73.83 | 59.457 | 133.287 | 73.83 | -0.86686 | 72.9631 | 95.108 | -13.8065 | 81.3015
27 | Real Estate - Nuclear Rate Base | 2.45 | 26.6492 | 29.0992 | 19.878 | -8.2369 | 11.6411 | 4 | 11.0492 | 15.0492 | 107.5099 | -71.5469 | 35.963
28 | Real Estate - Asset Service Fee | 1 | -0.52 | 0.48 | 1 | 3.735 | 4.735 | 0 | 0.2 | 0.2 | 27.6 | -26.2 | 1.4
29 | Real Estate - Renewable Generation Joint Use Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.071 | -30.071 | 0
30 | Subtotal | 3.45 | 26.1292 | 29.5792 | 20.878 | -4.5019 | 16.3761 | 4 | 11.2492 | 15.2492 | 165.1809 | -127.8179 | 37.363
31 | Microsoft Enterprise Agreement1 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | -23 | 0 | 0 | 0 | 0
32 | Clarington Corporate Campus2 | 197.5 | -197.5 | 0 | 2.5 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Corporate Headquarters3 | 0 | 0 | 0 | 0 | 183.1226 | 183.1226 | 0 | 0 | 0 | 0 | 0 | 0
34 | Subtotal | 197.5 | -197.5 | 0 | 2.5 | 180.6226 | 183.1226 | 23 | -23 | 0 | 0 | 0 | 0
35 | Enterprise System Modernization Projects- ASF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 89.104 | 89.104
38 | DNNP Operational Readiness Technology Projects- DNNP Asset Service Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Minor Fixed Assets | 3.2 | 1.25 | 4.45 | 3.2 | 2.8 | 6 | 3.2 | 3.8 | 7 | 9 | 0 | 9
40 | In-Service Capital Additions Before Adjustments | 275.98 | -161.6978 | 114.2822 | 100.408 | 238.3777 | 338.7857 | 104.03 | -4.8177 | 99.2123 | 269.2889 | -52.5203 | 216.7685
41 | OEB/Settlement Adjustment4 | -1.7 | 1.7 | 0 | -2.4 | 2.4 | 0 | -1.5 | 1.5 | 0 | 0 | 0 | 0
42 | Total In-Service Capital Additions Including Adjustments | 274.28 | -159.9978 | 114.2822 | 98.008 | 240.7777 | 338.7857 | 102.53 | -3.3177 | 99.2123 | 269.2889 | -52.5203 | 216.7685
Notes:
1 | Variance in 2023 and 2026 due to updated accounting treatment of these costs as OM&A (Ex. D3-1-1, s. 3.1.4).
2 | Corporate Headquarters includes the cost to acquire the building and associated renovation. The acquisition cost excludes costs associated with undeveloped land.
3 | For comparison with the Corporate Headquarters project, the "OEB Approved" column includes the Clarington Corporate Campus project in-service additions planned in EB-2020-0290. A deferral account for the Clarington Corporate Campus project was established in EB-2020-0290, and associated impacts were excluded from the EB-2020-0290 final payment amounts order.
4 | See EB-2020-0290, Ex. O, Tab 1, Sch. 1, Pg. 22 of 51, Table 14.

## D3-1-2_Table 5b
Numbers may not add due to rounding. | [10 empty] | Updated: 2026-05-21
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 5b
Table 5b
Comparison of In-Service Capital Additions - Support Services ($M) 2028-2031
Line |  | 2028 | (c)-(a) | 2029 | (e)-(c) | 2030 | (g)-(e) | 2031 | 2022-2026 | (j)-(h) | 2027-2031
No. | Business Unit | Plan | Change | Plan | Change | Plan | Change | Plan | Actuals & Budget | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j)
1 | IT - Nuclear Rate Base | 26.1589 | 8.2211 | 34.38 | -13.069 | 21.311 | -5.311 | 16 | 121.862 | 2.3959 | 124.2579
2 | IT - Regulated Hydroelectric Rate Base | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 2.594 | 4.906 | 7.5
3 | IT - Renewable Generation Joint Use Assets1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.075 | -0.975 | 1.1
4 | IT - Asset Service Fee | 53.6427 | -6.1767 | 47.4659 | -6.3659 | 41.1 | 5.173 | 46.273 | 341.1957 | -86.6142 | 254.5816
5 | Subtotal | 81.3015 | 2.0444 | 83.3459 | -19.4349 | 63.911 | -0.138 | 63.773 | 467.7267 | -80.2873 | 387.4394
6 | Real Estate - Nuclear Rate Base | 35.963 | -3.2195 | 32.7435 | 17.349 | 50.0925 | -26.3865 | 23.706 | 114.5145 | 135.5004 | 250.0149
7 | Real Estate - Asset Service Fee | 1.4 | 3 | 4.4 | -4 | 0.4 | 0 | 0.4 | 8.804 | 25.396 | 34.2
8 | Real Estate - Renewable Generation Joint Use Assets1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.071 | 30.071
9 | Subtotal | 37.363 | -0.2195 | 37.1435 | 13.349 | 50.4925 | -26.3865 | 24.106 | 123.3185 | 190.9674 | 314.2859
10 | Microsoft Enterprise Agreement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0058 | -0.0058 | 0
11 | Clarington Corporate Campus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Corporate Headquarters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.824 | -190.824 | 0
13 | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.8298 | -190.8298 | 0
14 | Enterprise System Modernization Projects- ASF | 89.104 | 0.92874 | 90.0327 | -58.3434 | 31.6894 | 88.8256 | 120.515 | 4 | 327.3411 | 331.3411
17 | DNNP Operational Readiness Technology Projects- DNNP Asset Service Fee | 0 | 0 | 0 | 132.6284 | 132.6284 | -126.1014 | 6.527 | 0 | 139.1554 | 139.1554
18 | Minor Fixed Assets | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 26.195 | 18.805 | 45
19 | In-Service Capital Additions Before Adjustments | 216.7685 | 2.7536 | 219.5221 | 68.1992 | 287.7213 | -63.8003 | 223.921 | 812.07 | 405.1518 | 1217.2219
20 | OEB/Settlement Adjustments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Total In-Service Capital Additions Including Adjustments | 216.7685 | 2.7536 | 219.5221 | 68.1992 | 287.7213 | -63.8003 | 223.921 | 812.07 | 405.1518 | 1217.2219
Notes:
1 | A 5-year average of the 2022-2026 actuals and budget in-service additions is used as a comparison to the 2027 plan amounts for Renewable Generation Joint Use Assets.

## D3-1-2_Table 6
Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 6
Table 6
Capital Project Listing - Support Services
Portfolio Projects (Unallocated)1
Potential
Line |  |  | Start
No. | Project Name | Category | Date
| (a) | (b) | (c)
Projects With Potential Cost >$10M and < $30M
1 | 89331 - Energy Markets - Technology Rationalization | Sustaining | 2026
2 | 89635 - SC DNNP Enterprise Resource Planning | Sustaining | 2025
Projects With Potential Cost ≥ $30M
3 | 87768 - Enterprise Asset Management | Sustaining | 2026
4 | 89629 - Supply Chain Enterprise Resource Planning | Sustaining | 2026
Notes:
1 | Projects with potential capital expenditures during IR term with an estimated total project cost of $10M or greater.

## D3-1-2_Table 7
Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 7
Table 7
Capital Projects - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Listing of Business Case Summaries Filed
|  |  | BCS |  |  | BCS
Line | Project |  | Approval |  | BCS | Status in
No. | Number | Business Case Summary (BCS) Title | Date | Project Stage | Status | EB-2020-0290
| (a) | (b) | (c) | (d) | (e) | (f)
1 | 84975 | Asset Suite 9 Upgrade | 2021-05-04 | Completed | Complete | n/a
2 | 87188 | DNNP Enterprise Asset Management | 2025-04-30 | Execution | Execution | n/a
3 | 83746 | Integrated HR Service Delivery | 2025-05-09 | Execution | Execution | n/a
4 | 89273 | Finance ERP Solution | 2025-10-01 | Planning | Development | n/a
5 | 87413 | Corporate Headquarters Renovation | 2024-07-11 | Execution | Execution | n/a
6 | 87414 1 | Corporate Headquarters Acquisition | 2023-01-20 | Complete | Complete | n/a
7 | 90092 | Security Project D | n/a | n/a | n/a | n/a
Notes:
1 | BCS does not reflect a project number as it was not assigned at the time of BCS drafting due to confidentiality. Project numbers were assigned in no particular order.

## D3-1-2_Table 8
Filed: 2025-12-12
EB-2025-0297
Exhibit D3
Tab 1
Schedule 2
Table 8
Table 8
Capital Projects - Support Services
(Capital Projects Impacting Rate Base or IR Term Asset Service Fees)
Status of Projects > $10M with 2020-2026 Final In-Service Dates in EB-2020-0290
|  |  | In-Service Date | Project Stage
|  |  | at Time of | at Time of | Current Project Status
Line | Project |  | EB-2020-0290 | EB-2020-0290 | Project | Projected/Actual
No. | Number | Project Name | Application | Application | Status | In-Service Date
| (a) | (b) | (c) | (d) | (e) | (f)
1 | 84975 | Asset Suite Upgrade | 2022-12-01 | Ongoing | Completed | 2023-12-01
2 | 82856 | Tempus Lifecycle Upgrade | 2020-12-01 | Closeout | Completed | 2020-12-01
3 | 82134 | Network Segmentation - Campus Switch Replacement Project | 2023-06-01 | Execution | Completed | 2023-12-01
4 | 84397 | Reimagine Program | 2020-04-01 | Execution | Completed | 2021-04-01
5 | 86070 | Reimagine Program 2.0 | 2022-06-01 | Planning | Completed | 2023-06-01
6 | 86018 | Microsoft Enterprise Agreement (EA) | 2020-12-01 | Execution | Completed | 2021-03-01
7 | 84230 | Pickering Communication System Improvement Wi-Fi | 2023-12-01 | Execution | Completed | 2024-12-01
8 | 82924, 83690, 83692, 83800 | Cyber Security - CSA N290.7 Compliance1 | 2020-12-01 | Closeout | Completed | 2020-12-01
9 | 84772 | Energy Market Application Refresh Program | 2023-12-01 | Ongoing | Ongoing | 2025-12-01
10 | 83746 | Integrated HR Service Delivery2 | 2025-12-01 | Execution | Completed | 2025-12-01
11 | 84696 | Workplace Transformation of Darlington Energy Center 2nd Floor | 2025-12-01 | Planning | Ongoing | 2027-12-01
Notes:
1 | Satisfaction of the CSA N290.7 cyber security standards is an ongoing compliance program comprised of nine distinct projects to address discrete requirements. The applicable projects of this program are provided on this table.
2 | Integrated HR Service Delivery combines SAP Payroll and HR System Replacement that were listed as separate projects in EB-2020-0290. Final in-service date used is the latter of the 2 replaced projects.