## HE Capital
D1-AMPCO-14 | [27 empty] | Updated: 2026-05-21
EB-2025-0297
Ref: D1-1-2 table 2, Table 2b | [27 empty] | Exhibit L-D1-AMPCO-014
Attachment 1
Capital Project Listing - Regulated Hydroelectric
Projects $10M - $30M Total Project Cost (Allocated)
Drivers of Variance to First Execution BCS
Line No. | Region | Facility | Project Name | Project Number | Category | Start Date | Final In-Service Date | Total Project Cost ($M) | Cost at First Execution BCS ($M) | Final In-Service Date at Execution BCS | Total In-Service ($M) | In-Service LTD ($M) | In-Service IR Term | In-Service 2025 | In-Service 2026 | SPI = EV/PV | Schedule Variance (SV) = EV-PV (hours) | Schedule Variance (SV) = EV-PV ($M) | CPI = EV/AC | Cost Variance = EV-AC | Cost Varinace to Execution BCS ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | Eastern | Matabitchuan | Replace Penstocks & Saddles | 80703 | Sustaining | 2009-12-11 | 2013-01-14 | 20.2 | 22 | 2012-12-01 | 17.8996 | 17.8996 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -1.8 | n/a | n/a | n/a | n/a | n/a | n/a
2 | Eastern | Otto Holden | Otto Holden GS - Replace Sluicegates & Rehabilitate Sluicegates System | 80717 | Sustaining | 2006-05-25 | 2015-11-04 | 22.05 | 23.8 | 2015-11-15 | 20.943 | 20.943 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -1.75 | n/a | n/a | n/a | n/a | n/a | n/a
3 | Niagara | Sir Adam Beck 2 | Sir Adam Beck II GS - Station Service Upgrades | 80666 | Sustaining | 2011-03-31 | 2019-04-29 | 14.12 | 9.261 | 2017-09-30 | 13.749 | 13.749 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 4.859 | -0.3 | 0.64527 | 5.065 | -0.857 | 0.63215 | -0.32784 | Others: Procurement
4 | Eastern | R.H. Saunders | R.H. Saunders GS - Replace Station Service Breakers | 80637 | Sustaining | 2012-02-15 | 2018-12-03 | 16.74 | 16.8 | 2017-12-31 | 16.6736 | 16.6736 | 0 | 0 | 0 | 0.95 | n/a | -0.776 | 1.02 | 0.352 | -0.06 | n/a | n/a | n/a | n/a | n/a | n/a
5 | Eastern | R.H. Saunders | R.H Saunders GS - Replace Powerhouse Crane | 80635 | Sustaining | 2008-08-26 | 2015-06-12 | 15.065 | 15.7 | 2014-11-30 | 14.0294 | 14.0294 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -0.635 | n/a | n/a | n/a | n/a | n/a | n/a
6 | Eastern | Lower Notch | Lower Notch GS - Unit G2 Capital Upgrades | 80694 | Sustaining (Refurbishment) | 2012-09-13 | 2018-06-01 | 15.47 | 13.7 | 2016-01-22 | 14.8859 | 14.8859 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 1.77 | n/a | n/a | n/a | n/a | n/a | n/a | The data is too old to provide a meaningful comparison, and the cost information from the first BCS execution was not broken down into the requested categories.
7 | Eastern | Lower Notch | Lower Notch GS - G1 Capital Upgrade | 80692 | Sustaining (Refurbishment) | 2011-11-22 | 2016-09-24 | 17.47 | 14.2 | 2015-01-23 | 16.8846 | 16.8846 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 3.27 | n/a | n/a | n/a | n/a | n/a | n/a | The data is too old to provide a meaningful comparison, and the cost information from the first BCS execution was not broken down into the requested categories.
8 | Eastern | Des Joachims | Des Joachims GS - Rewind Generators G1, G3, G5 | 80604 | Sustaining (Refurbishment) | 2010-09-07 | 2015-05-08 | 10.738 | 8.5 | 2015-03-30 | 10.4489 | 10.4489 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 2.238 | 0.099 | -0.015 | 8.023 | -1.368 | 0.041 | -4.625 | Others: Procurement
9 | Eastern | Chenaux | Chenaux GS - Replace Protections and Controls | 80596 | Sustaining | 2008-08-29 | 2019-11-25 | 14.241 | 13.5 | 2016-06-30 | 13.9802 | 13.9802 | 0 | 0 | 0 | 1 | n/a | 0 | 0.94 | -0.759 | 0.741 | n/a | n/a | n/a | n/a | n/a | n/a
10 | Western | Caribou Falls | Caribou Block Dam #2 Rehab | 83029 | Regulatory | 2016-03-14 | 2019-10-30 | 24.649 | 24.1 | 2019-12-01 | 24.6488 | 24.6488 | 0 | 0 | 0 | 1 | n/a | -0.1 | 1.02 | 0.4 | 0.549 | n/a | n/a | n/a | n/a | n/a | n/a
11 | Western | Manitou Falls | Sluicegate Replacement | 82940 | Sustaining | 2018-04-23 | 2021-09-15 | 25.448 | 24 | 2020-10-01 | 24.2999 | 23.5999 | 0 | 0.7 | 0 | n/a | n/a | n/a | n/a | n/a | 1.448 | n/a | n/a | n/a | n/a | n/a | n/a
12 | Western | Silver Falls | SLV G1 Rewind and New Core | 82385 | Sustaining (Refurbishment) | 2018-01-22 | 2022-12-05 | 21.434 | 16.78 | 2020-12-01 | 20.327 | 20.327 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 4.654 | 0.75 | 0.36 | 2.4 | -1.44 | 0.97 | 1.61 | Others: Procurement
13 | Western | Aguasabon | Surge Tank Replacement | 83610 | Sustaining | 2018-01-22 | 2023-08-31 | 26.36 | 26.25 | 2020-12-01 | 24.5405 | 24.5405 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0.11 | n/a | n/a | n/a | n/a | n/a | n/a
14 | Western | Whitedog Falls | WHD Sluicegate Replacement | 83031 | Sustaining | 2017-02-27 | 2021-12-03 | 16.88 | 16.2 | 2019-09-30 | 14.9417 | 14.9417 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0.68 | n/a | n/a | n/a | n/a | n/a | n/a
15 | Eastern | Des Joachims | DEJ - Controls - Repl. Generator Controls | 83353 | Sustaining | 2016-11-04 | 2022-06-17 | 13.125 | 14.28 | 2022-01-31 | 12.1987 | 12.1987 | 0 | 0 | 0 | 1 | n/a | -0.057 | 0.91 | -1.125 | -1.155 | n/a | n/a | n/a | n/a | n/a | n/a
16 | Eastern | Otto Holden | OTO - Capital Project Scope G7 1st Unit | 84385 | Sustaining (Refurbishment) | 2019-09-18 | 2022-09-21 | 12.459 | 7.811 | 2021-05-30 | 12.2751 | 12.2751 | 0 | 0 | 0 | 0.96 | n/a | -0.57 | 1.03 | 0.338 | 4.648 | n/a | n/a | n/a | n/a | n/a | n/a
17 | Eastern | Otter Rapids | OTR -T2/T1 Transformer Replacement | 82255 | Sustaining | 2017-03-13 | 2020-08-28 | 12.68 | 14.1 | 2019-09-30 | 11.9465 | 11.9465 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | -1.42 | n/a | n/a | n/a | n/a | n/a | n/a
18 | Western | Pine Portage | PIN Sluicegate Replacement | 82802 | Sustaining | 2016-03-14 | 2021-10-29 | 13.07 | 9.667 | 2017-10-01 | 11.8842 | 11.8842 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 3.403 | 0.09 | 0.23 | 4.22 | -1.18 | 0.01 | -
19 | Western | Whitedog Falls | WHD Sluicegate Repl. - Dogged #1-#4- #5-#6 | 84446 | Sustaining | 2019-08-12 | 2021-10-16 | 12.77 | 12.8 | 2021-12-01 | 11.4578 | 11.4578 | 0 | 0 | 0 | 1 | n/a | 0 | 0.98 | -0.2 | -0.03 | n/a | n/a | n/a | n/a | n/a | n/a
20 | Western | Caribou Falls | Sluicegate Replacement | 82799 | Sustaining | 2018-04-23 | 2023-10-20 | 17.25 | 16.6 | 2020-12-01 | 16.0286 | 15.9286 | 0 | 0.1 | 0 | n/a | n/a | n/a | n/a | n/a | 0.65 | n/a | n/a | n/a | n/a | n/a | n/a
21 | Eastern | R.H. Saunders | SAU - Headwork Crane Replacement | 83111 | Sustaining | 2016-04-28 | 2022-12-03 | 10.85 | 6.78 | 2019-10-15 | 10.7539 | 10.3539 | 0 | 0.4 | 0 | 0.97 | n/a | -0.314 | 0.98 | -0.218 | 4.07 | 0.087 | 0.476 | 4.449 | -0.615 | -0.199 | -0.041
22 | Eastern | Des Joachims | Replace Generator Breakers and Station Service Brks. | 80602 | Sustaining | 2011-11-30 | 2020-12-14 | 16.5 | 9.4 | 2015-12-30 | 15.8835 | 15.8835 | 0 | 0 | 0 | 1 | n/a | 0 | 1 | -0.084 | 7.1 | 1.12 | 1.42 | 3.655 | -1.76 | -0.265 | 5.4102 | Others: Procurement
23 | Eastern | Barrett Chute | Rewind Generators & Reinsulate Field Poles (G1-4) First Unit (G3) | 80980 | Sustaining (Refurbishment) | 2016-05-10 | 2023-11-30 | 13.682 | 13.7 | 2021-02-28 | 13.5935 | 13.5935 | 0 | 0 | 0 | 1 | n/a | 0 | 1 | -0.05 | -0.018 | n/a | n/a | n/a | n/a | n/a | n/a
24 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1-4) Second Unit (G4) | 84587 | Sustaining (Refurbishment) | 2019-07-12 | 2023-11-30 | 11.878 | 11.7 | 2023-03-31 | 11.7881 | 11.7881 | 0 | 0 | 0 | 1 | n/a | 0 | 1.06 | 0.736 | 0.178 | n/a | n/a | n/a | n/a | n/a | n/a
25 | Eastern | Barrett Chute | Capital Refurb Rewind Generators & Reinsulate Field Poles (G1) | 86082 | Sustaining (Refurbishment) | 2022-05-18 | 2024-05-24 | 11.455 | 11.4 | 2024-05-30 | 11.2825 | 10.5825 | 0 | 0.7 | 0 | 1 | n/a | -4 | 0.9 | -1.12 | 0.055 | n/a | n/a | n/a | n/a | n/a | n/a
26 | Eastern | Otter Rapids | Otter Runner Purchase | 80684 | Value Enhancing (Refurbishment) | 2010-04-10 | 2029-11-28 | 17.9 | 16.5 | 2025-09-30 | 17.6 | 0 | 13.2 | 4.4 | 0 | n/a | n/a | n/a | n/a | n/a | 1.4 | n/a | n/a | n/a | n/a | n/a | n/a
27 | Eastern | Otter Rapids | Otter Sluice Gate Upgrades | 82246 | Sustaining | 2019-03-19 | 2024-12-18 | 23.9 | 23.9 | 2024-11-01 | 23.4837 | 22.1837 | 0 | 1.3 | 0 | 0.98 | n/a | -0.5 | 1.01 | 0.2 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
28 | Eastern | Abitibi Canyon | Abitibi - Transformer Deck Roof Replacement | 82257 | Sustaining | 2019-02-09 | 2024-12-09 | 26.685 | 26.7 | 2024-11-01 | 22.643 | 21.643 | 0 | 1 | 0 | 0.92 | n/a | 0 | 0.92 | -2.1 | -0.015 | n/a | n/a | n/a | n/a | n/a | n/a
29 | Eastern | Stewartville | Replace AC Station Service Transformers, Switchgear and Distribution Panels | 83763 | Sustaining | 2018-06-25 | 2023-12-01 | 12.3 | 4.266 | 2023-11-30 | 11.9142 | 11.9142 | 0 | 0 | 0 | 0.98 | n/a | -0.23 | 0.93 | -0.792 | 8.034 | 1.71 | 0.98 | 4.81 | -0.1 | -0.08 | 0.9
30 | Eastern | Elliott Chute | Elliott - Service Gate and Gains Upgrade | 84534 | Sustaining | 2021-02-04 | 2024-11-13 | 13.187 | 9 | 2023-10-01 | 11.8878 | 11.5878 | 0 | 0.3 | 0 | 0.99 | n/a | 0.8 | 1.04 | 0.5 | 4.187 | 0.16 | 0.37 | 4.08 | -0.52 | 0 | 0.09 | Others: Procurement, Commissioning, Closeout
31 | Eastern | R.H. Saunders | Replacement of Excitation System All 16 Units | 82986 | Sustaining | 2016-07-06 | 2026-12-31 | 17.17 | 17.1 | 2026-12-31 | 15.0501 | 14.2501 | 0 | 0 | 0.8 | 1 | n/a | 49 | 0.95 | -0.741 | 0.07 | n/a | n/a | n/a | n/a | n/a | n/a
32 | Eastern | R.H. Saunders | Install Concrete Plug in Ice Sluice Drum Gate Openings | 84202 | Sustaining | 2017-03-28 | 2026-12-19 | 22.6 | 16.678 | 2024-11-29 | 22.5502 | 18.1502 | 0 | 0.8 | 3.6 | 0.96 | n/a | -0.902 | 0.96 | -0.831 | 5.922 | 0.573 | 0.188 | 4.939 | -0.377 | 0.227 | 0.367 | Others: Bill 124 Costs
33 | Niagara | DeCew Falls 2 | G1 Runner Shaft Replacement | 84558 | Sustaining (Refurbishment) | 2020-08-04 | 2024-11-29 | 19.5 | 17.716 | 2024-11-30 | 17.398 | 17.398 | 0 | 0 | 0 | 1 | -8.5605 | n/a | 0.9 | -1.96 | 1.784 | 0.591 | -0.032 | 0.63647 | -1.292 | -0.031 | 1.9365 | Others: Procurement, Commissioning, Closeout
34 | Niagara | Sir Adam Beck 1 | BK1 Tailrace Deck | 86053 | Sustaining | 2020-11-20 | 2025-05-14 | 18.93 | 20.5 | 2024-09-03 | 17.3882 | 17.0742 | 0 | 0.314 | 0 | n/a | n/a | n/a | n/a | n/a | -1.57 | n/a | n/a | n/a | n/a | n/a | n/a
35 | Niagara | Sir Adam Beck 2 | SAB2 Headgate Replt. | 86376 | Sustaining | 2021-03-18 | 2024-09-30 | 23.3 | 27.8 | 2024-12-12 | 22.9821 | 22.9821 | 0 | 0 | 0 | 1 | 0 | n/a | 0.97 | -0.74 | -4.5 | n/a | n/a | n/a | n/a | n/a | n/a
36 | Niagara | Sir Adam Beck 2 | SAB2 Rock Cliff Conc. Rehab | 86491 | Sustaining | 2021-07-06 | 2024-12-09 | 22.84 | 10.8 | 2024-06-06 | 20.9522 | 18.5522 | 0 | 2.4 | 0 | 0.97 | n/a | -0.73464 | 0.94 | -1.3967 | 12.04 | 0.162 | 0.023 | 14.333 | -2.358 | -0.173 | 0.06 | Others: Prourement, Closeout
37 | Niagara | Sir Adam Beck 2 | Battery Banks and DC System Upgrade | 80812 | Sustaining | 2018-07-27 | 2024-02-27 | 13.5 | 2.6 | 2019-12-13 | 11.4708 | 11.4708 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 10.9 | 1.687 | 0.29 | 7.68 | 0.359 | 0.738 | 0.098 | Others: Procurement, Closeout, Commissioning
38 | Western | Alexander | Stn. Switchgear, Protections & Ctrls. Repl. | 82378 | Sustaining | 2018-11-23 | 2023-12-01 | 27.5 | 14.9 | 2022-09-16 | 26.2176 | 25.1176 | 0 | 1.1 | 0 | 1 | -495.792 | n/a | 1 | -0.1 | 12.6 | 0.73 | 0.62 | 8.18 | -0.97 | 0.29 | 3.73 | Others: Procurement, Bill 124 Costs
39 | Western | Cameron Falls | T1 & T2 Replacement | 82390 | Sustaining | 2020-02-05 | 2025-02-24 | 25.05 | 19.5 | 2024-06-01 | 24.063 | 17.063 | 0 | 7 | 0 | 1 | -745.0354 | n/a | 0.98 | -0.6 | 5.55 | 0.95 | 1.12 | 5.05 | -2.61 | -0.03 | 1.07 | Others: Procurement
40 | Niagara | Sir Adam Beck 2 | BK2 Penstock Concrete Restoration | 87951 | Sustaining | 2024-06-14 | 2026-08-25 | 24.7 | 24.7 | 2026-05-05 | 24.6 | 0 | 0 | 15.6 | 9 | 0.98 | n/a | -0.32 | 1 | -0.0076 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
41 | Western | Caribou Falls | CAF 120/208V & Lighting Upgrade | 84432 | Sustaining | 2021-09-15 | 2024-01-23 | 10.225 | 10.22 | 2023-12-01 | 9.8039 | 9.4039 | 0 | 0.4 | 0 | 1 | n/a | 0 | 0.93 | -0.7 | 0.005 | n/a | n/a | n/a | n/a | n/a | n/a
42 | Eastern | R.H. Saunders | SAU - Concrete Rehabilitation | 89543 | Sustaining | 2024-12-17 | 2026-10-01 | 16.55 | 16.54 | 2026-10-15 | 13.006 | 5.206 | 0 | 7 | 0.8 | 0.96 | n/a | -0.45 | 1.02 | 0.206 | 0.01 | n/a | n/a | n/a | n/a | n/a | n/a
43 | Eastern | Bingham Chute | Bingham Chute GS Redevelopment | 86385 | Value Enhancing (Redevelopment) | 2021-06-24 | 2027-04-15 | 24 | n/a | n/a | 24 | 0 | 0.5 | 0 | 23.5 | 0.96054 | -996 | n/a | 0.973 | -0.14461 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
44 | Eastern | Crystal Falls | Crystal Falls Elect./Controls Upgrade | 82261 | Sustaining | 2020-11-10 | 2026-11-12 | 20.8 | n/a | n/a | 16.2 | 0 | 0 | 0 | 16.2 | 0.36 | n/a | -3.3 | 0.89 | -0.2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
45 | Eastern | Stewartville | STW - G5 Cap. Refurb. - Rwnd Gen. & Reinsul. | 82351 | Sustaining (Refurbishment) | 2024-10-10 | 2027-05-31 | 19.14 | n/a | n/a | 17.1 | 0 | 17.1 | 0 | 0 | 0.9 | n/a | -0.316 | 1.12 | 0.311 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
46 | Eastern | Otto Holden | OTO - New Turbine Runners | 83356 | Value Enhancing (Refurbishment) | 2017-01-30 | 2030-04-30 | 15.54 | 15.5 | 2029-09-30 | 15.36 | 0 | 15.36 | 0 | 0 | 0.7 | n/a | -1.45 | 0.96 | -0.135 | 0.04 | n/a | n/a | n/a | n/a | n/a | n/a
47 | Eastern | R.H. Saunders | SAU - Headgate Control Replacement | 86220 | Sustaining | 2023-11-27 | 2030-12-19 | 19.03 | n/a | n/a | 15.642 | 1.5121 | 11.4 | 0.82987 | 1.9 | 0.95 | n/a | -0.151 | 1.05 | 0.133 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
48 | Eastern | Coniston | Wanapitei Civil Upgrades | 86310 | Sustaining | 2021-12-21 | 2026-11-27 | 29.1 | n/a | n/a | 22.4 | 0 | 0 | 4.1 | 18.3 | 0.96 | n/a | -0.6 | 1.01 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
49 | Eastern | R.H. Saunders | SAU - Long Sault Dam Superstructure Automation (JW) (NYPA) | 87140 | Regulatory | 2023-03-01 | 2029-12-31 | 19.06 | n/a | n/a | 15.8 | 0 | 15.8 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
50 | Eastern | R.H. Saunders | SAU - 13.8KV Underground Feeder Eval. (JW) (NYPA) | 87141 | Regulatory | 2023-03-01 | 2025-12-31 | 20.8 | n/a | n/a | 17.5 | 0 | 17.5 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
51 | Eastern | Otto Holden | OTO - G1 Refurb - Turbine & Generator | 87545 | Sustaining (Refurbishment) | 2025-01-30 | 2027-04-30 | 13.3 | n/a | n/a | 12.03 | 0 | 12.03 | 0 | 0 | 0.99 | n/a | -0.014 | 1 | -0.004 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
52 | Eastern | Abitibi Canyon | ABI - Powerhouse Crane Refurb / Replace | 89078 | Sustaining | 2024-12-12 | 2028-05-15 | 20.5 | n/a | n/a | 17.2 | 0 | 17.2 | 0 | 0 | 1.03 | n/a | 0.073 | 1 | 0.2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
53 | Eastern | Abitibi Canyon | ABI - Unloading Crane Refurb/Replacement | 89079 | Sustaining | 2024-11-29 | 2028-01-30 | 15.26 | n/a | n/a | 12.8 | 0 | 12.8 | 0 | 0 | 0.13 | n/a | 0.6 | 0.76 | -0.026 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
54 | Western | Silver Falls | SLV Electrical Infrastructure Replacement | 82005 | Sustaining | 2021-03-18 | 2028-10-18 | 18.7631 | n/a | n/a | 18.67 | 0 | 18.67 | 0 | 0 | 0.91 | n/a | -0.26998 | 0.89 | -0.32712 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
55 | Western | Caribou Falls | CAF Electrical Infrastructure Replacement | 84430 | Sustaining | 2021-03-18 | 2027-12-03 | 23.4821 | n/a | n/a | 22.83 | 0 | 22.83 | 0 | 0 | 0.39 | n/a | -5.9466 | 1 | 0.94171 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
56 | Western | Manitou Falls | MOT T1 Replacement | 84436 | Sustaining | 2022-04-27 | 2027-02-24 | 12.6 | n/a | n/a | 10.72 | 0 | 10.72 | 0 | 0 | 0.93 | n/a | -1.8349 | 1.06 | 0.43096 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
57 | Western | Whitedog Falls | WHD Electrical Infrastructure Replacement | 84448 | Sustaining | 2021-03-18 | 2028-10-13 | 23.6306 | n/a | n/a | 22.68 | 0 | 22.68 | 0 | 0 | 1 | n/a | 0 | 0.98 | -0.2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
58 | Western | Pine Portage | Black Sturgeon Dam | 86369 | Sustaining | 2021-02-15 | 2031-12-15 | 17.1353 | n/a | n/a | 16.28 | 0 | 16.28 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
59 | Western | Aguasabon | G2 Rewind & Core Replacement | 86383 | Sustaining (Refurbishment) | 2021-08-09 | 2025-10-10 | 17.521 | 17.52 | 2025-10-01 | 16.6 | 0 | 0 | 16.6 | 0 | 0.97 | -3855.4881 | n/a | 1 | 0 | 0.001 | n/a | n/a | n/a | n/a | n/a | n/a
60 | Western | Cameron Falls | CAM - Block Dam 3-4 Life Extension | 89000 | Sustaining | 2025-06-12 | 2027-12-12 | 15.4239 | n/a | 2026-01-01 | 14.6 | 0 | 9.6 | 5 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
61 | Niagara | Sir Adam Beck 2 | SAB OH Site Prep and Facility Rehab | 86379 | Sustaining | 2021-08-31 | 2026-02-27 | 17.68 | 17.677 | 2026-02-27 | 15.7 | 0 | 0 | 15.7 | 0 | 0.98 | n/a | -0.37 | 1.22 | 3.13 | 0.003 | n/a | n/a | n/a | n/a | n/a | n/a
62 | Niagara | Sir Adam Beck 2 | BK2 Phse. Cranes Replacement | 89025 | Sustaining | 2025-01-13 | 2031-01-07 | 14.712 | n/a | n/a | 14.45 | 0 | 14.45 | 0 | 0 | 0.92 | n/a | -0.011015 | 0.53 | -0.11 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
63 | Eastern | Arnprior | ARN - Repl. AC Stn. Serv. Switchgear & Brkrs. | 80951 | Sustaining | 2022-07-14 | 2025-09-25 | 14.32 | 4.4 | 2024-04-30 | 13.7615 | 8.3615 | 0 | 5.4 | 0 | 0.97 | n/a | -0.434 | 0.95 | -0.66 | 9.92 | 1.62 | 0.96 | 7.43 | -0.18 | 0.03 | 0
64 | Niagara | Sir Adam Beck Pump GS | Hatchcover and Drive System | 82210 | Sustaining | 2024-04-11 | 2026-02-19 | 11.79 | 8.119 | 2023-10-20 | 11.1974 | 4.8974 | 0 | 5 | 1.3 | 1 | n/a | -0.036 | 1 | 0.013 | 3.671 | 0.45 | 0.41 | 0.32 | -0.18 | 0.28 | 2.4 | Others: Procurement, Closeout
65 | Eastern | Mountain Chute | MTN - Repl. AC Sta. Serv. Trnsfrmrs Switch | 82987 | Sustaining | 2022-07-14 | 2028-03-30 | 11.7 | 5.291 | 2022-06-30 | 10.6 | 0 | 3.3 | 0 | 7.3 | 0.78 | n/a | -1.484 | 0.69 | -2.365 | 6.409 | 1.3 | 0.4 | 3.5 | 1 | 0.2 | n/a
66 | Eastern | Abitibi Canyon | Abitibi - Breaker Roof Replt. | 83153 | Sustaining | 2023-03-20 | 2026-11-07 | 10.8 | 10.8 | 2025-01-08 | 8.5 | 0 | 0 | 0.5 | 8 | n/a | n/a | n/a | n/a | n/a | 0 | n/a | n/a | n/a | n/a | n/a | n/a
67 | Western | Cameron Falls | CAM G7 Capital Refurb | 83257 | Sustaining (Refurbishment) | 2019-08-12 | 2026-12-08 | 29.4 | n/a | n/a | 25.3 | 0 | 0 | 0 | 25.3 | 1.06 | n/a | 0.8 | 0.97 | -0.4 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
68 | Eastern | R.H. Saunders | SAU - Repl. Iroquois Dam 2 Cranes (JW) (OPG) | 86586 | Sustaining | 2024-05-07 | 2028-12-21 | 20.1 | n/a | n/a | 17 | 0 | 8.5 | 0 | 8.5 | 1.08 | n/a | 0.14 | 0.96 | -0.09 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
69 | Eastern | Barrett Chute | BAR - G2 Cap. Rfrb; Rwnd Gen. Reins. Fld. Pls. | 86077 | Sustaining (Refurbishment) | 2020-07-17 | 2025-04-07 | 10.475 | 10.3 | 2025-04-01 | 10.5 | 0 | 0 | 10.5 | 0 | 0.99 | n/a | -0.069 | 0.97 | -0.352 | 0.175 | n/a | n/a | n/a | n/a | n/a | n/a
70 | Eastern | Chenaux | CHE - PH Cranes 2 - Cntrls & Cndctr Upgrade | 86200 | Sustaining | 2021-12-20 | 2025-09-04 | 11.053 | 11.05 | 2025-07-04 | 8.5 | 0 | 0 | 8.5 | 0 | 0.99 | n/a | -0.116 | 0.94 | -0.508 | 0.003 | n/a | n/a | n/a | n/a | n/a | n/a
71 | Niagara | Sir Adam Beck 2 | SAB2 N and S Phse Cranes | 86438 | Sustaining | 2020-09-25 | 2025-08-29 | 10.544 | 6.56 | 2022-12-12 | 8.9408 | 8.4408 | 0 | 0.5 | 0 | 1.02 | n/a | 0.27 | 1.16 | 1.64 | 3.984 | 0.96555 | 0.50945 | 2.2497 | -1.012 | 0.113 | 1.1595 | Others: Procurement, Commissioning, Closeout & Inspection
72 | Eastern | Otto Holden | OTO - G8 Refurb - Turbine & Generator | 86477 | Sustaining (Refurbishment) | 2023-02-22 | 2025-04-11 | 13.6 | 9.98 | 2024-06-21 | 12.1 | 0 | 0 | 12.1 | 0 | 1 | n/a | -0.024 | 0.73 | -3.228 | 3.62 | 1.459 | 0.287 | 0.35305 | -1.082 | 0.633 | 2.143 | Others: Procurement
73 | Eastern | Otto Holden | OTO - G6 Refurb - Turbine & Generator | 86478 | Sustaining (Refurbishment) | 2024-02-07 | 2026-05-29 | 10.742 | 10.742 | 2026-05-29 | 10 | 0 | 0 | 0 | 10 | 0.98 | n/a | -0.165 | 0.6 | -4.366 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
74 | Western | Caribou Falls | CAF Block Dam 4 Rehabilitation | 86602 | Sustaining | 2021-07-28 | 2024-10-23 | 10.395 | 7.95 | 2023-11-01 | 10.0916 | 9.1916 | 0 | 0.9 | 0 | 0.99 | n/a | -0.1 | 1.02 | 0.2 | 2.445 | 0.26 | -0.26 | 2.45 | -0.05 | 0.03 | 0.01
75 | Eastern | Stewartville | STW - Access Rd and Bank Stabilization | 89572 | Sustaining | 2025-03-26 | 2026-06-26 | 10.68 | 10.6 | 2026-06-26 | 7.7 | 0 | 0 | 6.8 | 0.9 | 1 | n/a | 1 | 0.93 | -0.615 | 0.08 | n/a | n/a | n/a | n/a | n/a | n/a
76 | Eastern | Arnprior | ARN - Replace T1 Main Output Transformer | 87513 | Sustaining | 2024-12-16 | 2029-10-16 | 11.95 | n/a | n/a | 10 | 0 | 10 | 0 | 0 | 0.31 | n/a | -0.473 | 0.99 | -1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
77 | Niagara | Sir Adam Beck Pump GS | BKP Headworks Crane Replacement | 86920 | Sustaining | 2023-12-19 | 2027-10-22 | 19.6 | n/a | n/a | 16.8 | 0 | 16.8 | 0 | 0 | 1.03 | n/a | 0.17 | 1.09 | 0.47 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
78 | Eastern | Des Joachims | DEJ - Headpond and Tailrace Booms | 86204 | Regulatory | 2022-08-08 | 2028-09-30 | 10.8 | n/a | n/a | 5 | 0 | 5 | 0 | 0 | 0.98 | n/a | -0.015 | 1 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
79 | Niagara | Sir Adam Beck 2 | BK2 Hoist Refurbishment G11-18 | 84568 | Sustaining | 2020-09-23 | 2036-09-29 | 17.7 | n/a | n/a | 17.7 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
80 | Eastern | R.H. Saunders | Runner Replacement | 83104 | Value Enhancing (Refurbishment) | 2016-08-22 | 2028-03-31 | 17.9 | 35.2 | 2023-08-20 | 16.1 | 0 | 3.3 | 10 | 2.8 | 1.02 | n/a | 0.164 | 0.91 | -0.963 | -17.3 | n/a | n/a | n/a | n/a | n/a | n/a
81 | Eastern | Abitibi Canyon | Canyon Dam Downstream Concrete Rehab | 87192 | Sustaining | 2023-05-04 | 2026-02-11 | 24.8 | 22.2 | 2025-11-01 | 24.8392 | 21.1392 | 0 | 1.4 | 2.3 | 1 | n/a | -0.3 | 1 | -0.7 | 2.6 | 0.1 | -0.6 | 5.5 | -2.3 | 0 | -0.1
|  |  | Total Regulated Hydroelectric |  |  |  |  | 1396.653 |  |  |  | 682.984 | 295.0133 | 147.3439 | 140.5