## Table 1 c
D2-AMPCO-32 | [27 empty] | Filed: 2026-04-22
EB-2025-0297
Ref: D2-1-3 Table 1c | [27 empty] | Exhibit L
D2-AMPCO-032
|  | Capital Project Listing - OPG Nuclear Facilities Projects | [25 empty] | Attachment 1
|  | Projects ≥ $30M Total Project Cost (Allocated) | [19 empty] | Cost Driver Variance
|  | PROJECTS NOT IN EB-2020-0290 >$30 M | Project # | Category | BCS Tab # | Start Date | Final In-Service Date | Total Project Cost ($M) | Total Project Cost at D2-1-3 Attachment #1 Tabs 36-55 ($M) | Total In-Service Date at D2-1-3 Attachment #1 Tabs 36-55 | First Execution Business Case ($M) | Total In-Service ($M) | In-Service LTD ($M) | In-Service 2025 ($M) | In-Service 2026 ($M) | Forecast In-Service IR Term ($M) | SPI = EV/PV | Schedule Variance (SV) = EV - PV (hours) | CPI = EV/AC | Cost Variance = EV-AC ($M) | Variance to Approved Project Cost at D2-1-3 Attachment #1 ($M) | Variance: Project Management ($M) | Variance: Engineering ($M) | Variance: Construction ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
1 | DN | DN Public Address System Upgrade | 31708 | Sustaining | 36 | 2021-10-01 | 2027-03-01 | 51.6288 | 45 - 70 | 2026-12-15 | n/a | 40.567 | 0 | 0 | 17.378 | 23.189 | 0.92208 | -15410.2145 | 1.1 | 2.2153 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2 | DN | DN Breathing, Instrument and Service Air Compressor Replacement | 83933 | Sustaining | 37 | 2023-02-01 | 2030-02-01 | 64.1 | 55 - 75 | 2029-02-28 | n/a | 49.479 | 0 | 0 | 0 | 49.479 | 0.98901 | -241.1479 | 0.87 | -0.40859 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
3 | DN | DN Powerhouse Elevator Replacement | 84135 | Sustaining | 38 | 2021-08-01 | 2031-06-01 | 49 | 30 - 40 | 2030-03-29 | n/a | 38.701 | 0 | 6.5 | 6 | 26.201 | 0.90963 | -7773.4783 | 0.85 | -1.7316 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
4 | DN | DN Powerhouse Cranes Refurbishment | 84139 | Sustaining | 39 | 2022-12-01 | 2032-12-01 | 93.1 | n/a | 2032-05-15 | n/a | 72.1 | 0 | 0 | 0 | 59.2973 | 0.96111 | -210.9166 | 1 | -0.0013342 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
5 | DN | DN Vacuum Building Outage Power Operated Valves Replacement | 84552 | Sustaining | 40 | 2023-12-01 | 2028-10-01 | 95.2537 | 75 - 110 | 2027-05-31 | n/a | 76.934 | 0 | 0 | 0 | 76.934 | 0.87663 | -7261.4877 | 0.97 | -0.52098 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
6 | DN | Tritium Removal Facility Major Component Replacement Program | 84764 | Sustaining | 41 | 2021-11-01 | 2038-02-01 | 540.9504 | 400 - 600 | 2038-12-31 | n/a | 452 | 0 | 0 | 0 | 157.645 | 0.99792 | -238.0599 | 1.16 | 1.8458 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
7 | DN | DN Low Pressure Service Water Strainer Backwash Motorized Valves Replacement | 86280 | Sustaining | 42 | 2025-06-01 | 2028-05-01 | 31.9801 | 20 - 35 | 2028-05-30 | n/a | 22.204 | 0 | 0 | 0 | 22.204 | 0.61346 | -3858.0804 | 2 | 0.25974 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
8 | DN | Darlington Steam Generator Moisture Separator Replacement | 86693 | Sustaining | 43 | 2021-10-01 | 2025-12-01 | 359.2 | 381 | 2025-02-01 | 380.829 | 278.6123 | 170.1 | 107.977 | 0.5 | 0 | 1.0082 | 13118.6843 | 1.16 | 41.9908 | -21.8 | n/a | n/a | n/a | n/a | n/a | n/a
9 | DN | DN Motor Operated Valve Replacement Innage | 86795 | Sustaining | 44 | 2023-06-01 | 2029-09-01 | 32.8506 | 25 - 40 | 2030-08-21 | n/a | 19.304 | 0 | 0 | 0 | 19.304 | 0.93854 | -1622.0209 | 1.19 | 0.32929 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
10 | DN | DN Lighting Fixtures Light Emitting Diode Replacement | 86910 | Sustaining | 45 | 2023-04-01 | 2029-02-01 | 39.8805 | 39.8 | 2028-11-24 | 39.881 | 35.503 | 7.9 | 6.5 | 5.4 | 15.683 | 1.0657 | 7533.0939 | 0.92 | -1.549 | 0.080512 | n/a | n/a | n/a | n/a | n/a | n/a
11 | DN | DN Copper Upgrades Phase III | 86915 | Sustaining | 46 | 2024-12-01 | 2031-04-01 | 38.3007 | 25 - 40 | 2031-04-12 | n/a | 34.733 | 0 | 0 | 6.2 | 28.533 | 0.88843 | -798.5651 | 0.83 | -0.12177 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
12 | DN | DN Unit 2 and 3 Steam Generator Moisture Separator Replacement | 87151 | Sustaining | 47 | 2025-06-01 | 2027-12-01 | 275 | 275 | 2028-06-30 | 275 | 216.6148 | 0 | 0 | 81.309 | 135.3058 | 0.96982 | -9677.1737 | 1.35 | 10.9714 | -1e-06 | n/a | n/a | n/a | n/a | n/a | n/a
13 | DN | DN Tritium Removal Facility Cryogenic Refrigeration System Turbine Replacement | 87191 | Sustaining | 48 | 2023-10-01 | 2027-10-01 | 50 | 35 - 50 | 2027-09-30 | n/a | 37.122 | 0 | 0 | 0 | 37.122 | 0.89593 | -6220.5488 | 0.88 | -1.3281 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
14 | DN | DN Turbine Rotors Replacement6 | 87807 87811 | Sustaining | 49 | 2025-03-01 | 2032-07-01 | 2589 | 2,310 - 2,910 | 2032-07-23 | n/a | 2293.3 | 0 | 0 | 0 | 1692.711 | 0.93 | -2929.4104 | 1.02 | 1.5884 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
15 | DN | DN Smartops Sensor Integration | 87808 | Sustaining | 50 | 2024-05-01 | 2030-12-01 | 51.0184 | 38 - 58 | 2030-10-31 | n/a | 37.818 | 0 | 0.856 | 1.644 | 35.318 | 0.85276 | -2569.2963 | 1.15 | 0.22643 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
16 | DN | DN Unit 1 and 2 Generator Stator Rewind | 89281 | Sustaining | 51 | 2025-03-01 | 2030-12-01 | 350 | n/a | 2030-09-01 | n/a | 312.3 | 0 | 0 | 0 | 312.3 | 0.98926 | -87.1848 | 1.03 | 0.30014 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
17 | DN | DN Steam Generator Soft Chemical Clean | 89462 | Sustaining | 52 | 2024-12-01 | 2029-02-01 | 77.9404 | 60 - 90 | 2029-02-15 | n/a | 59.668 | 0 | 0 | 20 | 39.668 | 0.95707 | -3406.6144 | 1.27 | 2.2272 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
18 | PN | PN 058 Boiler Room and Turbine Hall Crane Upgrade | 89535 | Sustaining | 53 | 2025-01-01 | 2027-07-01 | 59.6669 | 40 - 70 | 2028-01-15 | n/a | 47.338 | 0 | 0 | 14.469 | 32.869 | 0.99233 | -60.5731 | 0.91 | -1.1791 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
19 | PN | PN 058 Turbine Auxiliary Building, Reactor Auxiliary Building Hoist & Cranes | 89536 | Sustaining | 54 | 2025-03-01 | 2029-12-01 | 47.7 | 40 - 60 | 2029-12-01 | n/a | 36.1 | 0 | 0 | 9.0196 | 27.0804 | 0.97989 | -306.5279 | 1.72 | 3.2048 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
20 | PN | P58 Second Simulator and Pickering Learning Centre Extension | 89581 | Regulatory | 55 | 2025-05-01 | 2028-03-01 | 39.6924 | n/a | 2027-09-30 | n/a | 28.8959 | 0 | 0 | 0 | 28.8959 | 0.64574 | -10094.949 | 1.27 | 0.90421 | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Total | [5 empty] | 4936.2627 |  |  |  | 4189.2941 | 178 | 121.833 | 161.9196 | 2819.7395