## Table 1b
Filed: 2026-04-22
EB-2025-0297
Ref: D2-1-3 Table 1b | [5 empty] | Exhibit L
D2-AMPCO-030
|  | Capital Project Listing - OPG Nuclear Facilities Projects |  |  |  | Attachment 1
|  | Projects ≥ $30M Total Project Cost (Allocated) | [25 empty] | Drivers of Variance
|  | ONGOING PROJECTS FROM EB-2020-0290 | Project # | BCS Tab # | Category | Start Date | Final In-Service Date | Final In-Service Date from 1st Execution BCS | Total Project Cost 0297 ($M) | Total Project Cost 0290 ($M) | Variance $ | Variance % | First Execution BCS ($M) | First Execution BCS 0290 ($M) | Total In-Service 0297 ($ M) | Total In-Service 0290 ($M) | In-Service LTD | In-Service 2025 | In-Service 2026 | Forecast In-Service IR Term | SPI = EV/PV | Schedule Variance (SV) = EV-PV (hours) | CPI = EV/AC | Cost Variance = EV-AC ($M) | Planned Hours | Earned Hours | Variance Total Project Cost to BCS ($M) | Variance: Cost Management ($M) | Variance: Project Management ($M) | Variance: Inspection ($M) | Variance: Engineering ($M) | Variance: Procurement ($M) | Variance: Construction ($M) | Variance: Commissioning ($M) | Variance: Contingency ($M) | Variance: Interest ($M) | Variance: Other ($M) | If Other, Please Explain
COMPLETED/DEFERRED/CANCELLED FROM EB-2020-0290
31 | DN | DN Shutdown Cooling Heat Exchanger Replacement | 31710 | 30 | Sustaining | 2012-11-01 | 2021-11-01 | 2018-09-01 | 85.518 | 111.4 | -25.882 |  | 56.085 | 56.085 | 73.8091 | 74.1 | 73.8091 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | 29.433 | 1.7206 | 9.1601 | 0 | 2.3216 | 1.427 | 18.1761 | 0.001719 | -3.24 | 0 | -0.14921
32 | DN | DN Auxiliary Heating System | 34000 | 31 | Regulatory | 2006-03-01 | 2018-06-01 | 2015-12-01 | 106.3597 | 107.149 | -0.78935 |  | 45.607 | 45.607 | 102.6442 | 102.1 | 102.6442 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | 60.7527 | 7.7435 | 2.3555 | 0 | 16.5553 | 7.3586 | 34.9124 | 1.7035 | -6.614 | -2.803 | -0.4172
33 | DN | DN Zebra Mussels Mitigation & Improvements | 38948 | S | Sustaining | 2012-11-01 | 2021-12-01 | 2016-07-01 | 37.1392 | 36.634 | 0.50519 |  | 21.481 | 21.481 | 37.1392 | 36.5 | 37.1392 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | 15.6582 | 1.9862 | 5.9447 | 0 | 2.3489 | 0.9458 | 5.3521 | 0.80934 | -1.57 | 0 | -0.15399
34 | DN | DN RS Primary Heat Transport Pump Motor Replacement4 | 73566, 80144, 36001 | 33 | Sustaining | 2015-07-01 | 2022-10-01 | 2019-06-01 | 77.8983 | 84 | -6.1017 |  | 26.7 | 26.7 | 72.0935 | 71.4 | 72.0935 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | 51.1983 | 2.4032 | 2.6722 | 7.5e-05 | -3.3052 | 42.4154 | 13.0855 | 0 | -0.7 | -4.2 | -1.1729
35 | DN | DN Steam Generator Level Control Valve Replacement | 80023 | 34 | Sustaining | 2015-01-01 | Cancelled | N/A | 9.3298 | 38.6 | -29.2702 |  | n/a | n/a | 0 | 38.5 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
36 | DN | DN Primary Heat Transport Pump Motor Overhaul | 80144 | 33 | Sustaining | 2015-07-01 | 2021-12-01 | 2019-06-01 | 43.5744 | 53.3 | -9.7256 |  | 102.8 | 102.8 | 42.6119 | 43.8 | 42.6119 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | -59.2256 | 1.6952 | -0.41625 | 0 | -3.3698 | 38.9651 | 5.2e-05 | 0 | -15.3 | -18.7 | -62.0999
37 | DN | DN Copper Piping Replacement | 83049, 83784, 83819 | 35 | Sustaining | 2016-08-01 | 2023-08-01 | 2022-12-01 | 44.3056 | 45.072 | -0.7664 |  | 29.334 | 29.334 | 42.8248 | 43.7 | 42.8248 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | 14.9716 | -0.95322 | -0.22905 | 0 | 1.3449 | 1.6372 | 13.2578 | 0 | 0.44 | 0 | -0.52655
|  | Total | [6 empty] | 404.1248 | 476.155 | -72.0302 | 0 | 282.007 | 282.007 | 371.1226 | 410.1 | 371.1226 | 0 | 0 | 0 | [6 empty] | 112.7881
-33.4302