June 5, 2026

DELIVERED BY EMAIL

Mr. Ritchie Murray

Registrar

Ontario Energy Board

2300 Yonge Street, Suite 2700

Toronto, Ontario M4P 1E4

Email: Registrar@oeb.ca

Dear Mr. Murray:

Re:  Application for Electricity Storage License (EB-2025-0183)

In May 2025, Alectra Energy Services Inc. and its partner Convergent Canada Acquisition Co. ULC, applied for an Electricity Storage License for Vaughan 3 Energy Storage 1 LP (“Vaughan 3”) for the purpose of operating a battery storage facility.

In a Decision and Order issued on July 17, 2025, the OEB approved the application, subject to the applicant providing the OEB with written confirmation that facility construction has been completed and that a state of readiness to commence commercial operation has been achieved. The applicants provided the OEB with an update on Vaughan 3 facility construction in a letter on May 5, 2026, which indicated that construction had progressed to 95% completion.

The applicant is pleased to report that Vaughan 3 facility construction is now materially complete. The facility received provisional ESA approval on May 26, 2026. The target timeframe for commercial operations to commence is mid-July 2026.

The applicants request that the OEB issue the electricity storage licence for the Vaughan 3 facility to enable the applicants to proceed with IESO market registration and commercial operation.

If the OEB requires any further information, please contact the undersigned.

Sincerely,

Peter Bifolchi

Peter Bifolchi, P. Eng.

Director, Distributed Energy Solutions Construction and Operations

Alectra Energy Solutions Inc.