## Project List Detailed Variance
Project # | Completion Year | Project | NET ISA Plan | NET ISA Actual | Net Variance Actual (%) | Variance Exceed +/- 10% (Yes/No) | Description of Project | Description of Variance | Variance Theme | Detailed Variance Rationale
1 | 2021 | MS11 T2 44kV reliability W. Lawler SS | 2660445 | 2954956 | 11.07% | Yes | Project to improve reliability and capacity for W. Lawler Substation in Whitby- adding new protective devices and upgraded transformer. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project | The detailed design and estimates developed by the designers were used to establish the Net ISA Plan. The primary driver of the variance was the use of a high-level estimate prepared during the early stages of the COVID-19 pandemic, which did not fully anticipate the material cost increases experienced during project execution. As a result, material costs were approximately $243k higher than planned, while labour, subcontractor, and vehicle costs increased by approximately $46k. The project scope of work remained consistent with the original plan.
[10 empty] | Net ISA Plan |  | Net ISA Actual
[10 empty] | 1. Labour | 441870.79 | 1. Labour | 365116.65
[10 empty] | 2. Material | 1315852.43 | 2. Material | 1558897.77
[10 empty] | 3. Vehicles | 58872.24 | 3. Vehicles | 90650.41
[10 empty] | 4. Contractor | 843850.9 | 4. Contractor | 940291
[10 empty] | Total | 2660445 | Total | 2954956
2 | 2023 | Des Newman (MS16) Upgrade | 1000000 | 1111367.41 | 11.14% | Yes | Substation Growth & Expansion project which involves installation of power transfomers and new feeders. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project | The original high-level scope estimate was used to establish the Net ISA Plan. The variance is primarily attributable to higher-than-anticipated substation equipment costs, including pad-mounted reclosers and high voltage cables, as material prices increased between the completion of the estimate in early 2021 and the purchase and installation of the equipment in 2022 and 2023. These increases resulted in material costs that were approximately $113k above the original estimate. The project's civil work had been completed in 2019 and did not contribute to the variance, as it was not subject to the inflationary impacts experienced during the COVID-19 period.
[10 empty] | Net ISA Plan |  | Net ISA Actual
[10 empty] | 1. Labour | 137500 | 1. Labour | 112058.83
[10 empty] | 2. Material | 843788.88 | 2. Material | 957292.58
[10 empty] | 3. Vehicles | 33000 | 3. Vehicles | 21635.55
[10 empty] | 4. Other/Contractor | 0 | 4. Contractor | 20380.45
[10 empty] | Total | 1014288.88 | Total | 1111367.41
3 | 2023 | Main St E (Nancy x Madill) Beaverton Ph2 | 633438 | 863302 | 36.29% | Yes | Planned Capital work related to replacement and removal of pole, installation of conductors, switches and transformers. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project | The Net ISA Plan was based on the designers detailed design and estimate. While the project scope did not deviate from plan, actual costs exceeded the estimate due to material prices increasing between the preparation of the estimate in the third quarter of 2021 and project execution in 2023. These material cost increases resulted in approximately $187k in additional material costs, while labour and subcontractor costs were approximately $42k higher than originally estimated.
[10 empty] | Net ISA Plan |  | Net ISA Actual
[10 empty] | 1. Labour | 15531.2 | 1. Labour | 31503.81
[10 empty] | 2. Material | 231658.48 | 2. Material | 419087.71
[10 empty] | 3. Vehicles | 1248.96 | 3. Vehicles | 1356.2
[10 empty] | 4. Other/Contractor | 385000 | 4. Contractor | 411354.28
[10 empty] | Total | 633438 | Total | 863302
4 | 2023 | Montgomery Park (Sandy Beach x Brock) | 538000 | 1007667.31 | 87.3% | Yes | System service, system reliability improvement project involving building of 13.8kV circuit | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project | The Net ISA Plan was based on the detailed design and estimate developed by the designer. The project scope did not deviate from plan; however, the original estimate did not include contractor costs required for the construction of the civil infrastructure, which was the primary driver of the variance. Additionally, material costs were higher than anticipated due to the underestimation of material pricing in the mid-2022 estimate. As a result, labour including contractor costs, and material costs exceeded the original estimate by approximately $342k and $206k, respectively.
[10 empty] | Net ISA Plan |  | Net ISA Actual
[10 empty] | 1. Labour | 211629.3 | 1. Labour | 109187.58
[10 empty] | 2. Material | 238206.14 | 2. Material | 444699.47
[10 empty] | 3. Vehicles | 84700 | 3. Vehicles | 9112.7
[10 empty] | 4. Other/Contractor | 0 | 4. Contractor | 444667.56
[10 empty] | Total | 534535.8 | Total | 1007667.31
5 | 2023 | P&C- James Collins SS- Control Hut/Recloser Controls Repl | 420000 | 964717.53 | 129.7% | Yes | Replacement of Control shed for James Collins substation in Port Hope and associated obsolete recloser controls. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project | The variance is primarily attributable to higher-than-estimated civil construction costs. The original estimate relied on historical costs from comparable projects completed prior to 2019, which did not reflect the greater extent of civil work required for this project when it was executed in 2023. Additionally, substation material costs were based on 2021 pricing and experienced inflationary increases before procurement and installation. Consequently, civil construction costs exceeded the original estimate by approximately $400k, while substation material costs were approximately $130k higher than planned.
[10 empty] | Net ISA Plan |  | Net ISA Actual
[10 empty] | 1. Labour | 144000 | 1. Labour | 266205.96
[10 empty] | 2. Material | 134580 | 2. Material | 266271.06
[10 empty] | 3. Vehicles | 24000 | 3. Vehicles | 63891.48
[10 empty] | 4. Other/Contractor | 120000 | 4. Contractor | 368349.03
[10 empty] | Total | 422580 | Total | 964717.53
6 | 2025 | Bowmanville Ave (Baseline x Hw | 1298686 | 1704701.39 | 31.26% | Yes | Road Relocation project driven request from City of Pickering to relocate/adjust poles in conflict with the culvert an watermain installation. | Variance attributable to labour and material costs exceeding the original estimate. | Planned Distribution Project | The planned project cost was based on an updated high-level estimate prepared in mid-2024. Actual material costs were approximately $271k higher than estimated, driven primarily by increases in high-voltage cable pricing prior to construction. Contractor costs also exceeded the estimate by approximately $198k due to additional tree trimming requirements, unforeseen civil work required to address soil contamination, and project delays associated with remediation efforts.
[10 empty] | Net ISA Plan |  | Net ISA Actual
[10 empty] | 1. Labour | 201500.84 | 1. Labour | 183768.83
[10 empty] | 2. Material | 1112385.67 | 2. Material | 1382911
[10 empty] | 3. Vehicles | 4535.74 | 3. Vehicles | 8510.81
[10 empty] | 4. Other/Contractor | 1836836.13 | 4. Contractor | 2035215.27
[10 empty] | Total Project Cost | 3038879.87 | Total Project Cost | 3610406
[10 empty] | Customer Portion of Cost | 1740193 | Customer Portion of Cost | 1905704.53
[10 empty] | Elexicon Portion of Cost | 1298686.8 | Elexicon Portion of Cost | 1704701.39