## NEPL
ATTACHMENT 1: Overhead and AFUDC Cost Estimate Calculation – NEPL Project
| Total | Previous Years | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [12 empty] | 2028 | [12 empty] | 2029 | [12 empty] | 2030
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Table 1 - Line Cost
Direct Capital Expenditure (Direct + Contingency) | 1158212933 | 5904162 | 351391 | 714114 | 810364 | 854041 | 757900 | 569226 | 473144 | 557356 | 911430 | 1821017 | 1828752 | 1624627 | 2046621 | 1732893 | 1738889 | 2170920 | 2172919 | 32571680 | 5945205 | 7295045 | 13818733 | 9629356 | 4529381 | 4890674 | 82595867 | 40696837 | 31220010 | 14786826 | 34239926 | 31546259 | 51820588 | 32124897 | 46093820 | 33582783 | 67784506 | 58613903 |  | 33684880 | 33680863 | 34294461 | 12286713 | 38081337 | 22990636 | 34153186 | 29167944 | 14666285 | 18736031 | 23836347 | 28817746 |  | 15696718 | 15987475 | 25504250 | 6639290 | 16771890 | 17248572 | 18186390 | 26216394 | 12753296 | 21839028 | 6488543 | 6397127 |  | 1823820 | 1801702 | 1687612 | 1062263 | 1062263 | 1062263 | 1054548 | 1054548 | 1054548 | 1060881 | 403496 | 133525
AFUDC (Cost) | 98650876 | 111556 | 22569 | 24702 | 27279 | 30469 | 33445 | 35656 | 37330 | 39208 | 42223 | 45917 | 52761 | 59819 | 63098 | 70578 | 76970 | 83406 | 91397 | 99423 | 215308 | 237145 | 263847 | 313783 | 349032 | 366313 | 378971 | 668702 | 813100 | 924898 | 979689 | 1102604 | 1216532 | 1401654 | 1518627 | 1684783 | 1807817 | 2050714 |  | 2251176 | 2377192 | 2503623 | 2631189 | 2682714 | 2824049 | 2913427 | 3041898 | 3153484 | 3215057 | 3290982 | 3384889 |  | 3522865 | 3589780 | 3657942 | 3759659 | 3795675 | 3867290 | 3940820 | 4017887 | 4123332 | 4182002 | 4272685 | 4309934 |  | - | - | - | - | - | - | - | - | - | - | - | -
Overhead (Cost) | 23224071 | 146237 | 7028 | 14282 | 16207 | 17081 | 15158 | 12275 | 9463 | 11147 | 18298 | 32585 | 54863 | 48739 | 40932 | 34658 | 34778 | 43418 | 43458 | 651434 | 118904 | 145901 | 276375 | 192587 | 90588 | 97813 | 1651917 | 813937 | 624400 | 295737 | 684799 | 630925 | 1036412 | 642498 | 921876 | 671656 | 1355690 | 1172278 |  | 681231 | 681151 | 685204 | 245049 | 760942 | 459128 | 682379 | 582674 | 292641 | 374036 | 476042 | 575670 |  | 313249 | 319065 | 509400 | 132101 | 334753 | 344287 | 363043 | 523643 | 254381 | 436096 | 129086 | 127258 |  | 36476 | 36034 | 33752 | 21245 | 21245 | 21245 | 21091 | 21091 | 21091 | 21218 | 8070 | 2670
Cumulative Capital Expenditure | 1280087880 | 6161955 | 380988 | 753098 | 853850 | 901591 | 806503 | 617157 | 519937 | 607711 | 971951 | 1899519 | 1936376 | 1733185 | 2150651 | 1838129 | 1850637 | 2297744 | 2307774 | 33322537 | 6279417 | 7678091 | 14358955 | 10135726 | 4969001 | 5354800 | 84626755 | 42179476 | 32657510 | 16007461 | 35904414 | 33279788 | 54073532 | 34169049 | 48534323 | 35939222 | 70948013 | 61836895 |  | 36617287 | 36739206 | 37483288 | 15162951 | 41524993 | 26273813 | 37748992 | 32792516 | 18112410 | 22325124 | 27603371 | 32778305 |  | 19532832 | 19896320 | 29671592 | 10531050 | 20902318 | 21460149 | 22490253 | 30757924 | 17131009 | 26457126 | 10890314 | 10834319 |  | 1860296 | 1837736 | 1721364 | 1083508 | 1083508 | 1083508 | 1075639 | 1075639 | 1075639 | 1082099 | 411566 | 136195
Removals | 159984 | [25 empty] | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 |  | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 |  | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444 | 4444
Expenditure after removals | 1279927896
Table 2 - Station Cost
Direct Capital Expenditure (Direct + Contingency) | 490002517.4405 | 959396 | 105617.55 | 195385.79 | 201482.3 | 193823.81 | 277791.39 | 668562.38 | 391205.65 | -51581.22 | 672517.66 | 4098370.3183 | 4101597.3183 | 4103597.3183 | 1356879.7908 | 1356879.7908 | 1358879.7908 | 686143.8058 | 959823.1808 | 9299292.0544 | 11658934.1159 | 966917.9189 | 969917.9189 | 4836692.2856 | 5803111.9474 | 8066477.6132 | 31913915.7629 | 12161339.3506 | 21261721.8362 | 6329213.204 | 20943256.185 | 3455193.4547 | 16315122.5443 | 30212553.7088 | 16026516.4659 | 27483909.5276 | 33281487.0833 | 32832851.2019 | 0 | 11662657.9833 | 12940429.7039 | 17192003.1661 | 3985283.4406 | 13025519.4017 | 7382763.6086 | 10614734.47 | 12227222.8488 | 3808038.1072 | 4275517.7739 | 15707944.9494 | 9038426.0728 | 0 | 3353770.5864 | 4463329.2212 | 7609825.3833 | 3444499.9197 | 3970414.9094 | 3457281.0289 | 3415958.4197 | 3415958.4197 | 3670629.0897 | 3440329.7531 | 3440329.7531 | 3443329.7531 | 0 | 840132.3933 | 840667.8378 | 844492.3933 | 504990.3933 | 504990.3933 | 507450.3933 | 492615.7267 | 492615.7267 | 497795.6156 | 11924 | 11924 | 11924
AFUDC (Cost) | 48005039.5502 | 15218 | 3760.16 | 4333.86 | 5045.32 | 5761.25 | 6629.73 | 8268.82 | 9987.36 | 10792.48 | 12082.14 | 14346.67 | 28917.9105 | 45319.9144 | 58950.5652 | 64204.6846 | 69477.0761 | 74775.2456 | 77588.5112 | 81429.9533 | 116316.8928 | 160105.6616 | 164260.4723 | 168440.8955 | 187024.576 | 209269.045 | 236294.8047 | 354935.1432 | 400942.4467 | 480757.8164 | 505630.4194 | 584626.6274 | 599227.5743 | 661430.7592 | 775235.5413 | 836974.1621 | 941290.244 | 1067401.2256 |  | 1186361.721 | 1232740.8166 | 1283935.7372 | 1350803.1949 | 1369756.4174 | 1421728.2965 | 1453307.8734 | 1496776.4368 | 1546271.0416 | 1565244.0758 | 1585985.8361 | 1648472.5253 |  | 1699615.372 | 1717704.9079 | 1739969.8466 | 1773975.7702 | 1792656.9002 | 1813351.8043 | 1832215.4762 | 1850990.7093 | 1869830.3893 | 1889678.8421 | 1908741.6696 | 1927869.9314
Overhead (Cost) | 37097867.1239 | 23517 | 2112.35 | 3907.71 | 4029.65 | 3876.48 | 5555.82 | 13601.25 | 7824.12 | -1031.62 | 13468.41 | 47563.26 | 369143.7586 | 369323.7586 | 94981.5854 | 94981.5854 | 95121.5854 | 48030.0664 | 67187.6227 | 650950.4438 | 816125.3881 | 67684.2543 | 67894.2543 | 338568.46 | 406217.8363 | 564653.4329 | 2553113.261 | 972907.148 | 1700937.7469 | 506337.0563 | 1675460.4948 | 276415.4764 | 1305209.8035 | 2417004.2967 | 1282121.3173 | 2198712.7622 | 2662518.9667 | 2626628.0961 |  | 816386.0588 | 905830.0793 | 1203440.2216 | 278969.8408 | 911786.3581 | 516793.4526 | 743031.4129 | 855905.5994 | 266562.6675 | 299286.2442 | 1099556.1465 | 632689.8251 |  | 268301.6469 | 357066.3377 | 608786.0307 | 275559.9936 | 317633.1927 | 276582.4823 | 273276.6736 | 273276.6736 | 293650.3272 | 275226.3802 | 275226.3802 | 275466.3802 |  | 67210.5915 | 67253.427 | 67559.3915 | 40399.2315 | 40399.2315 | 40596.0315 | 39409.2581 | 39409.2581 | 39823.6492 | 953.92 | 953.92 | 953.92
Cumulative Capital Expenditure | 575106000 | 998131 | 111490.06 | 203627.36 | 210557.27 | 203461.54 | 289976.94 | 690432.45 | 409017.13 | -41820.36 | 698068.21 | 4160280.2483 | 4499658.9875 | 4518240.9914 | 1510811.9414 | 1516066.0608 | 1523478.4523 | 808949.1178 | 1104599.3147 | 10031672.4515 | 12591376.3969 | 1194707.8349 | 1202072.6456 | 5343701.6411 | 6396354.3597 | 8840400.0911 | 34703323.8286 | 13489181.6418 | 23363602.0299 | 7316308.0767 | 23124347.0991 | 4316235.5585 | 18219559.9221 | 33290988.7647 | 18083873.3244 | 30519596.4519 | 36885296.294 | 36526880.5236 |  | 13665405.7631 | 15079000.5998 | 19679379.125 | 5615056.4763 | 15307062.1772 | 9321285.3577 | 12811073.7563 | 14579904.885 | 5620871.8164 | 6140048.0939 | 18393486.9319 | 11319588.4232 |  | 5321687.6053 | 6538100.4668 | 9958581.2606 | 5494035.6835 | 6080705.0023 | 5547215.3155 | 5521450.5695 | 5540225.8026 | 5834109.8062 | 5605234.9754 | 5624297.8029 | 5646666.0647 |  | 907342.9848 | 907921.2648 | 912051.7848 | 545389.6248 | 545389.6248 | 548046.4248 | 532024.9848 | 532024.9848 | 537619.2648 | 12877.92 | 12877.92 | 12877.92
Removals | 1861000
Expenditure after removals | 573245000